**Mozambique**

|  |  |
| --- | --- |
| **Programme Title:** | Environment Mainstreaming and Adaptation to Climate Change |
| **Programme number & MDTF ref:** | MDGF-1681-E-MOZ Env Climate (67152) |
| **Window:** | Environment & Climate Change |
| **Approved Budget by NSC (US$):** | 7 million |
| **Participating Organizations:** | FAO, UNDP, UNEP, UNHABITAT, UNIDO, WFP |
| **First Tranche transferred on:** | 22-Aug-2008 |
| **Second Tranche transferred on:** | 2-Mar-2010 |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:** |
| Climate change integrated into National Disaster Management Contingency Plan and district level Strategic Development Plan. Risk mapping completed in Chicualacuala and experience replicated in 6 other districts. Training provided in participatory planning to communities and government partners. Various types of training materials prepared and distributed. Exchanges of experience with other projects on-going. Community radio coverage for early warning increased. Network of community base animal health workers trained and equipped, improved livestock treatment centres built. Slaughter house being built. Household and community rainwater harvesting systems being installed. Community base forest management system elaborated, forest guards trained, management committees being legalised. Honey production being promoted. Expansion of area under irrigated agricultural production. Various studies linked to environment, climate change, livelihoods and coping strategies conducted. Renewable energy (solar) for water pumping installed. Programme of opening new boreholes underway. Integrated district wáter management plan being developed. Promotion and trials of agro-forestry and conservation agriculture. Training for communities in agro-processing. |
|  |
| **Problems and lessons learned:** |
| Managerial (remote project sites) UN Agency coordination, particularly with joint activities. Effective coordination with Government partners. |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** Not Reported |

CHARTS & FIGURES

As of 31 December 2010

