ANNEX 4.1

# Liberia Peacebuilding Fund

# QUARTERLY STATUS REPORT AS OF SEPTMBER 2010

| Recipient UN Organization: | UNHCR | PBF Priority Area: | 1: Fostering National Reconciliation and Conflict Management |
| --- | --- | --- | --- |
| Implementing Partner(s): | Justice and Peace Commission (JPC) Gbarnga and Cape Palmas |
| Project Number: | PBF/ LBR/A-1 (PBF/PP/R1/A1/06) |
| Project Title: | Community Empowerment: Peace, Human Rights, and Civic Participation |
| Total Approved Project Budget | 932,400.00 USD |
| Funds Committed: | 699,008.46 USD | Percentage of Approved: | 75% |
| Funds Disbursed: | 699,008.46 USD | Percentage of Approved: | 75% |
| SC Approval Date: | 9 October 2008 |
| Expected Project Duration: | 18 months | Forecast Final Date: | 31 December 2010 | Delay (Months): | 8 months |

| Outputs: | Progress: | Percentage of planned: |
| --- | --- | --- |
| JPC trained and equipped to implement CE Programme. | Completed. | 100% |
| 40 Community Empowerment Facilitators trained and equipped to become Training of Trainers | 42 Facilitators are the trained and equipped. | 100% |
| 90 GoL/UN/CSO stakeholders in the target counties are fully aware of CE Programme and ways it can be utilised to enhance their work. | GoL/UN/CSO Stakeholder workshops were held in district and county level and approximately 300 people were sensitized about the peace education workshops in Lofa, Nimba and Grand Gedeh. | 100% |
| 15,000 community members trained in Community Workshops. | From the beginning of the project, 9,101 citizens were trained in307 workshops in Lofa, Nimba and Grand Gedeh. During the reporting period, 79 workshops were conducted. | 61% |
| Opportunity Plan developed after each training at the community level. | 79 Opportunity Plan have been developed. | 48% |
| All Communities where Workshop is implemented are abreast of the Community Workshop graduates, content, and the Opportunity Plan. | 79 Community Workshops have been conducted abreast of the graduation ceremonies and the Opportunity Plans. | 48% |
| 5 minute trailer (to radio programme) on CE Programme (narrated by a high-profile, national KEY person) played at least five times in target communities. | The trailer was done by community leaders, government officials and a master trainer of peace education and disseminated through radio. | 100% |
| 3 hours of radio programmes per target community broadcast with discussion about the community workshops and the “Opportunity Plan”. | Completed. | - |
| 500 standout community workshop participants trained and equipped to become community workshop facilitators and form the PB Support Network to support the MIA PB Focal Point. | In total, 4 standout workshops (2 each in Lofa and Grand Gedeh) were conducted and 140 community members received advanced training on Peace Education. | 28% |
| 10. Established and sustained Peacebuilding Support Network throughout the field. | Support Network will be formed by the 500 standout community workshop participants. The training for them will start earlier in 2010. | 0% |

| Outcomes: | Progress: {In terms of Indicators} | Comments/Remarks: |
| --- | --- | --- |
| Skills/Knowledge: Problem-solving, negotiation, and mediation are understood by the community to address [potential] conflicts. | The project facilitated the creation of mediation committees in beneficiaries' communities through the Community Workshops. In those communities, citizens are now using the committees to settle conflicts such as SGBV and disrespect for authority, communal conflict and domestic issue. By doing so, the acquired skills in individual level are transferred to and utilized by other community members. | - |
| Behaviour: Problem-solving, negotiation, and mediation are used by the community to address [potential] conflicts and move toward reconciliation. |  | - |
| Skills: Individuals have improved communication skills. |  | - |
| Knowledge: Citizenry understand civic rights and duties, and human rights [and responsibilities]. | Increased understanding on civil rights and duties, and human rights is noted among ex-participants of the workshops. | - |
| Knowledge: Increased understanding of what is accountability and transparency. | Community members are now demanding accountability and transparency in administration of the affairs in their community. | - |
| Knowledge: Increased understanding of harm caused by bias, stereotypes, prejudice, and discrimination. | Ex-participants begin to understand conflict factors, social discrimination, bias, stereo types and effects | - |
| Attitude/Value: Increased cooperation through trust-building and understanding of similarities and differences. | Community members are working together through group farming, building guest house and a town hall, dramatizing peace messages to other communities. | - |
| Behaviour: Increased participation and inclusiveness in community decisions. | In some communities, the conduct of community activities is now being carried out largely through community meeting and collective agreement. | - |
| Attitude/Value: Increased empathy through respect, openness, and understanding. | Ex-participants of the workshops started to understand differences and similarities among people in the community and to appreciate other tribes and religion. | - |
| Skills: Programmatic/ Administrative/ Peacebuilding capacity of local IP, JPC, increased. | Strengthening institutional capacity of the Implementing partner still remains as a challenge. | - |
| 11. Knowledge/Acceptance: Increased understanding and community consensus on those [potential] conflicts hindering “inclusive growth” in their community. | Increased knowledge of peaceful co-existence as well as level of tribal tolerance is noted among ex-participants of the workshops. | - |

Challenges: