ANNEX 4.1

# Liberia Peacebuilding Fund

# QUARTERLY STATUS REPORT AS OF SEPTEMBER 2010

| Recipient UN Organization: | UNHCR | PBF Priority Area: | 2: Critical Intervention to Promote Peace and Resolve Conflict |
| --- | --- | --- | --- |
| Implementing Partner(s): | Liberia Peacebuilding Office (PBO) |
| Project Number: | PBF/LBR/D-10 |
| Project Title: | Small Grants to Support Initiatives for Peace Consolidation in Liberia |
| Total Approved Project Budget | 462,606.00 USD |
| Funds Committed: | 387,202.00 USD | Percentage of Approved: | 84% |
| Funds Disbursed: | 309,761.60 USD | Percentage of Approved: | 67% |
| SC Approval Date: | 1 December 2009 (Fund transfer date 11 Dec 2009) |
| Expected Project Duration: | 12 months | Forecast Final Date: | 31 December 2010 | Delay (Months): | 8 months |

| Outputs: | Progress: | Percentage of planned: |
| --- | --- | --- |
| PBO staffed with a finance assistant and equipped with office materials. | A finance assistant and UNHCR periodically visit partners and provide coaching. | - |
| 15 partner organizations awarded sub-contracts | Completed. 15 IPs signed a tripartite Memorandum of Understanding with PBO and UNHCR on 10 May 2010. Subsequently, the first tranche (80% of the total funding) of the grants was disbursed to the partners by the PBO. Most of the Small Grants Project hit the ground running in June 2010. | 100% |
| 15 partners trained in financial and narrative reporting, project management and basic M&E | In total 37 persons, including project managers, project officers and finance officers from 15 IPs trained in 4-day workshop on Project Planning and Management held from 6 to 9April. | - |
| Monthly status report and quarterly financial report submitted on time to UNHR in compliance with the UNHR procedures | To ensure timely reporting from 15 partners remains as a challenge. | - |
| Network among 15 partners are established and maintained | 15 partners had a first interaction in the training held in April 2010. PBO will convene periodic meetings with 15 IPs and facilitate information exchange, such as good practices and lessons learned among them. | - |

| Outcomes: | Progress: {In terms of Indicators} | Comments/Remarks: |
| --- | --- | --- |
| 75% of 15 partners implementing Small Grants Projects enhanced their technical and institutional capacities within the 12-month duration of the project. | The training held in April 2010 had an immediate positive effect on their knowledge in project management: right after the training, some IPs soon applied the acquired knowledge to improve their project documents, including logframe. | - |
| Improved partnership and coordination amongst peacebuilding efforts and Implementing Partners over a 12-month period. | The training provided the first opportunity to meet together. Through group work and interactive sessions, they were able to identify common issues they are facing in project management /financial control and share their idea on how to tackle with these issues. | - |
| At least 75% of targeted communities live in reconciliation, social tensions reduced and inter-intra community dialogue for peace consolidation increased over a 12-month period. | It is premature to measure the outcomes at this stage. | - |

Qualitative achievements against expected results:

Challenges:

Given that the project locations are geographically expanded, monitoring IPs where UNHCR field offices are not present is a challenge. Joint monitoring mission with PBO and other Ad-Hoc committee members should be encouraged.