UNITED NATIONS PEACEBUILDING FUND

FINAL PROGRAM NARRATIVE REPORT AS OF DECEMBER 2010

REPORTING PERIOD: MARCH 2009-DECEMBER 2010

PBF/LBR/D-4 (00073628)

Submitted by: UNFPA                                                                     Country and Thematic Area:

LISCO Building, Mamba Point

P.0.BOX 10-0274

1000 MONRVOVIA 10, LIBERIA

Program Title: Psychosocial and Community Support Program

Participating Organization: UNFPA

Program NO: PBF/LBR/D-4 (LBR5G42A/UJA04 Ref # PP/R2/A2-09)

MDTF Office Atlas No: 00073628

Implementing Partners:

Ministry of Health and Social Welfare in Partnership of American Refugee Committee –ARC

Program budget: $ 889,902:00

Program duration: 18 months with 3 months No Cost Extension;

Start Date: March 2009

End Date: December 2010

1: Purpose:

The project represents an integrated approach to community based psychosocial support  that includes training/capacity building, services delivery reinforcement of community-based safety networks combined with livelihoods extension and support.

The project has the following Peace Building Impact and key outcomes:

- Peace building impact: Individual and community members are better able to promote a peaceful co-existence, prevent and respond to traumatic events and social problems that have the potential to create conflict.

Key outcomes:

- Established and trained psychosocial support teams

- Psychosocial support services provided in communities

- Strengthened community based networks

- Livelihoods extension and empowerment provided

Outputs and Key Activities:

- Increased understanding of the nature and extent of community based psychosocial support (including livelihood support) in the target counties.

- Increased knowledge and skills among staff of the MOH&SW in terms of psychosocial support services through training and capacity building.

- Increased access to psychosocial support services in identified health facilities through a strengthened referral system, awareness/information provision and counseling.

- Increased livelihoods schemes for vulnerable persons, by provision of entrepreneurial activities.

ll: Resources:

Financial resources: 100% of the funding comes from the Liberia Peace Building Fund.

Human resources: ARC: 16 FTE national staffs. MOH&SW: 45 FTE national staffs

International Staff: One UNV Psychosocial Specialist

lll: Implementation and Monitoring Arrangements.

The program utilized a community based support implementation approach through intensive training of 210 community Network members in the three target communities. National Psychosocial Counselor trainers were recruited and re-trained on the program implementation mechanisms who also trained and capacity build MOH&SW Psychosocial Case Workers in the field. Joint missions to the project locations in Gbong, Margibi and Monsterrado Counties were undertaken by UNFPA, MOHSW and the ARC to monitor and assess the project implementation. The team held interactions with the project staff, network members and beneficiaries

During the monitoring, partner Agencies shared the outcomes and were able to build on the lessons learned so as to improve the program. An external final program evaluation was conducted and report is attached as Annexure 1:

IV: Results:

- Through UNFPA support, a baseline survey on psycho social and community support was conducted during the last quarter of 2009 in Bong, Margibi and Montserrado Counties by Ministry of Health and Social Welfare (MOHSW) in partnership of American Refugee Committee (ARC).

- During the 4th quarter of 2010 final evaluation of the program was conducted by an independent consultant and the report also highlights program results. See  annexure 1.

- Through UNFPA support 40 social workers, 3 facilitators, program coordinator and other support staff were recruited and deployed by the MOHSW in three Counties Bong, Margibi and  Montserrado in  seven Districts Salala, Suokoko, Jarquelleh, Kakata, Mambah Kaba, Po River and Careyburg,  and 21 Network Zones.

- UNFPA supported the MOHSW and ARC with the intensive training for social workers conducted for the social workers and facilitators to build the capacity and to facilitate establishment of sustainable psycho-social support services in Gbangba, Montserrado and Margibi Counties.

- Referral pathway developed and case workers trained on its implementation in three counties Bong, Margibi, Montserrado, 7 Districts Salala, Suokoko, Jarquelleh, Kakata, Mambah Kaba, Po River and Careyburg, and twenty-one Network Zones

- 21 Network Zones trainings completed in project sites in Bong, Margibi, and Montserrado.   Net work members totaling 210 were trained in making referrals.  Also conducted training for MOHSW local staff and community networks.

- Community awareness campaign on psycho-social and community support services completed by MOHSW and ARC staffs through support of UNFPA in 3 Counties (Bong, Margibi and Montserrado), 7 districts and 21 Network Zones.

- UNFPA supported the MOHSW in establishing a Steering Committee on Psycho-Social support with participation by Government, Civil Society and UN Agencies.  A number of meetings were held efforts made to avoid duplication and promote collaboration including development of a common psycho-social support training manual for Liberia.

Referral pathway was developed and case workers trained on its implementation in three counties Bong, Margibi, Montserrado, seven Districts Salala, Suokoko, Jarquelleh, Kakata, Mambah Kaba, Po River and Careyburg, and twenty-one Network Zones Salala, Maimu, Totota, Phebe, Zansue, Gbatalala, C. B. Dunbar, Sammay, Janyea, Kakata, Gbaye Town, Lakay-ta, Dolo town, Marshall City, Zeawhor, Banjor, Clay Ashland, Kpallah town, Careyburg, Bensonville, and Harrisburg. A directory of agencies, organizations and local government was compiled, printed and distributed among Case workers to coordinate in the implementation of the services in the target communities. Coding system was developed, Case managers and ARC staffs trained on the Coding structure of Bong county and Margibi Counties. Intensive initial and refresher training for Case workers were conducted in three counties (Bong, Margibi, Montserrado), seven Districts and twenty-one Network Zones 21 Network members’ refresher trainings were completed in all project sites in Bong, Margibi, and Montserrado. Net work members totaling 210 trained demonstrated increased knowledge in identification of psychologically disturbed clients, intervention modalities and making of referrals to other partners in the field. Psychosocial mental health awareness trainings and awareness raising were conducted in all the 7 districts within the projects sites and this lead to better understanding by the communities on mental health and SGBV issues. Increased understanding of the nature and extent of community based psychosocial support (including livelihood support) in the target communities. Increased knowledge and skills among MOH&SW staff in the identification of survivors and in the provision of psychosocial support services to survivors. This was achieved through intensive initial and refresher trainings that were conducted throughout the program implementation period. Increased livelihood schemes for 450 vulnerable persons/survivors by the provision of entrepreneurial grants. Baseline survey/needs assessment. A baseline survey was conducted from August 24, 2009 through Sept 1, 2009. In Bong County, the survey was held in Samay, Jorquella District, Gbatala, Suakoko District and Salala, Salala District. The comparison survey for Bong County was conducted in Palala Town. In Margibi County, the survey was conducted in Lackey-Ta, Kakata District, Dolo Town, Mamban-Kaba District. The comparison survey for Margibi County was conducted in Cotton Tree. In Montserrado County, the survey was conducted in Harrisburg, Careyburg District, Kpallah, St. Paul River District. Development of training manual on psychosocial counseling. Prior to this program, ARC was providing psychosocial counseling in Liberia and compiled a comprehensive training manual in 2005 that was used as a basis for modification for this project. In the first quarter of the program implementation, the program focused on reviewing the draft manual. Following review of the manual, other topics were added to tailor the manual to the planned project trainings. In July 2009, 25 training manuals were printed and distributed to the trainers and counselors. Training of trainers for 9 MOHSW staff and 6 ARC staff. From August 3 to 14, 2009, the Training of Trainers for 9 MOHSW plus 6 ARC trainers was successfully conducted. However, it was noted that the MOHSW staff did not attend the training consistently as there was much absenteeism during the training times. ARC trainers were assigned topics which they facilitated with the support of the Psychosocial Advisor and trainer. The MOHSW staff requested that ARC cover the project logframe in detail and ARC adjusted the schedule to accommodate the request. 2 weeks Training for 9 MOHSW County staff and 28 MOH district staff and 3 County Health staff in psychosocial counseling. Two-week training was held from August 2 to 14, 2009 on the Cuttington University Campus in Suakoko, Bong County. The objective of the training was to train MOHSW social workers in psychosocial skills development. Below are the topics covered during the two weeks: Introduction to counseling Overview of health, mental health, mental illness Traumatic events, causes and responses War trauma and its effects Introduction to treatment approaches/theories Communication skills A: attending and nonverbal Communication skills B: questioning and focusing Communication skills C: summarizing, paraphrasing & validating Empathy Community entry \ sensitization Problem solving Client assessment \ treatment, collaborative treatment planning SGBV code Understanding and working with grief Crisis and crisis intervention Working with survivors of SGBV (gender concepts) Referral pathway Monitoring and evaluation Vicarious trauma /self-care Recruitment 7 psychosocial counselors and 6 psychosocial trainers to provide training, mentoring, and support to MOHSW caseworkers in their assigned locations. Seven psychosocial counselors and six psychosocial counselor trainers were hired and signed contracts. They began work on July 1, 2009. A total of 28 social workers were employed by the MOHSW for this program: 6 will be counterparts to the ARC trainers while 7 social workers are counterparts with 7 ARC counselors. The rest of the social workers worked within the networks. The ARC and MOHSW staff provided a high quality of psychosocial support to clients in Margibi, Bong and Montserrado counties. The number of clients seen throughout the life of the program totaled more than 1,000. ARC tracked client data in a database. At the last update of the database in October 2010, there were a total of 921 clients entered in the database. Demographics of Clients: Cases: Initial data suggests there have been 185 GBV cases and 610 psychosocial cases There has been an average of 15.2 cases per counselor Symptoms upon initial assessment with counseling clients: Thirty to forty percent of the clients characterized themselves as “often” exhibiting depression symptoms such as difficulty falling asleep, worrying, crying easily and feeling sad. Clients were least likely to exhibit psychosomatic symptoms such as vomiting, diarrhea, stomach aches and difficulty breathing. 36 percent of clients on at least one occasion suicidal thoughts Clients were most likely to select “never have difficulty” for physical activities such as visiting friends, listening to the radio, doing domestic work, going to the market or attending the church/mosque. Less than 15% of the clients selected “not at all” for the majority of questions pertaining to post-traumatic stress disorder. These included feeling irritable, flashbacks, avoiding particular areas, bodily or emotional reactions to reminders of the trauma. 3 day start up training for community networks. Community networks were identified and established in all 21 communities with 10 members each. The objective of the training was to train network members in basic psychosocial skills development. Their initial training was completed September 7-16, 2009. Below are the topics covered: Overview of health, mental health, mental illness Traumatic events, causes and responses War trauma and its effects Community entry/sensitization Problem solving Understanding and working with grief Crisis and crisis intervention Working with survivors of GBV (gender concepts) Referral pathway Vicarious trauma / self-care Refresher training for MOHSW case workers and community network members were held in Bong, Margibi and Montserrado Counties December 1-16, 2009 and February 8-26, 2010. The February refresher was the third and final for the community networks. ARC further built upon the awareness campaigns and capacity building it conducted with community networks by allowing them to play a primary role in coordinating and conducting sensitization campaigns and in referring cases. Twenty-one community networks were established, each with ten members. They continue to carry out awareness campaigns and community network members conduct daily visits to clients to follow up on referrals. The high number of cases referred by community network members to the MOHSW counselors indicates the high levels of coordination between the two groups, as well as the increased acceptance and use of psychosocial support networks within the communities. Toward the end of the program, six of the community networks participated in lessons learned focus groups. Topics included their psychosocial knowledge, their ability to engage in a comforting and confidential manner with the clients and questions and challenges they encountered. Focus group discussions were held with members of the community networks to: Gauge the knowledge of the project beneficiaries on the quality of training, counseling and awareness sessions, and peace building aspects they had received so far. Verify the impacts of the project in the communities; identify lessons learned and challenges encountered in the implementation of the project. Below is a table of discussion locations, dates, and participants. For each group, members of the community networks were the participants of the discussions. # Location Activity Date M F Total 1 Gbarbga Town Focus Group Discussions 14/09/10 5 2 7 2 Totota Town Focus Group Discussions 15/09/10 6 2 8 3 Gbaye Town Focus Group Discussions 16/09/10 8 0 8 4 Zeewhor Focus Group Discussions 17/09/10 6 0 6 5 Bensonville Town Focus Group Discussions 20/09/10 6 2 8 6 Kpalleh Town Focus Group Discussions 21/09/10 4 4 8 Totals 35 10 45 Findings: From the responses recorded during the course of the discussions, ARC discovered that over 50% of the respondents had knowledge on what was covered in training, counseling and awareness, and peace building – the three topics covered in the discussions. The groups main strength was awareness raising in the communities assigned. In addition to this, 80% of the respondents were able to answer questions on trauma and mental health. Initially, the average network members had the enthusiasm and drive to work in the communities. Now however, it is estimated that approximately 35% have become inactive due to the lack of stipends. Some of those who became inactive were replaced. The issue of stipends was addressed by the facilitator by thanking them for their contributions and making clear that that the job they are doing is purely voluntary and to benefit their own communities. Community awareness campaign at county level. Community awareness and sensitization was conducted in all twenty-one network areas in October 2009. The series of one-day trainings was held from October 31 to November 5 for all twenty-one networks with a total of 210 network members participating. The awareness was conducted by ARC and MOHSW staff on the dates and in the locations in the table below. Date District Community # of People Reached Total Male Female October 29, 2009 Jorquella Samay 35 65 100 Janyea 44 75 119 Gbarnga 58 143 201 October 30, 2009 Salala Totota 28 43 71 Murmue 33 52 85 Salala 111 158 269 October 31, 2009 Suakoko Gbatala 43 28 71 Phebe 52 33 85 Zeazue 15 42 57 November 2, 2009 Kakata Lakayta 14 66 80 Gbaye Town 21 33 54 Kakata 39 55 94 November 3, 2009 Mamban Kaba Zeawoi 13 33 46 Dolo Town 68 77 145 Marshall 15 38 53 November 4, 2009 Careysburg Careysburg 28 33 61 Bensonville 30 39 69 Harrisburg 27 38 65 November 6, 2009 St. Paul Clay Ashland 56 77 133 Banjor 45 54 99 Kpallah 78 106 184 Total 7 districts 21 communities 853 males 1288 females 2141 2 day refresher Training for 9 MOHSW County staff and 28 MOH district staff and 3 County Health staff in psychosocial counseling. ARC conducted refresher trainings for the MOHSW staff approximately every 8 weeks in the program until August 2010 when the MOHSW took the lead role of training. Pre- and post-tests were conducted to determine the effectiveness of the training. Overall the average gain in knowledge from the pre- and post-tests was 25.59%. Scores by Location Total Average Change Bong (pre) Bong (post) Bong Gain Margibi (pre) Margibi (post) Margibi Change Mont. (pre) Mont. (post) Mont. Change Average 39.17 69.43 30.26 52.01 75.53 23.52 56.83 79.83 23 25.59 The objective of the refresher training was to bolster and test the knowledge of the MOHSW caseworkers on previous training in psychosocial and GBV topics. Below are the topics covered through refresher courses: Overview of health, mental health, mental illness Traumatic events, causes and responses War trauma and its effects Understanding and working with grief Crisis and crisis intervention Problem solving Referral pathway Vicarious trauma /self-care All trainings were conducted in an interactive manner with group work and role plays being the hallmark of the training. In the second quarter of 2010, MOHSW took the lead in conducting the refresher trainings with support and supervision provided by ARC. It was observed by ARC that the MOHSW trainers had greatly improved their ability to conduct thorough, well-understood and inclusive trainings. They became better at facilitating discussions and incorporating group presentations rather than simply lecturing. Workshop energy levels were consistently high due to the introduction of a set schedule and respect for opinions and speakers. ARC also observed that counselors demonstrated a strong understanding of the materials. They had mastered the necessary referral pathways and they could explain the intricacies and importance of psychosocial work in an easily understandable manner. Additionally, a two-day GBV training workshop was conducted for MOHSW and ARC counselors and trainers at the end of March 2010. This training brought together 30 participants from both the agencies. The training was conducted by the ARC National GBV Coordinator and two of the ARC GBV trainers. The objectives of this training were to give the participants a comprehensive overview of SGBV and counseling techniques for survivors of SGBV. The following topics were covered during the training workshop: Framework for a session Sex vs Gender Power, use of force, consent Human rights Survivors and perpetrators Types of GBV (SEA, Rape, DV) GBV and the law in Liberia Causes and contributing factors Prevention strategies After effects/consequences Response services Improving procedures for reporting and referral Improving interagency coordination Documentation 100 copies of BCC material developed and distributed to the MOHSW county staff. ARC’s Gender Based Violence Coordinator led a BCC workshop for Monrovia based ARC and MOHSW staff on September 24, 2010. The day-long workshop focused on the creation of taglines and images to increase knowledge of referral systems and encourage under-represented demographics to take advantage of the psychosocial counseling. ARC worked with a local artist to develop images to accompany the selected messages. The artist developed four illustrations to display on posters in the communities. The posters were taken to the communities for testing before final printing and distribution. Following a successful test, the posters were mass printed and distributed among the communities in October 2010. Counselors reported seeing an increase in clients following the distribution of materials. The BCC materials included messages that were based on the counselor and community networks suggestions. The messages incorporated topics that were focused on during training as well as topics that were brought up during counseling sessions. The four messaged developed for distribution were: rape, torture, worrying, and burnt houses. Each of the posters encouraged people suffering to go to the clinic and find a counselor. Business management training and start-up of selected micro-enterprises including grant disbursement. The following were strategies employed by the micro enterprise development program to enhance its implementation: Preliminary Assessment MED Trainings MED Client Baseline Database System MED Clients Follow-Up Evaluation The preliminary assessment of clients referred to the MED team by ARC and MOHSW caseworkers was geared to verify and ascertain whether clients referred to the program had been undergoing counseling and had active case files. Coordinating the MED activities with MOHSW case workers was a vital tool used to get all MOHSW staff and community support project actors involved in the implementation of the MED program. Coordinated activities included: Preliminary intake of MED clients was coordinated through joint referral by ARC and MOHSW case workers. All MED trainings were conducted with a joint support with MOH trainers, facilitators and caseworkers in inter-sectoral collaboration. An overview and strategies briefing on the MED program was held at the MOHSW. The MED training was geared to provide clients training in basic business skills to enable them to run profitable businesses and take care of their basic needs. The first phase MED training was conducted from April 12 to May 8, 2010 and the second phase from August 27 to September 4, 2010 in Bong, Margibi and Montserrado counties with the following basic business skills topics covered: Costing Marketing Market research Business and financial planning Basic record keeping Banking During the first phase of basic business and income skills trainings 295 clients (264 female, 31 male) received basic business skills management trainings in Bong, Margibi and Montserrado counties. During the second phase training, 150 MED clients (135 female, 20 male) received basic business skills management training. Prior to disbursement of the grants, each client was requested to open a bank account while ARC provided assistance. Following an in-depth verification exercise to determine the eligibility of the clients, the disbursements were directly deposited into their accounts. Below is the breakdown of the total case load of MED clients trained: County District Network location Male Female Total BONG Joquelleh Gbarnga 2 43 45 Janyea - 11 11 Samea - 12 12 Total 2 66 68 Salala Totota 2 12 14 Salala 1 14 15 Mamue 1 7 8 Total 4 33 37 Suakoko Phebe - 20 20 Zenzue 2 6 8 Gbatala - 11 11 Total 2 37 39 Bong total 8 136 144 MARGIBI Kakata Kakata 4 20 24 Lakayta 2 19 21 Gbaye Town 4 13 17 Total 10 52 62 Mambakaba Zeewhor 7 18 25 Dolo Town 6 16 22 Marshall 1 20 21 Total 14 54 68 Margibi total 24 106 130 MONTSERRADO Careysburg Careysburg 8 29 37 Bensonville 4 42 46 Harrisburg - 6 6 Total 12 77 89 St. Paul River Banjoh - 17 17 Kpallah 3 41 44 Clayashland 5 21 26 Total 8 79 87 Montserrado total 20 156 176 GRAND TOTAL 52 398 450 Percentage 12% 88% 100% The teams conducted follow up surveys eight weeks following the distribution of the first tranche of funds. The primary purpose of the survey was to ensure the grant was used for the intended purpose. The surveys also asked questions about savings, standards of living, etc. Round 1 MED Client Follow - Up Survey: The round 1 MED client follow up survey in Montserrado, Margibi and Bong counties was conducted from October 28 - November 16, 2010 with 277 clients interviewed across the three counties. Out of the 277 clients interviewed, 269 were eligible for the second grant, 8 misused the grant and 18 were absent due to relocation. Breakdown of round 1 MED client interviewed during the impact survey Counties Total case load Caseload interviewed Absentees Misused Of grant Clients eligible for full grant Montserrado 140 127 13 8 misused the grant from the 277 interviewed 269 Margibi 55 53 2 Bong 100 97 3 TOTAL 295 277 18 Percent 100% 94 % 6% 3% 91% Round 2 MED clients follow up survey: The round 2 MED client follow up survey in Montserrado, Margibi and Bong counties was conducted from December 13 - 18, 2010 with 125 clients (18 male, 107 female) interviewed across the three counties. All of the 125 clients interviewed were eligible for the second grant while 21 were absent due to relocation. Breakdown of round 2 MED clients interviewed during the impact survey: Counties Total case load Caseload interviewed Absentees Misused of grant Clients eligible for full grant Montserrado 34 28 6 None 125 Margibi 74 60 14 Bong 38 37 1 TOTAL 146 125 21 Percent 100% 86% 14% 0% 86% Disbursements of the total grant (first and second tranche) went into the established bank accounts of 420 MED clients (49 males, 371 female). Below is the overall disbursement statistics: GROUP # OF CLIENTS TRANCHE AMOUNT DISBURSED 1st Group 295 1st tranche $1,032,500.00 LD 269 2 tranche $941,500.00 LD Sub total $1,974,000.00 LD 2nd Group 146 1st tranche $511,000.00 LD 125 2nd tranche $437,500.00 LD Sub total $948,500.00 LD Grand Total 420 $2,922,500.00 LD As a result of the MED training conducted, local micro grant clients are practicing and effectively using concepts learned from the business training such as good marketing approaches, basic collection of market information, record keeping and banking as basic income allocations tool to grow their businesses. Entrepreneurial opportunities through training and start-up kits The skills training portion of the MED program was begun by selecting clients and collecting quotations for providers of the one month skills training. Community based trainers were hired through a vetting process to implement the training. ARC conducted an audit of the client list and the skills trainers with their facilities and quotations. Following the results of the audit, the list of client beneficiaries was reduced to 55 – mainly due to many beneficiaries receiving double benefits (also having benefited from the small grants) and locations where no training facilities were sufficient or clients were not able to reach qualified facilities. Additional locations were eliminated as many of the selected clients were engaged in fishing and unavailable for the training. MED skills training took place in Montserrado and Margibi counties for 55 clients (7 male, and 48 female) referred by the psychosocial case workers. Skills included baking, tie-dying, soap making, and hair dressing. Each participant received start-up assets to begin practicing their new trade upon completion of the training. Below is a breakdown of activity skills training clients: County Network Locations Male Female Total Montserrado Banjor - 7 7 Clay Ashland 1 5 6 Kpallah 1 18 19 Margibi Dolo Town 1 13 14 Zeewhor 4 5 9 Total 7 48 55 Percentage 13% 87%

IV: Future Plans: Though the project final date is over, there is a great need to continuation of the Psychosocial and Community support services within the communities.

End of Report: