# Liberia Peacebuilding Fund

# 3rd Quarter Status Report July-September 2010

| Recipient UN Organization: | UNDP | PBF Priority Area: To Promote peace and resolve conflicts | Priority Area 2: Critical Interventions to promote peace and resolve conflicts |
| --- | --- | --- | --- |
| Implementing Partner(s): | YMCA, LNP, UNMIL, Ministry of Transport, Bureau of Immigration and Naturalization |
| Project Number: | 00071058 (PBF/LBR/D-5) |
| Project Title: | Supporting Peaceful Reintegration of High Risk Youth into their Communities through Facilitating Rural Transport Livelihood Opportunities. |
| Project Objective & Scope | To enhance the socio-economic reintegration of high risk youth operating informal transport services (motorcycles) To promote mechanism for resolving conflict among motorcycle riders, communities and Police To ensure motorcyclists receive training on highway Codes and other safety measures in compliance with rule of law while riding thereby promoting human safety and properties |
| Total Approved Project Budget | US$ 250.000.00 |
| Funds Committed: | US$ 250,000.00 | Percentage of Approved: | 100% |
| Funds Disbursed: | US$ 143,383.00 | Percentage of Approved: | 57% |
| SC Approval Date: | 22nd March 2009 |
| Expected Project Duration: | 18 month | Forecast Final Date: | 2010 | Delay (Months): | n/a |

| Outputs: | Progress: | Percentage of planned: |
| --- | --- | --- |
| Motorcyclist mobilization meetings and technical training meetings held in target areas | 6 motorcyclist mobilization meetings held in three target areas/locations Increased involvement and participation by stakeholders in project communities | Completed |
| Leadership training workshops conducted with bike rider associations codes of conduct developed | 2 two days leadership training workshops for bike riders and union officials conducted. A Standard Operational Procedures (SOP) for bike riders associations developed. The SOP is functional and is being used as a relevant tool for guiding riders’ conducts | Completed |
|  | seven days technical training sessions held with 855 motorcyclists | Completed |
|  | Codes of conduct along with provisional requirements for admission to bike riders associations developed | Completed |
| Conflict management, problem solving and advocacy trainings conducted | 2 one-day conflict management/ problem solving and advocacy trainings with unions’ leaders and bike owners conducted. The training aimed at generating greater interactions/dialogue among Union leaders, bike riders and bike owners | Completed |
| Media and outreach activities to raise public awareness established | 2 local radio stations and 3 print media hired to raise public awareness and support to reintegration and peace-building in project communities | Completed |
| System with visibility and safety standards improved | To increase access to safety, 3 radio stations were hired to transmit basic road safety standards and messages in local vernaculars | Completed |
| Communication and peaceful conflict resolution enhanced. | 855 reflector jackets with riders tracking numbers produced and distributed. | Completed |
| Technical Committee Meeting in Monrovia | 4 technical committee meetings held Monrovia Information sharing enhanced and strengthened | Completed |

| Outcomes: | Progress: {In terms of Indicators} | Comments/Remarks: |
| --- | --- | --- |
| Well-organized mode of transport with safety standards and respect for traffic rules established and operational | This is leading to increased access to peace officers and community leadership structures by bike riders to amicably settle disputes as opposed to violence. The exercise is also navigating towards reduced incidences of accident rates and conflicts among riders and the public. This is evidenced by the improved relationship now existing among project beneficiaries and the public. | Relationship between enforce traffic relations still riders, passengers and communities continues to progressively improve. However, Feedback regarding female passengers’ refusal to wear helmets and the inability of officers to remain a challenge. |
| Improved coordination and control mechanism of bike riders Unions and membership development up scaled | This exercise has evidently accelerated public confidence in motor cycle riders. For example, Feedback from the field indicates that passengers now feel more secured to ride with uniformed riders than those without vest or uniforms. Management structures of the various unions have also been enhanced which is rapidly leading to improved relationship and co-existence among riders on the one hand and the public and communities on the other hand. Also due to improvement in management structures of the unions, more riders are taking membership with the unions. | 3 motor cycles unions capacity were built/enhanced. Of the 3 unions, Kakata and Gbarnga are proving to be success stories. Unions currently provides follow up supports to its members through meetings and field visits |
| Communication and peaceful conflict resolution enhanced | Interactions and co-existence among riders and, communities and the public have been enhanced |  |

Qualitative achievements against expected results:

At a macro level, the reintegration of beneficiaries of the project into the mainstream of societal and economic lives have accelerated and up scaled peaceful co-existence in communities where they live. As a result of training received, Motor cycle unions are strategically involved at every level of project implementation. Due to improvement in communication and coordination among stakeholders including police officers, riders and passengers, incidences of community fracas and clashes have reduced considerably. The various training components such as the psychosocial and peace building sessions continue to serve as an impetus in leveraging community buy-in and restoring hope and confidence once again in the riders. This aspect of project activity has also led to massive reduction in the number of traffic accidents and confusion involving motor cycle riders and passengers in project communities.

Challenges{If Necessary}:

The critical challenge currently being experienced is the unavailability of licenses for 855 participants of the project. The continuous lack of licenses for beneficiaries has a potential to undermine the progress/success of the project. This aspect of the program is very important and needs urgent redress.