LIBERIA

Supporting Peaceful Reintegration of High Risk Youth into their Communities through Facilitating Rural Transport Livelihood Opportunities

Progress Report

# April 1 – June 30, 2010

# Peace Building Fund

Wilfred Gray Johnson, Executive Director, PBF Office, MIA

_________________________

# Monroe Outland

# Programme Focal Point

_________________________

# John K. Walker

# ARR Pro Poor Growth Pillar

# Liberia Peace Building Fund

# 2ND Quarter Status Report April - June 2010

| Recipient UN Organization | UNDP | PBF Priority Area: To Promote peace and resolve conflicts | Priority Area 2: Critical Interventions to promote peace and resolve conflicts |
| --- | --- | --- | --- |
| Implementing Partner(s) | YMCA, LNP, UNMIL, Ministry of Transport, Bureau of Immigration and Naturalization |
| Project Number | PBF/LBR/D-5 (00071058) |
| Project Title | Supporting Peaceful Reintegration of High Risk Youth into their Communities through Facilitating Rural Transport Livelihood Opportunities. |
| Project Objective & Scope | To enhance the socio-economic reintegration of high risk youth operating informal transport services (motorcycles) To promote mechanism for resolving conflict among motorcycle riders, communities and police To ensure motorcyclists receive training on highway codes and other safety measures in compliance with rule of law while riding thereby safe guarding lives and property |
| Total Approved Project Budget | US$250.000.00 |
| Funds Committed | US$250.000.00 | Percentage of Approved | 100% |
| Funds Disbursed | 143,383.00 | Percentage of Approved | 57% |
| SC Approval Date | 22nd March 2009 |
| Expected Project Duration | 18 month | Forecast Final Date | 2010 | Delay (Months) | n/a |

| Outputs | Progress | Percentage of planned |
| --- | --- | --- |
| Motorcyclist mobilization meetings and technical training meetings conducted in identified areas | 3 motorcyclist mobilization meetings conducted in Kakata Increase stakeholders involvement and participation in trainings and meetings | Completed |
| Leadership training workshops conducted with motorbike rider associations codes of conduct developed | 2 days leadership training workshop for motorbike riders and union officials conducted Standard Operational Procedure (SOP) for motorbike riders associations developed SOP functional and being used as a relevant tool for guiding motorbike riders’ conducts | Completed |
|  | 7 days technical training sessions held with 188 motorbike riders | Completed |
|  | Codes of conduct along with provisional requirements for admission to motorbike riders associations developed | Completed |
| Conflict management, problem solving and advocacy trainings conducted | 2 days conflict management/ problem solving and advocacy training for motorbike unions’ leaders and motorbike owners conducted Training conducted to generate greater interactions/dialogue among motorbike union leaders, motorbike riders and motorbike owners | Completed |
| Media and outreach activities to raise public awareness established | 1 local radio station and one print media (newspaper) hired to raise public awareness as well as support reintegration and peace-building in communities | Completed |
| System with visibility and safety standards improved | Stickers on motorcycles and safety helmets carried on beneficiaries’ motorcycles for public awareness Liberia National Police enforced safety rules and regulations | Completed |
| Communication and peaceful conflict resolution enhanced | Peaceful approaches and coordination channels communicated to participants during training sessions and benefits of peaceful co-existence emphasized | Completed |

| Outcomes | Progress {In terms of Indicators} | Comments/Remarks |
| --- | --- | --- |
| Well-organized mode of transport with safety standards and respect for traffic rules established and operational | Level of engagement between police and motorbike union leaders on traffic, safety and welfare issues for motorcyclists enhanced Traffic related accidents involving commercial motorcycle riders reduced substantially as a result of on-going motorbike riders’ training exercises | Female passengers do not like wearing safety helmets |
| Improved coordination and control mechanism for motorbike unions and membership scaled-up | - Numbering of vests makes tracking of violators of motorcycle accidents easier - Coordination amongst motorbike unions improved as a result of union’s members participation in training sessions - Problem solving skills and relationship building skills improved amongst local motorbike unions after training sessions | Of the three motorbike unions, Kakata and Gbarnga are proving to be more successful in terms of coordination and leadership – i.e. follow up supports to its members and meetings and field visits |
| Communication and peaceful conflict resolution enhanced | Improved structural relationship between motorbike unions and law enforcement agencies on violations and/or crimes involving motorcycle union members |  |

Qualitative achievements against expected results

The reintegration and mainstreaming of motorbike riders in communities’ activities have positively enhanced relationship between the motorbike riders and various communities. Essentially, the various training sessions comprising psychosocial and peace building have greatly contributed in transforming the minds/attitudes of the motorbike riders and leadership of motorbike unions. These exercises have also built the capacity of motorbike riders/motorbike unions enabling them understand the basic traffic rules and regulations of motorbike riding. Overall, the outcomes of these exercises have resulted into effective communication and coordination particularly among police officers, motorbike riders and passengers, thus substantially reducing the level of community fracas and clashes.

Challenges{If Necessary}

One of the most disturbing issues affecting project implementation is inadequate resources to procure licenses for the 855 motorbike riders. However, UNDP-Liberia has agreed and authorized the redeployment of US$15,000 from its core funds to facilitate the procurement of some of the licenses. Even so, there is a need to mobilize resources to make up for the balance of US$7,500. It can be recalled that immediately after the launch of the project (September 2009), the Ministry of Transport informed the YMCA of a new price structure of US$25.00 for commercial motorcycle operators’ license as opposed to the original price of US$10.00. It is conceived that the inability of the project to secure licenses for motorbike riders could pose a potential danger to the successful implementation of the project and possibly, it would seriously undermine/impede project implementation. It is therefore imperative to urgently address the remaining budget shortfall of US$7,500 for the purchase of licenses.

| NATIONAL COUNCIL/YMCA OF LIBERIA |  |  |  |
| --- | --- | --- | --- |
| UNDP/YMCA SUPPORTING PEACEFUL REINTEGRATION OF HIGH RISK YOUTHS |
| FINANCIAL REPORT FOR THE PERIOD SEPTEMBER 1, 2009 - JUNE 30, 2010 |  |
| Budget Items | Budget | Expenditure | Variance |
|  |  | July 1, 09 - June 30, 10 |  |
| Contract |  |  |  |
| Liberian National Police | 2400 | - | 2,400.00 |
| Federation of Liberia Youth | 1200 | - | 1,200.00 |
| Motorcycle Union | 5000 | - | 5,000.00 |
| Training | - | - | - |
| Training & Empowerment | 60,000 | 24,607.55 | 35,392.45 |
| Behavioral Change/ Peace | 27,000 | 7,000.00 | 20,000.00 |
| Comm Relationship Center | 24,000 | 5,838.68 | 18,161.32 |
| Transportation | - | - | - |
| Fuel | 36,000.00 | 18,129.00 | 17,871.00 |
| Vehicle Maintenance & Spares Parts | 18000 | 5,107.00 | 12,893.00 |
| Supplies and Commodities | - | - | - |
| Food | 24,000.00 | 19,655.00 | 4,345.00 |
| Equipment | 0 | - | - |
| Identity Materials | 10000 | 6,220.00 | 3,780.00 |
| Safety Equipment | 20,000 | 48,500.00 | (28,500.00) |
| Equipment - Other | - | 1,100.00 | (1,100.00) |
| Monitoring & Evaluation | 1,300 | 550.00 | 750.00 |
| Miscellaneous / Communications | 3,600 | 2,227.25 | 1,372.75 |
| BANK CHARGES | - | 1,503.83 | (1,503.83) |
| Total | 232,500.00 | 140,438.31 | 92,061.69 |