ANNEX 4.1

# Liberia Peacebuilding Fund

# QUARTERLY STATUS REPORT AS OF June 2010

| Recipient UN Organization: | UNHCR | PBF Priority Area: | Fostering National Reconciliation and Conflict Management |
| --- | --- | --- | --- |
| Implementing Partner(s): | Liberia Peacebuilding Office (PBO) |
| Project Number: | PBF/LBR/D-10 |
| Project Title: | Small Grants to Support Initiatives for Peace Consolidation in Liberia |
| Total Approved Project Budget | 462,606.00 USD |
| Funds Committed: | 387,202.00 USD | Percentage of Approved: | 84% |
| Funds Disbursed: | 309,761.60 USD | Percentage of Approved: | 67% |
| SC Approval Date: | 1 December 2009 (Fund transfer date 11 Dec 2009) |
| Expected Project Duration: | 12 months | Forecast Final Date: | 31 December 2010 | Delay (Months): | 8 months |

| Outputs: | Progress: | Percentage of planned: |
| --- | --- | --- |
| PBO staffed with a finance assistant and equipped with office materials. | The project was able to recruit an experienced finance assistant and he started to work from 1 June 2010. For the first few months, UNHCR agreed with PBO that the assistant will spend his time twice a week in the Program Section in UNHCR to have a hands-on training on finance control. UNHCR will continue to provide periodical training and coaching to the assistant to ensure quality of finance management of 15 Implementing Partners (IPs). | - |
| 15 partner organizations awarded sub-contracts | Completed. 15 IPs signed a tripartite Memorandum of Understanding with PBO and UNHCR on 10 May 2010. Subsequently, the first tranche (80% of the total funding) of the grants was disbursed to the partners by the PBO. Most of the Small Grants Project hit the ground running in June 2010. | 100% |
| 15 partners trained in financial and narrative reporting, project management and basic M&E | 4-day training on Project Planning and Management was held from 6 to 9April. 37 persons, including Project managers, project officers and finance officers from 15 IPs participated. Bringing project and finance officers together facilitated better understanding between the cash flow and the field operation among them. | - |
| Monthly status report and quarterly financial report submitted on time to UNHR in compliance with the UNHR procedures | The first monthly narrative report was due on July 7, 2010 but only half of them submitted on time for the month of June. 15 partners are requested to submit a financial report on quarterly basis and first reporting will be early September 2010. The Finance Assistant is now developing the financial reporting format in Excel sheet. | - |
| Network among 15 partners are established and maintained | 15 partners had a first interaction in the training held in April 2010. PBO will convene periodic meetings with 15 IPs and facilitate information exchange, such as good practices and lessons learned among them. | - |

| Outcomes: | Progress: {In terms of Indicators} | Comments/Remarks: |
| --- | --- | --- |
| 75% of 15 partners implementing Small Grants Projects enhanced their technical and institutional capacities within the 12-month duration of the project. | The training held in April 2010 had an immediate positive effect on their knowledge in project management: right after the training, some IPs soon applied the acquired knowledge to improve their project documents, including logframe. | - |
| Improved partnership and coordination amongst peacebuilding efforts and Implementing Partners over a 12-month period. | The training provided the first opportunity to meet together. Through group work and interactive sessions, they were able to identify common issues they are facing in project management /financial control and share their idea on how to tackle with these issues. | - |
| At least 75% of targeted communities live in reconciliation, social tensions reduced and inter-intra community dialogue for peace consolidation increased over a 12-month period. | It is premature to measure the outcomes at this stage. | - |

Qualitative achievements against expected results:

Considering the reporting period is only the first month of the project, the progress in this area is limited.

Challenges:

Half of the IPs have yet to submit the monthly narrative report for June 2010. UNHCR, jointly with PBO will further work to ensure timely reporting. Given that the project locations are geographically expanded, monitoring for IPs where UNHCR field offices are not present is a challenge. Joint monitoring mission with PBO and other Ad-Hoc committee members should be encouraged.