# Liberia Peace Building Fund

# QUARTERLY STATUS REPORT AS OF (October-December, 2010)

| Recipient UN Organization: | UNDP | PBF Priority Area: | 3.3; 3.3.1 |
| --- | --- | --- | --- |
| Implementing Partner(s): | Ministry of Justice , Republic of Liberia |
| Project Number: | PBF/R2//A3/09 (PBF/LBR/E-3_ID00073629) |
| Project Title: | Strengthening the Ministry of Justice in Improving Prosecution Services |
| Total Approved Project Budget | 1, 082,000 USD |
| Funds Committed: | $1, 082,000 USD | Percentage of Approved: | 100% |
| Funds Disbursed: | $1, 071,680 USD | Percentage of Approved: | 99% |
| SC Approval Date: | January 22, 2009 |
| Expected Project Duration: | 18 Months | Forecast Final Date: | September 2010 | Delay (Months): | 4 months |

| Outputs: | Progress: | Percentage of planned: |
| --- | --- | --- |
| 1.Consultant for initial strategic planning recruited Initial training session for MOJ prosecutors’ strategic plan held. 3. Strategic plan drafted and Validated 4. Office space for OTD identified by MoJ and refurbished/ equipped 5. The head of OTD and 2 Assistants recruited by MoJ | 1. Completed 2. Completed 3. Strategic plan being drafted 4. completed 5. The Director of Training and Development has been recalled to her position as serving as Assistant Minister for Corrections and Rehabilitation of the Ministry of Justice for the past three months. | 1. 100% 2. 100% 3. 100% 4. 100% 5. 50% |
| 6.The Office of the Deputy Minister of Justice for Administration and Public Safety (DMA)'s capacity for operational management enhanced, and the development of standards and policies for prosecutors, including a code of conduct/ethics, supported | 6. Procurement of logistics to enhance the DMA’s operational need of the office and hiring of a Director of the OTD completed. Recruitment of consultant to develop code of conduct/ethic for the Ministry in progress. | 6. 75% |
| 7. Prosecutorial training needs and gaps identified by the OTD in a one-day workshop | 7. completed | 100% |

Qualitative achievements against expected results: October –November, 2010

During the 4th quarter under reviewed, follow up evaluation workshop The United Nations Development Programme in collaboration with the Ministry of Justice conducted evaluation forum on courts procedures for district attorneys, City Solicitors and police Investigators. The forum was conducted in Gbarnga City, Bong County from November 28th to 5th of December 2010. The forum brought together sixty participants from selected districts of the 15 counties. It can be recalled that several nationwide in-service- trainings were conducted for district attorneys, city solicitors and other law enforcement officers during the project cycle in 2010. In addition to the forum, a recruitment drive for 2 consultants; to develop comprehensive training package, and develop database for the Ministry of Justice was initiated. Applications were received and are being processed. EVALUATION FORUM IN GBARNGA, BONG COUNTY Participants in working session at the forum Cllr. Augustine Fayiah one of the Facilitators

Flashback during one of the nationwide in- service trainings