# Liberia Peace Building Fund

# QUARTERLY STATUS REPORT AS OF April –June 2010

| Recipient UN Organization: | UNDP | PBF Priority Area: | 3.1, 3.2 |
| --- | --- | --- | --- |
| Implementing Partner(s): | The Judiciary, Republic of Liberia |
| Project Number: | PBF/LBR/E-4 (PBF//R3/A3/09) |
| Project Title: | “Strengthening Public Defense” |
| Total Approved Project Budget | $750,066 USD |
| Project Objective and Scope | Long term war and insecurity has led to the disintegration of the Liberian legal system. Efforts to rebuild the trust of the Liberian people are ongoing by ensuring the rights of suspects, detainees and accused can be respected and provided access and opportunity for free and fair trials. One key area however, has not been adequately addressed: the rights of prisoners and defendants in the legal system. Pre-trial detainees are languishing in jail as a result of poor case management procedures, lack of transportation, and lack of legal representation. It is the responsibility of the Public Defenders’ Office to represent indigents, yet the office is poorly equipped to do so. The Public Defenders’ Office lacks both the logistical support and proper capacity to provide services so desperately needed by unrepresented indigents. While much emphasis has been placed on prosecution of the accused, the defence has not been given similar consideration. A fully functioning and just legal system should place equal emphasis on prosecution and defence and upholding the right to due process. This project duration is 12 months. |
| Funds Committed: | $682,844 USD | Percentage of Approved: | 91.0% |
| Funds Disbursed: | 95,539.75 | Percentage of Approved: | 13.9 |
| SC Approval Date: | January 22, 2009 |
| Expected Project Duration: | 12 Months | Forecast Final Date: | August 2010 | Delay (Months): | 4 Months |

| Outputs: | Progress: | Percentage of planned: |
| --- | --- | --- |
| 1. Identify and recruit a Public Defense Training Coordinator to be assigned with the Judicial Training Institute (JTI) to coordinate the development of a curriculum for training. 2. A comprehensive training manual and program established to train public defender through the Judicial Institute (JI) | 1. Public Defense coordinator has been recruited and the post of curriculum developer advertised. | 100% 50% |
| 3.Office space for 8 public defenders is identified/refurbished | 3. Offices for four public defenders identified and equipments, logistics including 14 pick-up trucks have been handed to Public Defenders. Salaries processed for PDs, Coordinator, PD’s Assistant for 6 months: January to June, 2010 | 100% |
| 4.Public defenders are available and dedicated to represent and protect the legal interest of individuals declared indigents 5. Public Defence monitor recruited to provide oversight monitoring of public defenders alongside the Training Coordinator on a roving basis. | 4. Public defenders have been identified and recruited by the Judiciary and deployed into counties. 5. In line with implementation plan and schedule, the second training was conducted in Monrovia from May 26-27 involving 14 Public Defenders. The objective of these training which were delivered by Counsellors Marcus Jones and Theophilus Gould were to sharpen the skills of Public Defenders in the areas of “Jury Selection and Opening Statement”. This was done in collaboration with the Judiciary Training Institute (JI). | 100% 50% |

| Outcomes: | Progress: {In terms of Indicators} | Comments/Remarks: |
| --- | --- | --- |
| Peace building Impact: An effective and accessible public defence system that underprivileged and economically challenged individuals, though accused of crimes, can rely and trust for adequate legal representation and protecting the right to due process. Key Outcomes: Citizens will have increasing confidence in public defence system and will begin to seek and rely on trained and equipped public defender to have their day in court. | As a result of this project’s intervention/support, Public defenders have increasingly gained confidence in their work triggering an increase in the number of representation on behalf of indigents. However, this progress is minimal and negligible at this stage Citizens now have access to public defenders due to their availability. This is evident by the number of cases being handled by the public Defenders in remote cities in Counties like Lofa, Bong, Grand Gedeh, Grand Kru, River Gee, Maryland and other counties. There are total of 21 public Defenders assigned in the 15 Counties | Access to legal representation by persons accused of crime has improved but the representation is inadequate due to lack of more defenders in these counties. |
| Number of prolong pre-trial detentions in withholding centres and at the Central Prison will decrease. Citizens rights to due process protected with greater appreciation of the cliché – “an accused is deemed innocent until proven guilty | Visitation to courts and prisons have increased in the respective assigned areas of the Public Defenders with the aim of providing legal services for indigent where required. |  |
| ”. A functional, trained and equipped criminal justice system comprising both strong and effective prosecution and public defence system. Citizens develop confidence in the fairness of the criminal justice system and its capacity to respect basic human rights. | The newly recruited Public Defenders are competent and young Law School graduates. Several trainings are scheduled which also match the level of support to improve and strengthen prosecutors. |  |

Qualitative achievements against expected results:

Key Achievements: Second phase of training conducted for Public Defender involving 14 public Defenders and the provision of salaries for the eight public defenders under the project. Additionally, provision of maintenance and repair of vehicles. Training has led to increased skills in providing adequate defences and maintenance of assigned vehicles ensures public defenders are available and able to reach needed clients thereby increasing accessibility and promoting justice. Next Steps: The second set of trainings will be conducted in July 22-23 and October 12-15 2010 respectively. In the same vein, it is expected that the Curriculum developer and a Public defenders’ monitor would be recruited and in place.

Challenges{If Necessary}:

The late start of project implementation activities due to delay in funds being made available will impact heavily on the completion of the project as originally planned. Delay in the submission of narrative and financial reports from national partners and the UNDP procurement processes continue to present some bottlenecks when recruiting and procuring services and logistics

Annex 1 (Additional elements such as photos, list of workshop participants etc

Pictorial of the Public Defenders Training

# Text boxes

Brain storming session by group

Public Defenders in training session

Public Defense Coordinator making remarks at the Training.

Public Defenders in training session