# Liberia Peacebuilding Fund

# QUARTERLY STATUS REPORT AS OF 16th September 2010

| Recipient UN Organization: | UNDP | PBF Priority Area: | Priority Area 3.3 Strengthening State Capacity for Development |
| --- | --- | --- | --- |
| Implementing Partner(s): | Ministry of Justice (MOJ) / Liberia National Police (LNP) |
| Project Number: | PBF/ LBR/ E7 (ID 70887) |
| Project Title: | Enhancing the relationship between the Police and Civilians in Communities |
| Project Objective & Scope | The objective of this project is to improve public trust in LNP and the criminal justice system, increase LNP presence in rural and high crimes areas and enhance community policing (seeking the communities cooperation in identifying and solving crimes problems through training, public awareness, logistics and infrastructural support). |
| Total Approved Project Budget | 750,000 USD |
| Funds Committed: | 750,000 USD | Percentage of Approved: | 100% |
| Funds Disbursed: | 625,000.00 | Percentage of Approved: | 83% |
| SC Approval Date: | April 2009 |
| Expected Project Duration: | 18 Months | Forecast Final Date: | December 2010 | Delay (Months): | Two Months |

| Outputs: | Progress: | Percentage of planned: |
| --- | --- | --- |
| Formalizing of a sustainable mechanism to enable through consultative process the effective development and implementation of crime prevention, public awareness activities in communities | Under this output, the project conducted at least two consultative meetings with local leaders and police officers on the sustainability of gains created by the sensitization campaign held in each of the eleven counties where the community policing countywide awareness and sensitization campaign and the leadership training seminar has been held. As a result of these meetings, a CP meeting group involving a representation of every sector of the community and with the oversight of the local government authority and the police has been established in most communities around the country. These CP groups will have the responsibility of implementing crime prevention awareness at community level. The project also held its regular weekly technical committee meeting with its implementing partners from the MOJ, LNP and UNPOL | 80% |
| National sensitization and awareness campaigns on community policing activities | The Countywide Community Policing awareness campaign has been launched in eleven out of the fifteen counties in Liberia (Grand Bassa, Margibi, Lofa, Grand Gedeh, Sinoe, Maryland, Nimba, River Gee, River Cess, Montserrado and Bong Countie) respectively. | 80% |
| Community Policing Best Practice Retreat | The practical guide manual on community policing which was developed during the two days best practice retreat on community policing for the training LNP officers and community leaders on the practical concept of community policing has been finalized and is awaiting clearance from the Inspector General of the LNP and the commissioner of the UN police in Liberia before publication. | 95% |
| 15 County training seminar for community leaders, LNP patrol, station commanders, MOJ and line ministries | Community Policing training seminar for community leaders, LNP patrol station commanders, MOJ and line ministries held in twelve out of fifteen counties in Liberia(Grand Bassa, Margibi, Lofa, Grand Gedeh, Sinoe, Maryland, Nimba, River Gee, River Cess, Montserrado, Grand Cape Mount and Bong Counties) | 85% |
| Renovation and Equipping of LNP Offices | 11 LNP stations were identified for renovation by LNP, UNPOL and UNDP assessment team to include five (5) police stations located in the leeward counties (Bong County Police HQ, Salala Police Station, Ganta Police Station, Maryland County Police HQ and Gbarpolu County Police HQ) and six (6) police stations located within central counties (Margibi County HQ, Bensonville, New kru Town, Hotel Africa, Grand Bassa County HQ, and Soul Clinic). Renovation is ongoing by UNPOLS | 60% |

| Outcomes: | Progress: {In terms of Indicators} | Comments/Remarks: |
| --- | --- | --- |
| Enhanced capacity of community-police intervention to address root causes of potential conflict at the community level | The capacity of community policing structures in communities strengthened to address conflicts resulting from civil disagreement and disorderly conduct in the community. | N/A |
| Increased citizen trust and cooperation through daily positive contacts with LNP patrol officers | Increase in emergency and non-emergency calls/contacts of citizens with police The launching of the awareness and sensitization campaign is kicked off by a clean-up campaign exercise. The cleanup campaign which is initiated by the officers of the Liberian National Police and members of communities is aimed at bringing the people closer to the police through voluntary community service. The campaign also involves a two days strategic leadership workshop for community leaders, civil society and police officers, a youth tournament, a parade and an indoor program. | N/A |
| Increased quality of life in communities through effective crime prevention strategies | Economic and development activities in communities improving due to confidence and assurance in the security. | N/A |
| Equal access to police for all citizens/communities and Increased quality of life in communities | More police station and depot renovated and police capacity enhance. | N/A |
| Increase awareness created on the roles and responsibilities of citizens in crime prevention and violence reduction | Community policing training conducted for community chairpersons and zonal heads, heads of women and youth organizations, heads of motorcycle and road transport unions and local government and traditional authorities who are in turn expected to share the information acquired with their respective constituent. | N/A |

Qualitative achievements against expected results:

Achievements during the period include the following: In order to ensure 1) LNP ownership of community policing and 2) increase in citizens’ role in information sharing on crime prevention and community security, a community policing leadership training seminar was conducted for police officers, community chairpersons and zonal heads, heads of women and youth organizations, heads of motorcycle and road transport unions and local government and traditional authorities in 12 out of l5 counties in Liberia. The total number of participants trained was 495 (390 males and 105 females) In the drive to increase awareness on the roles and responsibility of citizens in crime prevention, thereby resulting in 1) the decrease in mob violence and vigilantism 2) improved public trust in the LNP and the criminal justice system 3) enhanced citizen/civil society and police cooperation, a community policing awareness and sensitization campaign was launched in 11 counties in Liberia. The launch in each county saw the strong participation of women and youth groups, the marketing association, local and traditional authorities, community leaders, high schools, the community policing forum, the motorcycle and transport unions, the UNPOL site team, the Liberia Football Association and the traditional communicators of the UNMIL Community Outreach Section. To increase police capacity and effective service delivery thereby resulting in the reduction in the number of opportunistic crime perpetrated (robbery, burglary, theft), 11 LNP stations have been identified for renovation under this project by LNP, UNPOL and UNDP assessment team. Stations to be renovated include five (5) police stations located in the leeward counties (Bong County Police HQ, Salala Police Station, Ganta Police Station, Maryland County Police HQ and Gbarpolu County Police HQ) and six (6) police stations located within central counties (Margibi County HQ, Bensonville, New kru Town, Hotel Africa, Grand Bassa County HQ, and Soul Clinic). Renovation is ongoing by UNPOLS

Challenges{If Necessary}:

UNDP procurement and finance policies particularly with regards to the sourcing of three quotations for the purchase of goods and services, pre-financing of goods and services pose significant challenges due to limited infrastructure and business capacities in the remote areas. Inaccessible roads Poor communication network Delay in getting list of participants from LNP county HQ