Peacebuilding Fund

ANNUAL programme NARRATIVE progress report

REPORTING PERIOD: 1 january – 31 December 2010

| Programme Title & Number |  | Country, Locality(s), Thematic Area(s) |
| --- | --- | --- |
| Programme Title: Supporting the Liberia Anti-Corruption Commission Programme Number 00070666 MDTF Office Atlas Number: PBF/LBR/E-8 (PBF/PP/R5/A3/01) |  | Liberia, Nation-wide, Critical Interventions to and Resolve Conflict |

| Participating Organization(s) |  | Implementing Partners |
| --- | --- | --- |
| UNDP |  | Liberia Ant-Corruption Commission |

| Programme/Project Cost (US$) |  | Programme Duration (months) |
| --- | --- | --- |
| MDTF Fund Contribution: U$ 500,000 by Agency (if applicable) |  |  | Overall Duration; 18 months |  |
| Agency Contribution UNDP 25,000 |  |  | Start Date: 22 March 2009 |  |
| Government Contribution (if applicable) |  |  | End Date or Revised End Date, December 31st 2010 (if applicable) |  |
| Other Contribution (donor) (if applicable) |  |  | Operational Closure Date January 2011 |  |
| TOTAL: U$ 500,000 |  |  | Expected Financial Closure Date January 2012 |  |

| Programme Assessments/Mid-Term Evaluation |  | Submitted By |
| --- | --- | --- |
| Assessment Completed - if applicable please attach Yes No Date: __________________ Mid-Evaluation Report – if applicable please attach Yes No Date: __________________ |  | Name: Nessie Golakai Title:Assistant Resident Representative - Governance Participating Organization (Lead):Liberia anti-Corruption Commission Email address:Nessie.golakai@undp.org |

List of Acronyms and Abbreviations

AU………………………………..……………………..............................................………………..African Union

AWP…………………………………………………………….…................................................Annual Work Plan

CENTAL…………………….................................................Centre for Transparency and Accountability in Liberia

CSOs…………………………………….………………….............................................Civil Society Organizations

DEX……………………………………………………………………............................................Direct Execution

ECOWAS……………………….………........................................... Economic Community of West African States

GC………………………………..……................................................................................Governance Commission

GOL...........................................................................................................................................Government of Liberia

GAC…...................................…………………………………………….………….. General Auditing Commission

IMF……………………………………………..….……..........................................…..International Monetary Fund

LACC………………………………………..…..............................................Liberian Anti-Corruption Commission

MIA……………………………………………..….........................................…………. Ministry of Internal Affairs

MPEA………………………………………........................................... Ministry of Planning and Economic Affairs

MOU…………………………………..……………….........................................…Memorandum Of Understanding

MOJ.................................................................................................................................................. Ministry of Justice

NPRS……………………………………………............................................…National Poverty Reduction Strategy

PBF……………………………………………..……..………….…...........................................Peace Building Fund

TOR………………………………………….…………………..….........................................…Terms Of Reference

TRC………………………………………….…….......................................... Truth and Reconciliation Commission

UNDP…………………………………………...........................................United Nations Development Programme

UNMIL……………………………………….…..……..........................................United Nations Mission in Liberia

USAID……………………………...........................................United States Agency for International Development

ULSU…………...................................................................................................University of Liberia Student Union

WONGOSOL……………………………………….. .........................................Women NGO Secretariat of Liberia

# NARRATIVE REPORT FORMAT

# Purpose

- The underlying objective of the project is catalytic, that is, to respond the immediate need of the Commission to achieve functionality as key institution of good governance,

- by investigating allegations of corruption, building operational and public engagement capacity, and deterring corruption. The project, “Supporting the Liberia Anti-Corruption Commission (LACC)” seeks to address the challenges of corruption that threaten peace in  Liberia, by fostering democratic governance—good governance through the establishment of an integrity system in government, to enhance transparency and accountability in the management of state resources and assets. The scope of the project is the fifteen counties of Liberia.

# Resources

Financial Resources:

During the period under review UNDP Liberia made available U$ 25,000 of its core resources to the project to supplement project activities.

Human Resources:

The project was implemented by the Liberia Anti-Corruption Commission through the Office of the Executive Director. The Office of the Executive Director liaises closely with the Board of Commissioners who provided strategic oversight of the project implementation.

# Implementation and Monitoring Arrangements

The project was executed by UNDP utilizing the DEX modality. This means that UNDP will have full responsibility under this modality to ensure accountability, transparency, timely implementation, management and achievement of results. However some programme funds were transferred to the LACC through a Letter of Agreement for implementation, whilst UNDP was responsible for procurement of goods. The LACC was responsible for organizing workshops and recruitment and payment of consultants.

A Project Board comprising the Ministry of Planning as chair; UNDP as co-chair, the Governance Commission, the Liberia Anticorruption Commission (LACC), and the CSOs Advisory Committee was  established.

UNDP provided overall guidance, quality assurance and ensured that the project produced the results specified in the project document, to the required standard of quality and within the specified constraints of time and cost.

The Project Board was responsible for making, on a consensus basis, management decisions for a project when guidance is required by the Project Secretariat, including recommendation for UNDP/ Implementing Partner approval of project revisions.

In terms of direct procurement of goods, a letter of request from the implementing partners with detailed specification formed the basis of procurement request. Based on these request bids were then solicited through Request for proposals or invitation to bids. The Vendor with the best value for money was selected.

The specific mechanisms used to monitor the achievement of results in the annual work plan included:

- Quarterly progress report, technical and financial report prepared by the Project Manager for review by the Project Board and MDTF

- Annual progress report and financial report prepared by the annual work plan implementing agency and/or the ERP Atlas system at the end of the year;

- Quarterly meetings of the Project Board were convened to review progress reports and reports on monitoring visits so as to take necessary actions to ensure the project results are achieved and where possible, recommend a change in implementation strategy.

# Results

- Public Information to Counties: Supported the organization and conduct of public awareness campaigns on anti-corruption in the form of county forums in Cape Mount, Bong, Lofa, Nimba, and Grand Bassa counties ; and distributed Anti-Corruption promotional T-Shirts, Banners at these County Forum;

- Agreement on Collaborative Mechanism - Facilitated the meeting of amongst institutions of integrity; namely the General auditing Commission, Liberian anti-Corruption Commission and Ministry of Justice for enhanced coordination and collaboration in the fight against corruption.

- Incrreased Mobility of investigative Unit - Supported the procurement of one additional vehicle to enhance the mobility of the investigative unit of the LACC

- Memorandum of Understanding with the EFFC of Nigeria - Sponsored working visit and capacity development initiatives for (3) Three LACC’s Executives to the EFFC Nigeria;

# Future Work Plan (if applicable)

N/A project closed.

|  | Performance Indicators | Indicator Baselines | Planned Indicator Targets | Achieved Indicator Targets | Reasons for Variance (if any) | Source of Verification | Comments (if any) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Enhanced functionality of LACC |
| Output 1.1 Functional LACC Secretariat | Indicator 1.1.1 Secretariat fully equipped with personnel and functioning | No functioning Secretariat as Commission was newly established | Procurement of additional vehicle | Secretariat fully equipped and set up | Done | Asset list and on-site inspection | Fully Achieved |
| Output 1.2 Public Awareness and Sensitization | Indicator 1.2.1 Public Awareness such as billboards, flyers et all | Limited knowledge of the LACC its mandate operations and functions | Support Public awareness meetings in remaining 8 counties | County Consultation held in 5 of the remaining 8 , stickers, jingles etc produced | Consultations kicked off late and rainy season prevented deployment to last 3 counties | Public Awreness material, publications, jingles | Fully Achieved |
| Output 1.3 Training and capacity development for LACC staff and other relevant anti-corruption agencies | Indicator 2.1.1 LACC staff and individuals from related agencies trained and capacity adequately developed to be able to function effectively | Limited substantive knowledge on the working and operation of an anti-corruption entity | Train at least 3 LACC persons | 3 staff undertook study tour to Nigeria | Needs at the LACC were great. Additionally parallel projects were providing support to MoJ and GAC. | Training reports MoU with Nigerian EFTC | Partially Achieved |
| Output 1.4 Development of CSOs focused monitoring checklists of the public sector | Indicator 2.2.1 CSO focused monitoring checklist developed, launched and available for use | No governance assessment checklist including transparency index | Draft checklist developed | Checklist not achieved, one CSO working independently with some input from LACC and the Governance Commission | No consensus with CSOs on how to move ahead | Final checklist | Not Achieved |
| Output 1.4 Relationship with other anti-corruption agency | Letter of agreement on collaboration modalities | Unclear coordination mechanism between the Auditing Commission and LACC | MoU between LACC, MoJ and GAC | Minuted agreement between LACC, GAC and MoJ on how best to work together | No formal agreement was possible | Minutes of consultations, meetings, MoU between GAC and LACC | Achieved |

# Footnotes

The term “programme” is used for programmes, joint programmes and projects.

Priority Area for the Peacebuilding Fund; Sector for the UNDG ITF.

The start date is the date of the first transfer of the funds from the MDTF Office as Administrative Agent. Transfer date is available on the MDTF Office GATEWAY (http://mdtf.undp.org).

All activities for which a Participating Organization is responsible under an approved MDTF programme have been completed. Agencies to advise the MDTF Office.

# Text boxes

VI. INDICATOR BASED PERFORMANCE ASSESSMENT