SIERRA LEONE

PEACEBUILDING FUND

PROJECT STATUS REPORT

30 JUNE 2011

| Project No & Title: | PBF/SLE/C-2 Support to the Implementation of the Reparations Program as part of the Recommendations of the Truth and Reconciliation Commission. |
| --- | --- |
| Recipient UN Organization: | IOM | Priority Sector: | Democracy and Good Governance |
| National Authority: | National Commission for Social Action (NaCSA) |
| Location: | Nationwide |
| Project Cost: | USD 450,000 |
| SC Approval Date: | Dec 2010 | Starting Date: | January 2011 | Completion Date: | September 2011 |
| PBF Outcome priority area | Priority 2. Good governance and national reconciliation. Outcome 2 (PMP): Conflicts resolved peacefully and in a manner that supports the coexistence of all relevant actors/groups that were involved in conflicts that undermine peace building efforts Indicator UNJV: # of reparation victims who have received reparation benefits and using these to regain their dignity |
| Project Description: | There is a compelling need to urgently provide remedies to those persons identified by the TRC as victims of the war. The project continues the delivery of reparation to registered war victims. It will provide interim cash assistance, micro grants and emergency medical services to approximately 2,223 war victims based on vulnerability and needs assessment. It is envisaged that the success of this program will invaluably contribute to national reconciliation and enhance the peace consolidation process. This fulfils Government’s legal obligation in the Lomé Peace Agreement of 7th July 1999. |
| Immediate Objective: | NaCSA Reparation Directorate supported for continued delivery of reparation services. Registered caseload is reviewed and analyzed to develop: A) a clear policy for the delivery of benefits based on vulnerability criteria; B) a clear sustainability strategy on benefit delivery for different victim’s category Benefits are delivered to a number of war victims in line with benefit policy and vulnerability criteria. The phasing out strategy and the available resources to the second phase of the program will also guide the benefit delivery process. Reparations Directorate advocates to sensitize the Government of Sierra Leone on matters related to the sustainability of the reparation programme. |
| Project Status as of June 2011 |
| Funds disbursed: | USD 386,555.75 |
| Delivery rate: | 85.9% |
| Outputs delivered: | Caseload for potential beneficiaries were verified Reparations micro grants were paid to a total of 2,310 war victims out of a residual case load of 12,003. 1138 of these are Amputees who were not part of the residual case. NaCSA continues to provide medical assistance to 20 extremely vulnerable/emergency cases ID cards printed for 1,138 Amputees and 1172 VSV and war wounded verified from residual case. NaCSA continues to hold with the Ministry of Agriculture and food Security, the National Social Security and Insurance Trust (NASSIT) to include/mainstream war victims in their programmes. NaCSA continues to engage potential contributors to the Trust Fund for war victims. The Reparations Directorate continues to provide administrative and technical support to the Reparations process. |
| Achievements and challenges | Output delivery: The Directorate has successfully been able to prioritize critically vulnerable war victims to benefit from reparations payment using limited resources provided by the UN-PBF. Victims have been able to receive a second tranche of reparation micro grants meant to provide seed capital that will transform the lives of victims. A new drive that will contribute to the sustainability of the programme by mainstreaming it into key Government components is beginning to be discussed. Id card system has been designed as a way of verifying victims as potential beneficiaries of subsequent forms of reparations either through the social security scheme or otherwise. Outcome achievements (with reference to programme results and indicator of PMP): The second provision of payments to victims drives the total number of beneficiaries to 21,317 out of a total number of 32,100 victims that were initially registered and put on the database of the reparations program. This drives the total percentage of beneficiaries to 66.4% of total war victims. The Amputees and other war victims continue to record changes in their livelihoods as most used payments not only to pay school fees for their children but also to invest in small scale businesses in support of their families. One victim confessed “before this payment, I used to beg in the streets but now, I use proceeds from my business to take care of my family; I am beginning to regain my dignity”. The main challenge is the insurmountable number of victims as against available resources may in the future pose a security risk. Over 40% of victims are yet to receive any kind of reparations. |