**Peru**

|  |  |
| --- | --- |
| **Programme Title:** | Improving Nutrition and Food Security for the Peruvian Child: a Capacity Building Approach |
| **Programme number & MDTF ref:** | MDGF-2024-I-PER Children (67248) |
| **Window:** | Children, Food Security & Nutrition |
| **Approved Budget by NSC (US$):** | 6 million |
| **Participating Organizations:** | PAHO/WHO, WFP, FAO, UNODC, UNICEF |
| **First Tranche transferred on:** | 25-Nov-2009 |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:** |
| A model for health interventions at the family level underway. A model for integral health attention has been completed. Community level grass roots training on nutrition underway. Enhanced coordination with MoH substantive technical assistance for formulation of model for primary health attention. Founding partner of Results-Based Budget Group with participation of Ministry of Finance, Mesa de Concertación de Lucha contra la Pobreza, among others.  Implementation of adaptedECAs in Loreto due to UNODC – FAO joint action. |
| **Problems and lessons learned:** |
| * UN Agency coordination. Differences in managerial, administrative, HR procedures among participating UN Agencies. * Electoral period at regional level – high rotation of public servants / need to restart advocacy campaigns. * Weak articulation of three levels of government – need for enhancement of management capacities at regional and local levels. * Opportunity for further integration of EN CRECER in regional governments. * Tardiness in implementation of M&E strategy, including baseline. |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** Yes |

CHARTS& FIGURES

As of 31 December 2010

