**Peru**

|  |  |
| --- | --- |
| **Programme Title:**  | Integrated and adaptive management of environmental resources and climatic risks in High Andean micro-watersheds |
| **Programme number & MDTF ref:** | MDGF-1691-E-PER Env Climate (67154) |
| **Window:** | Environment & Climate Change |
| **Approved Budget by NSC (US$):** | 3.9 million |
| **Participating Organizations:** | PAHO/WHO, UNDP, UNEP, FAO |
| **First Tranche transferred on:** | 26-Sep-2008 |
| **Second Tranche transferred on:** | 22-Feb-2010 |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:** |
| Training programme for local government employees and community leaders completed. Adaptation plan for climate change currently under validation. Creation of a water governance platform underway. Training provided to organizations managing local water and sanitation schemes completed. Study on climate change and socio-economic conflict finalized.  |
|  |
| **Problems and lessons learned:** |
| UN Agency coordination. Coordination within government External to the JP (local elections).  |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** Yes |

CHARTS & FIGURES

As of 31 December 2010

