**Peru**

|  |  |
| --- | --- |
| **Programme Title:** | Inclusive creative industries: an innovative tool for alleviating poverty in Peru |
| **Programme number & MDTF ref:** | MDGF-2081-D-PER Private Sector (67264) |
| **Window:** | Development & Private Sector |
| **Approved Budget by NSC (US$):** | 5 million |
| **Participating Organizations:** | FAO, ILO, UNDP, UNESCO, UNIDO, UNWTO |
| **First Tranche transferred on:** | 10-Dec-2009 |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:** |
| Development of JP baseline in process.  Inventory of immaterial heritage in place.  Network development at regional level. |
|  |
| **Problems and lessons learned:** |
| JP has significant delays which are being addressed by the NSC.  Weak appropriation by government counterparts (solved in November 2010) |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** Not reported. Yes. |

CHARTS & FIGURES

As of 31 December 2010

