**Philippines**

|  |  |
| --- | --- |
| **Programme Title:** | Ensuring Food Security and Nutrition for Children 0-2 Years Old in the Philippines |
| **Programme number & MDTF ref:** | MDGF-2030-I-PHL (67249) |
| **Window:** | Children, Food Security & Nutrition |
| **Approved Budget by NSC (US$):** | 3.5 million |
| **Participating Organizations:** | FAO, ILO, UNICEF, WFP, WHO |
| **First Tranche transferred on:** | 19-Nov-2009 |

|  |
| --- |
| **ACTIVITIES Reported:** |
| **Main Substantive Activities:** |
| 74% of funds for 2010 committed. Exclusive breastfeeding activities (EBF) at the national and local level carried out, including launching a photo exhibit on breastfeeding (envisioned to be carried out in different parts of the country in the succeeding months of JP implementation). Organizing of peer support groups for EBF already started. Other EB F actvities for Year 1 (review of human milk bank guidelines in the Implementing Rules and Regulations of RA 10028: Expanded Breastfeeding Promotions Act; orientation of LGUs, media, and other professionals on the Milk Code; and training of monitors on Milk Code monitoring) completed. |
|  |
| **Problems and lessons learned:** |
| Coordination with a local government partner (unresponsive/lukewarm). External to the JP (bomb threats in Zamboanga). |
|  |
| **The programme reports relevant linkage to the UNDAF:** Yes |
| **The programme has communications strategy in place:** Yes |

CHARTS& FIGURES

As of 31 December 2010

