COUNTRY

PEACEBUILDING FUND

PROJECT STATUS REPORT

30 JUNE 2011

| Project No & Title: | PBF/SLE/C-3 Promoting human rights culture through support to the Human Rights Commission of Sierra Leone |
| --- | --- |
| Recipient UN Organization: | OHCHR | Priority Sector: | Good Governance |
| National Authority: | National Human Rights Commission |
| Location: | Country Wide |
| Project Cost: | USD 200,000 |
| SC Approval Date: | Dec 2010 | Starting Date: | June 2011 | Completion Date: | May 2012 |
| PBF Outcome and Priority area | Priority 2. Promoting Co-existence and Peaceful Conflict resolution. Programme Result 2 (PMP): Conflicts resolved peacefully in a manner that supports the co-existence of all relevant actors that are involved in conflicts that undermine peace building efforts. Indicator -:UNJV Enhanced national capacity for the protection and promotion of human rights |
| Project Description: | There has been a continuing trend toward respect for human rights. However, the underlying causes of the conflict have not been fully dealt with, and a number of internal and external human rights challenges identified by the Truth and Reconciliation Commission still remain to be addressed if the prevailing peace and stability is to be consolidated. Low levels of enjoyment of economic, social and cultural rights remain among the biggest challenges, as does internalizing the concepts of the freedom to engage in political activity and tolerance towards differing political points of view. Others include weakness of the justice sector, discrimination against women, child labor, and gender based violence, in particular Female genital Mutilation (FGM). This project intends to continue the support provided to the Human Rights Commission of Sierra Leone in the accomplishment of the eight goals in its 2009-2011 strategic plan, to promote the creation of a human rights culture by increasing HRCSL’s services to the communities as per its mandate and also contribute to the implementation of the TRC recommendations. |
| Immediate Objectives: | Strengthened Capacity of the Commission including its enhanced outreach ( Strategic goal 6) Enhanced capacity of civil society and government on human rights (Strategic goal 7) Enhanced human rights education including through community sensitization (Strategic Goals 4, 2, 5) Human rights situation throughout the country monitored and reported ( Strategic goal 1) Promotion of the rights to equality and non-discrimination ( Strategic goal 4) |
| Project Status as at June 30th 2011 |
| Funds disbursed: | 0.00 |
| Delivery rate: | 0 % |
| Outputs delivered: | None |
| Achievements and challenges | Output delivery: Money has just been transferred from the OHCHR accounts to that of the National Human Rights Commission of Sierra Leone. Outcome achievements (with reference to programme results and indicator of PMP): Explain briefly (4 to 5 short statements max.) -N.A - What has been planned, what has been actually achieved? It was planned that OHCHR be the recipient agent and will provide oversight during implementation. However, the HRCSL emphasized in the spirit of national ownership and top show case their increase in capacity, that the money be paid lump sum into their accounts. This meant that the funds must be converted first to grants which took time for the committee at HQ to meet and decide. - What worked? What did not? Fund management procedure inter earlier set up did not work. - How will the challenges be addressed? By transferring funds directly to the HRCSL. |