Turkey

| Programme Title: | Enhancing the Capacity of Turkey to Adapt to Climate Change |
| --- | --- |
| Programme number & MDTF ref: | MDGF-1680-E-TUR Env Climate (67151) |
| Window: | Environment & Climate Change |
| Approved Budget by NSC (US$): | 7 million |
| Participating Organizations: | UNDP, UNEP, FAO, UNIDO |
| First Tranche transferred on: | 11-Jun-2008 |
| Second Tranche transferred on: | 4-Aug-2009 |
| Third Tranche transferred on: | 30-Sep-2010 |

ACTIVITIES Reported:

Main Substantive Activities:

Stocktaking Analysis for National Climate Change Adaptation Strategy has been finalized, Participatory Vulnerability Analysis carried out, analysis of climate change adaptation in national legislation has been completed and the National Climate Change Adaptation Strategy of Turkey is drafted. Training needs were identified to enhance the capacity to adapt to climate change, and various different capacity development programs were realized. Climate projections based on three global models have been completed. Climate change information portal “agora.itu.edu.tr” has been prepared and complementary to this activity, climate modeling trainings for regional end-users were organized. The eco-efficiency pilot projects, focusing on efficient water use have been implemented in six companies from food, beverage, metal and textile sectors. Flood and drought early warning systems and Environmental Monitoring Information System development processes have been initiated. Seyhan River Basin Stakeholders Analysis, Livelihoods Analysis, Ecosystem Analysis and participatory problem analysis by systems approach were finalized. Filming of the Seyhan River Basin documentary has been completed. All activities of UNJP were shared with general public through several communication activities. (Poster presentation at 5th World Water Forum, panel discussions, participating national initiatives, TV-radio interviews, Climate Change Adaptation chapter in National Geographic special edition on water, Climate Arena meetings, etc.); exit and sustainability strategy and model developed

Problems and lessons learned:

Financial reporting difficulties due to different formats used by the partner UN Agencies; difficulties in distributing joint costs; procurement and disbursement difficulties and different rules used by some of UN Agencies. Lessons learned: (a) the value, add, enhanced development impact and sustainability of the interventions through a vertical linkage among the beneficiaries, the regional governments, agencies and the central state apparatus (b) development of robust models and methodologies for replication; and (c) importance of factoring in sustainability and exit strategy at the design stage of the interventions.

The programme reports relevant linkage to the UNDAF: Yes

The programme has communications strategy in place: Yes

CHARTS & FIGURES

As of 31 December 2010