# United Nations Development Group Iraq Trust Fund

# Project #:  C10-12

# Date and Quarter Updated:  2011-Q1, April 4, 2011

| Participating UN Organisation: UNIDO | Sector: PWG Inclusive Economic Growth |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Iraqi Ministry of Industry and Minerals |

| Title | Enterprise Development through Information and Communication Technologies (EDICT) |
| --- | --- |
| Geographic Location | All districts of Baghdad, Thi Qar and Erbil |
| Project Cost | USD 2,940,000 |
| Duration | 24 months |
| Approval Date (SC) | 02.09.2009 | Starting Date | 10.09.2009 | Completion Date | 10.09. 2011 |
| Project Description | The project is designed to encourage the establishment of small- and medium-sized enterprises (SMEs) in Iraq, and the creation of employment opportunities for Iraqi people through the promotion of domestic and foreign investment in the productive sectors of the economy. The project will build on the resources and success of UNIDO project “Enterprise Development and Investment Promotion for the SME sector in Iraq”. In this regard, the following will be sought: Enhance capacities of Iraqi institutions on providing enterprise development services through the use of information and communication technologies, and Facilitate the creation of new enterprises and increase competitiveness of existing enterprises in order to provide employment and income generating opportunities for the people and to reduce poverty. For these activities, the Ministry of Industry and Minerals in Baghdad, KRG Ministry of Trade and Industry and Thi Qar Provincial Council will serve as counterpart/host institutions. In these regards, the project support government’s efforts in promoting economic development through fostering private sector and UN Development Assistance Framework (UNDAF) outcome on job creation. |

Development Goal and Immediate Objectives

Encourage the establishment/expansion of small- and medium-sized enterprises (SMEs) in Iraq, and the creation of employment opportunities for Iraqi people through the promotion of domestic and foreign investment in the productive sectors of the economy. Enhance capacities of Iraqi institutions on providing enterprise development services with the use of information and communication technology. Facilitate the creation of new enterprises and increase competitiveness of existing enterprise in order to provide employment and income generating opportunities for the people and to reduce poverty.

| Outputs, Key activities and Procurement |
| --- |
| Outputs | Enterprise Development Units (EDUs) have increased capacity to deliver training modules local entrepreneurs. Enhanced capacities of EDUs to provide business advisory services to existing and new enterprises. |
| Activities | Prepare a comprehensive proposal for the revision of Institutional set up in the governorate of Erbil, Baghdad and Thi Qar, Conduct participatory workshops with all stakeholders to present and discuss the proposal. Amend proposal according the results of the workshop. Establish a Project Steering Committee involving the main counterparts to oversee the project activities and advice as necessary. Finalize contract with UNINETTUNO Telematic University Organize kick-off meeting for the endorsement of the project work-plan and institutional set up Carry out assessment of local conditions on ICT status in each governorate, including internet bandwidth, the extent of spread of satellite television, computer literacy among potential beneficiaries, internet usage Carry out a detailed assessment of equipment required to equip and make operational a technological pole within the EDU (by UNINETTUNO) Based on the assessment, procure, install and commission three technological pole for e-learning within the premises of EDU (in each Governorate) (by UNINETTUNO) Create, publish and update on monthly basis a UNIDO dedicated web platform to support e-learning activities (by UNINETTUNO) Adapt UNIDO training material on EDIP and SPX according UNINETTUNO required to be properly broadcasted by Satellite TV and Internet (UNINETTUNO) Distance learning capacity building of 6 counsellors and 6 tutors on UNINETTUNO methodology for remote counselling and tutoring (by UNINETTUNO) Production of 360 hours of UNIDO (EDIP and SPX) training modules by UNINETTUNO (160h of video-lessons and 200h of training materials) Broadcast training course through Internet for 24 months and through satellite TV for 12 months. (by UNINETTUNO) Encourage and promote EDUs on-line service and activities through local business community Official launch of EDU with e-learning component (in each governorate) Organize on-line interactive sessions to consolidate training learning of on-line students Organize on-line counselling sessions to support trained entrepreneurs Monitor enrolment/registration/ course completion of interested on-line and off-line entrepreneurs Organize two classroom Training of Entrepreneurs per Governorate |
|  | Provide business advisory to entrepreneurs and local SMEs (on-line and off-line) through EDU based counsellors Preparation of EDU counselling reports Provide support through business counsellors placed at EDU to entrepreneurs and local SMEs on legal/procedural requirements to start/expand their business Provide continuous mentoring support through international EDIP specialist to EDU`s counsellors and trainers to provide quality services Organize mentoring missions/workshops with EDUs on how to improve efficiency and effectiveness of EDU |
| Procurement | 3 technology poles (for each target governorate), each comprised of 12 computers and video-conference facilities |

| Funds Committed | USD 2,276,330 | % of approved | 77% |
| --- | --- | --- | --- |
| Funds Disbursed | USD 1,010,839 | % of approved | 34% |
| Forecast final date | February 31, 2011 | Delay (months) | 6 |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Men | 81 | 47% |
| Women | 12 |  |
| Children | NA | NA |
| IDPs | NA | NA |
| Others | NA | NA |
| Indirect beneficiaries | NA | NA |
| Employment generation (men/women) | 345 | NA |

| Quantitative achievements against objectives and results | % of planned |
| --- | --- |
| Number of technological infrastructure in place | 3 | 100% |
| Number of training courses recorded | 2 | 50% |
| Number of entrepreneurs (male/ female) trained online | Pending | Pending |
| a. Number of entrepreneurs (male/ female) trained (offline) | 93 | 47% |
| b. Number of offline training courses | 4 | 60% |
| % of trainees (male/ female) passing the training assessment | Pending | Pending |
| Number of counselling reports prepared | 38 | 38% |
| Number of mentoring visits (per EDU) conducted by technical experts to advise EDU staff | 4 | 65% |

Qualitative achievements against objectives and results

While UNIDO has been working with UNINETTUNO, the contractor for the ICT component of the project, to install these technical equipments required to conduct e-learning courses, the EDUs have resumed services that were launched during UNIDO’s recently-closed EDIP programme with some alterations within the framework of EDICT. This has allowed UNIDO to expand its impact on the ground by supporting more business/investment projects as well as SMEs, ultimately contributing to poverty reduction through investment, employment and income generation in Iraq.

Main implementation constrains & challenges (2-3 sentences)

Due to unforeseen administration issues involving Iraqi customs, the receipt of technology poles by the EDUs in all targeted governorates were delayed by three months. Since these poles are crucial for project implementation, this resulted in a delay in the overall launch of the project.