[Discharge and Reintegration assistance to maoist army - drama]

Final PROGRAMME  Narrative report

1 January 2009 – 31 May 2010

| Programme Title & Number |  | Country, Locality(s), Thematic Area(s) |
| --- | --- | --- |
| - Programme Title: Discharge & Reintegration Assistance to Maoist Army - DRAMA - Programme Number: UNPFN/A-6 - MDTF Office Atlas Number: 0071690 |  | Nepal UNPFN: Cantonment / Reintegration |

| Participating Organization(s) |  | Implementing Partners |
| --- | --- | --- |
| United Nations Development Programme – UNDP |  | - The programme was implemented under the auspices of the Government of Nepal, Ministry of Peace and Reconstruction (MoPR) - Main Partners: UNDP, UNMIN, UNFPA and UNICEF - Other Partners: Semi/Non-Governmental Organizations: TITI, UCEP, Alliance Nepal and MEDEP/UNDP) |

| Programme/Project Cost (US$) |  |  | Programme Duration (months) |  |
| --- | --- | --- | --- | --- |
| MDTF Fund Contribution: by Agency (if applicable) | 3,392,216 |  | Overall Duration | 24 Months |
| Agency Contribution - UNDP | 1,027,265 |  | Start Date | 01 January 2009 Fund was transferred on 25 March 2009 |
|  |  |  | Original end date | 31 Dec 2010 |
| Government Contribution (if applicable) |  |  | Revised End Date, (if applicable) | 31 May 2010 |
| Other Contribution (donor) - DFID | 115,403 |  | Operational Closure Date | 31 May 2010 |
| TOTAL: | 4,534,884 |  | Expected Financial Closure Date | 31 May 2010 |

| Final Programme/ Project Evaluation |  | Submitted By |
| --- | --- | --- |
| Evaluation Completed N/A Yes No Date: __________________ Evaluation Report - Attached Yes No |  | - Name: Shantam Khadka / Ahmad Khalid Zhuanday - Title: Programme Specialist / Information Management, Reporting & M&E Coordinator - Participating Organization (Lead): UNDP Lead, UNICEF, UNFPA - Contact information: shantam.khadka@undp.org / Khalid.zhuanday@undp.org |

Abbreviations

| AMMAA | Agreement on the Monitoring and Management of Arms and Armies |
| --- | --- |
| AMO | Arms Monitoring Office |
| BCPR | Bureau for Crisis Prevention and Recovery |
| CAAFAG | Children Associated with Armed Forces and Armed Groups |
| CPA | Comprehensive Peace Agreement |
| CTEVT | Council for Technical Education and Vocational Training |
| DFID | Department for International Development |
| DREAM | Disarmament, Demobilization, Reintegration and Arms Management |
| D&R | Discharge and Rehabilitation |
| GoN | Government of Nepal |
| IDDRS | Integrated Disarmament, Demobilization and Reintegration Standards |
| ILO | International Labor Organization |
| IP | Implementing Partner |
| I/R | Integration and Rehabilitation |
| JMCC | Joint Monitoring and Coordination Committee |
| JMTs | Joint Monitoring Teams |
| LTAs | Long Term Agreements |
| MCS | Maoist Cantonment Site |
| ME | Micro-Enterprises |
| MEDEP | Micro-Enterprises Development Programme |
| MoPR | Ministry of Peace and Reconstruction |
| PSP | Principal Service Provider |
| RIS | Rehabilitation Information System |
| ROs | Regional Offices |
| SC | Special Committee |
| SGBV | Sexual and Gender Based Violence |
| SLC | School Leaving Certificate |
| SPSS | Statistical Package for Social Science |
| TC | Technical Committee |
| TITI | Training Institute for Technical Instruction |
| TPO | Trans-Cultural Psychosocial Organization |
| UCEP | Underprivileged Children’s Education programme |
| UCPN-M | United Communist Party of Nepal – Maoist |
| UNCT | United Nations Country Team |
| UNDAF | United Nations Assistance Framework |
| UNDP | United Nations Development Programme |
| UNFPA | United Nations Population Fund |
| UNICEF | United Nations Children’s Fund |
| UNIRP | United Nations Interagency Rehabilitation Programme |
| UNMIN | United Nations Assistance Mission in Nepal |
| VMLRs | Verified Minors and Late Recruits |
| VST | Vocational Skills Training |

Table of contents

FINAL PROGRAMME REPORT	4

1.1	Background	4

1.2	Purpose	4

1.1.	Assessment of the Programme	4

1.2.	Project Results	5

1.2.1.	Formal Discharge of the 4,008 disqualified Maoist army personnel	5

a)	Conduct Information Consultation in all Maoist cantonment sites	5

b)	Formal Discharge Process	6

1.2.2.	Reintegration and Rehabilitation Support to VMLRs	7

1.2.3.	Additional Achievements Contributing to the Programme	9

c)	Assessment of Foreign and Domestic Labor Market Opportunities:	9

d)	Managed DREAM Database and Analysis	10

e)	Provided Support to UNMIN and JMCC on the cantonment management:	10

f)	Living Condition of the Maoist Members (19,602) improved	11

g)	Other Results contributing to the Output and/or Outcome:	11

ANNEXes to the report	15

Annex-A: Information and Consultation	15

Annex-B: Profiling Survey	19

Annex-C: Key Strategic Lessons Learned from Discharge Process	27

Annex-D: Snapshots from the discharge process	29

Annex-E: Analysis of Demand for Employment Opportunities in Foreign Countries	34

# FINAL PROGRAMME REPORT

- purpose

## Background

Following 10 years of conflict, Nepal’s main political parties (the Seven Party Alliance – SPA) and the Communist Party of Nepal – Maoist (CPN-M) signed a Comprehensive Peace Accord (CPA) on the 21 November 2006. Subsequently, a document detailing the modalities for the monitoring of the arms and armed personnel of both sides – the Agreement on Monitoring of the Management of Arms and Armies (AMMAA) – was signed by the parties and witnessed by the Special Representative of the UN Secretary General.

Within this context and under the overall guidance of the United Nations Mission in Nepal (UNMIN), the United Nations Country Team (UNCT) – specifically the United Nations Development Programme (UNDP) and the United Nations Children’s Fund (UNICEF) - conducted the registration and verification of the Maoist combatants who were located within seven main cantonments and twenty-one satellite sites across the country. As a result of this verification process, the Maoist combatants were categorized in two main groups: a) those verified as regular members of the Maoist army (19,602 individuals); and b) those disqualified (4,008 individuals) on the grounds of being minors (defined in the AMMAA as those born after 25 May 1988) or late recruits (those who joined the Maoist army after the ceasefire of 25 May 2006). Under the AMMAA, both verified minors and late recruits (VMLRs) are not eligible for inclusion in the Maoist army and were recommended to be discharged from the Maoist cantonments immediately.

## Purpose

This Project primarily supports the Government of Nepal (GoN) in the implementation of the Comprehensive Peace Agreement (CPA).  The active elements of the project in 2009 concern the following areas:

  - Support the Government of Nepal with the discharge and rehabilitation of the 4,008 disqualified Maoist army personnel who were identified as late-recruits and minors during the UN led Verification Process;

  - Developing concepts and procedures provide strategic advisory, technical and logistic support to the Government of Nepal to facilitate the planning and implementation of the discharge and rehabilitation programme.

In-line with the United Nations Development Assistance Framework (UNDAF), the discharge and rehabilitation assistance to Maoist army was planned and implemented successfully and is expected to support the consolidation of peace in Nepal. UNDP in close coordination and collaboration with the Ministry of Peace and Reconstruction (MoPR) of the GoN, UNICEF, UNFPA and UNMIN and other international partners, designed and implemented key elements of the aforementioned objectives.

- ASSESSMENT OF PROGRAMME/ PROJECT RESULTS

## Assessment of the Programme

Following completion of the verification process as mentioned earlier, the disqualified combatants continued to live in the cantonments together with other verified members of the Maoist army personnel for two years and the discharge and rehabilitation (DR) of these disqualified individuals was to represent not only a critical element in implementing the AMMAA but also a fundamental step in the overall peace and reconciliation process in Nepal. Under the overall leadership of UNMIN, the UNCT worked in close collocation with the Government of Nepal (GoN) to develop a framework to provide assistance for the smooth discharge and rehabilitation of the disqualified individuals back to civilian life. This was guided by international standards and best practices, and grounded in the contextual realities of Nepal. UNDP with the dedicated team of experts supported MoPR in the planning, implementation and monitoring of the discharge and rehabilitation programme and also provided technical and logistical support to MoPR and the Technical Committee on discharge and rehabilitation. In addition, UNDP also provided ongoing support to the UNMIN Arms Monitoring Office (AMO), on sharing of data, bar-coding and re-bar-coding of weapons and ammunition stored at Maoist cantonments. The project continued managing contracts for 28 AMO Support Force staff, and the seven-member Joint Monitoring and Coordination Committee (JMCC).

The technical preparation work for discharge and rehabilitation was a collaborative effort between UNDP, UNICEF and UNFPA. On the political front, UNMIN – in close coordination with the United Nations Special Representative of the Secretary-General for Children and Armed Conflict - were involved in negotiations to determine the conditions for the discharge and rehabilitation of the disqualified Maoist combatants. The successful rehabilitation of these individuals, through the facilitation of realistic employment and livelihood opportunities was seen as an important step towards bringing a sustainable degree of peace to the country. Following are key outputs achieved.

## Project Results

## Formal Discharge of the 4,008 disqualified Maoist army personnel

Following completion of the UN led verification process of the Maoist army personnel in December 2007 that resulted in the 4008 Maoist combatants verified as Minors (2973) or Late Recruits (1035), a Steering Committee (SC) with representation from UN, UCPN-Maoist under the leadership of the Government of Nepal as well as Technical Committee (TC) with similar representation to implement the decisions of the SC was formed. As the participation of UCPN-Maoist in the technical committee was critical, this ensured a common understanding of the procedures and enabled the Maoist to be well informed of the precise steps of the process. The technical committee also facilitated the UN’s ability to rapidly prepare the logistical and technical aspects of the process on an efficient manner.

As a result of continuous negotiations with government and the UCPN-Maoist, the Government and UCPN-Maoists reached an agreement to resume the process of discharge and rehabilitation of the disqualified Maoist army personnel. Accordingly a paper outlining stages to discharge and rehabilitation was developed. The paper laid out the following milestone stages:

- Information and Consultation,

- Profiling Survey

- Discharge from the cantonment,

- Transit Center,

- Rehabilitation Programme and

- Post-training support

## Conduct Information Consultation in all Maoist cantonment sites

Of the six stages of the D&R programme, the first step – information and consultation was carried out in seven cantonment sites and 21 satellite camps across Nepal. The objective of this process was to inform the disqualified on the discharge and rehabilitation programme and collect their view points on the programme. The project provided technical and logistic support for the overall planning and implementation of this process. It was led by the government of Nepal through the Technical Committee which was participated by the Communist Party of Nepal – Maoist (UCPN-M) and representative of UN Country Team (UNDP, UNICEF and UNFPA). Key activities carried out by the programme were as followings:

- Developed concept note and Prepared timelines and deployment plan

- Planned and deployed required logistics

- Planned and organized orientation training to the team which also including Government, UCPN-Maoist and the Technical Committee (TC) members

- Assisted the Technical Committee in the overall implementation of the process including facilitation of communication between the field team, MoPR and other stakeholders.

- Produced report based on the findings from the programme implementation and submitted to the UN senior management, TC and Steering Committee (SC).

Click for a detailed paper on Information and Consultation Process as ANNEX-A

The second stage (profiling survey) was not conducted due to disagreement by UCPN-Maoist who refused to allow Government and UN access to disqualified Maoist combatants inside the cantonments. However, the Government with support from the UNCT had made all the necessary preparations including development of complete implementation plan, concept note, questionnaire, timeline and budget. For details refer to ANNEX-B

## Formal Discharge Process

In view of the agreements, the Steering Committee chaired by the Minister of Peace and Reconstruction, with representation from UCPN-Maoist and senior UN officials helped to provide policy guidance and direction. Under the Steering Committee, the Technical Committee also helped in planning and overseeing the technical implementation of the discharge process.

On 16 December 2009 – after two years of negotiation - a UN Security Council mandated Action Plan for the discharge of disqualified Maoist army Personnel and related tasks was signed by the UN, the GoN and the UCPN- Maoist. The Action Plan highlighted the overall framework for the discharge process and made clear that rehabilitation packages will be offered to all disqualified individuals.

Under the guidance of Representative of Secretary-General in Nepal and leadership of the Resident Coordinator, a joint UNCT intervention with discharge and monitoring team structure, facilitated exceptional coordination and cooperation among the UN agencies. UNDP in close collaboration with UNMIN, UNICEF and UNFPA led the planning for discharge and rehabilitation of these individuals with technical and logistical support to MoPR and the relevant committees. As a result of the agreed action plan, 2,394 (60%) of the 4,008 disqualified individuals were officially discharged from the Maoist cantonments between 7 Jan to 8 Feb 2010. The remaining 1614 (40%) of the disqualified were officially discharged in an absentia signed by the UCPN-M in March 2010. The UN team was comprised of approximately 70 UN personnel from UNDP, UNICEF, UNFPA, UNMIN and OHCHR (monitoring of the 1612 action plan) where common understanding of the well-defined and complimentary roles and responsibilities of UN agencies and teams was ensured. Refer to ANNE-C for detailed strategic lessons learned from the discharge process. Following are key statistical figures from the discharge process in the first quarter of 2010.

Figure 1: Cumulative Discharge Matrix

| Main Cantonment Site (MCS) | Total # disqualified in 2007 | Minors Discharged |  |  | Late Recruits Discharged |  |  | Total Discharged Officially |  | Absentees Discharged |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Male | Female | Total | Male | Female | Total | Total | Rate (%) | Total | (%) |
| MCS 1 (Ilam) | 878 | 251 | 80 | 331 | 107 | 38 | 145 | 476 | 54.2% | 402 | 45.8% |
| MCS 2 (Sindhuli) | 372 | 107 | 48 | 155 | 35 | 11 | 46 | 201 | 54.0% | 171 | 46.0% |
| MCS 3 (Chitwan) | 586 | 122 | 60 | 182 | 45 | 31 | 76 | 258 | 44.0% | 328 | 56.0% |
| MCS 4 (Nawalparasi) | 622 | 156 | 106 | 262 | 75 | 24 | 99 | 361 | 58.0% | 261 | 42.0% |
| MCS 5 (Rolpa) | 450 | 140 | 97 | 237 | 28 | 3 | 31 | 268 | 59.6% | 182 | 40.4% |
| MCS 6 (Surkhet) | 630 | 258 | 156 | 414 | 53 | 27 | 80 | 494 | 78.4% | 136 | 21.6% |
| MCS 7 (Kailali) | 469 | 174 | 88 | 262 | 51 | 23 | 74 | 336 | 71.6% | 133 | 28.4% |
| KTM Security | 1 |  |  |  |  |  |  |  |  | 1 |  |
| Total Number | 4008 | 1208 | 635 | 1843 | 394 | 157 | 551 | 2394 | 60.0% | 1614 | 40.0% |
| % Out of Total Discharged |  | 50% | 27% | 77% | 16% | 7% | 23% | 100% |  |  |  |
| % Per Category / Gender |  | 66% | 34% | 100% | 72% | 28% | 100% |  |  |  |  |

Please refer to ANNEX-C for snapshots from discharge process.

Figure 2. Discharge Process Flow

## Reintegration and Rehabilitation Support to VMLRs

With the completion of the discharge process, the UN Interagency approach with participation of UNDP, UNICEF, UNFPA and ILO was adopted to support the rehabilitation of these discharged VMLRs. In response to the changing political scenario and the emerging needs, the programme revised all the strategic documents regarding rehabilitation of the disqualified Maoist combatants.

In order to ensure the smooth implementation of the rehabilitation programme throughout the country, UNDP established five regional offices and hired and trained the required staff to facilitate implementation of the rehabilitation programme. Also, a toll-free phone system was established which served as the first line of contact for dischargees who wished to opt for rehabilitation packages. The toll-free phone is open 6 days a week to provide initial counseling, set appointments and refer them to respective regional offices for detailed career and psychosocial counseling and registration rehabilitation.

A set of four sectoral rehabilitation support packages including options for vocational skills training – VST, Micro-Enterprises– ME and Non-Formal education are offered through UNDP, Formal Education and Psychosocial Counseling through UNICEF, Health related trainings through UNFPA while ILO will enhance the capacity of UNDP implementing partners for VST to deliver high quality vocational skills training and also to improve their labor market assessment skills. UNDP, through a competitive bidding process, signed Long-Term Agreements (LTAs) with the following four principle service providers across the country that sub-contracted with service providers at the local level where they have no coverage to support transition of these VMLRs from military to civilian life.

- Training Institute for Technical Instruction (TITI) to deliver services on VST in eastern and mid-western development regions.

- Underprivileged Children’s Education Programme (UCEP) to deliver services on VST in central development region.

- Alliance for Social Mobilization (Pvt.) Ltd. (Alliance Nepal) to deliver service on VST in western and far-western development regions.

- Micro-Enterprises package was delivered through existing UNDP project, Micro-Enterprises Development Programme (MEDEP) and terms of reference was revised.

In addition, in view of the demands from dischargees and changing market needs, UNDP organized meetings with the government and semi government organizations to explore additional rehabilitation packages and look for possible collaborations and partnership during the implementation of rehabilitation programme. As a result, contracts were revised with the implementing partners and additional options were added into the menu of rehabilitation.

Building on the successful coordination and collaboration among the UN Country Team that resulted in the successful discharge of the VMLRs, a joint UNCT approach was adopted for the rehabilitation of these individuals. As a result, a comprehensive interagency rehabilitation programme proposal and document including annual work-plans, results and resources framework and budget was developed to UN Peace Fund which was approved by the UNPF executive committee during the second quarter of 2010. Accordingly, the implementation of the rehabilitation programme through a joint project called UN Interagency Rehabilitation Programme (UNIRP) will continue over a two year period starting from June 2010 until 31 May 2012. As of May 2010, following are key achievements in the implementation of rehabilitation programme:

Figure 3. Summary of Key Statistics

| Steps in Rehabilitation Process | Of the total 4008 individuals discharged |  |  |
| --- | --- | --- | --- |
|  | Male | Female | Total |
| VMLRs who have made first contact through the toll-free phone number | 1138 | 303 | 1441 (36%) |
| VMLRs who have received career counseling and been referred for training or education | 554 | 249 | 803 (20%) |
| Individuals who are currently in training or education | 290 | 118 | 408 (10%) |

Figure 4. Breakdown of VMLR participants by package in various steps of rehabilitation

| Rehabilitation Packages | # of VMLRs counselled and referred for training / education | # of VMLRs currently in training or education | # of VMLRs who have completed training | # of VMLRs employed after completion of training |
| --- | --- | --- | --- | --- |
| Vocational Skills Training | 272 (5% female) | 169 (2% female) | 2 (1%) | They appeared for skill test |
| Micro-Enterprises | 242 (60% female) | 143 (59% female) | 1 (4%) | 1 |
| Education | 205 (37% female) | 96 (32% female) | - | - |
| Health Training | 48 (17% female) | 00 (00% female) | - | - |
| Total | 803 (31% female) | 782 (37% female) | 3 (1%) | 1 |
|  |  |  | Rate of employment | 33% (of the total 3) |

Figure 5. UN Interagency Preparation for Rehabilitation

The programme conducted regular monitoring and follow-up on the rehabilitation process while more focus was given on monitoring of competency level of learning that individuals are attending. Similarly, the programme hired a socio-economic opportunity mapping consultant to develop strategy for post-training employment and map potential local employment and microcredit opportunities for the rehabilitation participants.

As a result of the interagency collaboration and relevant agencies specific expertise, an inclusive programming approach has been adopted to support other vulnerable young people in the community as per the Paris Principle Guidelines. Through UNICEF’s experience on working with CAAFAG, support to such other vulnerable groups has been integrated in the programme to avoid further stigmatization of discharged minors and late recruits. The focus on socio-reintegration and rehabilitation of these VMLRs is ensured by making provision of psychosocial support, establishing response mechanism to address protection concerns and engaging VMLRs in the community based peace-building activities. Each of the five regional offices has two psychosocial counselors to provide psychosocial services in training centers, schools and in the community through trained social workers. A referral mechanism has been established to refer cases require clinical and critical psychosocial interventions to specialized agencies. This takes advantage of CAAFAG Working Group’s network and district level capacity supported by UNICEF since 2007.

## Additional Achievements Contributing to the Programme

## Assessment of Foreign and Domestic Labor Market Opportunities:

UNDP conducted an assessment of foreign labor market employment opportunities with the aim to learn about trends and tendencies in the foreign employment market to inform the design of rehabilitation programme. The data and information was collected from the local vacancy announcements made for foreign employment, compiled and a comprehensive report was prepared. Following this, UNDP also initiated assessment of the opportunities in the domestic market. Refer to detailed report in the ANNEX-E.

## Managed DREAM Database and Analysis

UNDP is the custodian of the Disarmament, Demobilization, REintegration and Arms Management – DREAM database generated during the registration and verification process in 2007. UNDP provides support to the government, UNICEF and particularly UNMIN Arms Monitors Office with Maoist army database management, weapons database and bar-coding management. The database team has been providing support to both UNMIN and the Government of Nepal in generating various data on both 4008 disqualified Maoist combatants and the regular Maoist army. For instance, the team developed personal profiles of the 19,602 regular Maoist army and created nominal rolls for salary payment.

Following the completion of the verification process, UNDP carried out a comprehensive study and analysis (100+pages) of the data about Maoist army personnel including Minors, Late Recruits and Maoist regular members collected during registration (January 16th to February 19th 2007) and the verification data (June 19th to December 26th 2007). The analysis provides baseline information about the demographic and socio-economic profiles of VMLRs which can be used to inform the design of tailored rehabilitation support packages to facilitate the transition of these VMLRs from military to civilian life. As a result, this study greatly contributed in the planning for discharge and rehabilitation of these individuals particularly in the absence of profiling survey which was stopped by the Maoist. The study on Maoist regular members (19,000+) will be used for possible UNDP’s intervention in the rehabilitation of the 19,000 Maoist members.

The project in consultation with other UN partners initiated the development of a comprehensive UNCT common database (Rehabilitation Information System) including database for discharge process, toll-free telephone database and SMS text messages software that largely benefited the programme in the smooth implementation of discharge and rehabilitation programme. These databases will be operational in 3rd and 4th quarter of 2010.

Besides, UNDP continued updating personal profiles of Maoist army personnel as well as their weapons and ammunitions files/records into the DREAM database. This database served as the main data source for the whole discharge and rehabilitation programme. In addition, UNDP also provided technical and logistic support in the production of barcodes and stickers for security personnel and weapons of the Maoist army personnel.

## Provided Support to UNMIN and JMCC on the cantonment management:

To assist UNMIN Arms Monitoring Officers, UNDP continued the positioning of 29 support force staff that are based in 7 cantonment sites and also provided administrative and logistic support to Joint Monitoring and Coordination Committee (JMCC).

The JMCC is composed of representatives from the UN, Nepal National Army and UCPN-Maoist army. It was formed with the objective to report on the compliance of the parties as per the agreements to the Secretary-General and to Government for resolution. The JMCC has the following three main functions:

- To assist the parties in implementing Agreement on Monitoring and Management of Arms and Armies (AMMAA) and is the central coordinating body for monitoring arms and armies in accordance with the terms of AMMAA.

- To serve as dispute resolution mechanism and resolve all disputes and military or operational difficulties, complaints, questions or problems regarding implementing of AMMAA.

- To assist in confidence building and work to gain the trust and confidence of the parties and promote the overall goals of this agreement among the people in Nepal.

In order to achieve the above goals, the JMCC operates according to the following basic principles:

- Resolve all problems and disputes at the lowest level possible i.e. delegation of authority to Joint Monitoring Teams (JMTs)

- Promote Joint problem-solving and build trust and confidence through active efforts to appropriately investigate and report on all incidents of concern to the parties and,

- Build on lessons learned in the process

The JMTs assist the JMCC at the local level and through site visits. The JMTs comprise one international monitor as the team leader and one monitor from Nepal Army and one from the Maoist army. The JMTs have the following tasks:

- Village and community visits and liaison with the civilian community;

- Cooperation with other UN-agencies, and liaison with international organizations and non-governmental organizations;

- Assistance to the parties in creating a favorable operational environment for the conduct of the ceasefire by information sharing and defusing local tension;

- A pro-active concept for initiation of conflict management at the local level; and,

- Investigation of complaints linked to possible alleged violations of the agreement, reference paragraph 5.1 of AMMAA, and to recommend measures to ensure compliance.

## Living Condition of the Maoist Members (19,602) improved

An assessment by the Ministry of Peace and Reconstruction indicated that many regular Maoist combatants lack basic necessities i.e. warm blankets and adequate footwear and clothing. The UNMIN Cantonment Conditions Working Group composed of UN agencies and donors also noted that winterization support was urgently needed including blankets and other basic necessities.

On January 1st 2009, UNDP received a formal request from the Foreign Aid Coordination Division in the Ministry of Finance to urgently procure basic clothing, footwear and blankets for the regular members of the Maoist army cantoned in 7 sites and 21 satellite camps across Nepal. In consultations with UNMIN, UNDP explored the possibility of expediting the process of procurement considering the standard UNDP public tendering and procurement approval process. As a result, UNDP procured and delivered basic clothing (warm blankets, jackets, shoes, track suit, socks and woolen cap) to the 19,602 Maoist members in all seven cantonments.

## Other Results contributing to the Output and/or Outcome:

- Compilation of daily media clippings on Peace building and recovery issues in Nepal to inform the programme of the political developments at the national level.

- As part of the planning for discharge and rehabilitation of the disqualified, carried out an assessment on Cantonment Based Training.

- Developed concept paper on the need for national D&R commission in Nepal.

- Worked together with UNICEF and UNFPA on the development of Minimum Standards on D&R process in Nepal.

- At the request of MoPR, drafted a proposal to establish office for MoPR on Discharge and Rehabilitation Programme.

- Arranged training and orientation workshop to UN Country Team on DDR through experts from BCPR, Geneva.

- Carried out an assessment to map additional training opportunities and worked with national body for tourism – Nepal Academy of Tourism and Hotel Management - to provide tourism related trainings.

- Developed Terms of Reference for Steering Committee on Discharge and Rehabilitation, Technical Committee and Technical Committee members. Provided technical advisory support to the newly established committees on Discharge and Rehabilitation programme.

- Report on how achieved outputs have contributed to the achievement of the outcomes and explain any variance in actual versus planned contributions to the outcomes. Highlight any institutional and/ or behavioral changes amongst beneficiaries at the outcome level.

The official release of the VMLRs from the Maoist cantonments that occurred during January and February 2010 was a preliminary step towards peace and reconciliation process in Nepal and also a critical element in implementation of AMMAA. The discharge of these individuals is considered as a milestone in the overall peace process and has opened dialogue for the integration and rehabilitation (I/R) of the regular Maoist army personnel. As a result of political developments and changes, some elements of the initial discharge plan was not implemented i.e. individual profiling survey of VMLRs was blocked by the Maoists.

- Explain the overall contribution of the programme to the Strategy Planning Framework or other strategic documents as relevant, e.g.: MDGs, National Priorities, UNDAF outcomes, etc.

In accordance with the UNDAF, this project contributed to key elements of the peace process in Nepal. Discharge of the 4008 disqualified combatants helped end the political deadlock and paved the way for fresh political discussion and confidence building.

- Explain the contribution of key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

As a joint UNCT intervention, UNDP in close coordination and collaboration with UNMIN, UNICEF, UNFPA, ILO, and government of Nepal – Ministry of Peace and Reconstruction and the Maoists led the design and implementation of the project. The UN Interagency approach has been successful in optimizing significant institutional strengths and developing synergetic outputs with each agency taking relevant responsibilities.

- Who have been the primary beneficiaries and how they were engaged in the programme/ project implementation? Provide percentages/number of beneficiary groups, if relevant.

The primary beneficiaries of the project are 4,008 disqualified minors and late recruits of the Maoist army. Because of the political nature of the programme, there was no access to project beneficiaries over a period of two years. It was difficult to learn about the aspirations of the target group and incorporate them into the design of the programme, however, as part of the technical led by the Government, the UN Country Team managed to get some data during Information and Consultation Process. The UN Country Team has access to these participants as they come to register for rehabilitation programme.  Last but not least, all the elements of the discharge process and the rehabilitation packages were discussed and approved by both the committees except individual profiling survey. Also, in exception, the Maoist however, registered their reservation against the rehabilitation packages.

- Highlight the contribution of the programme on cross-cutting issues pertinent to the results being reported.

Considering the social stigma and the associated problems for women participants, the programme developed a comprehensive support matrix for women to facilitate their access and participation in the programme. The support includes special support to pregnant and lactating women, provision of caretaker, baby food, special paid maternity leave, support to people with disabilities, additional stipend for women who travel from their places of origin for training/education.

- Has the funding provided by the MDTF/JP to the programme been catalytic in attracting funding or other resources from other donors?  If so, please elaborate.

The fund provided by MDTF/JP greatly contributed in the first phase of the programme implementation. This allowed UNDP to be able to response to the need and to position itself as key stakeholder in the Nepali Peace Process. Successful implementation of the first phase of the programme attracted donors to continue their support through the MDTF/JP in implementing the rehabilitation programme.

- Provide an assessment of the programme/ project based on performance indicators as per approved project document using the template in Section IV, if applicable.

NA

- EVALUATION & LESSONS LEARNED

- Report on any assessments, evaluations or studies undertaken relating to the programme and how they were used during implementation. Has there been a final project evaluation and what are the key findings? Provide reasons if no evaluation of the programme have been done yet?

NA

- Explain, if relevant, challenges such as delays in programme implementation, and the nature of the constraints such as management arrangements, human resources, as well as the actions taken to mitigate, and how such challenges and/or actions impacted on the overall achievement of results.

As the discharge and rehabilitation of verified minors and late recruits was highly dependent on the political developments, clear political buy-in by the Government of Nepal, Maoist leadership and also, support from Maoist at central and local levels to facilitate smooth access to rehabilitation was crucial to contribute to national ownership, management of expectations and sensitivities, and the sustainability of the outputs. As a result, the discharge of the disqualified Maoist combatants that was expected to be carried out in 2009, took place in early 2010.

- Report key lessons learned that would facilitate future programme design and implementation, including issues related to management arrangements, human resources, resources, etc.,

National ownership of the process is vital: Clear political and sound leadership buy-in and support is required to contribute to national ownership, management of expectations and sensitivities, and the sustainability of the outputs.

Global lessons adapted to Nepali context: All rehabilitation programmes are implemented in a unique context. However, lesson learned and best practices from other programmes are equally applicable in most of the reintegration and rehabilitation programmes. Adaption of international lessons learned from other similar programmes proved to be extremely useful.

Individual profiling with socio-economic mapping is vital: The UN was denied access to cantonments prior to discharge process to gather individuals’ profiles, needs and aspirations. As a result, programme designed the rehabilitation packages with limited information on VMLRs and their interest assuming their needs and information within the context of peace process in Nepal.

Expectations must be managed: Artificially high expectation of the VMLRs from the UN rehabilitation programme has created a situation of confusion which has seriously challenged full access of the VMLRs to rehabilitation programme. Nothing worthwhile has been done by the UCPN-M to manage these expectations. Because of high expectations, VMLRs refuse to take up jobs because the start salary is lower than their expectations (NRs. 5,000-6,000).

UN Country Team Approach: The UN interagency approach involving UNDP, UNICEF, UNFPA, and ILO to program development and implementation has been successful in optimizing significant institutional strengths and developing synergetic outputs.

Rehabilitation option packages should not be linked exclusively to government endorsed curriculums. There are often other options in high demand within the market that might not be part of the government standard curriculum.

IV. INDICATOR BASED PERFORMANCE ASSESSMENT

|  | Performance Indicators | Indicator Baselines | Planned Indicator Targets | Achieved Indicator Targets | Reasons for Variance (if any) | Source of Verification | Comments (if any) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 1: Disqualified Minors and Late Recruits discharged from Maoist cantonments and reintegrated into civilian life Outcome 2: Basic Living Conditions Improved for Verified Regular Members Staying in the Cantonments |  |  |  |  |  |  |  |
| Output 1.1 - Disqualified Late Recruits are Successfully Discharged from Cantonments in line with Integrated DDR Standards | Indicator 1.1.1 % of those who would have gone through the discharge process | NA | 1,035 | 1,035 |  | DREAM database Rehabilitation Information System – RIS, UNCT and UNMIN reports | 2973 Minors were also released from the Maoist cantonments |
| Output 1.2 - Disqualified Late Recruits are Provided with Reintegration Opportunities | Indicator 1.2.1 Number of disqualified Late Recruits who are enrolled in the reintegration programme | NA | 1,035 | 878 referred for one of the four rehabilitation packages (VST, ME, health training or education) - data as of May 2010 | Enrollment still ongoing. | Rehabilitation Information System – RIS database and reports, |  |
| Output 1.3 - Improved Living Conditions for 19,602 Verified Regular Members of the Maoist army in the Cantonments | Indicator 1.3.1 % of those who have basic clothing, footwear and warm blankets | NA | 19,602 | 19602 |  | UNDP Report, UNMIN Report |  |

# ANNEXes to the report

## Annex-A: Information and Consultation

Context Background:

To end the 10 years long conflict, Nepal’s main political parties (the Seven Party Alliance – SPA) and the Communist Party of Nepal – Maoist (CPN-M) signed a Comprehensive Peace Accord (CPA) on the 21 November 2006. Subsequently, a document detailing the modalities for the monitoring of the arms and armed personnel of both sides –Agreement on Monitoring of the Management of Arms and Armies (AMMAA) – was signed by the parties and witnessed by the Special Representative of the UN Secretary General.

Under the overall guidance of United Nations Mission in Nepal (UNMIN), UNDP and UNICEF - conducted the registration and verification of the Maoist combatants who were cantoned in seven main cantonments and 21 satellite sites across the country. As a result of verification process, Maoist combatants were categorized in two main groups; a) verified as regular members of Maoist army (19, 602) and b) disqualified individuals (4008), “Minors” (According to the AMMAA, combatants found to be born after 25 May 1988) or “Late Recruits” (individuals who joined the Maoist army after the ceasefire of 25 May 2006). As stipulated in the AMMAA the disqualified individuals had to be discharged and rehabilitated back to civilian life.

In close collaboration with Ministry of Peace and Reconstruction (MoPR), the UN Country Team has developed a framework to provide assistance for the smooth discharge and rehabilitation of the disqualified individuals. The preparations for discharge and rehabilitation are guided by international standards and best practices with due consideration of the Nepali context. The work has been a collaborative effort between UNDP, UNICEF and UNFPA. The Government of Nepal and UCPN-Maoist have agreed on six stages to complete the Discharge and Rehabilitation of the disqualified individuals. The stages involve: 1) information and consultation, 2) socio-economic profiling survey, 3) discharge from cantonments, 4) transition centres, 5) Rehabilitation and 6) Post-training and rehabilitation support.

Recently, the Government of Nepal and UCPN-M agreed to resume the discharge and rehabilitation of the disqualified individuals. In this regard, a Steering Committee (SC) chaired by Minister of Peace and Reconstruction with representation from UCPN-Maoist and UN Senior Officials is formed to provide policy guidance and political oversight to the process. A Technical Committee (TC) with representation from the same parties as mentioned above is also established, in order to plan and oversee the technical implementation of the process. UNCT will continue working with MoPR through responsible committees (SC and TC) to plans and facilitate a smooth discharge and rehabilitation of the disqualified individuals. This paper outlines activities proposed for the stage-I of the D&R process (Information and Consultation).

Objective:

The aim of information and Consultation is to provide information to the disqualified combatants on the agreed framework for discharge and rehabilitation and receive their views and opinions on the proposed rehabilitation assistance.

Content:

The Information and Consultation serves as the first and foremost important process with politically sensitive nature. It is a starter and has a determining role for the rest of the stages. Government and UCPN-M leadership inform the disqualified individuals on their status and officially declare their discharge from the cantonment and subsequent rehabilitation back to civilian life. Disqualified individuals feedbacks and recommendations will be incorporated into the overall rehabilitation programme. Government and UCPN-M will also have the critical job of managing the unrealistic expectations of the disqualified individuals.

The first stage of the process was officially launched on 11 October 2009 through a high-level visit to MCS 2 (Sindhuli). This visit was led by Minister of Peace and Reconstruction and UCPN-M senior representatives with participation of UN senior officials including the RSG, Heads of UN agencies and other UN and MoPR senior officials. The Technical Committee initiated the first stage of the work after the official launch of the process at this particular cantonment. The results and lessons learned from the first information and consultation visit will be incorporated into the overall information and consultation plan.

The Information and Consultation Process will begin prior to the Profiling Survey. It will happen in all cantonments and Satellite camps one after another. It will contain separate sessions/discussions with Maoist Division Commanders/deputy commanders and the disqualified individuals. The process will be facilitated by MoPR and widely supported by Maoist leadership. The feedbacks received from the field will contribute to the development of tailored rehabilitation assistance programme. The ultimate objective of the information and consultation is to mentally prepare the disqualified combatants for the rehabilitation programme and learn about their aspirations and concerns. There will be an initial discussion held with division commanders who will facilitate the process, followed by a more interactive and direct session with the target group for a period of two hours. These interactions will happen in small group of 30-50 individuals.

Proposed Methodology:

- A one-day training and orientation session for the technical team on information & Consultation prior to deployment to the field.  Briefing session for the technical experts on the details of the visit, script and presentation to be used and overall approach to be followed, including contingency plan for unforeseen reactions.

- MoPR will lead the team and facilitate the whole process. UN will participate, at the discretion of the UN, in support of the process agreed between Maoist and Government

- Maoist leadership will assure the full cooperation and participation of respective division commanders.

- Division commanders will ensure the target group are informed in advance and are gathered ahead of the arrival of the information and consultation team.

- Group Discussions will last for about two hours with a group of 30-50 disqualified combatants. Information and Consultation to happen in a sequential manner in all cantonments and Satellite camps

Teams deployment:

- The technical team for Information & Consultation will be composed of two teams (A&B) divided into two sub-groups (A 1&2 and B 1&2) with 4-5 individuals in each sub-group, who will be working in two separate cantonments.

- Teams A (1&2) will move to MCS-3 and MCS 1 and return back to Kathmandu to review the results. While the team B (1&2) will move to MCS 7, MCS 6 and lastly to MCS 5 respectively. Team (A) will also cover the last cantonment (MCS 4) after incorporating the results from MCS 3 and MCS 1.

- Saturdays are considered as days off to give the teams time to manage their personal rendezvous.

- Transportation to all cantonment sites is planned to be by road, only for MCS 5 (Rolpa) airlifting is maybe anticipated. (Detailed timeline attached).

Proposed Agenda

- Upon arrival Preliminary Discussion with Maoist Commander and Deputy Commander

- To brief the Division Commander on the objectives of the Information and Consultation.

- To seek support in the arrangement of the sessions particularly arrangement of venue and gathering of the disqualified individuals.

- Ask for division commanders’ presence in the sessions including delivery of opening remarks.

- Assigning two senior commanders (preferably Division Commander and Deputy Commander) to accompany the information and consultation sessions.

- Group Discussion in a group of 25-30 with disqualified combatants.

- Facilitation by MoPR and the Division Commander

- Opening by Cantonment Commander and briefing on the latest developments and future plans with elaboration on the agreed framework.

- Introduction and briefing by MoPR on context and objective of the visit.

- Technical Session by technical expert from Maoist Commander and MoPR on proposed packages and future interventions.

- Plenary Session: (Facilitator Maoist Commander with MoPR support)

  - Open Discussion

  - Q&A

- Wrap up and closing:

  - MoPR and Division Commanders.

- Team Composition:

The technical team is comprised of four sub-groups divided into two teams with 4-5 individuals in each group. The proposed team composition for each sub-group is as the followings:

- One representative from MoPR

- One representative from the Maoists

- Two to three people from UN.

Timeline:

Based on the deployment plan the whole exercise will be completed in a minimum of 20 days.

Required Resources:

- HR: Information and Consultation will be led by the Government of Nepal supported by UCPN-Maoist. UN will technically and logistically support the planning and implementation of the process.

- Budget: The estimated budget for this stage of the process is estimated US$ 36,158.

Minimum standards for Information and Consultation

- Must take place in all cantonments and satellite camps.

- Must be managed by Government and supported by UCPN-M.

- Must be monitored by UN.

- Maoist representation is a must throughout the process implementation.

Preliminary Activities prior to Information and Consultation process:

- Steering Committee to discuss and clarify questions rose during the first information and consolation visit.

- Agree on the modality and timeline for Information and Consultation.

- Modify the presentation to incorporate lessons learned during first information and consultation.

- Develop logistics and deployment plan to mobilize resources in a timely manner.

- Organize a one day orientation workshop on information and consultation plan including sessions on the lessons learned from the visit to MCS-2.

- Share the plan with division commanders prior to the visit.

- Division Commanders to brief and prepare the disqualified for information and consultation.

Operational and logistics Constraints:

- Confirmation of the deployment plan specifications.

- Timely introduction of Government representatives who will lead the process.

- Availability of two Maoist representatives for each team.

- Maoist protest programmes countrywide.

- Availability of UN vehicles for the transportation of UN staff.

- Communications from the field.

- DSA and mission expenses for Government and Maoist Personnel.

## Annex-B: Profiling Survey

Stage II of the Discharge Process

Profiling Survey

Context Background:

Following the 10 years of conflict, Nepal’s main political parties (the Seven Party Alliance – SPA) and the Communist Party of Nepal – Maoist (CPN-M) signed a Comprehensive Peace Accord (CPA) on the 21 November 2006. Subsequently, a document detailing the modalities for the monitoring of the arms and armed personnel of both sides – the Agreement on Monitoring of the Management of Arms and Armies (AMMAA) – was signed by the parties and witnessed by the Special Representative of the UN Secretary General.

Under the overall guidance of United Nations Mission in Nepal (UNMIN), UNDP and UNICEF - conducted the registration and verification of the Maoist combatants who were cantoned in seven main cantonments and 21 satellite sites across the country. As a result of verification process, Maoist combatants were categorized in two main groups; a) verified as regular members of Maoist army (19, 602) and b) disqualified individuals (4008), “Minors” (According to the AMMAA, combatants found to be born after 25 May 1988) or “Late Recruits” (individuals who joined the Maoist army after the ceasefire of 25 May 2006). As stipulated in the AMMAA the disqualified individuals had to be discharged and rehabilitated back to civilian life.

In close collaboration with Ministry of Peace and Reconstruction (MoPR), the UN Country Team has developed a framework to provide assistance for the smooth discharge and rehabilitation of the disqualified individuals. The preparations for discharge and rehabilitation are guided by international standards and best practices with due consideration of the Nepali context. The work has been a collaborative effort between UNDP, UNICEF and UNFPA. The Government of Nepal and UCPN-Maoist have agreed on six stages to complete the Discharge and Rehabilitation of the disqualified individuals. The stages involve: 1) information and consultation, 2) socio-economic profiling survey, 3) discharge from cantonments, 4) transition centres, 5) Rehabilitation and 6) Post-training and rehabilitation support.

Recently, the Government of Nepal and UCPN-M agreed to resume the discharge and rehabilitation of the disqualified individuals. In this regard, a Steering Committee (SC) chaired by Minister of Peace and Reconstruction with representation from UCPN-Maoist and UN Senior Officials is formed to provide policy guidance and political oversight to the process. A Technical Committee (TC) with representation from the same parties as mentioned above is also established, in order to plan and oversee the technical implementation of the process. UNCT will continue working with MoPR through responsible committees (SC and TC) to finalize the plan and facilitate a smooth discharge and rehabilitation of the disqualified individuals. This paper outlines activities proposed for the stage II of the process (Profiling Survey).

Objective:

The aim of Profiling Survey is to collect information on socio-economic profiles of the disqualified Maoist combatants in order to inform the design of Rehabilitation Assistance Packages. The results of the survey will contribute to the further tailoring of training, education and employment assistance to meet the needs and aspirations of these individuals.

Content:

The Profiling Survey plan includes a concept paper, timeline, deployment plan with details of logistics, a training workshop and a data analysis component. Prior to the Profiling Survey exercise there will be a training workshop for the Profiling Survey Team on the survey, the questionnaire, methodology, survey administration, collection of data and its management and subsequent analysis as well as the code of conduct. The Profiling Survey will be carried out through a semi structured questionnaire. The Survey Questionnaire will be finalized through a pre-testing exercise in one of the cantonments followed by an actual survey in all seven cantonments. The questionnaire will capture data and information related to demography, educational qualifications and relevant skills, economic status, special needs and their expectations.

After the completion of the data collection, it will be compiled, processed and analyzed with validation to happen in one of the cantonments. The findings of the survey will be used to enhance and further tailor the rehabilitation packages according to the needs.

Proposed Methodology:

It will be a government led process where each team will be led by a representative from the Government accompanied by representatives from UNMIN, UNDP, UNICEF and UNFPA.

The survey will be undertaken in the following steps:

- Staging of the preparatory workshop and revision of  the survey questionnaire

- Piloting and testing the questionnaire in one of the cantonments

- Carrying out survey in all seven main cantonment sites and satellite camps for the disqualified Maoist Army personnel

- Each ex-combatant will be interviewed only once through a face-to-face interview

- Female caseworkers will be available to create gender sensitive environment.

- Compilation, translation and feeding into relevant database, rechecking and cleaning of the data entered

- Conversion and migration of the data in SPSS and tabulation and subsequent analysis of the data

- Validation of patterns, trends and conclusions through Focus Group Discussion

- Drafting the report based on the findings and recommendation

The Survey team will go through a seven day orientation workshop. The Profiling Survey will happen in accordance to the timeline and deployment plan agreed upon by the Technical Committee. The logistics for the profiling survey will be arranged through UNCT and UNMIN with support from Government and UCPN-Maoist.

Team Composition:

It will be a government led process supported by UN country team and UNMIN. The actual survey will be carried out by a team of 40 UN hired enumerators.

Timeline:

Based on the deployment plan the whole Profiling Survey will be completed in minimum 45 days including one week orientation workshop, two weeks field data collection and a minimum of three weeks data entry and analysis of the survey findings. Attached is the tentative timeline.

Required Resources:

- HR: The proposed number of staff required to carry out the Profiling Survey is tentatively 40.

- Budget:  The estimated budget for the minimum 45 day exercise of Profiling Survey is = 131000 USD. Attached please find the detailed budget.

Preliminary Activities prior to profiling survey process:

- Agree on the modality and a realistic timeline for profiling survey process.

- Discuss and finalize the profiling survey plan including finalization of the questionnaire.

- Recruit and train qualified enumerators.

- Organize profiling survey orientation training workshop.

- Coordinate and agree the profiling survey plan with Division Commanders prior to the survey conduct.

- Maoist leadership to show commitment in providing free and fair environment where disqualified individuals are allowed to make a choice of their own.

Minimum Standards for Profiling Survey:

- Enumerators must be qualified and appropriately trained.

- Survey must be conducted one-on-one by enumerators in a confidential setting.

- Female enumerators should interview female disqualified individuals.

- UN to manage and use the data for analytical purposes.

- Any information gathered during the profiling must be kept confidential and must only be used for programming purposes.

- Assign UN monitors to oversee the profiling survey.

- Disqualified individuals are provided adequate information to enable them make an informed decision.

Operational and logistical Constraints:

- Timely request from MoPR for recruitment of qualified enumerators.

- Confirmation of profiling survey deployment plan with specifications.

- Orientation workshop for proper training of the enumerators.

- Availability of UN vehicles for the transportation of UN staff.

- Maoist protest programmes countrywide.

- Accommodation and food of the survey team at the cantonment site.

- DSA and mission expenses for Government and Maoist Personnel.

- Basic field kit and equipment for the survey team including communication equipment meeting basic security requirements.

- Availability of two logistic persons to support the profiling teams in the field.

UN Support to Profiling Survey:

In close collaboration with MoPR, UN will provide technical, financial and logistics support for the planning and implementation of Profiling Survey.

- Development of concept, timeline, logistic and deployment plan

- Recruitment of qualified enumerators and support staff.

- Finalization of the questionnaire and its translation into Nepali.

- Prepare detailed workshop agenda and curriculum.

- Make all necessary arrangements and organize the training workshop to enumerator.

- Agree on a practical approach of survey administration and presentation to the disqualified combatants in the cantonment.

- Food and accommodation arrangements more specifically in MCS5 (Rolpa).

- Support the actual deployment and conduct of the profiling survey.

Government role:

Ministry of Peace and Reconstruction as a lead agency may consider the following for a successful planning and implementation of the process;

- Send request to UN for the recruitment of qualified enumerators to carry out the survey.

- Negotiate and agree with the Maoist leadership on the planned Profiling Survey including process timeline and approach.

- Lead the team and facilitate the whole process. UN national and international staff will participate, at the discretion of the UN, in support of the process agreed between UCPN-M and Government

- Ensure full support and cooperation from the Maoist leadership.

- Ensure that division commanders inform the target group in advance and are prepared for the process.

- Manage expectations and grievance of the disqualified combatants.

UCPN-Maoist role:

- Maoist leadership to ensure free and fair environment for profiling survey process.

- Inform the division commanders to ensure their support for the profiling survey.

- Division Commanders to mentally prepare the disqualified and ensure their participation in the survey.

- Manage expectations and grievance of the disqualified combatants.

Survey Form for Profiling of Maoist army Personnel

GENERAL AND DEMOGRAPHIC INFORMATION

1. 	Full Name: ……………………………………………………………………………………………………………..

2. 	PLA I.D Card No.: …………………………..               Barcode No.: ………………………………………………..

3. 	Address:

Permanent Address: 	District: ……………………….………. Municipality/ VDC: ……………..…....… Ward No: ……………………….…..… Tele: ………………………….

Temporary Address (Cantonment): ……………………………………………..……………

4. 	Date of Birth: 	Year: …….. ........	Month: …..........

5. 	Sex: 	[  ] Female  	[  ] Male

6. 	Family size: ……………..

7. 	Marital Status:	[  ] Unmarried 	[  ] Married	[  ] Widow/widower	[  ] Divorced	[  ] Separated

8. 	If married, where is your spouse/partner?

[  ] Living together 	[ ] Not living together …………………………………………………..

9. 	Do you have children? 	[  ] Yes      [  ] No	[  ] Pregnant (ASK ONLY MARRIED WOMEN)

10. 	If yes, please mention their gender and age?

No of daughters:   	(  )   	Mention Age:  (  ), (  ), (  ), (  ), (  )

No of sons: 	(  )	Mention Age:  (  ), (  ), (  ), (  ), (  )

11.	What are your children doing? ....................................................................................................................

12. 	Where do your children live?  	[   ] Live with me in the cantonment	[   ] Live elsewhere

13. 	Are you nursing/lactating? 	 [   ] Yes 	[   ] No

Have any complication during pregnancy or delivery? ...................................................................................................

14.	Do you have any other dependents e.g. parents, in-laws, siblings, who require your full-time support?

[   ] Yes   If yes, please specify: ………………………………………………………………………….

[   ] Parents 	[   ] Grand Parents	[   ] In-laws	[   ] Siblings 	[   ] Others

[   ] No

15.	Are you in regular contact with your family?

[   ] Yes. If yes, How often last year……..................................................		[  ] No

16. 	Have noticed any sleeping disorder, loss of appetite, anxiety or fear?	[   ] Yes 	[   ] No

17. 	Do you have any health problem/s?	[   ] Yes 	[   ] No

If yes, please explain:

What kind of health problem: …………………………….   Since when: ………………………

What treatment have you received so far? ......................................................................................

18. Please mention if you have physical weakness?

a) ………………………………..   b) ………………………………….  C) ……………………………………...

19. Have you taken any vocational or technical training?	[   ] Yes	[   ] No

(Fill in the followings if you have previously taken skill training)

Subject of the training: ………………………………………………………

Duration of the training:  Year: ……………...  Month: …………….…… Day: ………..…

Name of the training institute: ………………………………………………………………

20. Based on your qualifications and capacities, please prioritize the skills training or educational opportunity you want to pursue. [PLEASE EXPLAIN AVAILABLE TRAINING AND EDUCATIONAL OPPORTUNITIES]

SOCIO-ECONOMIC INFORMATION

1. 	What do you plan to do after you leave cantonment site?

[  ] Go for further education 	[  ] Start a small business	[  ] Go for skills training

[  ] Household chores	[  ] Resume my previous work	[  ] Go for overseas job

[  ] Service/job	[  ] Others: …………………………………………………….

2. 	What were you doing before you joined the Moist army? …………………………………………………………..

3. 	Where do you want to live/settle after you leave the cantonment?

If you know, please specify the address:

Village/Tole: …………………...  VDC/Municipality: …………………...  District: ………………

4. 	Do you have any problem returning home?	[  ] Yes: 	[  ] No:

If yes, please explain: …………………………………………………………………………….

5. 	Do you own land?

[  ] Yes, registered in own name	[  ] Yes, registered in parents name	[  ] Yes, registered in spouse’s name

[  ] No	[  ] Others, specify: ..............................................................................................

EDUCATIONAL BACKGROUND

1. 	Can you read and write Nepali language?	[   ] Yes 	[   ] No

2. 	Can you read and write other languages?	[ ] Yes, 	[   ] No

If yes please specify: ………………………………………………………………………………………….

3. 	What is your level of education? Please mention the class you have passed. …………….………… Class

[   ] Primary	[   ] Lower Secondary	[   ] Secondary

[   ] Higher Secondary / Proficiency Certificate Level	[   ] Bachelors	[   ] Masters

[   ] Others, specify: …………………………………………………………………………………………...

4. 	Are you interested in pursuing further education?

[   ] Yes, if yes, what formal or informal	[   ] No

5. 	Are there any barriers to pursue further education or training?	[   ] Yes	[   ] No

If yes, you can tick the following boxes:

[   ] Family	[   ] Social	[   ] Financial	[   ] No school

[   ] Others, specify: ………………………………………………………………………………………...

TO BE FILLED IN BY ENUMERATORS AFTER INTERVIEW

Please note your observations about the interviewee:

Enumerator: ………………………… Signature of Interviewee: ……………………

Signature…………………………………………...

Location/Place: ………………………………….…	Date: …………..../………..../....................

Profiling Survey Flow

## Annex-C: Key Strategic Lessons Learned from Discharge Process

- Two years after the completion of the UN led verification process in December 2007 that resulted in 2973 verified as minors and 1035 late recruits, the release and reintegration of these verified minors and late-recruits was secured by the signing of the Action Plan after several rounds of negotiation.  Discharge process was complicated and exacerbated due to delay between the time of verification and discharge which meant that out of total verified minors, 80% of them were found adults at the time of discharge, with different expectations for their future and non-awareness of their status as disqualified.

- In July 2009, Steering Committee (SC) with representation from UN, UCPN-M under the leadership of the Government of Nepal as well as a Technical Committee (TC) with similar representation to implement the decisions of the SC was formed.  The UCPN-M participation in the Technical Committee was critical in the joint UN and UCPN-M development of agreed operational modalities for the discharge process. This ensured a common understanding of the procedures and enabled the Maoists to be well informed of the precise steps of the process.  The shared understanding on the technical process and procedures was further ensured by an overview of the process that was annexed to the Action Plan. It was essential to avoid potential stalling of the process during implementation due to technical difficulties as it clearly outlined the steps to be taken.

- The Technical Committee also facilitated the UN’s ability to rapidly prepare the logistical and technical aspects of the process on an efficient manner. Central level clarity and agreement on technical issues limited the division commanders’ ability to unilaterally determine decisions or create ongoing discussions on emerging issues. For example, transport drop-off points were a contentious issue in most cantonments and usually required prolonged negotiations through the discharge process in each cantonment. This was due to lack of agreement at the beginning with UCPN-M key people, though this point was agreed with the Technical Committee in a later stage after learning the lesson from first cantonments.

- Maoists did not at any stage acknowledge the different status of the disqualified combatants particularly the verified minors. The Action Plan was signed in the context of securing the release of the 4008 disqualified Maoist army personnel both minors and late-recruits. Similarly within the operation plan developed in consultation with Maoist leadership and considering the context of Nepal, the verified minors and late-recruits were included within the same process and this was an inflexible position of the UCPN-M in the process. This had an impact on the ability of UN to provide the specific support required for the verified minors and international standards for Child release had to be compromised.

- The discharge process took place with the UCPN-M’s political will to fulfil their enduring obligation to release the disqualified, with motivation to restore their recognition and to respond to the constant pressure from the International Community in order to move the peace process forward.  The UCPN-M declared the process as ‘unilateral’ which restricted the responsibility and ownership only to UCPN-M party with little engagement from the Government of Nepal and other political parties. The UN technically facilitated the release in accordance with the Action Plan and operational procedures where limited access was given to UN to practice international standards.

- Discharge process was logistically huge operation where UNDP was in charge to procure logistics and services (food, accommodation of the team, transportation of discharges etc), hire and train the required staff, arrange cash transfer to each cantonment for dischargees transitional and transportation allowances and ensure cantonment wise deployment in a timely and efficient manner. These all had to be done in a very short notice of less than one month and the whole discharge operation was completed in seven cantonment sites in only 38 days. All UNDP system supported the implementation of this operation by giving priority and not saying No to discharge.

- Under the guidance of Representative of Secretary-General in Nepal and leadership of the Resident Coordinator, an inter-agency discharge and monitoring team structure facilitated exceptional coordination and cooperation between the UN agencies.  The UN team comprised of approximately 70 UN personnel from UNDP, UNICEF, UNFPA, UNMIN and OHCHR (monitoring of the action plan). There was a common understanding on the well-defined and complimentary roles and responsibilities of UN agencies and different teams.  Team members were assigned roles based on the caseload and necessity to minimize UN visibility at the discharge venue.  Team Leaders facilitated transparent and cohesive team work.  A high degree of professionalism and team spirit was observed.

- UN teams displayed adaptability and flexibility to address changes in the planned process as necessary.   For example, thirty six disqualified were registered to sit for the School Leaving Certificate (SLC) ‘Sent Up’ (pre-examination) after the discharge process.  This information was not communicated in advance to the Discharge Team.  As the government school was located inside the cantonment, the discharge team leaders agreed that the education of the disqualified should not be disrupted by requiring those enrolled to depart the cantonment prior to their exam. It was agreed that the 36 disqualified will formally depart the cantonment site on completion of the seven-day examination.  A discharge and monitoring team was later deployed to the cantonment site to support the discharge of the remaining disqualified.  Special needs cases, such as pregnant women due to give birth and ill persons were accommodated as requested.  Due to the high proportion of absentees, the UN agreed with the UCPN-M that disqualified personnel absent from the discharge process could join discharge processes in subsequent cantonments.

- Consistency in the engagement and presence of team leaders and key staff leading different components of the process was important to maintain team cohesiveness and ensure lessons learnt and tactical insights were built and acted upon on a daily basis. The UN senior managements at the Kathmandu level provided excellent leadership and support by enabling the team leaders to make instant decisions to emerging issues at the cantonments.

- The presence and role of the UCPN-M representatives of the Technical Committee throughout the discharge process was crucial.  Issues arising were addressed through the Technical Committee members as first point of contact, limiting space for independent decisions to be made by Maoist army focal points in each cantonment.  The UCPN-M Technical Team members also enabled the UN greater leverage in its negotiations with Maoist army focal points.

- UN national staff was well represented in the Technical Committee. National representation was important to ensure visible national ownership of the process, build relationships with the UCPN-M representatives and fully benefit from the capacity and contextual expertise of national staff.

- Nominating focal points from the Maoist army commanders in each cantonment to cooperate with the UN and oversee the discharge process was instrumental in gaining cooperation and accountability for the process.

- Requesting the UCPN-M to provide a list of dischargees in advance of the process was key to technical planning and smooth implementation of the technical process. The lists that the UCPN-M submitted in advance provided information about the tentative number of dischargees who would be participating in the discharge process from each cantonment allowed UN team to better plan the process timeline and number of staff involved.

- Despite of UN’s readiness to offer rehabilitation packages during the discharge process, the UCPN-M did not allow the UN team to have detailed career counseling on individual basis to offer the rehabilitation packages to interested dischargees. However, it was observed that dischargees’ expectations were raised to the highest level opposing the UN offered packages at the time of discharge.

Picture 1.  Screening and Cross-checking in DREAM database maintained by UNDP

Annex-D: Snapshots from the discharge process

Picture 2 Briefing and Orientation

Picture 3 Civilian ID Card Printing

Picture 4 Registration for Discharge and Information Sharing

Picture 5 Civilian Clothing Distribution

Picture 6 Cash Voucher Entry and Signing of Discharge List

Picture 7 Discharge Ceremony

Picture 8 Discharge and Transportation

Picture 9 Health Team helping a female dischargee

Picture 10 Health Support to Children of Dischargees

## Annex-E: Analysis of Demand for Employment Opportunities in Foreign Countries

1. Introduction

  - The Context

As a result of registration and Verification of Maoist army personnel conducted during 2007, 4008 individuals were disqualified from the process. Accordingly, UNDP engaged to support the government by preparing rehabilitation packages. During the early phase of this work, UNDP identified some of the training packages based on the recommendations by practitioners in the field. Later, it was felt necessary to assess demands for different kinds of training in the market, particularly in foreign countries. Therefore, this study with limited objectives was initiated.

  - Objectives of the study

The Discharge and Rehabilitation team is making preparations without specific information of the employment market – inside and outside the country. Therefore, in order to make these planning more precise and accurate, it is necessary to understand the demands in the market. Therefore, the overall objective of this study is to gain better insight into the job demands in countries where there are opportunities for   the Nepalese youths.

  - Methodology

Due to limitation with time and resources, it was not possible to go for a full-fledged labor market study to have in-depth analysis of the demands in and outside the country. However, the need to collect information which could inform about employment tendencies within local and foreign market was still felt. . Therefore, a quick approach was followed to capture the data and information from the vacancy announcements made for foreign country employment.

The vacancy announcements made in the Kantipur Daily between January 2008 to August 2009 were considered for the study.  The data and information from this vacancy advertisement were collected and entered into the Statistical Package for Social Science (SPSS) computer software. The data was analyzed to basically generate the frequency that could explain the demand.

  - Limitations of the Study

As the intention of this study was to only get indications in the labor market, followings limitations have to be considered before generalizing the findings of the study:

- There are other newspapers as well where the employers make such announcements which have not been covered by this study. Therefore, caution is required to make conclusions based only on the results derived from this study.

- Similarly, this study covers only period mentioned in section 1.3, therefore, this study also does not cover the announcements for the whole period.

- Another important limitation with this study is the difficulty in capturing the re-advertised positions. This is because the employers might have re-announced the same positions but this is never mentioned in the announcements.

- Also, the employer who is ultimately going to hire these individuals might have used different agencies (manpower companies) for making announcements for the same positions. But this issue was difficult to capture in this study.

2. Analyses and Major Findings

2.1 Labor Demand by Countries under Study

Traditionally, Nepalese youth join the British and Indian army as security personnel. More recently, Nepalese youth have started to work in other countries as skilled, semi-skilled and unskilled workforce. Therefore, the demand in various countries for these youth is analyzed and presented in Table 2.1.

Table 2.1: Labor Demand By Country

| Name Of the Country | Total | Percent |
| --- | --- | --- |
| UAE | 24838 | 32 |
| Qatar | 22622 | 29 |
| Saudi | 13872 | 18 |
| Bahrain | 5420 | 7 |
| Oman | 5046 | 6 |
| Malaysia | 3281 | 4 |
| Lebanon | 1116 | 1 |
| Israel | 997 | 1 |
| Kuwait | 882 | 1 |
| Libya | 340 | 1 |
| Bhutan | 65 | 0 |
| N/A | 55 | 0 |
| Macau | 44 | 0 |
| Maldives | 23 | 0 |

As per the data presented in Table 2.1, by far  most of the advertised posts were in Gulf countries, particularly in United Arab Emirates (UAE) where the demand was highest (32 percent), followed by Qatar (29  percent), Saudi Arabia (18 percent) and Bahrain (7 percent) 4 percent, Malaysia, 1 percent in Israel and Lebanon respectively. Only small proportion (less than 1 percent) was in demand in Maldives, Macau and Bhutan.

The Government is making preparations to send workers to eastern and central European countries like Romania, Poland and Ukraine (Katmandu Post, 2009).

2.2 Employment Opportunity by Major Occupational Groups

The various areas for which there is demand in these countries have been presented in Fig 2.1. The data present important findings. As per the data, of the total 78601 openings, 34 percent was accounted for support staff, followed by construction and extraction (25 percent). Similarly transportation, hotel and security related fields accounted for 11, 8 and9 percent respectively. On the other hand clothing, computer/IT and inspection and monitoring constituted only 1 percent of the total demand. Fig 2.1: Employment Opportunity by Major Occupational Groups

2.3 Demands for Construction related jobs

As presented by Fig 2.1, construction and extraction related jobs occupied the second highest category of demand. Based on the results from the analysis, the data which indicate the demands for these jobs are presented in Table 2.2. The results clearly presents that mason and carpenter accounted for 20.2 percent and 19.2 percent of the total demand for the construction and extraction jobs. Similarly, fixer was in third position in the hierarchy followed by mechanic, electrician, fitter, scaffolder, painter, plumber and welder.

Table 2.2: Demand for Construction related work

| Position | Total Number | Percent | Minimum Salary | Maximum Salary |
| --- | --- | --- | --- | --- |
| Mason | 3931 | 20.20 | 9250 | 40000 |
| Carpenter | 3738 | 19.21 | 9000 | 190000 |
| Fixer | 2083 | 10.70 | 11000 | 70000 |
| Mechanic/Technicians | 1846 | 9.4 | 9000 | 160000 |
| Electrician | 1630 | 8.3 | 11370 | 60000 |
| Fitter | 1591 | 8.1 | 10399 | 120000 |
| Scaffolder | 1045 | 5.3 | 12000 | 152568 |
| Painter/Denter | 795 | 4 | 10200 | 90000 |
| Plumber | 746 | 3.8 | 10800 | 140000 |
| Welder | 697 | 3.5 | 11900 | 56640 |
| Fabricator | 667 | 3.4 | 14000 | 240000 |
| Rigger | 305 | 1.5 | 10200 | 137735 |
| Installer | 130 | 0.66 | 20000 | 30000 |
| Insulator | 129 | 0.66 | 10399 | 55000 |
| Blaster | 87 | 0.44 | 11370 | 60000 |
| Laminator | 20 | 0.10 | 22000 | 22000 |
| Plater | 15 | 0.07 | 16000 | 16000 |
| Grand Total | 19455 |  |  |  |

The demand in construction, extraction, and repair and maintenance occupation hardly requires any degree. With proper skills training, individuals can get through jobs in these areas. If they have experience in the relevant field, it will be further easier to tap the employment opportunity.

Although, literacy being the minimum educational criteria, people with ability to communicate in English and prior relevant experience help them get better salary. Most of the advertisements for these occupations hardly mention any education details but to be eligible they have to undergo training for minimum 1 month.

Experienced fabricator, carpenter, technician/electrician, fitter, scaffolder, plumber, rigger can earn more than NRs 100,000 rupees per month which is of course excluding the expenses required for food and accommodation which could be also often provided by employer. The range of salary indicates that people with right skills and experience could earn as much as people with higher level of degree and skills.

Of the total 19455 demands, 11 percent was accounted for by fixer. As also presented by the data on remuneration they receive, they can earn up to NRs. 70,000 per month.

As this trade is not included in the package prepared by UNDP, inclusion of this training in the package could be helpful.

2.4 Demands for Care Givers

As indicated by data for demands in the foreign employment market, there has been good demand for care givers. Therefore, the relevant data in this opportunity was analyzed and the results are presented in Table 2.3.

Table 2.3: Demand for Care Givers

| Position | Total Number | Percent | Minimum Salary | Maximum Salary |
| --- | --- | --- | --- | --- |
| Care Giver | 1157 | 1.0 | 10215 | 97035 |
| Grand Total | 1157 |  |  |  |

(Source: Kantipur, 2008/09)

As per the data in the table, compared to the total demand for various kinds of skills, that for caregiver does not look significant. Yet, in the absolute terms, there was demand for 1,157 which is approximately 1 percent of the total (78601).

As per the information presented in the announcements, it is an opportunity mainly for women. Women with high school graduate can earn up to NRs. 70,000 per month. However, if some have appropriate training and good communication skills, an individual may earn up to NRs. 97,000.

The training packages should therefore include, session on planning, recognizing illness and depression and safety measures as well as training  sessions on how to communicate with seniors.

Language and communication skills in English, Hindi and language of the host country are additional requirements for caregivers.

2.5 Demands in Tourism related work abroad

Tourism is one of the attractive employment sectors both at local and international market.  As per the Economic Survey (2008/09), it has contributed 1.5 percent to the GDP (GoN/MoF, 2008/09) in Nepal.

The study therefore analyzed demands for tourism related work in other countries. The results are presented in Table 2.4.

Table 2.4: Demand in Tourism Sector

| Position | Total Number | Percent | Minimums alary | Maximum Salary |
| --- | --- | --- | --- | --- |
| Cook | 1064 | 25.5 |  |  |
| Crew | 674 | 16.2 | 22500 | 22500 |
| Waiter/Waitress | 583 | 14.0 | 46000 | 46000 |
| House Keeping | 374 | 9.0 | 16200 | 16200 |
| Customer Service | 346 | 8.3 | 10350 | 56000 |
| Kitchen Worker | 302 | 7.2 | 12000 | 20000 |
| Attendant | 253 | 6.1 | 10800 | 32505 |
| Steward | 195 | 4.7 | 18130 | 76000 |
| Food Server | 77 | 1.8 | 11550 | 15170 |
| Barista | 51 | 1.2 | 11550 | 15470 |
| Room Boy | 48 | 1.2 | 21670 | 68000 |
| Dish Washer | 41 | 1.0 | 12000 | 33000 |
| Hostess | 33 | 0.8 | 12000 | 61694 |
| Baker | 32 | 0.8 | 20000 | 31500 |
| Bell BOY | 25 | 0.6 | 11400 | 20864 |
| Butler | 20 | 0.5 | 20000 | 64688 |
| Buthcher | 19 | 0.5 | 8200 | 81014 |
| Juice Junkie | 12 | 0.3 | 17772 | 21910 |
| Bar Man | 10 | 0.2 | 9094 | 270000 |
| Salad Maker | 8 | 0.2 | 10104 | 64000 |
| Grand Total | 4167 |  |  |  |

From the data in Table 2.5, it is obvious that there was large demand for cook (25.5 percent) followed by crew (16.1 percent), Waiter/Waitress (13.9 percent), housekeeping (8.9 percent) and Customer Service (8.3 percent). The demands for kitchen worker, stewards, were also relatively high.

A further break down of the cook trade shows that the demand for Continental Cook is the highest followed by Chinese, Asian and Indian cook (Fig 2.2).

Fig 2.2: Demands for Cooks by Types

Similar to the demand for cooks, there has also been good demand for waiter/waitress and crews. However, language skill is a must for this kind of employment. English is the pre-requisite as the individual needs to constantly interact with clients.

The demand for this occupation by country was also analyzed and the results are presented in Table 2.5. As per the data, it is clear that United Arab Emirates accounted for half (52.2 percent) of the demand followed by Qatar (21.43 percent) and Oman (16.23 percent).

Table 2.5: Demands for Cook by Country

| Name of the Country | Cook Required | Percentage |
| --- | --- | --- |
| UAE | 556 | 52 |
| Qatar | 228 | 21 |
| Oman | 173 | 16 |
| Bahrain | 92 | 9 |
| Saudi | 10 | 1 |
| Libya | 3 | 0 |
| Maldives | 2 | 0 |
| Total | 1064 |  |

2.6 Demand for Security related Job

As indicated by the data (Fig 2.3) there is recently good demand for security related jobs. A study carried out by Pradhan et al (2004) capturing data from 2001-2002 showed a small number who went abroad for this work.  The security related jobs sector is getting popular and the demand is growing in foreign countries.

Fig 2.3: Demand in Security Related Job

As per the data in figure 2.3 altogether, 6,950 individuals which make  9 percent of the total demand have gone abroad for security related work.

This finding proves that there is good demand for security related jobs in foreign markets.

The data also shows that of the total demand for security related jobs; by far most (92 percent) was for security guards. Therefore, this fact needs to be considered while designing any kind of training.

2.7 Demands for Other Unskilled Jobs

One of the main reasons for people picking unskilled jobs is their inability to afford training and lack of access to information. Consequently these individuals are forced to work under harsh and difficult working environment with minimum remuneration.

As per the data in table 2.6, altogether 26,776 individuals who accounts for 34 percent of the total demand, went for unskilled jobs. Among them, the highest demand was for labor followed by cleaner and helper. The minimum salary offered for these individuals highlights the importance of the skill training.

Table 2.6: Demand for unskilled labor

| Position | Total Number | Percent | Minimum Salary | Maximum Salary |
| --- | --- | --- | --- | --- |
| Labor | 12979 | 48.59 | 13000 | 120000 |
| Cleaner | 5386 | 20.16 | 8000 | 50000 |
| Helper | 5311 | 19.88 | 8000 | 55000 |
| Worker | 2950 | 11.04 | 8000 | 84704 |
| Portage | 50 | 0.18 | 12035 | 12035 |
| Porters | 30 | 0.11 | 30000 | 30000 |
| Total | 26706 |  |  |  |

3.

Conclusions and Recommendations

As mentioned in Sub-Section 1.3 Methodologies, data and information on vacancy announcements made for foreign country employment was analyzed and major findings and results are presented in Section 2. Following conclusion is made based on the findings of the market signaling exercise. .

- As per the findings, Nepalese youths have been on demand in various countries, particularly the Middle East. The available data do not sufficiently indicate demand in other countries. Therefore, making efforts to understand the needs and demands of the countries where there is demand could be one priority for employment and training system in Nepal.

- There is good demand for both skilled and unskilled jobs. As mentioned in Section 2.3, with reasonable skills training, individuals can get employment opportunity that may ensure good remuneration.

- Based on the data, it can be inferred that the remuneration that is provided to individuals highly correlated with the skills and experience they possess. Therefore, this finding suggests for relevant skills training and experience.

- Although the announcements categorically do not specify the sex of the individuals, there are some trades which specially mention vacancy only for females. For instance, care giver is an opportunity highly targeted for women. Of the total demand, 5 percent was exclusively for women.

Recommendations

- There might be demands for such employment opportunities in countries other than analyzed in this study. Therefore, government has to collect information on this aspect and make necessary preparations for availing employment opportunities.

- It is necessary to offer training in the areas identified in Section 2.3 which may facilitate finding employment with better remuneration.

- As indicated by data in the relevant section, there were also high levels of demand for unskilled job. However, the remuneration they were paid was less compared to the skilled workforce. In addition, it is said that the unskilled individuals have to work in harsh environment.  The only way to avoid these difficulties is to go for proper skill training.

- Since there is good demand for care giver which could be easily taken by females with education, training and language ability, this can be targeted for females.

References

- Katmandu Post, 2009… Kathmandu.

- GoN/MoF, 2008/09, Economic Survey, Fiscal Year 2008/09, GoN/ MoF, Kathmandu

- Pradhan, H., Acharya, A. and Neupane M. (2004), Demands for Labor in Foreign Countries, Council for technical Education and Vocational Training, Bhaktapur.

The term “programme’ is used for programmes, joint programmes and projects

Priority Area for the Peace-building Fund; Sector for the UNDG ITF

The start date is the date of the first transfer of the funds from the MDTF Office as Administrative Agent. Transfer date is available on the MDTF Office GATEWAY (http://mdtf.undp.org).

All activities for which a Participating Organization is responsible under an approved MDTF programme have been completed. Agencies to advise the MDTF Office

Participants have just started completing trainings and will be facilitated for possible employment and micro-credit linkages. Some are busy preparing their business plans while participants under VST appeared for skill testing conducted by national body for technical training.

Of those opted for Health Training, some are awaiting the prerequisite entrance exams as scheduled in the summer months while others are on stand-by pending achievement of required quota of participants in the specific courses.