Vietnam

| Programme Title: | Green Production and Trade to Increase Income and Employment Opportunities for the Rural Poor |
| --- | --- |
| Programme number & MDTF ref: | MDGF-2065-D-VNM (67261) |
| Window: | MDGF Private Sector Development |
| Approved Budget by NSC (US$): | 4 million |
| Participating Organizations: | FAO, ILO, ITC*, UNCTAD*, UNIDO |
| First Tranche transferred on: | 2-Mar-2010 |

*ITC and UNCTAD are two non-resident agencies and ITC is the lead UN coordinating agency

ACTIVITIES Reported:

Main Substantive Activities:

Baseline and value chains studies for rattan and bamboo, lacquer, sericulture, hand-made paper, and seagrass completed and validated. Training materials prepared and national trainers have been trained in a number of areas: (i) cultivation of raw materials; (ii) occupational safety and health; (iii) business management; (iv) Cleaner Production and Design for Sustainability: (v) group formation. Companies/enterprises supported by a team of foreign designers to develop new sustainable product collections that meet market demand abroad. Support to companies before/during/after trade fair participation, including exhibition of new product collections, resulted in a large number of enquiries and orders. Vietcraft supported in the successful organization of the International home decor and giftware fair ‘LifeStyle Vietnam’ in HCMC, thereby raising the profile and competitiveness of Viet Nam as a key exporter. Local dialogue and ownership at province level strengthened through LED Forums. Entrepreneurial behaviours and skills of company managers/owners strengthened.

Problems and lessons learned:

The coordination among the five agencies needed improvement at the start of the Programme. In order to overcome this, the PMU has developed common working modalities that were agreed by 5 agencies at PMC level. Coordination has improved since. The design of the Joint programme was not detailed enough to determine precisely what was needed to upgrade value chains concerns in target localities.

The programme reports relevant linkage to the UNDAF: Yes

The programme has communications strategy in place: Yes

CHARTS & FIGURES

As of 31 December 2010