CENTRAL FUND FOR INFLUENZA ACTION

PROGRAMME QUARTERLY PROGRESS UPDATE

30 June 2008

| Participating UN or Non-UN Organization: | World Food Programme |  | UNCAPAHI Objective(s) covered: |  | Objective 7 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Implementing Partner(s): | NA |  |  |  |  |  |
| Programme Number: | CFIA- A12 |  |  |  |  |  |
| Programme Title: | Supporting the Humanitarian Common Services through provision of data management and mapping tools |  |  |  |  |  |
| Total Approved Programme Budget: | US$ 279,484 |  |  |  |  |  |
| Location: | AHI pandemic humanitarian response operations with focus and roll-out in candidate countries and logistic corridors |  |  |  |  |  |
| MC Approval Date: | 20 February 2008 |  |  |  |  |  |
| Programme Duration: | 12 Months | Starting Date: | 04/03/2008 | Completion Date: |  | 28/02/2009 |
| Funds Committed: | US$ 115, 284 |  |  | Percentage of Approved: |  | 41% |
| Funds Disbursed: | US$ 18,284 |  |  | Percentage of Approved: |  | 6% |
| Expected Programme Duration: | 12 Months | Forecast Final Date: | 28/02/2009 | Delay (Months): |  | None |

| Outcomes: | Achievements/Results: | Percentage of planned: |
| --- | --- | --- |
| An online user-friendly mapping and information dynamic mapping tool for provision of Humanitarian Common Services in a pandemic environment is created. | Schedule of activities and achievables outlined. Technical criteria defined in detail with input received from a number of stakeholders. | 24 % |
| Qualitative achievements against outcomes and results: |  |  |
| In line with the outcome as outlined above, the basic technical details that were defined and agreed upon are : - methodology for a user friendly mapping tool to visualize contingency plans with focus on food assistance and logistic corridors - developed analysis tools, to highlight most suitable solutions during the changing scenarios associated with pandemic humanitarian response operations |  |  |