YEM Color-Coded Annual Work Plan for the Second Year of Implementation

Draft for Quarter 2 2010

Green            = Completed, Yellow           = Ongoing, Red          = Delayed, Purple          = Not Started.

| Annual targets | Activities | TIME FRAME YEAR 2 | UN AGENCY | RESPONSIBLE PARTY | PLANNED BUDGET |
| --- | --- | --- | --- | --- | --- |
|  |  | Q1 | Q2 | Q3 | Q4 |  |  | Source of Funds | Budget Description | Amount |

| JP Output 1.1: National migration policy informed by stronger national knowledge base and knowledge sharing |
| --- |
| Stakeholders agreed on the platform for the migration information, and its format and objectives | 1.1.1 (Y1 1.1.2, RF1.1.2) Technical meeting on establishing a platform for migration information. | * G | G |  |  | ILO UNFPA | CASS | MDG-F | Training | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 1.1.2 (Y1 1.1.3, RF 1.1.2) Compilation of required information with standardized data definitions | * Y | Y |  |  | ILO | CASS | MDG-F | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Equipment | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | MISC | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 1.1.3 (RF 1.1.2) Select appropriate media, establish platform, compile information, incl. existing data, research papers, JP documents. | P | * Y | * | * | ILO | CASS | MDG-F | Personnel | 5,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 10,000 |
|  |  |  |  |  |  |  |  |  | Total | 15,000 |
|  |  | P | * Y | * |  | UNFPA | CASS | MDG-F | Contracts | 15,000 |
|  |  |  |  |  |  |  |  |  | Total | 15,000 |
|  | 1.1.4 (RF 1.1.3) Produce white papers, hold seminars and conduct launches | P | P | * | * | ILO | CASS | MDG-F | Personnel | 5,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 7,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 18,000 |
|  |  |  |  |  |  |  |  |  | Supplies | 5,000 |
|  |  |  |  |  |  |  |  |  | Total | 35,000 |
|  |  | P | * Y | * | * | ILO | CALSS | MDG-F | Contracts | 10,000 |
|  |  |  |  |  |  |  |  |  | Total | 10,000 |

| JP Output 1.2: Policy advocated and awareness raised and capacity built between and amongst government, civil society and young people at national and local levels. |
| --- |
| A coordinated mechanism of registration of migrant/left behind children in sending and receiving areas developed and piloted for replication and policy formulation, and advocated for upscaling | 1.2.1 (RF 1.2.1) Identify national consultants and establish expert team | * Y | Y |  |  | UNICEF | NWCCW MPS | MDG-F | Personnel (consultants) | 7,000 |
|  |  |  |  |  |  |  |  |  | Total | 7,000 |
|  | 1.2.2 (RF 1.2.1) Conduct field assessment in pilot sites on mechanism of registration of migrants, especially migrant and left behind children, and submit report with recommendation | P | * Y | * |  | UNICEF | NWCCW MPS | MDG-F | Personnel (travel) | 8,000 |
|  |  |  |  |  |  |  |  |  | Total | 8,000 |
| A dialogue mechanism and social/legal support network developed for migrants and young people in rural areas | 1.2.3 (Y1 1. 2.4, RF1.2.2) Develop and test counseling mechanism for returned migrants and pre-departure youth in selected sites, through cooperation with village administrators, specialized institutes, enterprises to provide a better mental preparation for their urban life | * Y | * Y |  |  | UNESCO | DRC CASS | MDG-F | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 3,887 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Total | 3,887 |
|  | 1.2.4 (Y1 1.2.3, RF 1.2.2) Develop and test counseling mechanism for returned migrants and pre-departure youth in selected sites, through cooperation with village administrators, specialized institutes, enterprises to provide a better mental preparation for their urban life | * R | * Y | * | * | UNESCO | DRC | MDG-F | Contracts | 30,000 |
|  |  |  |  |  |  |  |  |  | Personnel | 10,000 |
|  |  |  |  |  |  |  |  |  | Total | 40,000 |
|  | 1.2.5 (Y1 1.2.5, RF1.2.3) Organize Regular Inter-ministerial Forums to facilitate situation-and-policy-oriented dialogue and cooperation between and among government, civil society organizations, young migrant representatives and other related individuals | * Y | * Y |  |  | UNESCO | DRC CASS | MDG-F | Training | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 10,000 |
|  |  |  |  |  |  |  |  |  | Total | 10,000 |
|  | 1.2.6 (RF 1.2.3) Organize Regular Inter-ministerial Forums to facilitate situation-and-policy-oriented dialogue and cooperation between and among government, civil society organizations, young migrant representatives and other related individuals | P | * Y |  | * | UNESCO | DRC | MDG-F | Contract | 27,000 |
|  |  |  |  |  |  |  |  |  | Personnel | 8,000 |
|  |  |  |  |  |  |  |  |  | Total | 35,000 |
|  | 1.2.7 (RF 1.2.4) Conduct trainings for civil society actors to improve their working strategies in order to effectively represent young migrants’ interests in dialogues with government/ policy makers. | P | * Y | * | * | UNESCO | DRC | MDG-F | Contracts | 33,000 |
|  |  |  |  |  |  |  |  |  | Personnel | 9,000 |
|  |  |  |  |  |  |  |  |  | Total | 42,000 |
| Advocacy and awareness raising to promote social inclusion of migrant workers and to protect their rights in risk sectors | 1.2.8 (Y1 1.2.6, RF1.2.5) Produce a guideline for creation of social/legal support network for migrants in risk sectors | * Y | * Y |  |  | UNESCO | DRC CASS | MDG-F | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 16,000 |
|  |  |  |  |  |  |  |  |  | Total | 16,000 |
|  | 1.2.9 (RF 1.2.5) Produce a guideline for creation of social/legal support network for migrants in risk sectors | P | * Y | * | * | UNESCO | DRC (+Tsinghua University) | MDG-F | Contract | 19,000 |
|  |  |  |  |  |  |  |  |  | Personnel | 4,000 |
|  |  |  |  |  |  |  |  |  | ODC | 2,000 |
|  |  |  |  |  |  |  |  |  | Total | 25,000 |
| Key findings on barriers of migrants to urban society, issues and challenges of governance for social inclusion, to be prepared for awareness campaigns | 1.2.10 (RF 1.2.6) Complete the development of tools, contents, and awareness campaign activities | * Y | * Y |  |  | UNDP | MOCA | MDG-F | Contract | 16,000 |
|  |  |  |  |  |  |  |  |  | Total | 16,000 |
|  | 1.2.11 (RF 1.2.7) Implement awareness raising activities on participatory community governance and social inclusion for young migrant workers. | P | * Y | * | * | UNDP | MOCA | MDG-F | Training of counterparts | 37,000 |
|  |  |  |  |  |  |  |  |  | Total | 37,000 |
| Advocacy and gender awareness raised to promote social inclusion of domestic workers along with the need for legislative reform and protection for young female domestic workers. | 1.2.12 (RF 1.2.10) Organize training workshops for policy makers and administrators from labor and social security departments, and relevant civil society partners on issues and concerns of women domestic workers, including on laws and policies related to domestic workers, social protection, gender based discrimination etc. | P | * R |  |  | UNIFEM | ACWF | MDG-F | Training of counterparts | 15,000 |
|  |  |  |  |  |  |  |  |  | Personnel | 2,000 |
|  |  |  |  |  |  |  |  |  | Total | 17,000 |
|  | 1.2.13 (RF 1.2.11) Organize consultations with recruiting agencies, and relevant civil society partners in recruitment and contracts, including ethical code of conduct. | P | * R |  |  | UNIFEM | ACWF | MDG-F | Training of counter-parts | 7,000 |
|  |  |  |  |  |  |  |  |  | Personnel | 3,000 |
|  |  |  |  |  |  |  |  |  | Total | 10,000 |

| JP Output 1.3 Policy implementation strengthened through piloting of models and the participation of migrants in policy dialogue. |
| --- |
| Participatory consultations to better understand migration trends, institutional mechanism to protect young migrants | 1.3.1 (RF 1.3.1) Policy consultation conference with participation of government, enterprises, communities, schools and young migrant workers, to present and examine the findings of studies in Hangzhou and Changsha, analyze institutional arrangement and existing problems concerning social inclusion for migrant workers, and discuss the solutions | P | * R |  |  | UNDP | NDRC | MDG-F | Training of counterparts | 26,000 |
|  |  |  |  |  |  |  |  |  | Total | 26,000 |
|  | 1.3.2 (RF 1.3.1) “Policy report on public service to promote social inclusion for migrant worker”, based on results of studies and consultations done at national and local levels | P | * Y | * |  | UNDP | NDRC | MDG-F | Contract | 20,000 |
|  |  |  |  |  |  |  |  |  | Total | 20,000 |
|  | 1.3.3 (RF 1.3.2) Designing, consultation and initial testing of performance indicator system on social inclusion for mobile population in receiving urban communities, considering to incorporate some relevant existing urban performance indicators | P | P | * | * | UNDP | NDRC | MDG-F | contract | 10,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 10,000 |
|  |  |  |  |  |  |  |  |  | Total | 20,000 |
|  | 1.3.4 ( RF 1.3.2) Workshop to disseminate the “policy report on public service to promote social inclusion for migrant workers”, engaging representatives from different sectors at national and local levels | P | P |  | * | UNDP | NDRC | MDG-F | Training of counterparts | 10,000 |
|  |  |  |  |  |  |  |  |  | Total | 10,000 |
| Community demonstrative mechanism implemented and capacity built for CSOs’ and social workers’ delivery of social inclusion programmes | 1.3.5 ( RF 1.3.3) Identify institutional issues, and existing national and international practices; design implementation framework and guideline for delivery mechanism between CSOs, social workers and governments; draft framework for CSO capacity building; and provide training programs for selected CSOs to implement grassroots programs | P | * Y | * | * | UNDP | MOCA | MDG-F | contracts | 44,000 |
|  |  |  |  |  |  |  |  |  | Total | 44,000 |
|  | 1.3.6 ( RF 1.3.4) Mechanism for community social programmes are executed in 5 pilot districts by CSOs selected through bidding process | * Y | * Y | * | * | UNDP | MOCA | MDG-F | contract | 150,000 |
|  |  |  |  |  |  |  |  |  | Total | 150,000 |
|  | 1.3.7 (RF 1.3.5) Conduct monitoring and mid-term assessment of the 5 pilots, for the purpose of up-scaling | P | Y | * |  | UNDP | MOCA | MDG-F | Personnel | 4,000 |
|  |  |  |  |  |  |  |  |  | Total | 4,000 |
| Platform developed for sharing the knowledge and experiences to protect rights of domestic workers especially domestic workers by national labor laws. | 1.3.8 (RF 1.3.6) Develop policy dialogues involve CSOs and female migrant workers with government to address gender concerns particularly the needs of domestic workers, including recruitment/contract practices, procedures, and protection measures | P | P |  | * | UNIFEM | ACWF | MDG-F | Training of counter-parts | 7,000 |
|  |  |  |  |  |  |  |  |  | Personnel | 3,000 |
|  |  |  |  |  |  |  |  |  | Total | 10,000 |
| A set of guidelines for employment services and MOUs between sending and receiving areas, and a piloting strategy developed | 1.3.9 (RF 1.3.9) Campaign carried out in pilot sites to encourage more young people to migrate through formal channels. | P | * Y | * |  | ILO | MOHRSS | MDG-F | Contracts | 10,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 5,000 |
|  |  |  |  |  |  |  |  |  | Total | 15,000 |
|  | 1.3.10 (RF 1.3.10) Local system developed to better share job information in pilot sites. | P | * Y | * |  | ILO | MOHRSS | MDG-F | Contracts | 10,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 5,000 |
|  |  |  |  |  |  |  |  |  | Total | 15,000 |
|  | 1.3.11 (RF 1.2.11) Monitoring of private recruitment agencies to build network of legitimate formal migration channels in area, and capacity building as required. | P | P | * | * | ILO | MOHRSS | MDG-F | Contracts | 10,000 |
|  |  |  |  |  |  |  |  |  | Total | 10,000 |
|  | 1.3.12 (RF 1.3.12) Capacity building and participatory approaches adopted to improve the quality of career guidance and counseling (using tools developed under 2.2.5). |  |  | * | * | ILO | MOHRSS | MDG-F | Training of counterparts | 15,000 |
|  |  |  |  |  |  |  |  |  | Total | 15,000 |
|  | 1.3.13 (RF 1.3.13) Internal review of employment services in pilot areas, specifically looking at the effect on decent work indicators, and workshops at provincial and national level to highlight results from pilot areas. | P | P | * | * | ILO | MOHRSS | MDG-F | Contracts | 10,000 |
|  |  |  |  |  |  |  |  |  | Total | 10,000 |

| JP Output 2.1 Access to non-formal education for migrants to prevent premature entry into the labor force improved. |
| --- |
|  | 2.1.1 (Y1 2.1.3, RF2.1.3) Develop flexible courses for out-of-school children and over-age children | * G | G |  |  | UNICEF | CAST | MDG-F | Contract | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
| Flexible courses developed and pilot-tested for out-of-school children and over-aged children | 2.1.2 (RF 2.1.4) Flexible courses developed, tested and adjusted both in sending and receiving areas. | * Y | * Y | * | * | UNICEF | CAST | MDG-F | Training of counterparts | 40,000 |
|  |  |  |  |  |  |  |  |  | Total | 40,000 |
|  | 2.1.3 (RF 2.1.4) Carry out TOT training for trainers | P | * R | * | * | UNICEF | CAST | MDG-F | Training of counterparts | 20,000 |
|  |  |  |  |  |  |  |  |  | Total | 20,000 |
|  | 2.1.4 (RF 2.1.5) Courses provider and channels identified; Courses could be accessed by out-of-school children and over-aged children. | P | * R | * |  | UNICEF | CAST | MDG-F | Personnel | 11,545 |
|  |  |  |  |  |  |  |  |  | Total | 11,545 |
|  | 2.1.5 (RF 2.1.5) Workshop on experience sharing and courses promotion. | P | P |  | * | UNICEF | CAST | MDG-F | Contracts | 10,000 |
|  |  |  |  |  |  |  |  |  | Total | 10,000 |
| Volunteer tutoring/mentoring programme implemented for in-school migrant youth, evaluated and documented. | 2.1.6 (Y1 2.1.7, RF2.1.10) Implement, monitor and assess suitability of volunteer programme and undertake course corrections. | * Y | Y |  |  | UNDP | UNV/CYVA | MDG-F | Transport | 10,000 |
|  |  |  |  |  |  |  |  |  | Supplies | 10,000 |
|  |  |  |  |  |  |  |  |  | Total | 20,000 |
|  | 2.1.7 (RF 2.1.10) Implement, monitor and assess suitability of volunteer programme and undertake course corrections | * Y | * Y |  |  | UNDP | UNV/CYVA | MDG-F | Personnel | 54,867 |
|  |  |  |  |  |  |  |  |  | Total | 54,867 |

| JP Output 2.2 Access to vocational training for migrants and young people in rural areas improved to prevent premature entry to the labor force and increase self-employment opportunities. |
| --- |
|  | 2.2.1 (Y1 2.2.2, RF2.2.2) Review of curriculum of regular junior secondary schools and secondary TVET schools in sending places | * Y | G |  |  | UNESCO | CNIER | MDG-F | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 3611 |
|  |  |  |  |  |  |  |  |  | Total | 3,611 |
| Training needs of young people in the rural areas and young migrant workers in urban areas identified and specific training tools developed for them. | 2.2.2 (Y1 2.2.3, RF2.2.3) Assess the educational and skill profiling as well as employability of young graduates of the schools mentioned in 2.2.2 | * Y | G |  |  | UNESCO | CNIER | MDG-F | Personnel | 3,400 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  | Y |  |  | ILO | MOHRSS | MDG-F | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Total | 3,400 |
|  | 2.2.3 (RF 2.2.3) Assess educational and skill profiling as well as employability of graduates of regular junior secondary schools and secondary TVET schools in sending areas (incl. young migrant tracer study) | * R | * Y |  |  | UNESCO | CAEA | MDG-F | Personnel | 13,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 7,000 |
|  |  |  |  |  |  |  |  |  | Total | 20,000 |
|  | 2.2.4 (Y1 2.2.4, RF2.2.4) Identify knowledge and skills needed to upgrade young graduates’ employability and develop recommendations on policy and curriculum | * Y | G |  |  | UNESCO | CNIER | MDG-F | Personnel | 5,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Total | 5,000 |
|  | 2.2.5 (RF 2.2.4) Identify knowledge and skills needed to upgrade young graduates’ employability and develop recommendations on policy and curriculum. | * R | * G |  |  | UNESCO | CAEA | MDG-F | Contracts | 10,000 |
|  |  |  |  |  |  |  |  |  | Total | 10,000 |
|  | 2.2.6 (Y1 2.2.5, RF2.2.5) Develop apprenticeship programme, work study schemes and occupational guidance and counseling programme Work under this output is reliant on the completion of related research. The first drafts of baseline surveys delivered by advisory team were returned for revisions and supplementary survey activities have been conducted to ensure the quality of reports and sufficient information for developing the training programmes. Currently in process of finalizing the reports. | * R | R |  |  | ILO | MOHRSS | MDG-F | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 2.2.7 (Y1 2.2.6, RF2.2.6) Test pre-employment training programmes in sending places | * R | R |  |  | ILO | MOHRSS | MDG-F | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 2.2.8 (RF 2.2.6) Test pre-employment training programmes in sending areas with various training institutions. Work under this output is reliant on the completion of related research. | P | * R | * |  | ILO | MOHRSS | MDG-F | Personnel | 9,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 26,000 |
|  |  |  |  |  |  |  |  |  | Supplies | 5,000 |
|  |  |  |  |  |  |  |  |  | Total | 40,000 |
|  | 2.2.9 (Y1 2.2.7, RF2.2.7) Conduct a study to evaluate skills and employability of young people/migrants and analyze their training needs. | * Y | Y |  |  | ILO | MOHRSS | MDG-F | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 2.2.10 (Y1 2.2.8, RF2.2.7) Skills and employability evaluation workshop Work under this output is reliant on the completion of related research. | * R | Y |  |  | ILO | MOHRSS | MDG-F | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 2.2.11 (Y1 2.2.9, RF 2.2.8) Conduct study to define key sectors for absorbing young people/migrants as employees and as potential entrepreneurs | * Y | Y |  |  | ILO | UNIDO/MOHRSS | MDG-F | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 2.2.12 (Y1 2.2.10, RF 2.2.8) Present findings at workshops with participation of youth and migrant representatives for feedback to design sector specific skills training Work under this output is reliant on the completion of related research. | * R | Y |  |  | ILO | UNIDO |  | Training | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 2.2.13 (Y1 2.2.11, RF 2.2.9) Conduct study to evaluate labour demand and skills requirements of transnational companies and other private sector entities in order to tailor training for young people/migrants Currently in process of finalizing the reports. | * Y | Y |  |  | ILO | UNIDO/MOHRSS | MDG-F | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 2.2.14 (Y1 2.2.12, RF 2.2.9) Present findings at workshops with participation of youth and migrant representatives for feedback to design appropriate technical training | * R | Y |  |  | ILO | UNIDO/MOHRSS | MDG-F | Training | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 2.2.15 (Y1 2.2.13, RF2.2.10) Develop skills up-grading training for young migrants in receiving places Work under this output is reliant on the completion of related research and stakeholder consultation. | * R | * R |  |  | ILO | MOHRSS | MDG-F | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 2.2.16 (Y1 2.2.14, RF 2.2.10) Develop skills up-grading training for young migrants in receiving places Work under this activity is reliant on the completion of related research and stakeholder consultation. | * R | * R |  |  | ILO | UNIDO/MOHRSS | MDG-F | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 2.2.17 (RF 2.2.10) Develop skills upgrading programmes based on labor/ sector training needs analysis. Work under this activity is reliant on the completion of related research and stakeholder consultation. | * R | * R |  |  | ILO | MOHRSS | MDG-F | Personnel | 5,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 10,000 |
|  |  |  |  |  |  |  |  |  | ODC | 5,000 |
|  |  |  |  |  |  |  |  |  | Total | 20,000 |
|  |  | * R | * R |  |  | UNIDO | MOHRSS | MDG-F | Contracts | 20,000 |
|  |  |  |  |  |  |  |  |  | Total | 20,000 |
|  | 2.2.18 (RF 2.2.11) Pilot-test skills upgrading training needed in the private sector and skills recognition programmes. Work under this activity is reliant on the completion of related research and stakeholder consultation. | P | * R | * |  | ILO | MOHRSS | MDG-F | Training of counterparts | 15,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 5,000 |
|  |  |  |  |  |  |  |  |  | supplies | 5,000 |
|  |  |  |  |  |  |  |  |  | Total | 25,000 |
|  |  | P | * R | * |  | UNIDO | MOHRSS | MDG-F | Contracts | 30,000 |
|  |  |  |  |  |  |  |  |  | Total | 30,000 |
|  | 2.2.19 (Y1 2.2.15, RF2.2.12) Adapt SYB training for rural youth | * R | R |  |  | ILO | MOHRSS | MDG-F | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Equipment | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 2.2.20 (Y1 2.2.16, RF 2.2.12) Develop technical business start up training for rural youth | * R | * R |  |  | ILO | UNIDO/MOHRSS | MDG-F | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 2.2.21 (RF 2.2.12) Develop skills, self-employment, management and productivity-improvement upgrading training for rural youth. Work under this activity is reliant on the completion of related research and stakeholder consultation. | P | * R |  |  | UNIDO | MOHRSS | MDG-F | Contracts | 10,000 |
|  |  |  |  |  |  |  |  |  | Total | 10,000 |
|  | 2.2.22 (Y1 2.2.17, RF2.2.13) Pilot test of SYB for rural youth Work under this output is reliant on the completion of related research. | * R | R |  |  | ILO | MOHRSS | MDG-F | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 2.2.23 (Y1 2.2.18, RF 2.2.13) Pilot test technical business start up training for rural youth Work under this output is reliant on the completion of related research. | * R | R |  |  | ILO | UNIDO/MOHRSS | MDG-F | Contract | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 2.2.24 (RF 2.2.13) Pilot-test business start-up training and related services for rural youth. Work under this activity is reliant on the completion of related research and stakeholder consultation. | P | * R | * |  | ILO | MOHRSS | MDG-F | Personnel | 10,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 10,000 |
|  |  |  |  |  |  |  |  |  | Total | 20,000 |
|  |  | P | * R | * |  | UNIDO | MOHRSS | MDG-F | Contracts | 20,000 |
|  |  |  |  |  |  |  |  |  | Total | 20,000 |
|  | 2.2.25 (Y1 2.2.19, RF 2.2.14) Train youth associations in sending places to develop business opportunities | * G | * G |  |  | ILO | ACYF | MDG-F | Training | 0 |
|  |  |  |  |  |  | ILO | UNIDO/ACYF | MDG-F | Training | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 2.2.26 (RF 2.2.14) Train youth associations to work with youth groups to generate business ideas, launch enterprises, and create mentoring and partnership opportunities. | P | * Y | * |  | ILO | ACYF | MDG-F | Personnel | 5,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 10,000 |
|  |  |  |  |  |  |  |  |  | Total | 15,000 |
|  |  | P | * Y | * |  | UNIDO | ACYF | MDG-F | Contracts | 20,000 |
|  |  |  |  |  |  |  |  |  | Total | 20,000 |

| JP Output 2.3 Safe migration information and training for young people strengthened. |
| --- |
|  | 2.3.1 (Y1 2.3.1, RF2.3.1) Bring together expert team (including young migrants and partners from health, labor, gender, and education fields) to evaluate needs of young migrants and the existing safe migration/life-skills training materials | * G | G |  |  | UNFPA | CFPA | MDG-F | Contract | UNFPA 2,500 |
|  |  |  |  |  |  |  |  |  |  | UNIFEM 2,500 |
|  |  |  |  |  |  |  |  |  | Total | 5,000 |
| Common and comprehensive Life Skills Training Package developed for different delivery channels based on the needs of migrants | 2.3.2 (RF 2.3.2) Pilot areas and schools selected. Set up link with pilot sites counterparts, liaison and planning strategies | Y | * Y |  | * | UNICEF | ACWF and local education authorities in Cang County | MDG-F | Training of counterparts | 15,000 |
|  |  |  |  |  |  |  |  |  | Total | 15,000 |
|  | 2.3.3 (Y1 2.3.5, RF2.3.4) Produce and Print Life Skills Training Package Printing is expected to start in July. | * R | * R |  |  | UNICEF | ACWF | MDG-F | Contracts | 35,000 |
|  |  |  |  |  |  |  |  |  | Total | 35,000 |
|  | 2.3.4 (RF 2.3.5) Carry out TOT programme for schoolteachers and trainers. | * Y | * Y |  |  | UNICEF | ACWF and local education authorities in Cang County | MDG-F | Personnel (training) | 20,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 40,000 |
|  |  |  |  |  |  |  |  |  | ODC | 20,000 |
|  |  |  |  |  |  |  |  |  | Total | 80,000 |
|  | 2.3.5 (RF 2.3.6) Implement training and skills raised among students. Conduct TOT training for students in selected schools | P | Y | * | * | UNICEF | ACWF and local education authorities in Cang County | MDG-F | Personnel (training) | 6,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 10,000 |
|  |  |  |  |  |  |  |  |  | ODC | 810 |
|  |  |  |  |  |  |  |  |  | Total | 16,810 |
|  | 2.3.6 (Y1 2.3.7, RF2.3.7) Life skill training in pilot schools monitored, evaluated and results/lessons learned and documented | * G | * G |  |  | UNICEF | ACWF | MDG-F | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 2.3.7 (RF 2.3.7) Evaluate the effectiveness of the trainings, document good practice/ lessons learned. | P | * Y |  | * | UNICEF | ACWF and local education authorities in Cang County | MDG-F | Personnel (consultants) | 5,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 5,000 |
|  |  |  |  |  |  |  |  |  | ODC | 2,000 |
|  |  |  |  |  |  |  |  |  | Total | 12,000 |
|  | 2.3.8 (Y1 2.3.9, RF2.3.8) Print Life Skills Training Package for vocational training institutions in pilot sites | * Y | * Y |  |  | ILO | MOHRSS | MDG-F | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 2.3.9 (RF 2.3.8) Develop, test and revise the Life Skills Training Package for young people in vocational training institutions. | P | * Y | * | * | ILO | MOHRSS | MDG-F | Contracts | 10,000 |
|  |  |  |  |  |  |  |  |  | Total | 10,000 |
|  | 2.3.10 (RF 2.3.9) Carry out local level training for staff of vocational training institution, and refresher TOT. | P | * Y | * | * | ILO | MOHRSS | MDG-F | Training of counterparts | 25,000 |
|  |  |  |  |  |  |  |  |  | Total | 25,000 |
|  | 2.3.11 (Y1 2.3.11, RF2.3.10) Fine-tune Life Skills Training Programme for workplaces in pilot sites | * R | * Y |  |  | ILO | CEC/ACFTU | MDG-F | Contract | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 2.3.12 (Y1 2.3.12, RF2.3.10) Print Life Skills Training Package for workplaces in pilot sites | * R | * Y |  |  | ILO | CEC/ACFTU | MDG-F | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 2.3.13 (RF 2.3.10) Develop, test and revise the life skills training package for young migrants in workplaces. | P | * Y | * | * | ILO | ACFTU/ CEC | MDG-F | Training of counterparts | 6,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 4,000 |
|  |  |  |  |  |  |  |  |  | Total | 10,000 |
|  | 2.3.14 (Y1 2.3.13, RF2.3.11) Carry out local training on delivering Life Skills package to trainers in workplaces in pilot sites | * R | Y |  |  | ILO | CEC/ACFTU | MDG-F | Training | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 2.3.15 (RF 2.3.11) Carry out local level training for workplace training staff and local volunteers. | P | * Y | * | * | ILO | ACFTU/ CEC | MDG-F | Personnel | 5,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 15,000 |
|  |  |  |  |  |  |  |  |  | Total | 20,000 |
|  | 2.3.16 (Y1 2.3.14, RF2.3.12) Develop Life Skills Training modules for community centers in pilot sites | * Y | * Ｇ |  |  | UNESCO | CAEA/CNIER | MDG-F | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Personnel | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 1,000 |
|  |  |  |  |  |  |  |  |  | Misc. | 3,190 |
|  |  |  |  |  |  |  |  |  | Total | 4,190 |
|  | 2.3.17 (RF 2.3.12 and 2.3.13) Carry out training for community center staff and local volunteers. | * R | * Y | * | * | UNESCO | CAEA | MDG-F | Personnel | 13,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 42,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 15,000 |
|  |  |  |  |  |  |  |  |  | Total | 70,000 |
|  | 2.3.18 (RF 2.3.14) Design and deliver TOT training for trainers identified from pilot sites on life skills, protection of labor rights, relevant support services, HIV/AIDS prevention, and violence against women and so on | P | * R |  |  | UNIFEM | ACWF | MDG-F | Training of counterparts | 20,000 |
|  |  |  |  |  |  |  |  |  | Personnel | 2,000 |
|  |  |  |  |  |  |  |  |  | Total | 22,000 |
|  | 2.3.19 (Y1 2.3.16, RF2.3.15) Print Life Skills Training modules for peer-education in pilot sites | * R | * Y |  |  | UNFPA | CFPA | MDG-F | Contracts | 13,000 |
|  |  |  |  |  |  |  |  |  | Total | 13,000 |
|  | 2.3.20 (RF 2.3.15) Carry out peer education trainings using LST package | P | * Y | * |  | UNFPA | CFPA | MDG-F | Contract | 18,000 |
|  |  |  |  |  |  |  |  |  | Personnel | 2,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 20,000 |
|  |  |  |  |  |  |  |  |  | Total | 40,000 |

| JP Output 3.1 Registration of migrant children promoted to enhance their protection and access to social services. |
| --- |
| Standard operation procedure for the registration and referral of migrant children developed and implemented in existing pilot receiving cities with a large inflow of migrants | 3.1.1 (R F 3.1.3) Advocacy of replication of the standard registration system in the pilot sites | P | * Y | * |  | UNICEF | NWCCW MPS | MDG-F | Training of counterparts | 15,000 |
|  |  |  |  |  |  |  |  |  | Total | 15,000 |
|  | 3.1.2 (RF 3.1.3 ) Capacity building including purchase supplies and training in SOPs for registration and referral of migrant children for registration staff , community workers and referral of children in the pilot sites | P | * Y | * |  | UNICEF | NWCCW MPS | MDG-F | Supplies, Commodities, Equipment and Transport | 20,000 |
|  |  |  |  |  |  |  |  |  | Personnel (training) | 25,000 |
|  |  |  |  |  |  |  |  |  | Total | 45,000 |
|  | 3.1.3 (RF 3.1.4) Technical support in project implementation and field monitoring. | * P | * Y | * | * | UNICEF | NWCCW MPS | MDG-F | Contracts | 26,000 |
|  |  |  |  |  |  |  |  |  | Personnel (travel) | 8,000 |
|  |  |  |  |  |  |  |  |  | Total | 34,000 |
| A coordinated mechanism of registration of migrant/left-behind children between sending and receiving areas developed and piloted for replication and policy formulation at local and national levels | 3.1.4 (RF 3.1.8) Training on child rights and services delivery for government stakeholders involved in the registration, referral services and supports for migrant and left behind children. | P | * Y | * | * | UNICEF | NWCCW MPS | MDG-F | Training of counterparts | 28,000 |
|  |  |  |  |  |  |  |  |  | Personnel (training) | 40,000 |
|  |  |  |  |  |  |  |  |  | Total | 68,000 |
|  | 3.1.5 (RF 3.1.9) Review the application of the registration system with a focus on the sharing of data/information between the sending and receiving areas and improve the system as necessary | P | P | * | * | UNICEF | NWCCW | MDG-F | Personnel (consultants) | 8,000 |
|  |  |  |  |  |  |  |  |  | Total | 8,000 |

JP Output 3.2 Community centers enhanced in providing comprehensive, gender responsive learning opportunities, information and referral services.

|  | 3.2.1 (Y1 3.2.1, RF3.2.1) Conduct expert review of existing community centers and identify the roles and responsibilities of community learning centers | * Y | * Ｇ |  |  | UNESCO | CAEA ACWF | MDG-F | Contracts | 0 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | Travel | UNESCO 3,000 |
|  |  |  |  |  |  |  |  |  | Total | 3,000 |
|  | 3.2.2 (Y1 3.2.2, RF3.2.2) Build up network with local communities, training providers, service providers, employers, local governments, community organizations, labor unions, etc. | * Y | * Ｇ |  |  | UNESCO | CAEA ACWF | MDG-F | Training | 0 |
|  |  |  |  |  |  |  |  |  | Misc. | UNESCO 1,000 |
|  |  |  |  |  |  |  |  |  | Total | 1.000 |
| Community centers enhanced in providing comprehensive gender responsive learning opportunities, information and referral service | 3.2.3 (RF 3.2.2) Build up network with local communities, training providers, service providers, employers, local governments, community organizations, labor unions, etc. | * R | * Y | * | * | UNESCO | CAEA | MDG-F | Contracts | 20,000 |
|  |  |  |  |  |  |  |  |  | Total | 20,000 |
|  |  | Y | * Y |  | * | UNICEF | ACWF and local street government, communities in Tianjin | MDG-F | Training of Counterparts | 4,000 |
|  |  |  |  |  |  |  |  |  | Total | 4,000 |
|  | 3.2.4 (Y1 3.2.3, RF3.2.3) Establish relations with local partners and draw up strategic plan to improve young people’s access to job information, labor rights protection, training opportunities, etc. | * Y |  |  |  | ILO | MOHRSS | MDG-F | Training | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 3.2.5 (Y1 3.2.4, RF3.2.3) Carry out specific needs-based activities linking the community centers with the labor bureau, public and private employment agencies, vocational training centers, and workers’ and employers’ organizations | * Y | * |  |  | ILO | MOHRSS | MDG-F | Contracts | 10,000 |
|  |  |  |  |  |  |  |  |  | Total | 10,000 |
|  | 3.2.6 (RF 3.2.3) Conduct small-scale needs-based activities with the local labor bureau, employer’s and workers’ organizations, employment agencies and vocational training institutions. | P | * | * | * | ILO | MOHRSS | MDG-F | Personnel | 10,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 21,000 |
|  |  |  |  |  |  |  |  |  | Supplies | 3,000 |
|  |  |  |  |  |  |  |  |  | Total | 34,000 |
|  | 3.2.7 (RF 3.2.4) Provide training and support services (by trained teachers 2.3.14) for domestic workers in 3 pilot sites on life skills, rights protection and so on to meet the specific needs and challenges faced by young female domestic workers. | P | P | * | * | UNIFEM | ACWF | MDG-F | Training of counterparts | 30,000 |
|  |  |  |  |  |  |  |  |  | Personnel | 1,000 |
|  |  |  |  |  |  |  |  |  | ODC | 1,840 |
|  |  |  |  |  |  |  |  |  | Total | 32,840 |
|  | 3.2.8 (RF 3.2.6) Train the community facilitators and volunteers of the selected pilot community centers with the SOP. | P | * Y | * | * | UNESCO | CAEA | MDG-F | Contracts | 55,000 |
|  |  |  |  |  |  |  |  |  | Supplies, Commodities, Equipment and Transport | 5,000 |
|  |  |  |  |  |  |  |  |  | Total | 60,000 |
|  |  | * R | * Y |  |  | UNICEF | ACWF and local street government, communities in Tianjin | MDG-F | Personnel (training) | 5,000 |
|  |  |  |  |  |  |  |  |  | Supplies, Commodities, Equipment and Transport | 15,000 |
|  |  |  |  |  |  |  |  |  | Total | 20,000 |
|  | 3.2.9 (RF 3.2.7) Provide migrants with comprehensive, gender responsive learning opportunities, information and referral services. Activities planned in quarter 2. | P | * Y | * | * | UNESCO | CAEA | MDG-F | Contract | 35,000 |
|  |  |  |  |  |  |  |  |  | Personnel | 5,000 |
|  |  |  |  |  |  |  |  |  | Total | 40,000 |
|  |  | * R | * Y | * | * | UNICEF | ACWF and local street government, communities in Tianjin | MDG-F | Contracts | 1,000 |
|  |  |  |  |  |  |  |  |  | ODC | 4,000 |
|  |  |  |  |  |  |  |  |  | Total | 5,000 |
|  | 3.2.10 (RF 3.2.8) Provide technical support and monitoring to the actual piloting community centers. | P | * Y | * | * | UNESCO | CAEA | MDG-F | Personnel | 13,000 |
|  |  |  |  |  |  |  |  |  | Contract | 3,000 |
|  |  |  |  |  |  |  |  |  | ODC | 4,000 |
|  |  |  |  |  |  |  |  |  | Total | 20,000 |
|  |  | * Y | * Y | * | * | UNICEF | ACWF and local street government, communities in Tianjin | MDG-F | Personnel (Consultant) (travel) | 3,000 |
|  |  |  |  |  |  |  |  |  | Training of Counterparts | 4,000 |
|  |  |  |  |  |  |  |  |  | Supplies, Commodities, Equipment and Transport | 500 |
|  |  |  |  |  |  |  |  |  | Total | 7,500 |
|  | 3.2.11 (Y1 3.2.6, RF3.2.9) Monitor the implementation and document lessons learned | * G | G |  |  | UNICEF | ACWF | MDG-F | Travel | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 3.2.12 (RF 3.2.9) Evaluate the effectiveness of the trainings, document good practice/lessons learned | P | * Y |  | * | UNICEF | ACWF and local street government ,communities in Tianjin | MDG-F | Personnel (Consultant) | 5,000 |
|  |  |  |  |  |  |  |  |  | Total | 5,000 |
| JP Output 3.3 Access to basic health information and care for migrants and left-behind youth improved. |

| *D*esign and testing of health promotion model to promote use of appropriate health services by migrant youth. | 3.3.1 (Y1, 3.3.1, RF3.3.1) Expert team review of existing services and care available for young migrants conducted by UN agencies and partners (international best practice review and workshop). | * Y | * G | * | * | WHO | MOH | MDG-F | Contracts | 0 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 3.3.2 (RF 3.3.2) City level multi-stakeholder meetings (WF, education, FP, education etc.) | * G | Y |  |  | WHO | MOH | MDG-F | Contracts | 22,000 |
|  |  |  |  |  |  |  |  |  | Total | 22,000 |
|  | 3.3.3 (RF 3.3.6) Health education activities for promotion of health risks awareness, healthy behavior and utilization of services using social marketing approach | * Y | * Y | * |  | UNFPA | MOH | MDG-F | Personnel | 6,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 40,000 |
|  |  |  |  |  |  |  |  |  | Total | 46,000 |
|  | 3.3.4 (RF 3.3.7) Develop, print and pilot resource training materials with involvement of youth groups in collaboration with "Healthy City" pilot areas | * Y | * Y |  |  | UNICEF | MOH | MDG-F | Contracts | 22,000 |
|  |  |  |  |  |  |  |  |  | Total | 22,000 |
|  |  |  |  |  |  | WHO | MOH | MDG-F | Contracts | 28,000 |
|  |  |  |  |  |  |  |  |  | Total | 28,000 |
|  | 3.3.5 (RF 3.3.8) Peer education activities to increase health knowledge and health risks awareness | * Y | * Y | * |  | UNFPA | MOH | MDG-F | Contracts | 43,050 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 10,000 |
|  |  |  |  |  |  |  |  |  | Total | 53,050 |
|  | 3.3.6 (RF 3.3.9) Capacity building of service providers on counseling skills and youth friendly services’ package | Y | * G |  |  | UNFPA | MOH | MDG-F | Training of counterparts | 40,000 |
|  |  |  |  |  |  |  |  |  | Total | 40,000 |
|  | 3.3.7 (RF 3.3.10) Cascade trainings for service providers | * Y | * Y | * | * | WHO | MOH | MDG-F | Contracts | 95,000 |
|  |  |  |  |  |  |  |  |  | Total | 95,000 |
|  | 3.3.8 (RF 3.3.11) Establishment of youth friendly services (seed money) | P | Y | * |  | UNFPA | MOH | MDG-F | Contracts | 27,500 |
|  |  |  |  |  |  |  |  |  | Total | 27,500 |
|  | 3.3.9 (RF 3.3.13) Ongoing assessment, reporting and consultative meetings | * Y | * Y | * | * | WHO | MOH | MDG-F | Personnel | 7,000 |
|  |  |  |  |  |  |  |  |  | Contracts | 14,000 |
|  |  |  |  |  |  |  |  |  | Total | 21,000 |
| JP Output 3.4 Implementation and enforcement of existing legislation for migrant workers strengthened and safe migration ensured. |
|  | 3.4.1 (Y1 3.4.3, RF3.4.2) Conduct training for labor authorities in pilot sites | * Y | * G |  |  | ILO | MOHRSS | MDG-F | Training | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
| Capacity building materials developed to support the implementation and enforcement of relevant labor legislation, and capacity enhanced among young female migrants in risk sectors | 3.4.2 (RF 3.4.2) Conduct training for labor authorities at different levels on how to implement and enforce the relevant legislation. | * R | * Y | * |  | ILO | MOHRSS | MDG-F | Personnel | 10,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 18,000 |
|  |  |  |  |  |  |  |  |  | ODC | 7,000 |
|  |  |  |  |  |  |  |  |  | Total | 35,000 |
|  | 3.4.3 (Y1 3.4.4, RF3.4.3) Propose a code of conduct approach based on a review of national and international good practices on how employers’ and workers’ organizations can support the implementation of the law. | * Y | * Y |  |  | ILO | ACFTU, CEC | MDG-F | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 3.4.4 (Y1 3.4.5, RF3.4.3) Hold tripartite consultation workshop to validate the code of conduct approach | * R | * Y |  |  | ILO | ACFTU, CEC | MDG-F | Training | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 3.4.5 (Y1 3.4.6, RF3.4.4) Conduct training on code of conduct for employers’ and workers’ organizations in pilot sites | * R | Y |  |  | ILO | ACFTU, CEC | MDG-F | Training | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 3.4.6 (RF 3.4.4) Conduct training for workers and employers in the pilot sites on how to implement code of conduct and good practices. | P | * Y | * | * | ILO | ACFTU/ CEC | MDG-F | Personnel | 5,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 14,000 |
|  |  |  |  |  |  |  |  |  | ODC | 1,000 |
|  |  |  |  |  |  |  |  |  | Total | 20,000 |
|  | 3.4.7 (Y1 3.4.7, RF3.4.5) Conduct review of contracts, wages (including piece-rate) and working time in the garment and footwear manufacturing sector | * R | Y |  |  | ILO | MOHRSS, ACFTU, CEC | MDG-F | Contracts | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 3.4.8 (Y1 3.4.8, RF3.4.5) Hold policy consultation seminar with tripartite constituents on the findings of the study and international experience | * R | * Y |  |  | ILO | MOHRSS, ACFTU, CEC | MDG-F | Training | 0 |
|  |  |  |  |  |  |  |  |  | Total | 0 |
|  | 3.4.9 (RF 3.4.6) Carry out and monitor awareness-raising activities for workers and employers on contracts, wages and working time standards. | P | P | * | * | ILO | ACFTU/ CEC | MDG-F | Personnel | 5,000 |
|  |  |  |  |  |  |  |  |  | Training of counterparts | 10,000 |
|  |  |  |  |  |  |  |  |  | Total | 15,000 |
|  | 3.4.10 (Y1 3.4.9, RF3.4.8) Conduct studies on female migrants working in low-end service industry | * Y | Ｇ |  |  | UNESCO | CASS, Tsinghua University | MDG-F | Contract | 0 |
|  |  |  |  |  |  |  |  |  | Travel | 5,000 |
|  |  |  |  |  |  |  |  |  | Total | 5,000 |
|  | 3.4.11 (RF 3.4.9) Awareness rising and training on legal rights, health, and sexual harassment for female migrants working in low-end service industry. | * R | * Y | * | * | UNESCO | Tsinghua University | MDG-F | Contracts | 20,000 |
|  |  |  |  |  |  |  |  |  | Total | 20,000 |
|  | 3.4.12 (RF 3.4.10) Assisting migrants who want to find jobs outside of the low-end service industry by providing testing and career guidance counseling, services. | * R | * Y | * | * | UNESCO | Tsinghua University | MDG-F | Contracts | 18,000 |
|  |  |  |  |  |  |  |  |  | Total | 18,000 |
|  | 3.4.13 (RF 3.4.11) Creation of psychological and legal support network for migrants working in the low-end service industry | * R | * Y | * | * | UNESCO | Tsinghua University | MDG-F | Contract | 20,000 |
|  |  |  |  |  |  |  |  |  | Total | 20,000 |