The Government of Papua New Guinea and the United Nations in PNG

2011 Annual Work Plan for

# Environmental Management & Sustainable Livelihoods

# Country: Papua New Guinea

UNCP Outcome:	Sustainable Livelihoods and Population

Expected Intermediate Outcome:	Communities apply national policies and regulatory  	frameworks to implement environmentally sustainable 	livelihood opportunities including community based 	ecotourism, non-timber forest products, sustainable 	agriculture and ecoforestry

Expected Output(s):	Output10.1. Department of Environment and Conservation has the capacity to develop, implement and monitor policies and regulatory framework to promote environmental sustainability

Output10.3. Rural communities have the awareness and mechanism to apply innovative environmentally sustainable income earning opportunities, including community based ecotourism, non-timber forest products, sustainable agriculture and ecoforestry

Implementing partner:	Department of Environment and Conservation

Responsible Parties and other Partners:	Department of National Planning and Monitoring

ExCom Agency	UNDP

The Sustainable Livelihoods programme promotes rational and balanced utilization of Papua New Guinea’s natural resources, through improved environmental management and sustainability while promoting environmentally-friendly employment and income-generation opportunities for poverty reduction and improved living standards. This Annual Work Plan (AWP) includes the following two outputs: DEC has the capacity to develop, implement and monitor policies and regulatory framework to promote environmental; and rural communities have the awareness and mechanisms to apply innovative environmentally sustainable income earning opportunities, including community based ecotourism, non-timber forest products, sustainable agriculture, marine resource management and eco-forestry. It will be supported through the DEC Capacity Strengthening Project and Global Environment Facility funded projects including: GEF-funded Sustainable Land Management (SLM), National Capacity Self-Assessment, Community-based Forest and Coastal Conservation and Resource Management in PNG and GEF Small Grants Programme for PNG. Separate AWPs for the GEF projects are attached and will have distinct budget for accounting purposes as per the UNDP-GEF requirements.

| Programme Period: 2008 – 2012 Programme Component: Sustainable Livelihoods Intervention Title: Environmental Management and Sustainable Livelihoods Award ID: 00049234 Project #: 00059880 Duration: 2011 | Estimated annualized budget: USD 1,490,000 Allocated resources: USD 770,000 - Government - Regular (UNDP): USD 350,000.00 - Other: - Donor: GEF: USD 420,000.00 Unfunded budget: USD 720,000.00 |
| --- | --- |

Agreed by (Implementing Partner): __________________________________________

Dr. Wari Iamo

Secretary,

Department of Environment and Conservation

Agreed by (Ex-Com Agency):_________________________________________________

Mr. David McLachlan-Karr

Resident Representative,

United Nations Development Programme

| Expected output |  | Indicators |  |  |  |  |  |  | Baseline | Annual Target |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 10.1 |  | Protected Areas policy and legislation are made available |  |  |  |  |  |  | No | Yes |  |
| Department of Environment and Conservation has the capacity to develop, implement and monitor policies and regulatory framework to promote environmental sustainability |  | # of natural resource-related government sectors have incorporated principles of environmental sustainability into their planning and strategies |  |  |  |  |  |  | No | 4 |  |
|  |  | Regulatory guidelines and policies on natural resources management and environmental sustainability made available to public |  |  |  |  |  |  | No | Yes |  |
|  |  | 3/4 of new policies/strategies of natural resource related departments reflect on and integrate environmental sustainability principles |  |  |  |  |  |  | No | Yes |  |
|  |  | Update MDG 7 indicators annually |  |  |  |  |  |  | No | 1 |  |
|  |  | # of natural resource-related private, government and civil society sectors represented in government's environmentally sustainable economic growth agenda |  |  |  |  |  |  | No | 3 |  |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |  |
| Approval of Community-based Forest and Coastal Conservation and Resource Management in PNG Project by GEF |  |  |  |  |  |  |  |  | DEC | UNDP |  |
| Cost benefit Analysis of Environmental Mainstreaming completed for selected relevant sectors |  |  |  |  |  |  |  |  |  |  |  |
| NEC Endorsement on Environmentally Sustainable Economic Growth (ESEG) Policy led by Department of Environment and Conservation |  |  |  |  |  |  |  |  |  |  |  |
| Documentation of Sustainable Land Management Best Practices in PNG Completed |  |  |  |  |  |  |  |  |  |  |  |
| Stakeholder consultation on ESEG Policy Completed |  |  |  |  |  |  |  |  |  |  |  |
| Review of relevant natural resources guidelines, codes of practices, standards and policies on Sustainable Land Management |  |  |  |  |  |  |  |  |  |  |  |
| Activities |  |  | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
| Assist DEC submit project proposals to Global Environment Facility |  |  | x | x | x | x | GEF, UNDP + others | Technical Assistance, Contractual Services, Rental & Maintenance - Others, IT, Travel, Supplies, Miscellaneous | 620,000 | 800,000 |  |
| Expected output |  | Indicators |  |  |  |  |  |  | Baseline | Annual Target |  |
| 10.3 |  | # of communities participate on innovative environmentally sustainable income earning opportunities |  |  |  |  |  |  | No | 2 |  |
| Rural communities have the awareness and mechanisms to apply innovative environmentally sustainable income earning opportunities including community-based eco-tourism, non-timber forest products, sustainable agriculture and eco-forestry |  | # of community based eco-tourism strategy piloted in selected communities |  |  |  |  |  |  | No | 2 |  |
|  |  | # of applications received by SGP that promote environmentally sustainable income earning opportunities |  |  |  |  |  |  | No | 6 |  |
|  |  | GEF SGP Programme Framework made available |  |  |  |  |  |  | No | Yes |  |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |  |
| GEF SGP Country Programme Strategy for PNG finalized and distributed |  |  |  |  |  |  |  |  | DEC | UNDP |  |
| Conduct capacity building training workshops for NGOs/CBOs |  |  |  |  |  |  |  |  |  |  |  |
| SGP monitoring and evaluation guidelines developed and applied through quarterly progress reporting by project proponents |  |  |  |  |  |  |  |  |  |  |  |
| Activities |  |  | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
| GEF SGP Programme Implementation |  |  | x | x | x | x | UNDP + others | Technical Assistance, Contractual Services, Rental & Maintenance - Others, IT, Travel, Supplies, Miscellaneous | 150,000 | 300,000 |  |