The Government of Papua New Guinea and the

United Nations in PNG Annual Work Plan for 2011 for

HIV and AIDS

Country: Papua New Guinea

UNCP Outcome(s)	By 2012, the rate of HIV infection is halted and government provides services to those people living with and affected by HIV and AIDS

Expected Intermediate Outcome(s)

By 2012, a coordinated effective national response (leads) to a decrease in transmission of HIV and provides services to decrease the impact of HIV on individuals, families and communities living with or affected by HIV.

Expected Output(s)

- NACS coordinates development and implementation of prevention interventions, linked to NHS, for more at risk groups, youth populations and women and girls who experience gender-based violence.

- NACS and NDoH develop and integrate condom programme into their HIV and STI prevention and reproductive health policy and programmes.

- NDoH effectively coordinates programme activities to ensure all pregnant women and their partners have access to the full range of Prevention of Parent to Child transmission of HIV (PPTCT) interventions through strengthened Mother and Child Health (MCH) services.

- NDoH effectively monitors the implementation of national policies, guidelines and strategies for testing, care and treatment.

- NDoH effectively coordinates, develops and provides training on paediatric Anti-Retroviral Therapy (ART), HIV testing and counselling and adult ART.

- Health system has capacity to provide supply, equipment and infrastructure to improve access and quality of all HIV services with emphasis in priority provinces.

- CSOs and networks addressing HIV issues have the organizational and human capacity to actively engage in all levels of national HIV programmes.

- The national M&E system has the capacity to produce quality data and strategic information to monitor and guide an evidence-informed national and provincial response.

- Leaders at national and provincial levels are actively promoting universal access and human rights and gender issues related to HIV, and putting them on the developmental agenda.

Implementing partner: National AIDS Council Secretariat (NACS) and National Department of Health (NDoH)

Responsible Parties and other Partners: NACS, NDoH, Department of Community Development (DfCD), National HIV and AIDS Training Unit (NHATU), Marie Stops, Shalom Care, Provincial AIDS Committee Secretariats (PACS), University of PNG (UPNG), Young Men’s Christian Association (YMCA), Susu Mamas, Burnet Institute, Country Coordination Mechanism (CCM), PNG Alliance of Civil Society Organisation (PACS), Business Alliance against HIV and AIDS (BAHA)

Participating Ag): UNAIDS, UNDP, UNFPA, UNICEF, UNIFEM, WHO

Narrative The main goal of the HIV and AIDS task team annual work plan for 2011 is to realign the UN support to the country response with the new National HIV and AIDS Strategy (NHS) 2011-2015. To do so, the task team has revised its results matrix to allow for a more comprehensive and harmonised work plan aligned with the NHS and its top ten priority interventions considering the comparative advantages of the individual participating UN agencies as well as the collective unique characteristics of the Joint UN team on AIDS strengths and opportunities.

| Element of the budget | Estimated budget in USD | Funded in USD | Unfunded in USD |
| --- | --- | --- | --- |
| Output 1Total | 1,232,000 | 452,000 | 780,000 |
| Output 1 UNAIDS | 27,000 | 27,000 | 0 |
| Output 1 UNDP | 655,000 | 135,000 | 520,000 |
| Output 1 UNFPA | 140,000 | 70,000 | 70,000 |
| Output 1 WHO | 30,000 | 20,000 | 10,000 |
| Output 2 Total | 285,000 | 70,000 | 215,000 |
| Output 2 UNAIDS | 20,000 | 20,000 | 0 |
| Output 2 UNFPA | 195,000 | 50,000 | 145,000 |
| Output 3 Total | 1,513,500 | 376,500 | 1,137,000 |
| Output 3 UNICEF | 1,041,500 | 314,500 | 727,000 |
| Output 3 WHO | 472,000 | 62,000 | 410,000 |
| Output 4 Total | 1,117,500 | 390,000 | 727,500 |
| Output 4 UNICEF | 27,500 | 20,000 | 7,500 |
| Output 4 WHO | 1,090,000 | 370,000 | 720,000 |
| Output 5 Total | 458,600 | 118,600 | 340,000 |
| Output 5 UNICEF | 60,000 | 50,000 | 10,000 |
| Output 5 WHO | 398,600 | 68,600 | 330,000 |
| Output 6 Total | 124,800 | 24,800 | 100,000 |
| Output 6 WHO | 124,800 | 24,800 | 100,000 |
| Output 7 Total | 787,000 | 337,000 | 450,000 |
| Output 7 UNAIDS | 108,000 | 108,000 | 0 |
| Output 7 UNDP | 385,000 | 85,000 | 300,000 |
| Output 7 UNFPA | 59,000 | 29,000 | 30,000 |
| Output 7 UNIFEM | 175,000 | 115,000 | 60,000 |
| Output 7 WHO | 60,000 | 0 | 60,000 |
| Output 8 Total | 1,389,000 | 499,000 | 890,000 |
| Output 8 UNAIDS | 145,000 | 145,000 | 0 |
| Output 8 UNDP | 355,000 | 60,000 | 295,000 |
| Output 8 UNFPA | 1,000 | 1,000 | 0 |
| Output 8 UNICEF | 370,000 | 20,000 | 350,000 |
| Output 8 UNIFEM | 1,000 | 1,000 | 0 |
| Output 8 WHO | 517,000 | 272,000 | 245,000 |
| Output 9 Total | 1,155,000 | 185,000 | 970,000 |
| Output 9 UNAIDS | 115,000 | 50,000 | 65,000 |
| Output 9 UNDP | 790,000 | 70,000 | 720,000 |
| Output 9 UNIFEM | 165,000 | 30,000 | 135,000 |
| Output 9 WHO | 85,000 | 35,000 | 50,000 |
| AWP Total | 8,062,400 | 2,452,900 | 5,609,500 |
| AWP UNAIDS | 415,000 | 350,000 | 65,000 |
| AWP UNDP | 2,185,000 | 350,000 | 1,835,000 |
| AWP UNFPA | 395,000 | 150,000 | 245,000 |
| AWP UNICEF | 1,879,000 | 604,500 | 1,274,500 |
| AWP UNIFEM | 341,000 | 146,000 | 195,000 |
| AWP WHO | 2,847,400 | 852,400 | 1,995,000 |
| TOTAL |  | 9,590,600 | 22,188,000 |

Agreed by:

______________________________________

Agreed by:

______________________________________

| Expected output | Indicators | Baseline | Annual Target |
| --- | --- | --- | --- |
| Output 1: NACS coordinates development and implementation of prevention interventions, linked to NHS, for more at-risk groups, youth populations and women and girls who experience gender-based violence | Number of reports coming out of a multi-sectoral prevention task force is established with a secretariat at NACS | 0 | 4 |
|  | Costed implementation and operational plans exist for more at-risk populations, youth and women and girls who experience gender-based violence | 0 | 0 |
| Annual Deliverable |  |  |  |  |  |  | Resp. Party | UN Agency |
| By 2011, FBOs have the capacity to care, protect and support Most Vulnerable Children, boys and girls in priority provinces | NACS, DfCD | UNICEF |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Roll out of training and monitoring support for the protection, care and support of Most Vulnerable Children in priority provinces | X | X | X |  | UNICEF | Workshops, travel | $20,000 | $30,000 |
| Evaluation of MVC training |  |  |  | X | UNICEF | TA, travel, workshops | $0 | $30,000 |
| Subtotal | $20,000 | $60,000 |
| Annual Deliverable |  |  |  |  |  |  | Resp. Party | UN Agency |
| Development of the Technical Support Plan for the prevention priority areas of National HIV/AIDS Strategy | NACS | UNAIDS |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| TA for drafting technical needs assessment | X |  |  |  | UNAIDS | TA, travel, workshops | $20,000 | $0 |
| Consultation workshop | X |  |  |  | UNAIDS | Workshops | $7,000 | $0 |
| Subtotal | $27,000 | $0 |
| Annual Deliverable |  |  |  |  |  |  | Resp. Party | UN Agency |
| Community engagement and capacity enhancement systems/mechanism from selected provinces in place to develop and implement community based initiatives on HIV prevention | NACS | UNDP, UNFPA (lead UNDP) |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Conduct Community Capacity Enhancement methodology enrolment workshops in selected provinces, districts and at local level | x | x |  |  | UNDP | travel, workshops | $10,000 | $30,000 |
| Support the establishment of CCE steering committees at national and provincial levels | x | x |  |  | UNDP | travel, workshops | $0 | $30,000 |
| Support Community Conversations and reporting in selected communities from specific provinces | x | x | x | x | UNDP | travel, workshops | $10,000 | $60,000 |
| National Workshop to align CCE-CC Key results indicators with NHS and National M&E Plan | x | x |  |  | UNDP | TA, travel, workshops | $10,000 | $40,000 |
| Support and conduct CCE-CC monitoring visits | x | x | X | x | UNDP | travel, workshops | $5,000 | $20,000 |
| National level CCE CC skills alignment workshop with all community volunteers and facilitators |  |  |  | x | UNDP | travel, workshops | $0 | $20,000 |
| TA to support government departments in rolling out of community engagement strategies at community level | x | x | x | x | UNDP | TA | $0 | $250,000 |
| TA to Provincial AIDS Council Secretariat on HIV prevention activities in a religious setting |  | x | x |  | UNFPA | TA | $0 | $15,000 |
| Two provincial HIV and GBV prevention trainings with religious leaders in two high prevalence provinces |  | x | x |  | UNFPA | workshop, travel | $0 | $40,000 |
| Development and printing of HIV prevention and GBV awareness material |  | x | x |  | UNFPA | artwork, printing | $0 | $10,000 |
| Monitoring visit of HIV prevention trainings |  |  |  | x | UNFPA | travel | $0 | $5,000 |
| Subtotal |  |  |  |  |  |  |  | $35,000 | $520,000 |
| Annual Deliverable |  |  |  |  |  |  | Resp. Party | UN Agency |
| Supportive legal and policy framework in place for accessibility of HIV/AIDS related services for Most At Risk Populations | NACS | UNDP |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Conduct a situational analysis of existing supportive and punitive laws and policies in regards to access/provision of HIV/AIDS related services for MARPS | X |  |  |  | UNDP | TA, travel, workshops | $30,000 | $0 |
| Develop an advocacy strategy based on findings from the analysis of policy and legal frameworks | X | X |  |  | UNDP | TA, travel, workshops | $30,000 | $0 |
| Conduct policy advocacy sessions/dialogues at both national level (targeting strategic government institutions including Parliamentarians, Law and Justice Sector, and law enforcement institutions i.e. police) and provincial level |  | X | X | X | UNDP | travel, workshops | $20,000 | $40,000 |
| Support the review of specific laws and policies including but not limited to HAMP Act, Criminal Code, Summary Offences Act, and other legislations which have impact in HIV response | X | X | X | X | UNDP | TA, travel, workshops | $20,000 | $30,000 |
| Subtotal | $100,000 | $70,000 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Strategic targeted interventions to guide and implement prevention of HIV in youth populations are in place | NACS, NHATU, Marie Stops, Shalom Care, PACS, UPNG, YMCA | UNICEF, UNFPA (Lead by UNFPA) |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| National HIV Training plan for youth prevention for out of school youth implemented | X | X | X | X | UNICEF | Training | $70,000 | $30,000 |
| Support to NGOS, CBOs for strengthening outreach service for youth, youth hotline in place and functional, targeted youth prevention programming | X | X | X | X | UNICEF | CASH | $60,000 | $30,000 |
| Operational Plan for NSH section of the youth section under development |  |  | X | X | UNICEF | TA, workshops | $0 | $50,000 |
| Operational Plan for NSH section of the youth section under development |  |  | x | x | UNFPA | TA Workshops | $20,000 | $0 |
| Peer Education conducted at university and with (in and out of school) youth through church network. (Funding in Health AWP) | x | x | x | x | UNFPA | TA, training | $0 | $0 |
| Weekly radio and television broadcasting on ICPDs; gender, HIV & AIDS and reproductive health. (Funding under Health AWP) | x | x | x | x | UNFPA | TA, campaign | $0 | $0 |
| TA for HIV prevention in the form of two national staff | x | x | x | x | UNFPA | TA | $50,000 | $0 |
| UNICEF NOB Staff costs | x | x | x | x | UNICEF | Salary | $40,000 | $0 |
| Support capacity building through attendance at workshops for prevention | x | x | x | x | UNICEF | training | $10,000 | $10,000 |
| Subtotal | $250,000 | $120,000 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| By 2011 12 hospitals are able to provide PEP services | NDOH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Train 20 HCW PEP provision |  | X | X |  | WHO | Training workshop | $20,000 | $10,000 |
| Conduct supportive supervision for PEP services | X | X | X | X | WHO | TA cost | $0 | $0 |
| Support forecasting and procurement of PEP drugs |  | x | x | x | WHO | TA cost | $0 | $0 |
| Distribution and roll out of PEP kits |  | X | X | X | WHO | Supply | $0 | $0 |
| Subtotal | $20,000 | $10,000 |
| Total for Output 1 | $452,000 | $780,000 |
| Expected output | Indicators | Baseline | Annual Target |
| Output 2: NACS and NDOH develop and integrate condom programming into their HIV and STI prevention and reproductive health policy and programmes | Number of meeting reports coming from a multi-sectoral condom committee established and works effectively with support from a secretariat at NACS/NDoH | 0 | 4 |
|  | A joint framework exists on condom programming | 0 | 1 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Condom committee secretariat re-established | NACS | UNFPA |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| TA to secretariat of condom committee |  | X | x | x | UNFPA | TA | $0 | $30,000 |
| Comprehensive condom programming Operational plan developed |  |  | x | x | UNFPA | Workshop | $10,000 | $0 |
| High visibility advocacy activity on condoms |  |  |  | x | UNFPA | media, high-level meetings | $15,000 | $15,000 |
| Support to NACS for prevention activities | x | x | x | x | UNFPA | workshop | $25,000 | $0 |
| For reproductive health condom program see maternal health task team |  |  |  |  | WHO |  | $0 | $0 |
| Subtotal | $50,000 | $45,000 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| User friendly map and database established within NACS and NDoH for condom supply and programming | NACS, NDOH | UNFPA, UNAIDS (Lead by UNFPA) |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| TA for design of GIS for condom supply and programming |  |  | x | x | UNAIDS | TA | $0 | $20,000 |
| TA for design of GIS for condom supply and programming |  |  | X | X | UNFPA | TA | $0 | $80,000 |
| Materials for GIS |  |  | x | x | UNFPA | Maps | $0 | $20,000 |
| Subtotal | $0 | $120,000 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Comprehensive STI programme review report | NDOH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Support review of STI treatment guidelines |  | X | X |  | WHO | Workshop | $0 | $20,000 |
| Establish technical working group for STI programme |  | x |  |  | WHO | Workshop | $0 | $10,000 |
| Conduct workshop on elimination of congenital syphilis |  | X | X |  | WHO | Workshop | $0 | $20,000 |
| Review of STI recording and reporting forms | x | X | X | X | WHO | TA | $0 | $0 |
| TA support mobilized as required for STI programme |  | x |  |  | WHO | TA | $0 | $20,000 |
| Subtotal | $0 | $70,000 |
| Total for Output 2 | $50,000 | $235,000 |
| Expected output | Indicators | Baseline | Annual Target |
| Output 3: NDOH effectively coordinates programme activities to ensure all pregnant women and their partners have access to full range of Prevention of Parent to Child Transmission of HIV interventions through strengthened mother and child health services | The number of monitoring reports for a costed operational plan for PPTCT | 0 | 4 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Up to date evidence-based guidelines on PPTCT endorsed by the Government and framework for referral linkages with MCH and GBV and social support services available | NDOH | UNICEF |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Support to the TWG meetings at national level and coordination meetings at regional level (4 regions) at least one meeting in each region | X | x | x | x | UNICEF | Meetings, conference hire, travel | $20,000 | $0 |
| One high visibility advocacy event held for key messages in PPTCT |  |  | X | X | UNICEF | event | $0 | $2,500 |
| Revised treatment guidelines for PPTCT endorsed, printed and disseminated | X | X |  |  | UNICEF | Workshop | $0 | $5,000 |
| Technical support to setting up of Management unit for PPTCT at NDOH (TORS, Supportive supervision), support quarterly monitoring of the implementation of the plan, and increase information sharing on issues related to PPTCT within the MCH framework | X | X | X | X | UNICEF | TA | $0 | $0 |
| Subtotal | $20,000 | $7,500 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Comprehensive training package with Job Aids and a system for mentoring support available for PPTCT for all levels of health care delivery | NDOH | UNICEF, WHO (Lead by UNICEF) |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Agency completes the Training package for PPTCT and this is endorsed by NDOH | x | x |  |  | UNICEF | Contract | $20,000 | $0 |
| Training package for PPTCT printed and disseminated |  | x | x | x | UNICEF | Artwork, printing, shipping | $0 | $30,000 |
| Job aids for PPTCT finalized and disseminated | x | x | x | x | UNICEF | Artwork, printing, shipping | $20,000 | $20,000 |
| PPTCT training curriculum (all 4 components) rolled out and a team of master trainers created (one master trainers workshop and one regional level workshop) with an effort to work with institutions to explore institutionalization of PPTCT training |  |  | x | x | UNICEF | Training, travel, workshops | $0 | $100,000 |
| HCW trained in PPTCT program |  | X | X |  | WHO | Training, travel, workshops | $20,000 | $10,000 |
| HCW trained in HIVQUAL program (Paeds/Adults/PMTCT) | X |  | X |  | WHO | Training, supply, workshops, TA | $42,000 | $20,000 |
| Support the implementation of comprehensive linked services in six hospitals |  | X | X | X | WHO | TA | $0 | $60,000 |
| Pilot warm lines in selected two provinces linked with centres of excellence |  | x | x | x | UNICEF | TA | $0 | $5,000 |
| 2 centres of excellence (urban and rural) set up and functioning as per NDOH TOR | x | x | x | x | UNICEF | Supply, travel | $20,000 | $0 |
| Streamlining supportive supervision in the field by developing TORs for supervisory visits, checklists and support to piloting initiatives like mentoring teams (tech support) | x | x |  |  | UNICEF | TA | $0 | $0 |
| Exposure visits for staff and NGOs completed to support quality implementation of the program (two visits within PNG) |  | x | x | x | UNICEF | Travel | $0 | $20,000 |
| Participation in regional and global workshops and conferences based on need | x | x | x | x | UNICEF | Travel | $10,000 | $10,000 |
| Support to nutrition counseling on HIV/AIDS - training and materials inputs | x | x | x | x | UNICEF | TA | $0 | $0 |
| Subtotal | $132,000 | $275,000 |
| Annual Deliverable |  |  |  |  |  |  | Resp. Party | UN Agency |
| System for PPTCT program monitoring and regular supply of drugs and commodities put in place at all levels of health care delivery | NDOH | UNICEF |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Work with lab systems to ensure availability of same day results in ANC, continuous supply of diagnostic kits - syphilis, HIV kits, ARV drugs, OI drugs, supply of condoms in all ANC sites, check lists for management of supplies | x | x | x | x | UNICEF | TA | $0 | $0 |
| Work closely with NHIS and MCH systems for streamlining medical records integrating HIV information, developing coding systems for positive mothers and children, reviewing women's health books, comprehensive M and E framework for program monitoring | x | x | x | x | UNICEF | TA | $0 | $0 |
| Subtotal | $0 | $0 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| By 2011, one replicable model exist in five PPTCT program elements namely , community outreach, strong referral linkages, increased male partner participation in ANC, increase in positive women involvement and continuum of care | Susu Mamas, NDoH, NACS, DfCD, Catholic Health, FHI | UNICEF |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Support to ensure linkages with GBV services, social support services (tech support, link with gender task team, MVC etc), including working with male role models and leaders in communities in select provinces (addressed in coordination meetings at sub national levels, and within existing community outreach programs) | x | x | x | x | UNICEF | TA | $0 | $0 |
| Support to NGOs, CBOs for strengthening outreach services, male partner involvement in ANC, positive women involvement and continuum of care services related to MCH and PPTCT programmes |  | x | x | x | UNICEF | CASH | $10,000 | $120,000 |
| Subtotal | $10,000 | $120,000 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Technical support assistance provided to NDoH and partners on PPTCT and Pediatric AIDS on a continual basis and attendance at workshops | UNICEF, WHO | UNICEF, WHO (Lead by UNICEF) |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| UNICEF P4 HIV/AIDS Specialist | X | x | x | x | UNICEF | Salary | $150,000 | $150,000 |
| UNICEF P3 PPTCT and Pediatric AIDS Specialist |  | X | X | X | X | UNICEF | Salary | $50,000 | $250,000 |
| UNICEF Programme Assistant |  | X | X | X | X | UNICEF | Salary | $4,500 | $4,500 |
| WHO staff |  |  | X | X | WHO | Salary | $0 | $300,000 |
| Capacity building through attendance at international workshops (does this mean funding of participants to go to meetings?) | X | X | x | x | UNICEF | Workshop | $10,000 | $10,000 |
| Capacity building through attendance at international workshops | x | x | x | x | WHO | Workshop | $0 | $20,000 |
| Subtotal | $214,500 | $734,500 |
| Total for output 3: | $376,500 | $1,137,000 |
| Expected output | Indicators | Baseline | Annual Target |
| Output 4: NDOH effectively monitors the implementation of national policies, guidelines and strategies for testing, care and treatment | Percentage of UA indicators that NDOH reports annually with valid data | 57 | 60 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Up to date evidence based guidelines endorsed by the Government on Pediatric ART and framework for referral linkages with MCH and child protection services available | NDOH | UNICEF |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Support to the TWG meetings at national level and coordination meetings at regional level (4 regions) at least one meeting in each region | x | x | x | x | UNICEF | TA | $20,000 | $0 |
| One high visibility advocacy event held for key messages in Pediatric AIDS |  |  | x | x | UNICEF | TA | $0 | $2,500 |
| Workshop/meeting held to finalize revision of treatment guidelines for Pediatric ART | x | x |  |  | UNICEF | TA | $0 | $5,000 |
| Technical support to setting up of Management unit for Pediatric AIDS at NDOH (TORs, supportive supervision), support quarterly monitoring of the implementation of the plan, and increase information sharing on issues related to Pediatric AIDS within the MCH framework | x | x | x | x | UNICEF | TA | $0 | $0 |
| Subtotal | $20,000 | $7,500 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Updated adults ART treatment guidelines endorsed by the Government, printed, disseminated to health facilities and follow up its implementation | NDOH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Review HIV care and treatment guidelines | x | x |  |  | WHO | Workshop | $10,000 | $0 |
| Support the update of ART training materials | X | X | X | X | WHO | Workshop | $0 | $0 |
| Print the updated ART guidelines and training materials |  |  | X | X | WHO | printing | $10,000 | $10,000 |
| Support ART training of HCW as per updated materials |  | X | X | X | WHO | Training | $0 | $0 |
| Support refresher training of HCW on ART |  | X | X | X | WHO | Training | $0 | $0 |
| Conduct 4 supervisory visits for ART services quality improvement | X | X | X | X | WHO | Travel | $10,000 | $0 |
| Support ART mentorship at treatment sites |  | X | X | X | WHO | Travel | $10,000 | $0 |
| Support ARV drugs forecasting and procurement process | X | X | X | X | WHO | TA | $0 | $250,000 |
| Support PR to smoothly manage and report GFATM activities | X | X | X | X | WHO | TA | $0 | $0 |
| Support advocacy for treatment support for PLHIV | X | X | X | X | WHO | workshop | $0 | $0 |
| Support to conduct HIV drug resistance surveillance | x | x | x | x | WHO | research | $50,000 | $0 |
| WHO TA | X | X |  |  | WHO | TA | $40,000 | $160,000 |
| Subtotal | $130,000 | $420,000 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Continual technical support provided to NDOH | NDOH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| WHO TA |  |  |  |  | WHO |  | $240,000 | $300,000 |
| Subtotal | $240,000 | $300,000 |
| Total for output 4 | $390,000 | $727,500 |
| Expected output | Indicators | Baseline | Annual Target |
| Output 5: NDOH effectively coordinates, develops and Pediatric ART, HIV testing and counseling and adult ART | # of trained health care workers providing HIV services in 8 priority provinces | 1700 | 120 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Comprehensive training package with Job Aids and a system for mentoring support available for Pediatric ART for all levels of health care | NDOH | UNICEF |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Agency completes the Training package for Pediatric ART | X | X |  |  | UNICEF | contract | $20,000 | $0 |
| Training package for Pediatric ART printed and disseminated (artwork, printing and dissemination costs) |  | X | X |  | UNICEF | Printing, Artwork, shipping | $10,000 | $0 |
| Job aids for Pediatric ART finalized and disseminated | X | X | X | X | UNICEF | (artwork, printing, dissemination) | $10,000 | $0 |
| Pediatric ART training curriculum rolled out and a team of master trainers created (one master trainers workshop and one regional level workshop) with an effort to work with institutions to explore institutionalization of Pediatric ART training |  |  | X | X | UNICEF | Training, workshops | $10,000 | $10,000 |
| Support development of check lists and TORs for supportive supervision in the field for Pediatric ART (tech support) |  |  | X | X | UNICEF | TA | $0 | $0 |
| Subtotal | $50,000 | $10,000 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Comprehensive training package on HIV testing and treatment rolled out to the District level in priority provinces. | NDOH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Training for health care workers on Integrated Management Adult Illnesses and training of CHWs in STI/HIV Prevention Toolkit |  | x | x |  | WHO | workshops, travel | $0 | $100,000 |
| Training in HIV testing through HIV/TB collaborative activities | x | x | x | x | WHO | TA, supply, Travel | $48,600 | $20,000 |
| ART Treatment Adherence intervention activity supported for adults and PPTCT |  | x | x | x | WHO | Cash, TA | $0 | $100,000 |
| Training in PICT and the new testing algorithm for health care workers | x | x | x | x | WHO | workshops, travel | $20,000 | $100,000 |
| Conduct regular supervision of HIV testing quality assurance | X | X | X | X | WHO | Travel | $0 | $10,000 |
| Support forecasting and procurement of HIV and STI test kits | X | X | X | X | WHO | workshops, TA | $0 | $0 |
| Subtotal | $68,600 | $330,000 |
| Total for output 5 | $118,600 | $340,000 |
| Expected output | Indicators | Baseline | Annual Target |
| Output 6: Health systems has the capacity to provide supplies, equipment and infrastructure to improve access and quality of all HIV services with emphasis on priority provinces | Number of facilities providing HIV services in 8 priority provinces | 15 | 20 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| NDOH has the capacity to supply drugs and commodities and monitor Quality HIV programme. | NDOH | UNICEF |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Work with lab systems to ensure availability of Dried blood spot tests, PCR tests for early infant diagnosis, continuous supply of ARV drugs, OI drugs, cotrimoxazole, check lists for management of supplies for Pediatric ART | x | x | x | x | UNICEF/WHO | TA | 0 | 0 |
| Work with MCH in reviewing child health books, comprehensive M and E framework for program monitoring for Pediatric ART | x | x | x | x | UNICEF | TA | 0 | 0 |
| Support EQAS workshop for HIV program. | x | x | x | x | WHO | Workshop/supplies/TA | $24,800 | $50,000 |
| Support Lab Supplies and commodities |  | x | x | x | WHO | Supplies/TA | $0 | $50,000 |
| WHO TA | x | x | x | x | WHO | TA | $0 | $0 |
| Sub Total | $24,800 | $100,000 |
| Total for output 6 | $24,800 | $100,000 |
| Expected output | Indicators | Baseline | Annual Target |
| Output 7: CSOs and the networks addressing HIV issues have the organization and human capacity to actively engage in all levels of HIV programmes | Numbers of CSOs supported with organizational development initiatives | 3 | 4 |
|  | Number of PACS with CSO representation | 2 | 3 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Mechanism in place to support organization and networks with most at risk populations | NACS | UNFPA, UNDP, UNIFEM, UNAIDS (Lead by UNDP) |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| 5 CSOs receive tailor made support to undertake community initiatives | x | x | x | x | UNDP | training | $15,000 | $70,000 |
| Conduct operational research on Universal Access for women and girls | x |  |  |  | UNDP | consultancy | $50,000 | $20,000 |
| Training manual for Christian Leaders Alliance | x | x | x | x | UNAIDS | consultancy | $8,000 | $0 |
| Preparation and dissemination of Stigma Index report | X | X |  |  | UNAIDS | printing | $5,000 | $0 |
| TA to support CSOs working with populations at risk | x | x | x | x | UNAIDS | TA | $70,000 | $0 |
| Prevention and advocacy for sex workers and MSM and the follow up on the national action plan on HIV and sex-work |  | x | x | x | UNFPA | workshop, travel | $29,000 | $30,000 |
| Support to PACSO to develop a countrywide Database for CSOs | x | x |  |  | UNDP | TA | $10,000 | $20,000 |
| International UNV/ AYAD for institutional capacity development PACSO and selected CSOs |  |  |  |  | UNDP | training | $0 | 120,00 |
| Support to CSOs to attend international workshops and conferences | x | x | x | x | UNDP | travel, workshops | $10,000 | $70,000 |
| Mapping of sex worker hot spots in NCD |  | x | x | x | UNAIDS | consultancy, workshop | $25,000 | $0 |
| AIDS Competence Process (ACP) networks supported for community initiatives in 6 priority provinces | x | x | x | x | WHO | Workshops | $0 | $60,000 |
| Deliver training to positive women, women affected by HIV and women advocates working in gender and HIV | x | x | x | x | UNIFEM | Training, TA, Travel | $70, 000 | 30, 000 |
| Mentoring and coaching sessions for positive women, women affected by HIV and women advocates and their organisations for resource mobilization and advocacy | x | x | x | x | UNIFEM | Meetings, reports | $45, 000 | $30, 000 |
| Subtotal | $222,000 | $270,000 |
| Total for Output 7 | $222,000 | $270,000 |
| Expected output | Indicators | Baseline | Annual Target |
| Output 8: The national M & E system has the capacity to produce quality data and strategic information to monitor and guide an evidence informed national and provincial response | Number of provinces reporting in the annual surveillance and M & E report | 5 | 8 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| National and International monitoring reports submitted on time | NACS, NDOH, Burnett Institute, Research Institutes | ALL (Lead by UNAIDS) |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Support workshops/meetings related to UA reporting | x |  |  |  | UNDP | travel, workshops | $10,000 | $0 |
|  | x |  |  |  | UNFPA | workshop | $1,000 | $0 |
|  | x |  |  |  | WHO | Workshops | $10,000 | $0 |
|  | x |  |  |  | UNICEF | workshop | $10,000 |  |
|  | x |  |  |  | UNIFEM | workshop | $1,000 | $0 |
| Support Integration of HIV related indicators into CEDAW reporting | x | x | x | x | UNDP | TA, travel, workshops | $30,000 | $0 |
| Develop and finalize monitoring template for PPTCT and Pediatric AIDS synergized with national reporting systems | x | x | x | x | UNICEF | TA, Travel, Supply | $0 | $50,000 |
| Support system strengthening in M and E for PPTCT and Pediatric AIDS by inclusion of M and E module in all training programmes and working closely with PROMEST and surveillance teams | x | x | x | x | UNICEF | TA | $0 | $0 |
| Support operational research on select topics on PPTCT and Pediatric AIDS including setting up of a sub working group on research | x | x | x | x | UNICEF | supply, TA, research proposal | $10,000 | $300,000 |
| Conduct national AIDS Spending assessment | x | x |  |  | UNAIDS | TA | $20,000 | $0 |
| Review and update HIV Surveillance Plan | x | x |  |  | UNAIDS | TA | $0 | $0 |
| TA support for IRG mission |  | X | X |  | WHO | Travel | $0 | $15,000 |
| Technical support to NACS M&E unit (TA) | x | x | x | x | UNDP | TA | $0 | $250,000 |
| Conduct 3 provincial workshops on quality data generation and use |  | x | x | x | WHO | Workshops | $60,000 | $0 |
| Support IRG mission related provincial visits |  | x |  |  | UNDP | travel, workshops | $0 | $5,000 |
| TA support for M & E and surveillance | x | x | x | x | WHO | TA | $100,000 | $140,000 |
| Review and update HIV Surveillance Plan |  | x | x | x | WHO | TA | $20,000 | $30,000 |
| Subtotal | $272,000 | $790,000 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Support NDOH/NACS implement their M&E activities related to the HIV national programme | NACS | UNAIDS, UNDP, WHO (Lead by WHO) |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| TA support for review and quality assurance of data collecting mechanisms |  | x |  |  | UNAIDS | TA | $20,000 | $0 |
|  | x | x | x | x | WHO | TA | $10,000 | $0 |
| Training for NAC/PACS on data quality, storage and quality reporting |  | x |  | x | UNDP | Training | $10,000 | $30,000 |
| CRIS follow up Maintenance of software and database | x | x | x | x | UNDP | Training, workshop | $10,000 | $10,000 |
| M & E training at Midol University |  | x |  |  | WHO | Training | $20,000 | $10,000 |
| Conduct workshop on provincial data management |  | x | x |  | WHO | workshop | $20,000 | $20,000 |
| CRIS support and follow up |  | x | x | x | UNAIDS | TA | $0 | $0 |
| Conduct supportive supervision to sites to provide services and data generation | X | X | X | X | WHO | TA | $0 | $0 |
| Support quality HIV surveillance implementation at different sites |  | x | x | x | WHO | TA | $0 | $0 |
| Support and participate in HIV M&E/Surveillance coordination meetings | X | X | X | X | WHO | TA | $0 | $0 |
| Support NDOH collect, manage and report quality ART data | X | X | X | X | WHO | TA | $32,000 | $0 |
| TA support to improve HIV data management | x | x | x | x | WHO | TA | $0 | $30,000 |
| Subtotal | $122,000 | $100,000 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Database established for research studies, HIV and AIDS and related behavior | NACS | UNAIDS |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Designing a web-based database |  | x | x | x | UNAIDS | TA | $25,000 | $0 |
| Subtotal | $25,000 | $0 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Analysis of Modes of Transmission Report conduced and report disseminated | NDOH | UNAIDS |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| TA for analysis of trends within available data |  | x | x |  | UNAIDS | TA | $30,000 | $0 |
| Data verification and triangulation workshop |  |  | x |  | UNAIDS | TA | $20,000 | $0 |
| Printing and dissemination of report |  |  |  | x | UNAIDS | Printing | $30,000 | $0 |
| Subtotal | $80,000 | $0 |
| Total for Output 8 | $499,000 | $890,000 |
| Expected output | Indicators | Baseline | Annual Target |
| Output 9: Leaders at National and Provincial levels are activity promoting Universal Access and Human Rights and Gender Issues related to HIV and putting them on the development agenda | Number of provinces allocating fund for HIV activities out of the provincial development fund budgets | 3 | 6 |
|  | Number of provinces integrating HIV between their sectoral programmes (such as education, transport, industry/mining, tourist, agriculture, etc) as well as the work place | 1 | 3 |
|  | Number of gender initiatives incorporated into national and provincial planning and activities | 1 | 5 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| One UN strategy to support NHS is developed and implemented | NACS/NDOH | UNAIDS |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Development of a new strategy for rolling over into the next three years |  |  | x | x | UNAIDS | Consultant, Workshop | $0 | $50,000 |
| Subtotal | $0 | $50,000 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Selected strategic leaders (including parliamentarians, youths, women, provincial and local leaders, religious and traditional leaders) at national and provincial levels understand and have access to improved leadership practices in addressing HIV | NACS | UNDP |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Follow up on TLDP (Transformational Leadership Development Program) i.e. positive women, women leaders, traditional leaders. | x |  |  |  | UNDP | Workshops, Trainings | $20,000 | $20,000 |
| Support to the finalization of the leadership engagement strategy and implementation | x | x | x | x | UNDP | TA, travel, meetings | $10,000 | $60,000 |
| Support Breakthrough Initiatives for provincial leadership coaches | x | x | x | x | UNDP | Workshops, Trainings | $10,000 | $40,000 |
| Conduct Provincial Monitoring visits for LDP Programme | x | x | x | x | UNDP | travel, meetings | $10,000 | $20,000 |
| Evaluate the LDP initiatives in selected provinces |  |  |  | x | UNDP |  | $0 | $40,000 |
| Certification national Leadership Development Programme Coaches | x |  |  |  | UNDP | travel, meetings | $10,000 | $20,000 |
| Conduct LDP orientation workshops for Media | x | x | x |  | UNDP | Workshops, Trainings | $10,000 | $20,000 |  |
| HIV Programme Specialist | x | x | x | x | UNDP | TA | $0 | $280,000 |  |
| Subtotal | $70,000 | $500,000 |  |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |  |
| Mechanism in place to support and integrate HIV and AIDS in provincial Development Planning and Budgeting, and Social Protection Initiatives | NACS | UNDP |  |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
| Conduct training/workshops for selected government departments/priority provinces on HIV/AIDS development planning and budgeting |  |  | x | x | UNDP | TA, Workshops, meetings | $0 | $50,000 |  |
| Support NACS developing and in rolling out social protection initiatives |  | x | x |  | UNDP | TA, Workshops, meetings | $0 | $30,000 |  |
| Support strategic public and private sectors to integrate HIV in the social protection initiatives at all levels | x | x | x |  | UNDP | Workshops, Trainings | $0 | $60,000 |  |
| TA Provincial and Local level Development Planning and Budgeting, and social protection | x | x | x | x | UNDP | TA | $0 | $80,000 |  |
| Subtotal | $0 | $220,000 |  |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |  |
| Mechanisms and processes in place for gender mainstreaming for NACS | NACS | UNIFEM, UNAIDS (Lead by UNIFEM) |  |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
| Support NACS in the establishment of a gender working group | x | x | x | x | UNIFEM | training | $0 | $50,000 |  |
| Gender audit conducted for NACS and selected PACS | X | x |  |  | UNIFEM | consultancy | $15,000 | $15,000 |  |
| Adoption of gender responsive budgeting in NACS | x | x |  |  | UNIFEM | training | $15,000 | $0 |  |
| Review of HIV M & E Framework with a gender lens | x | x | x | x | UNIFEM | TA and meetings | $0 | $20,000 |  |
| Develop initiatives and programmes that address gender and HIV |  |  | x | x | UNAIDS | workshop | $0 | $25,000 |  |
| Provision of TA for NACS to coordinate gender mainstreaming into national and provincial HIV response | x | x | x | x | UNIFEM | TA | $0 | $50,000 |  |
| WHO work included in gender health plan (See Gender-Based Violence AWP for details of activities and budget) |  |  |  |  | WHO |  | $0 | $0 |  |
| Subtotal | $30,000 | $160,000 |  |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |  |
| PNG CCM receives support for monitoring of current GFATM grants and application for new grants | CCM, NACS, NDoH | ALL (Lead by UNAIDS) |  |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |  |
| Providing TA to CCM Secretariat to monitor effectively the implementation of GFATM grant | X | X | X | X | UNAIDS | TA | $0 | $40,000 |  |
| Providing TA to CCM Secretariat to monitor effectively the implementation of GFATM grant | X | X | X | X | WHO | TA | $35,000 | $50,000 |  |
| Subtotal |  |  |  |  |  |  |  | $35,000 | $90,000 |  |
| Total for Output 9 |  |  |  |  |  |  |  | $135,000 | $1,020,000 |  |
| Total for Workplan | $2,267,900 | $5,499,500 |  |