The Government of Papua New Guinea and the United Nations in PNG 2011 Annual Work Plan for

Crisis Prevention

Country: Papua New Guinea

UNCP Outcome(s): 	Governance and crisis management: Government develops and implements effective governance and crisis management policies

Expected Intermediate Outcome(s):	National and provincial level Governments apply effective crisis management and prevention policies, strategies and techniques

Expected Output(s):	Provincial level Government and key national Government institutions are the capacity to promote peace building, community security and advocacy

Implementing partner:	Prime Minister’s Office, GoPNG

Responsible Parties and other Partners:	Prime Minister’s Office, GoPNG

ExCom Agency	UNDP

Participating Agency:	UNDP

Narrative

The Department of the Prime Minister & National Executive Council in collaboration with the UN has developed the Nation Building Programme, which was launched in 2008 and fully began implementation in 2009. The programme focuses on nation building, crisis prevention and recovery. It supports tyhe Papua New Guinea VISION 2050, which seeks to place PNFG among the top 50 countries in the UN Human Development Index by 2050. This wok plan outlines the community security and peacebuilding activities to be implemented througout 2011. The programme aims to build the capacity of the Government of Papua New Guinea (GoPNG) at national, provincial and local level as well as supporting community level structures that can enhance security and open the way for sustainable, conflict-sensitive development.

In its support to GoPNG in 2011, the Nation Building Programme will support i) the statistical evaluation of PM Dep.'s daily crime summary 2009 and 2010 which will provide analytical data for subsequent interventions, ii) the development of a National Guns Control Implementation Strategy, iii) the development of a National Security Policy, iv) a Natural Resource Management Analysis in close collaboration with GoPNG and other stakeholders, and v) the establishment of a Small Grants Mechanism.

Programme Period:		2008 - 2012

Programme Component:	Nation Building (Community Security & Peace Building)

Intervention Title:

Budget Code:			______________

Duration:			2011

Total Estimated annualized budget:	 US$ 612,000

- Unfunded budget:	US$ 537,000

- Funded budget:		US$ 75,000

Allocated resources

- Government                  	 ___________

- Regular 	                              ___________

Other:

- UNDP:			75,000

- Donor			___________

Agreed by:

Agreed by:

Expected output; Indicators; Baseline; Annual Target. Output 5.2.. Provincial level Government and key national Government institutions have the capacity to promote peace building, community security and advocacy; # Advocacy materials and knowledge products published or shared; N/A; 3. # CSOs receiving peace building small grants; N/A; 30. # Peace Building trainings, including PDAs, conducted; N/A; 6. # Provincial strategies on community security in place; N/A; 3. National coordinating body on weapons and community security in place; N/A; Yes. # Provinces with available threat perception data pertaining to violence, including GBV; N/A; 3. # Provinces with data on conflict/natural disaster related deaths and injuries; N/A; 3. # Provinces with available hazard mapping (natural disaster risk); N/A; 3. # Provinces with data on masculine attitudes towards GBV; N/A; 3. Annual Deliverable; Resp. Party; UN Agency. Statistical evaluation of PM Dep.'s daily crime summary 2009 and 2010 is undertaken and database is updated; PM Dep.; UNDP. Activities; Q1; Q2; Q3; Q4; Source of funds; Budget Description; Amount (funded); Amount (unfunded). Carry out statistical crime analysis; X; Statistician; 0; 8,000. Conduct needs assessment for crime database update and use of data; X; 1 national consultant; 0; 8,000. Miscellaneous; X; X; X; X; Miscellaneous; 0; 1,000. ACTIVITY TOTAL; 0; 17,000. Annual Deliverable; Resp. Party; UN Agency. National Guns Control Implementation Strategy is developed; PM Dep.; UNDP. Activities; Q1; Q2; Q3; Q4; Source of funds; Budget Description; Amount (funded); Amount (unfunded). Provide technical & strategic advice towards the formulation of an implementation strategy; X; X; consultation, national travel; 0; 20,000. Provide technical advice towards the establishment of a guns control mechanism or body; X; X; consultation meeting, national travel; 0; 30,000. Miscellaneous; X; X; X; X; Miscellaneous; 0; 1,000. ACTIVITY TOTAL; 0; 51,000. Annual Deliverable; Resp. Party; UN Agency. National Security Policy developed; PM Dep; UNDP. Activities; Q1; Q2; Q3; Q4; Source of funds; Budget Description; Amount (funded); Amount (unfunded). Provide technical and strategic advice toward the formulation of a National Security Policy; X; X; X; X; Pacific Center (PC TA); travel national; consultations; 20,000; 20,000. Support PM Dep in stakeholder consultation; X; X; X; X; Pacific Center (PC TA); travel (national), consultations, south-south TA; 30,000; 50,000. Miscellaneous; 0; 1,000. ACTIVITY TOTAL; 50,000; 71,000. Annual Deliverable; Resp. Party; UN Agency. Natural Resource Management (extractives) Analysis carried out and respective follow-up support provided to PM Dep in close collaboration of relevant stakeholders and GoPNG.; PM Dep.; UNDP. Activities; Q1; Q2; Q3; Q4; Source of funds; Budget Description; Amount (funded); Amount (unfunded). Research, analysis and recommendations; X; contracts for 1 team leader, 2 experts (governance and extractive resources), travel (national); 0; 20,000. Support for UNDP Regional Conference on Natural Resource Management; X; X; documentation; travel (internat'l); 0; 15,000. Support to strengthen PM Dep's capacities on Natural Resource Management; X; X; X; national consultant, meetings, consultations, travel (national); 0; 20,000. Miscellaneous; Miscellaneous; 0; 1,000. ACTIVITY TOTAL; 0; 56,000. Annual Deliverable; Resp. Party; UN Agency. Small Grants Mechanism established; PM Dep; UNDP. Activities; Q1; Q2; Q3; Q4; Source of funds; Budget Description; Amount (funded); Amount (unfunded). Set up & implement effective small grants mechanism; X; Pacific Center (CPAD); travel (national), consultations; 5,000; 0. Manage small grants for local level CSSC activities; X; X; X; Pacific Center (CPAD); grants, meetings with recipients of grants, monitoring; 10,000; 40,000. Train CSOs in capturing innovative activities; X; X; Pacific Center (CPAD); training material; workshop; 10,000; 0. Miscellaneous; X; X; X; X; 0; 1,000. ACTIVITY TOTAL; 25,000; 41,000. Annual Deliverable; Resp. Party; UN Agency. Project Management & Project Administration; PM Dep; UNDP. Activities; Q1; Q2; Q3; Q4; Source of funds; Budget Description; Amount (funded); Amount (unfunded). Technical and Strategic advice; X; X; X; X; Project Manager CS/PB; 0; 180,000. Operations and Administrative Support; X; X; X; X; Admin Assistant (NO), Driver, Travel; 0; 70,000. Finalize establishment and maintain UNDP sub-office; X; Equipment, rent, bills, security; 0; 50,000. Miscellaneous; X; X; X; X; Miscellaneous; 1,000. ACTIVITY TOTAL; 0; 301,000.