The Government of Papua New Guinea and the United Nations in PNG

2011 Annual Work Plan for

Health

Country: Papua New Guinea

Main implementing partner: National Department of Health

Responsible Parties and other Partners:

Participating Agencies: UNFPA, UNICEF, WHO

Narrative

The health task team annual work plan aims to guide and support the implementation of the National Health Plan 2011-2020, which was launched in August 2010. The contribution of the UN partners aligns under three sub-task teams: 1) Maternal and child health; 2) Communicable diseases; and 3) Health systems (including noncommunicable diseases and health promotion).

Maternal and child health

As agreed, WHO, UNICEF and UNFPA will work in close collaboration with other Development Partners in the spirit of the Paris Declaration on Aid Effectiveness, with Health Sector Improvement Program (HSIP) (SAWP framework in PNG), to improve overall access to MCH services. Special attention is given to assure that the rights of children for health and development, especially in vulnerable groups are respected and that women and families are empowered to claim their rights in relation to their health.

This Annual Work Plan was developed in close collaboration with National Department of Health technical advisors of Family Health Unit and representatives of professional societies (PNG Pediatric Society and Obstetric and Gynecologist Society).

As decided during the planning meeting in Loloata in October 2010, the MCH Annual Work Plan follows the guideline of the National Health Plan to achieve Key Result Area 4 (Improve Child Survival) and Key Result Area 5 (Improve Maternal Health). In addition the Health Team committed support for any other request from Government in case of disasters that could put at risk children and pregnant women.

Communicable diseases

The partners will continue their long-standing work on communicable diseases, including in improving access to safe water and adequate sanitation.  The National Health Plan made reducing the burden of communicable diseases as one of its priority, under Key Result Area 6. National capacity for dealing with TB, malaria, lymphatic filariasis and other neglected tropical diseases will be supported, particularly on the development of surveillance systems and the aspects of prevention, case management and control.

Health systems (including noncommunicable diseases and health promotion)

The work of the task team will focus on providing technical assistance to strengthen implementation of the primary health care policy and help deliver universal access to quality health services. Key result areas that will be supported include KRA1 (Improving service delivery), KRA2 (Strengthening partnerships and coordination with stakeholders) and KRA 3 (Strengthening health systems and governance.

The ongoing epidemiological transition and rapid increase in the burden from noncommunicable diseases will be addressed through promotion of healthy lifestyles (KRA 7). Particular attention will be made on supporting setting-based approaches, such as health-promoting schools, healthy workplaces, healthy villages, and other components of the healthy island approach.

| Programme Period: 2008 - 2012 Programme Component: Budget Code: Duration: 2011 | Estimated annualized budget: 11 597 249 Allocated resources: Funded: 7 843 749 Unfunded: 3 753 500 Total: 11 597 249 |
| --- | --- |

| Dr Clement Malau Secretary, Department of Health Signature: ________________________ Date: ________________________ | Dr William Adu-Krow WHO Representative Signature: ________________________ Date: ________________________ |
| --- | --- |

UNCP Outcome(s): 7 - Health

Expected Intermediate Outcome(s):

Sub Programs and Expected Outputs

Sub Program One: Maternal and child health

Output 7.1: Increased immunization coverage, roll-out of child survival interventions and IMCI, increased proportion of children exclusively breastfed and introduction and expansion of oral rehydration therapy at community level.

Output 7.2: Increased provision of quality maternal and reproductive health services, including health promotion interventions especially in remote and underserved areas.

Sub Program Two: Communicable diseases

Output 7.3: In at least three targeted provinces improved access to safe water and adequate sanitation and promotion of healthy behaviour practices have been undertaken through implementation of Healthy Islands approach.

Output 7.4: Capacity strengthened for the prevention, case management and control of malaria and filariasis.

Output 7.5: Capacity strengthened for the control of tuberculosis and sustained elimination of leprosy.

Sub Program Three: Health systems (including noncommunicable diseases and health promotion)

Output 7.6: Strengthened health system that support enhanced evidence based practices, coordination among stakeholders and improved health outcomes and delivery of health services.

Output 7.7: Support cost-effective use of medical products and technologies (incl. laboratory services) by health workers, practitioners and consumers at health facilities.

Output 7.8: To prevent and reduce disease, disability and premature death from chronic noncommunicable diseases and prevent or reduce risk factors for health conditions.

| Output 7.1 |  | Agency | Estimated | Funded | Unfunded |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | WHO | 945,000 | 625,000 | 320,000 |
|  |  |  |  | UNICEF | 1,123,500 | 653,500 | 470,000 |
|  |  |  |  | UNFPA | 0 | 0 | 0 |
|  |  |  |  | Total | 2,068,500 | 1,278,500 | 790,000 |
|  |  |  |  | % | 100% | 62% | 38% |
| Output 7.2 |  | Agency | Estimated | Funded | Unfunded |
|  |  |  |  | WHO | 1,005,000 | 365,000 | 640,000 |
|  |  |  |  | UNICEF | 313,500 | 218,500 | 95,000 |
|  |  |  |  | UNFPA | 1,445,000 | 865,000 | 580,000 |
|  |  |  |  | Total | 2,763,500 | 1,448,500 | 1,315,000 |
|  |  |  |  | % | 100% | 52% | 48% |
| MCH - subtotal |  | Agency | Estimated | Funded | Unfunded |
|  |  |  |  | WHO | 1,950,000 | 990,000 | 960,000 |
|  |  |  |  | UNICEF | 1,437,000 | 872,000 | 565,000 |
|  |  |  |  | UNFPA | 1,445,000 | 865,000 | 580,000 |
|  |  |  |  | Total | 4,832,000 | 2,727,000 | 2,105,000 |
|  |  |  |  | % | 100% | 56% | 44% |

| Output 7.3 |  | Agency | Estimated | Funded | Unfunded |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | WHO | 0 | 0 | 0 |
|  |  |  |  | UNICEF | 447,500 | 352,500 | 95,000 |
|  |  |  |  | UNFPA | 0 | 0 | 0 |
|  |  |  |  | Total | 447,500 | 352,500 | 95,000 |
|  |  |  |  | % | 100% | 79% | 21% |
| Output 7.4 |  | Agency | Estimated | Funded | Unfunded |
|  |  |  |  | WHO | 2,545,221 | 1,839,221 | 706,000 |
|  |  |  |  | UNICEF | 0 | 0 | 0 |
|  |  |  |  | UNFPA | 0 | 0 | 0 |
|  |  |  |  | Total | 2,545,221 | 1,839,221 | 706,000 |
|  |  |  |  | % | 100% | 72% | 28% |
| Output 7.5 |  | Agency | Estimated | Funded | Unfunded |
|  |  |  |  | WHO | 1,079,278 | 767,778 | 311,500 |
|  |  |  |  | UNICEF | 0 | 0 | 0 |
|  |  |  |  | UNFPA | 0 | 0 | 0 |
|  |  |  |  | Total | 1,079,278 | 767,778 | 311,500 |
|  |  |  |  | % | 100% | 71% | 29% |

| CD - subtotal |  | Agency | Estimated | Funded | Unfunded |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | WHO | 3,624,499 | 2,606,999 | 1,017,500 |
|  |  |  |  | UNICEF | 447,500 | 352,500 | 95,000 |
|  |  |  |  | UNFPA | 0 | 0 | 0 |
|  |  |  |  | Total | 4,071,999 | 2,959,499 | 1,112,500 |
|  |  |  |  | % | 100% | 73% | 27% |
| Output 7.6 |  | Agency | Estimated | Funded | Unfunded |
|  |  |  |  | WHO | 1,276,000 | 1,236,000 | 40,000 |
|  |  |  |  | UNICEF | 0 | 0 | 0 |
|  |  |  |  | UNFPA | 0 | 0 | 0 |
|  |  |  |  | Total | 1,276,000 | 1,236,000 | 40,000 |
|  |  |  |  | % | 100% | 97% | 3% |
| Output 7.7 |  | Agency | Estimated | Funded | Unfunded |
|  |  |  |  | WHO | 935,000 | 805,000 | 130,000 |
|  |  |  |  | UNICEF | 0 | 0 | 0 |
|  |  |  |  | UNFPA | 0 | 0 | 0 |
|  |  |  |  | Total | 935,000 | 805,000 | 130,000 |
|  |  |  |  | % | 100% | 86% | 14% |
| Output 7.8 |  | Agency | Estimated | Funded | Unfunded |
|  |  |  |  | WHO | 482,250 | 116,250 | 366,000 |
|  |  |  |  | UNICEF | 0 | 0 | 0 |
|  |  |  |  | UNFPA | 0 | 0 | 0 |
|  |  |  |  | Total | 482,250 | 116,250 | 366,000 |
|  |  |  |  | % | 100% | 24% | 76% |
| HHS - subtotal |  | Agency | Estimated | Funded | Unfunded |
|  |  |  |  | WHO | 2,693,250 | 2,157,250 | 536,000 |
|  |  |  |  | UNICEF | 0 | 0 | 0 |
|  |  |  |  | UNFPA | 0 | 0 | 0 |
|  |  |  |  | Total | 2,693,250 | 2,157,250 | 536,000 |
|  |  |  |  | % | 100% | 80% | 20% |
| Health total |  | Agency | Estimated | Funded | Unfunded |
|  |  |  |  | WHO | 8,267,749 | 5,754,249 | 2,513,500 |
|  |  |  |  | UNICEF | 1,884,500 | 1,224,500 | 660,000 |
|  |  |  |  | UNFPA | 1,445,000 | 865,000 | 580,000 |
|  |  |  |  | Total | 11,597,249 | 7,843,749 | 3,753,500 |
|  |  |  |  | % | 100% | 68% | 32% |

| Expected output | Indicators |  |  |  |  |  |  | Baseline | Annual Target |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Output code 7.1 |  |  |  |
| Increased immunization coverage, roll-out of child survival interventions and IMCI, increased proportion of children exclusively breastfed and introduction and expansion of oral rehydration therapy at community level | National measles coverage | 54% | 65% |
|  | New IMCI Guidelines finalized and being implemented | 0 | Yes |
|  | Number of Baby Friendly Hospitals Accredited | 1 | 4 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Technical support provided to NDoH to increase coverage of child immunization in all Provinces (National Health Plan 2011-2020; Objective 4.1, strategies 4.1.1 and 4.1.2) | NDoH | WHO, UNICEF |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| 1. Strategy 4.1.1: Ensure every facility, every day, has the capacity to immunize children |  |  |  |  |  |  |
| 1.1 Technical Assistance and financial support to identified low-performing districts using supportive supervision tool and focused facility level support using RED Strategy | X | X | X | X | WHO | DFC | 0 | 50,000 |
|  | X | X | X | X | UNICEF | Cash | 35,000 | 45,000 |
| 1.2. Printing of EPI manual and policy | X | X |  |  | WHO | DFC | 0 | 10,000 |
|  | X | X |  |  | UNICEF | Cash | 10,000 | 0 |
| 1.3. Injection safety assessment and implementation of injection safety procedures |  | X | X |  | WHO | DFC | 10,000 | 0 |
| 1.4. Review of MNTE risk assessment and preparation of Plan of Action | X | X |  |  | WHO | DFC | 5,000 | 0 |
|  | X | X |  |  | UNICEF | Cash | 10,000 | 0 |
| 1.5. Support to Pediatric Surveillance Officer for M E Surveillance | X | X | X | X | WHO | Contract SSA | 15,000 | 0 |
| 1.6 Effective Vaccine Stock Management | X | X |  |  | WHO | DFC | 25,000 | 0 |
| 1.7 Data Quality Audit and Data management | X | X |  |  | WHO | Cash | 15,000 | 0 |
|  | X | X |  |  | UNICEF | DFC | 10,000 | 0 |
| 1.8. Convenience Sero Survey of Hep B |  | X | X |  | WHO | DFC | 20,000 | 0 |
| 2. Strategy 4.1.2: Conduct supplementary immunization programs every three years or more frequently as needed. |  |  |
| 1. Support to SIA Social mobilization materials |  |  | X |  | UNICEF | Cash | 25,000 | 25,000 |
| 2. Support to Planning for SIA 2012 including micro planning and review of 2010 |  | X | X |  | UNICEF | Cash | 25,000 | 0 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Technical support provided to NDoH to reduce case fatality rates for pneumonia in children through acceleration of roll-out of Integrated Management of Childhood Illnesses (IMCI) to all Provinces (National Health Plan 2011-2020; Objective 4.1, strategies 4.2.1, 4.2.2 and 4.4.3) | NDoH | WHO UNICEF |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| 3. Strategy 4.2.1: Increase the number of health facilities that have the capacity to implement IMCI. |  |  |
| 3.1 Final revision of IMCI training materials including HIV/AIDS | X | X |  |  | WHO | DFC | 5,000 | 10,000 |
|  | X |  |  |  | UNICEF | Cash | 5,000 | 0 |
| 3.2 Printing IMCI training materials |  | X | X |  | WHO | AWP | 5,000 | 10,000 |
|  |  | X | X |  | UNICEF | Cash | 10,000 | 10,000 |
| 3.3 Revising Baby Health Record Book |  | X |  |  | WHO | DFC | 0 | 10,000 |
|  |  | X |  |  | UNICEF | Cash | 5,000 | 0 |
| 3.4 Printing Baby Health Record Book |  |  | X | X | UNICEF | Cash | 15,000 | 35,000 |
| 3.5 Develop training materials for IMCI coordinators | X | X |  |  | WHO | DFC | 10,000 | 0 |
|  | X | X |  |  | UNICEF |  | 5,000 | 0 |
| 3.6 Provincial IMCI coordinators training workshop |  | X | X | X | WHO | DFC | 0 | 20,000 |
|  |  | X | X | X | UNICEF | Cash | 20,000 |  |
| 3.7 IMCI Follow-up trainings (one for each region) | X | X | X | X | WHO | DFC | 5,000 | 5,000 |
| 4. Strategy 4.2.2: Increase the percentage of communities with capacity to implement IMCI |  |  |
| 4.1 Adaptation of training materials on Community IMCI |  | X | X |  | WHO | DFC | 0 | 25,000 |
| 4.2 Printing of training materials for community IMCI |  |  | X | X | UNICEF | Cash | 10,000 | 15,000 |
| 4.3 Preparation and planning for implementation of community IMCI in 2012 |  | X | X | X | UNICEF | Cash | 10,000 | 0 |
| 5. Strategy 4.2.3: Ensure antibiotics are available every day at every facility to combat pneumonia in children under five. |  |  |
| 5.1 Developing and testing of the checklist to assess availability of drugs and equipment for implementation of IMCI strategy and monitoring and evaluation of IMCI. |  | X | X |  | WHO | Cash | 5,000 | 5,000 |
| 5.2 Procurement of oxygen concentrators for 3 hospitals - 6 concentrators. |  | X | X | X | WHO | Cash | 0 | 20,000 |
| 5.3 Training of health workers on oxygen therapy |  |  | X | X | UNICEF | Cash | 10,000 | 0 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Technical support provided to NDoH to decrease neonatal deaths (National Health Plan 2011-2020; Objective 4.3, strategies 4.3.1, 4.3.2 and 4.3.3) | NDoH | WHO UNICEF UNFPA |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| 6. Strategy 4.3.1: Ensure that every facility has the capacity to provide life-saving support to the neonate. |  |  |
| 6.1 Updating 8 Step Check list for Neonates |  | X | X |  | WHO | DFC | 0 | 5,000 |
|  |  | X | X |  | UNICEF | Cash | 5,000 | 0 |
| 6.2 Printing and distribution of 8 Step Check list for Neonates |  |  | X | X | WHO | DFC | 0 | 10,000 |
|  |  |  | X | X | UNICEF | Cash | 10,000 | 10,000 |
| 6.3 Training on neonatal resuscitation |  | X | X | X | WHO | DFC | 0 | 20,000 |
|  |  |  | X | X | UNICEF | Cash | 10,000 | 0 |
| 6.4 Printing leaflets on newborn care |  | X |  |  | UNICEF | Cash | 10,000 | 10,000 |
| 6.5 Support for continuing medical education of Pediatricians. | X | X | X | X | WHO | Cash | 0 | 10,000 |
|  |  |  | X |  | UNICEF | Cash | 7,500 | 0 |
| 6.6 Supply of newborn care kits (including IEC material and supplies for neonatal infection prevention to NCD, EHP, Simbu and WHP) | X | X | X | X | UNICEF | Cash | 10,000 | 5,000 |
| 7. Strategy 4.3.2: Increase tetanus toxoid coverage of antenatal mothers. |  |  |
| 7.1 Preparing and implementing IEC campaign on antenatal care and tetanus toxoid immunization |  |  | X | X | WHO | DFC | 10,000 | 0 |
|  |  |  | X | X | UNICEF | Cash | 10,000 | 0 |
| 8. Strategy 4.3.3: Improve maternal health services, and improve supervised deliveries. |  |  |
| This activity is implemented under output 7.2. | X | X | X | X |  |  |  |  |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Technical support provided to NDoH to reduce malnutrition in children under the age of five years. (National Health Plan 2011-2020; Objective 4.4, strategies 4.4.1, 4.4.2 and 4.4.3) | NDoH | WHO UNICEF |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| 9. Strategy 4.4.1: Advocate and promote excusive breastfeeding. |  |  |
| 9.1 Review of National Nutrition Policy (to include IYCF, Micronutrients, HIV, Lifestyle Diseases) | X |  |  |  | UNICEF | Cash, TA | 20,000 | 0 |
| 9.2 Review Existing Guidelines/Strategy for Nutrition Programme and develop Operational Plan |  |  |  |  | UNICEF | Cash, TA | 20,000 | 0 |
| 9.3 National Workshop to discuss Draft Reviewed Nutrition Policy |  |  |  |  | UNICEF | Cash | 10,000 | 0 |
| 9.4 Workshop for Consensus on Nutrition Operational Plan |  |  |  |  | UNICEF | Cash | 10,000 | 0 |
| 9.5 Develop Communication Strategy on Nutrition including promotion of Exclusive Breast feeding |  |  |  |  | UNICEF | Cash | 10,000 | 0 |
| 9.6 Advocate for expansion and support mother and baby friendly hospital initiative through advocacy to hospital management of regional hospitals | X | X | X | X | WHO | DFC/AWP | 0 | 15,000 |
|  | X | X | X | X | UNICEF | Cash | 5,000 | 0 |
| 9.7 Technical support for rolling-out COMBI plan for breastfeeding |  | X | X |  | WHO | Consultancy | 0 | 20,000 |
|  |  |  | X | X | UNICEF | Cash | 0 | 10,000 |
| 10. Strategy 4.4.2: Ensure all babies and children under five have access to supplementary feeding when and where they required it. |  |  |
| 10.1 Facilitating and support for 2 IYCF counseling training at provincial level |  |  | X | X | WHO | Cash | 0 | 25,000 |
|  |  |  | X | X | UNICEF | Cash | 0 | 25,000 |
| 10.2 Implementation of IYCF counseling training at community levels (2 trainings) |  | X | X | X | UNICEF | Cash | 50,000 | 50,000 |
| 10.3 Support research on supplementary feeding |  | X | X |  | WHO | DFC | 0 | 20,000 |
|  |  |  |  |  | UNICEF | Supply | 5,000 |  |
| 10.4 Support NDoH in strengthening National System on iodized salt monitoring through training of quarantine officers in main sea ports on usage of iodine checker machines to control and maintain the level of over 90% universal salt iodization in imported salt. |  | X | X |  | UNICEF | Cash | 10,000 | 5,000 |
| 11. Strategy 4.4.3: Ensure all babies and children under five have access to supplementary feeding when and where they required it. |  |  |
| 11.1 Research on breastfeeding, supplementary feeding and micronutrient practices on Vitamin A in PNG |  | X | X |  | WHO | DFC | 0 | 30,000 |
| Project support costs | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Staff costs | X | X | X | X | WHO | Staff | 230,000 | 0 |
|  | X | X | X | X | UNICEF | Staff | 186,000 | 175,000 |
| Other costs | X | X | X | X | WHO | Other | 265,000 | 0 |
|  | X | X | X | X | UNICEF | Other | 60,000 | 50,000 |
| Expected output | Indicators |  |  |  |  |  |  | Baseline | Annual Target |
| Output code 7.2 |  |  |  |
| Increased provision of quality maternal and reproductive health services, including health promotion interventions especially in remote and underserved areas. | # of Districts with increased capacity to implement family planning package | 0 | 20 |
|  | # Adolescent Reproductive Health Strategy completed | 0 | 1 |
|  | # of districts with comprehensive strategies on promotion of ante-natal care and supervised births | 2 | 6 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Technical assistance to NDoH to increase family planning coverage in the PNG. (National Health Plan 2011-2020; Objective 5.1, strategies 5.1.1, 5.1.2 and 5.1.3) | NDoH | WHO UNFPA UNICEF |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| 1. Strategy 5.5.1: Ensure every health facility has the capacity to offer family planning services at all times |  |  |
| 1.1 Printing Family Planning (FP) policy. | X | X | X | X | UNFPA | Transfer | 20,000 | 0 |
| 1.2 Conduct regional workshops to introduce FP policy. | X | X | X | X | UNFPA | Transfer | 10,000 | 25,000 |
| 1.3 Collaboration with Human Resource Branch to disseminate FP policy and include it in the training curriculum for health workers |  |  | X | X | UNFPA | Transfer | 10,000 | 20,000 |
| 1.4 Revising Sexual and Reproductive Health Policy and developing Woman Health, Adolescent Health and Man Health Policies. |  | X | X |  | WHO | APW/DFC | 10,000 | 0 |
| 1.5 Provincial RHCS Training (Wewak): USD$10,000 (in-country costs) |  | X |  |  | UNFPA/SRO | Transfer | 10,000 | 0 |
| 1.6 Recruitment of RHCS Focal Points ( CCP Programme Officer and RHCS Officer): | X |  |  |  | UNFPA/SRO | Transfer | 30,000 | 0 |
| 1.7 Translation Family Planning IEC materials into local language (Motu). |  | X | X |  | WHO | APW | 5,000 | 0 |
| 2. Strategy 5.5.2: Advocate for the advantages of having fewer children and increased spacing of children. |  |  |
| 2.1 Development and testing of advocacy materials on having fewer children (comics) |  | X |  |  | WHO | APW | 5,000 | 0 |
| 2.2 Support for CCP Strategy Implementation | X | X | X | X | UNFPA | Transfer | 0 | 100,000 |
| 2.2 Printing advocacy materials on Family Planning |  |  | X |  | WHO | Supply | 10,000 | 5,000 |
| 3. Strategy 5.5.1: Extend the reach of village health volunteers (VHV) program and community-based distribution systems. |  |  |
| 3.1 Technical assistance for updating training aids for village health volunteers to promote Family Planning at community level. | X | X | X |  | WHO | DFC | 0 | 5,000 |
| 3.2 Printing training aids for village health volunteers. |  |  |  | X | UNFPA | Transfer | 0 | 20,000 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Technical assistance to NDoH to increase capacity of the health sector to provide safe and supervised deliveries. (National Health Plan 2011-2020; Objective 5.2, strategies 5.1.1, 5.1.2 and 5.1.3) | NDoH | WHO UNFPA UNICEF |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| 4. Strategy 5.2.1: Increase number of facilities capable of providing supervised deliveries. |  |  |
| 4.1 Technical Assistance in developing plan to upgrade Health Centres to provide comprehensive maternal health services including deliveries. |  | X | X |  | UNFPA | Transfer | 0 | 50,000 |
| 4.2 Technical Assistance in funds mobilization to upgrade Health Centres to provide comprehensive maternal care services. |  | X | X | X | WHO | TA | 0 | 10,000 |
| 5. Strategy 5.2.2: Increase the numbers of health workers skilled in obstetric care. |  |  |
| 5.1 Support for midwifery training |  | X | X | X | WHO | DFC | 5,000 | 20,000 |
|  |  | X | X | X | UNFPA | Transfer | 30,000 | 0 |
| 5.2 Hospital attachment for rural staff (nurses/CHWs) for 8 weeks in 5 provinces with poor indicators |  | X | X | X | UNFPA | Transfer | 25,000 | 0 |
| 5.3 Support for continuing medical education of Obstetricians and Gynecologists. |  | X | X | X | UNICEF | Cash | 7,500 | 10,000 |
|  |  | X | X | X | UNFPA | Cash | 25,000 | 0 |
| 5.4 Sponsor 10 Candidates for PSRH Meeting Honiara |  |  | X |  | UNFPA | Cash | 10,000 | 0 |
| 6. Strategy 5.2.3: Ensure every health facility is capable of providing quality service/support before, during and after pregnancy. |  |  |
| 6.1 Procuring and distributing EmOC equipment |  | X | X | X | WHO | Cash | 0 | 10,000 |
|  |  | X | X | X | UNFPA | Transfer | 0 | 75,000 |
| 6.2 Procurement and distribution of VHV/Midwifery /Neonatal Supplies for health facilities with lowest district ANC and supervised delivery rates in focal province |  |  |  |  | UNICEF | Cash | 25,000 | 25,000 |
| 6.3 Emergency procurement and distribution of EmOC drugs in case of identified gaps |  | X | X | X | UNFPA | Transfer | 45,000 | 0 |
|  |  | X | X | X | UNFPA | Transfer | 0 | 0 |
| 6.4 Developing and distribution of IEC materials and job aids on PPTCT | X | X | X | X | WHO | Cash | 10,000 | 0 |
|  |  | X | X | X | UNICEF | Cash | 0 | 10,000 |
| 6.5 Monitoring and evaluation of maternal health services |  | X | X | X | WHO | Cash | 5,000 | 5,000 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Technical assistance to NDoH to improve access to emergency obstetric care (EOC). (National Health Plan 2011-2020; Objective 5.3, strategies 5.3.1, 5.3.2 and 5.3.3) | NDoH HSIP UPNG YWCA | WHO UNFPA UNICEF |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| 7. Strategy 5.3.1: Increased the capacity of all facilities to provide essential EmOC. |  |  |
| 7.1 Review training guideline and materials on Emergency Obstetric Care. | X | X | X | X | WHO | DFC | 5,000 | 10,000 |
|  | X | X | X | X | UNFPA | Transfer | 35,000 | 0 |
| 7.2 Conducting training on EmOC in 2 Regions |  | X |  |  | UNFPA | Transfer | 20,000 | 0 |
|  | X | X | X | X | UNICEF | Cash, Training | 10,000 | 0 |
|  | X | X | X | X | UNFPA | Transfer | 30,000 | 0 |
| 7.3 EmOC consultation meeting and EmOC assessment in selected districts. | X | X | X | X | WHO | DFC | 0 | 20,000 |
|  |  | X | X |  | UNICEF | Supply | 15,000 | 0 |
|  |  | X | X |  | UNFPA/SRO | Transfer | 100,000 | 0 |
|  |  | X | X |  | UNFPA | Transfer | 50,000 | 0 |
| 8. Strategy 5.3.2: Increase the number of facilities capable of providing comprehensive obstetric care. |  |  |
| 8.1 Rapid assessment of comprehensive obstetric care to upgrade district hospitals to provide comprehensive maternal health care including caesarean section. |  | X | X | X | WHO | DFC | 0 | 10,000 |
|  |  | X | X | X | UNFPA | Transfer | 0 | 50,000 |
| 8.2 Support for communication strategy for maternal health response. |  | X | X | X | WHO | Supplies/DFC | 5,000 | 15,000 |
|  | X | X | X |  | UNFPA | Transfer | 10,000 | 0 |
|  | X | X | X | X | UNICEF | Supplies | 20,000 | 10,000 |
| 9. Strategy 5.3.3: Ensure every maternal death is investigated and audited and practice improved. |  |  |
| 9.1Technical assistance in rapid assessment of maternal death |  | X | X | X | UNFPA | Transfer | 25,000 | 0 |
| 9.2 Support in conducting maternal death audit in selected district |  | X | X | X | WHO | DFC | 0 | 5,000 |
|  |  | X | X | X | UNFPA | Transfer | 0 | 20,000 |
|  |  | X | X | X | UNICEF | Cash | 15,000 | 10,000 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Technical assistance to NDoH to improve sexual and reproductive health for adolescents. (National Health Plan 2011-2020; Objective 5.4, strategies 5.4.1 and 5.4.2) | NDoH HSIP UPNG YWCA | WHO UNFPA UNICEF |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| 10. Strategy 5.4.1: Increase the knowledge of adolescents about sexual and reproductive health. |  |  |
| 10.1 Printing and distributing PNG Youth and Adolescent Health (YAH) training package |  | X | X | X | UNFPA | Cash | 30,000 | 0 |
| 10.2 Scholarship for postgraduate study for managers of YAH at national level | X | X | X | X | UNFPA | Transfer | 0 | 10,000 |
| 10.3 Support for clinical attachment program on adolescent health in other countries | X | X | X | X | WHO | Cash | 0 | 10,000 |
| 10.4 Monitoring and evaluation of adolescent health | X | X | X | X | UNFPA | Cash | 20,000 | 0 |
| 10.5 Operational research on adolescent health | X | X | X | X | UNFPA | Cash | 25,000 | 0 |
| 10.6 Technical support for development of Adolescent Health policy, guideline and standards | X | X | X | X | WHO | TA | 20,000 | 0 |
|  |  | X | X | X | UNICEF | Cash | 10,000 | 0 |
| 10.7 Technical support to developing monitoring framework for adolescent and youth health for National Health Information System (NHIS). | X |  |  |  | UNFPA | Transfer | 10,000 | 0 |
|  | X | X |  |  | WHO | Cash | 10,000 | 0 |
| 11. Strategy 5.4.2: Increase cross-sectoral collaboration with schools and strengthen education of students in sexual and reproductive health. |  |  |
| 11.1 Annual program meetings for stakeholders in youth and adolescent health |  |  | X | X | WHO | Cash | 0 | 20,000 |
| 11.2 Development and testing of educational package on sexual and reproductive health for schools |  | X | X | X | WHO | Cash | 5,000 | 20,000 |
| 11.3 Summit on partnership on youth and adolescent health |  | X |  |  | UNFPA | Transfer | 0 | 115,000 |
| 11.4 Working in collaboration with Department of Education and Churches on program of HIV/AIDS prevention in adolescents. |  | X | X |  | UNFPA | Transfer | 0 | 10,000 |
| 11.5 Peer education training and counseling training on HIV & AIDS, reproductive health and gender issues among adolescents and university students at UPNG | X | X | X | X | UNFPA | Transfer | 25,000 | 0 |
| 11.6 Expansion and replication of university peer education programme to other universities in Madang, Lae and Goroka |  | X | X | X | UNFPA | Transfer | 0 | 50,000 |
| 11.7 Production of peer education manual with NDoH and NACS for university students |  | X | X | X | UNFPA | Transfer | 0 | 10,000 |
| 11.8 Evaluation of the Peer education program at university |  | X | X | X | UNFPA | Transfer | 10,000 | 0 |
| 11.9 TA to peer education programme at universities. Staff at UPNG | X | X | X | X | UNFPA | Transfer | 16,000 | 0 |
| 11.10 IEC material and Video production on peer education program at the university | X | X | X | X | UNFPA | Transfer | 15,000 | 10,000 |
| 11.11 Procurement and maintenance of project equipment at UPNG | X | X | X | X | UNFPA | Transfer | 10,000 | 15,000 |
| 11.12 Support to the peer education programme of YWCA for (in and out of school) youth and young women | X | X | X | X | UNFPA | Transfer | 25,000 | 0 |
| 11.13 Design, Develop & Produce IEC- martial on Adolescent reproductive health and rights through YWCA | X | X | X | X | UNFPA | Transfer | 10,000 | 0 |
| 11.14 TA to peer education programme and TOKstret programme. Salary, facility and training of staff at YWCA | X | X | X | X | UNFPA | Transfer | 35,000 | 0 |
| 11.15 Procurement of project equipment and maintenance of existing project equipment at YWCA | X | X | X | X | UNFPA | Transfer | 10,000 | 0 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Involvement of churches in reproductive health, HIV & AIDS and gender activities (National Health Plan 2011-2020; Objective 2.2, strategies 2.2.1 and 2.2.2) | YWCA | UNFPA |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| 12. Strategy 2.2.1 Village awareness campaign In Saundaun province by AOG fraternity and strengthening of church partnership with JLC/Destiny Church Simbu |  |  |
| 12.1 Village awareness campaign In Sandaun province by AOG fraternity and strengthening of church partnership with JLC/Destiny Church Simbu |  | X | X |  | UNFPA | Cash | 10,000 | 0 |
| 12.2 Refreshment training with religious leaders on HIV & AIDS, reproductive health and youth issues |  | X | X |  | UNFPA | Cash | 10,000 | 0 |
| Annual Deliverable |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Increased knowledge and skills on different issues related to the ICDPs; such on HIV and AIDS, reproductive health, gender among youth and general public in PNG (National Health Plan 2011-2020; Objective 7.3, strategies 7.3.3 - Increase individual's and communities' involvement in their own health) | YWCA | UNFPA |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| 13. Strategy 7.3.3 Implement strategies that empower the community and the individuals to take ownership and direction of their health and the health of their families. |  |  |
| 13.1 Weekly radio and television broadcasting on HIV & AIDS, reproductive health and gender issues | X | X | X | X | UNFPA | Cash | 38,000 | 0 |
| 13.2 Production of video on Gender, HIV & AIDS and reproductive health issues in PNG for educational purposes through YWCA |  | X | X |  | UNFPA | Cash | 10,000 | 0 |
| 13.3 Awareness on gender, HIV & AIDS and reproductive health issues among students through sports, theatre, radio/TV and music/World AIDS day celebration |  | X | X |  | UNFPA | Cash | 26,000 | 0 |
| 13.4 IEC campaign to increase rates of antenatal care and supervised deliveries. | X | X | X | X | WHO | Supply/DFC | 5,000 | 15,000 |
| 13.5 Support VHV-CHW outreach activities including monitoring and evaluation in selected districts of 2 provinces (Milne Bay and Simbu) | X | X | X | X | UNICEF | Cash | 10,000 | 0 |
| Project support costs | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Staff costs | X | X | X | X | WHO | Tech. Staff | 0 | 460,000 |
|  | X | X | X | X | UNICEF | Tech. Staff | 56,000 | 0 |
|  | X | X | X | X | UNFPA | Tech. Staff | 45,000 | 0 |
| Other costs | X | X | X | X | WHO | Other | 265,000 | 0 |
|  | X | X | X | X | UNICEF | Other | 50,000 | 30,000 |
|  | X | X | X | X | UNFPA | Other | 0 | 0 |

| Expected output | Indicators |  |  |  |  |  |  | Baseline | Annual Target |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Output code 7.3 |  |  |  |
| In at least three targeted provinces improved access to safe water and adequate sanitation and promotion of healthy behavior practices have been undertaken through implementation of Healthy Islands approach | No of health facilities with improved water and sanitation facilities | 21 | 30 |
|  | No of schools with improved water and sanitation facilities | 24 | 30 |
|  | No of communities have access to safe drinking water and sanitation facilities | 12 | 20 |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Enhanced capacity of PNG provincial partners to advocate hygiene and sanitation concepts and practices, including hand washing to schools, health centres and village communities that will result behavioral changes in the long term. | NDoH | UNICEF |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Established Water and Sanitation Committees in Eastern Highlands, Western Highlands, and Simbu provinces to meet every 4 months to coordinate with NGOs and prioritize WES activities including contributing to the production of project WES Newsletter and conducting consultation meeting. |  |  | X | X | UNICEF | Travel | 2,500 | 0 |
| Engage one international consultant to develop social marketing concept and plan on WES to be to be introduced in Eastern Highlands province. | X | X | X | X | UNICEF | Contract, Travel | 35,000 | 25,000 |
| Engage one local consultant through the Education Department to revise and improve the existing hygiene curriculum. |  | X |  |  | UNICEF | Travel | 10,000 | 0 |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Support 6 child-friendly schools, 6 health centres, and 6 communities to have access to safe and well-maintained water supply, basic sanitation and hygiene facilities. | NDoH | UNICEF |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Timely procurement and delivery of supplies and equipment for 69 rain water catchments systems, 3 gravity-fed systems, and 90 latrines in Eastern Highlands, Western Highlands, and Simbu provinces. | X | X |  |  | UNICEF | Supplies | 240,000 | 0 |
| Facilitate construction, supervision, and transportation expenses support for government counterparts during implementation of WES facilities for six child-friendly schools, nine health centres, and aid posts, nine rural communities in Eastern Highlands, Western Highlands and Simbu provinces. | X | X | X | X | UNICEF | Travel | 50,000 | 0 |
| Annual Deliverable |  |  |  | Resp. Party | UN Agency |
| Support selected schools, health centres and village communities with safe access to water supply and adequate sanitation in response to cholera prevention and conduct preparatory activities to respond to un-expected emergency situations. | NDoH | UNICEF |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Contingency fund to support WASH emergencies in affected areas as and when necessary. |  | X |  |  | UNICEF | Travel | 5,000 | 60,000 |
| Programme Support Costs | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Programme Support Cost; UNICEF WES Monitoring and Field Trip | X | X | X | X | UNICEF | Travel | 10,000 | 10,000 |
| Expected output | Indicators |  |  |  |  |  |  | Baseline | Annual Target |
| Output code 7.4 |  |  |  |
| Capacity strengthened for the prevention, case management and control of malaria and filariasis | Number of minilabs procured and provided | 0 | 6 |
|  | Number of provinces supported in the implementation of MDA | 0 | 6 |
|  | Number of workshops conducted for microscopy | 0 | 3 |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Assistance to NMCP in developing strategies in sustainability of the programme | NDoH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| International TA to develop sustainable programme strategies | X | X |  |  | WHO | TA | 26,250 | 0 |
| To provide routine technical support on malaria, vector-borne disease and other parasitic diseases | X | X | X | X | WHO | Salary | 240,000 | 0 |
| To provide routine technical support on rolling out of ACT and RDT | X | X | X | X | WHO | Salary | 180,000 | 60,000 |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Procurement and provision of microscopes and slides for malaria diagnosis | NDoH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| To procure and provide 72 compound microscopes with mirror illumination units | X |  |  |  | WHO | procurement | 741,000 | 0 |
| To procure and provide slide, lancets, stains and reagent | X |  |  |  | WHO | procurement | 308,947 | 0 |
| Annual Deliverable |  |  |  | Resp. Party | UN Agency |
| Establishment of QA for public and private sector healthcare networks-- Improve and expand laboratory quality assurance | NDoH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| International technical assistance to assess capacity and support QA of public and private laboratories |  |  |  | X | WHO | TA | 13,125 | 0 |
| Technical assistance to conduct microscopy workshop |  |  |  | X | WHO | TA | 13,125 | 0 |
| Support of test of RDT quality batch testing | X | X | X | X | WHO | lab test | 57,274 | 0 |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Improve antimalarial drug and RDTs supply management system | NDoH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| International technical assistance on forecasting, procurement and supply management |  | X | X |  | WHO | TA | 26,250 | 0 |
| International Technical Assistance on Improve infrastructure and strengthen logistics for malaria control program at all levels (RDT, ACT, ITM, insecticide etc.) | X |  |  | X | WHO | TA | 51,250 | 0 |
| Procurement of Mini Lab and its consumables | X | X |  |  | WHO | procurement | 182,000 | 0 |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| To improve filariasis control programme. | NDoH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| To provide routine technical support to filariasis control programme | X | X | X | X | WHO | SSA salary and duty travel cost | 0 | 25,000 |
| Conduct refresher training for team leaders and supervisors of local MDA teams | X |  | X |  | WHO | Training | 0 | 46,000 |
| Implement MDA in the provinces and morbidity case reporting |  | X |  |  | WHO | field operation | 0 | 150,000 |
| Training on home-based self-care among registered individual patients presenting with acute or chronic phase of filariasis | X | X | X | X | WHO | Training | 0 | 150,000 |
| TA for training on surgical management among patients with urogenital manifestations of lymphatic filariasis | X | X | X | X | WHO | TA | 0 | 150,000 |
| Advocacy in three provinces in preparation for MDA |  |  | X |  | WHO | advocacy | 0 | 60,000 |
| Identify 2 sentinel sites for NIP and ARB for baseline survey. Conduct ICT card survey for LF |  |  | X |  | WHO | field survey | 0 | 20,000 |
| Conduct baseline study/assessment for DEC implementation |  |  | X |  | WHO | field survey | 0 | 10,000 |
| Manus and Central Province--Identify 2 sentinel sites for MF survey. Conduct ICT card survey for LF and if possible a STH survey in schools. |  | X | X |  | WHO | field survey | 0 | 20,000 |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| To implement filariasis control programme in other Provinces |  |  |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Conduct deworming programme for children |  |  | X |  | WHO | Supplies and TA | 0 | 15,000 |
| Expected output | Indicators |  |  |  |  |  |  | Baseline | Annual Target |
| Output code 7.5 |  |  |  |
| Capacity strengthened for the control of tuberculosis and sustained elimination of leprosy. | Comprehensive TB National Laboratory network plan integrated into Health Systems | No plan | Plan developed |
|  | MDR-TB patient services initiated at provincial PMDT sites | 0 | 3 |
|  | Develop strategic framework for Leprosy control for 2011 to 2015 | 0 | 1 |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Enhanced quality of TB Surveillance in the country | NDoH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| 1.1. Conduct meeting between Government and Partner Agencies to launch the Stop TB Strategy |  |  | X | X | WHO | TA | 3,018 | 0 |
| 1.2. Recruit/retain one National and three Regional Lab Coordinators |  |  | X | X | WHO | TA | 65,818 | 0 |
| 1.3. Conduct refresher training of laboratory personnel for sputum microscopy and undertake lab supervision in provinces | X | X | X | X | WHO | Training | 65,236 | 0 |
| 1.4 Print new recording and reporting formats based on the Stop TB Strategy |  |  | X | X | WHO | Supplies | 86,007 | 0 |
| 1.6 International meetings / trainings on Stop TB Strategy |  |  | X | X | WHO | Travel | 10,100 | 0 |
| 1.7 Recruit/retain/hire international and local technical advisors for various components of the Stop TB Strategy (Un Staff, STCs, SSAs) | X | X | X | X | WHO | TA | 380,488 | 0 |
| 1.8 Supervise / training visits to the provinces and BMUs for Stop TB Strategy and TB/HIV |  | X |  |  | WHO | Training | 20,422 | 0 |
| 1.9 Procure and supply computers and communication facilities | X | X |  |  | WHO | Supplies | 21,683 | 0 |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Comprehensive TB Lab networking Plan for quality assurance established | NDoH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| 2.1. Technical Assistance visits by international Laboratory experts |  | X | X |  | WHO | TA | 0 | 30,000 |
| 2.2. Training on Lab culture and Drug Sensitivity Testing (DST) |  | X | X |  | WHO | Training | 11,082 | 0 |
| 2.3. IATA training for handling, packaging and air transport of sputum specimens |  | X | X | X | WHO | Training | 0 | 12,000 |
| 2.4 Operationalise a sputum transportation network for DST and culture | X | X | X | X | WHO | Support services | 0 | 25,000 |
| 2.5 Procure lab reagents for DST | X | X | X | X | WHO | Supplies | 75,000 | 0 |
| 2.6 Training, equipment, consumables and maintenance for rapid TB diagnostics |  | X | X | X | WHO | TA, supplies | 0 | 50,000 |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Technical assistance for phased expansion of PMDT (Programmatic Management of Drug resistant TB) | NDoH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| 3.1 Publishing and printing of MDR-TB guidelines and WHO PMDT training modules |  |  | X | X | WHO | Supplies | 0 | 10,000 |
| 3.2 Technical assistance visits by GLC |  | X |  |  | WHO | TA | 0 | 25,000 |
| 3.3 National trainings on MDR-TB for PMDT sites | X | X |  |  | WHO | Training | 0 | 19,500 |
| 3.4 Procure PPE items, filters, ventilators and UV lights for TB infection control for hospital wards and patient waiting areas |  | X |  |  | WHO | Supplies | 0 | 45,000 |
| 3.5 Print recording and reporting formats |  | X |  |  | WHO | Supplies | 0 | 10,000 |
| 3.6 Planning and review meetings | X |  |  | X | WHO | TA | 0 | 5,000 |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| TB-HIV collaborative activities scaled up in PNG | NDoH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| 4.1 Training on TB-HIV collaboration |  | X |  |  | WHO | Training | 8,924 | 10,000 |
| 4.2 Joint Collaborative National meetings | X |  | X |  | WHO | TA | 0 | 10,000 |
| 4.3. Publish and print TB-HIV guidelines | X |  |  |  | WHO | Supplies | 0 | 10,000 |
| 4.4 TB-HIV data collection and analysis | X | X | X | X | WHO | TA | 10,000 | 0 |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Technical assistance for estimating burden of Leprosy and for sustaining good quality services for Leprosy patients | NDoH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| 5.1. Programme Evaluation to estimate the burden of Leprosy in the country | X |  |  |  | WHO | TA | 10,000 | 30,000 |
| 5.2. Review and development of Leprosy control policy framework and Strategic Plan for 2011-2015 |  | X |  |  | WHO | TA | 0 | 10,000 |
| 5.3 Publish and Print Strategic Plan and policy guidelines |  | X |  |  | WHO | Supplies | 0 | 10,000 |

| Expected output | Indicators |  |  |  |  |  |  | Baseline | Annual Target |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Output code 7.6 |  |  |  |
| Strengthened health system that support enhanced evidence based practices, coordination among stakeholders and improved health outcomes and delivery of health services | Number of provinces supported in their implementation of the Provincial Health Authority Act (PHAA) | 1 | 3 |
|  | Number of policy briefs on human resources for health developed | 0 | 2 |
|  | Number of nursing institutions assessed for rehabilitation | 0 | 2 |
|  | Number of fellowships supported | 0 | 4 |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Improved national capacity and practice for governing, steering and regulating the health sector through (1) evidence-based policy dialogue (ii) policy analysis (iii) greater transparency and accountability for performance and (iv) more effective intersectoral collaboration. | NDoH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Support for the operationalisation of the Health SWAp | X | X | X | X | WHO | Technical assistance | 45,000 | 0 |
| Support for the annual sector review |  |  |  | X | WHO | Technical assistance | 0 | 0 |
| Fellowships to support strengthening in the areas of Health Policy and Health Financing |  | X | X | X | WHO | Training | 25,000 | 0 |
| Technical Officer and Coordinator posts (P4, P5 -- 25% full time equivalent) | X | X | X | X | WHO/AusAID | Technical assistance | 222,000 | 0 |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Improved health workforce knowledge-base and quality data and strengthened national capacity in health workforce planning, management and governance. | NDoH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Support for the development, production and utilization of health labor force reports for planning at the provincial and district level |  | X | X |  | WHO | Technical assistance | 60,000 | 0 |
| TA for the development of a human resource policy and plan | X | X |  |  | WHO | Technical assistance | 40,000 | 0 |
| Support for the development of the NEC submission for increase in staff ceilings and funding of the new workforce plan |  | X |  |  | WHO | Technical assistance | 0 | 0 |
| Review of undergraduate nursing and community health worker curriculums including strengthening teaching components on maternal and reproductive health | X | X | X | X | WHO | Technical assistance | 25,000 | 0 |
| Support for the three training institutions for nursing - Mendi, Lae and Goroka schools of nursing, including assessment and submission of investment proposal | X | X | X |  | WHO | Technical assistance | 0 | 40,000 |
| Technical Officer and Coordinator posts (P4, P5 -- 25% full time equivalent) | X | X | X | X | WHO/AusAID | Technical assistance | 222,000 | 0 |
| Annual Deliverable |  |  |  | Resp. Party | UN Agency |
| Increased production of competent health workers and skill-mix relevant for population health needs. | NDoH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| TA to assist the maternal health command post to strengthen the capacity of the midwifery schools | X | X | X | X | WHO | Technical assistance | 90,000 | 0 |
| Fellowships to support the strengthening of the health care workforce particularly in the areas of Public Health and Epidemiology. | X | X | X | X | WHO | Training | 50,000 | 0 |
| Training and technical support on data generation and reporting |  | X |  |  | WHO | Training | 35,000 | 0 |
| Training and technical support on data standards and validation process for quality control |  |  | X |  | WHO | Training | 35,000 | 0 |
| Training on analysis skills; technical support on specific analysis areas |  |  | X |  | WHO | Training | 35,000 | 0 |
| Technical Officer and Coordinator posts (P4, P5 -- 25% full time equivalent) | X | X | X | X | WHO/AusAID | Technical assistance | 222,000 | 0 |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Improved management and organization of health service delivery, through both public and private providers and networks, reflecting the principles of integrated primary health care with increase coverage, equity and quality of health services, leading to a better health outcome. | NDoH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| TA to implement the Provincial Health Administration Act | X | X | X | X | WHO | Technical assistance | 45,000 | 0 |
| Strengthening of partnerships between NDoH, churches and other non-state actors | X | X | X | X | WHO | Technical assistance | 40,000 | 0 |
| TA to improve health system financing in terms of the availability of funds, social and financial risk protection, equity, access to services and efficiency of resource use. Assessment of present status of user fees. | X | X |  |  | WHO | Technical assistance | 45,000 | 0 |
| Expected output | Indicators |  |  |  |  |  |  | Baseline | Annual Target |
| Output 7.7 |  |  |  |
| Support cost-effective use of medical products and technologies (incl. laboratory services) by health workers, practitioners and consumers at health facilities | Status of implementation of 100% kits | Nil | Kits ready for dispatch |
|  | Number of laboratories with functional microscope services | 50 | 80 |
|  | Number of blood collection from voluntary non-remunerated blood donors | 60% | 65% |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Improved capacity of the procurement and distribution systems within the health sector | NDoH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Feasibility study on outsourcing |  |  |  | X | WHO | Technical assistance | 0 | 25,000 |
| TA for implementation of 100% kits | X | X | X | X | WHO | Travel | 0 | 10,000 |
| Translation of 100% kit packaging labels and consumer medicines information from English to Tok Pisin | X |  |  |  | WHO | Technical assistance | 0 | 3,000 |
| TA for strengthening medicines regulation and quality assurance | X | X | X | X | WHO | Technical assistance | 0 | 0 |
| TA for revision of Medicines and Cosmetics Act 1999 |  |  | X |  | WHO | Technical assistance | 0 | 12,000 |
| MOU with WHO prequalified lab for drug sample testing |  | X |  |  | WHO | Travel | 0 | 5,000 |
| TA for rational use of drugs | X | X | X | X | WHO | Technical assistance | 0 | 0 |
| Revision and publication of Standard Treatment Guidelines for adults | X | X |  |  | WHO | Technical assistance | 0 | 20,000 |
| TA for the updating of the medical and dental catalogue |  |  | X |  | WHO | Technical assistance | 0 | 7,500 |
| TA for development and publication of medicines formulary |  |  | X | X | WHO | Technical assistance | 0 | 7,500 |
| Technical Officer post (P4 -- 100% full time equivalent) | X | X | X | X | WHO | Technical assistance | 217,000 | 0 |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Improved blood transfusion service based on international best practices that will provide access to adequate safe blood and blood products. | NDoH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Conduct one national level training workshops on recruitment and retention of voluntary non-remunerated for blood donor recruiter s |  | X |  |  | WHO | Training | 25,000 | 0 |
| Advocacy for voluntary non-remunerated blood donations – Celebration of World Blood Donor Day |  | X |  |  | WHO | Advocacy | 2,000 | 0 |
| Conduct one national level training workshop for laboratory staffs on blood screening for TTIs including blood group serology and compatibility testing |  |  | X |  | WHO | Training | 25,000 | 0 |
| One national level training workshop for BTS and lab supervisors on Quality Management System in BTS including strengthening of data management and reporting system |  |  | X |  | WHO | Training | 21,000 | 0 |
| Technical Officer post (P4 -- 33% full time equivalent) | X | X | X | X | WHO | Technical assistance | 72,000 | 0 |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Improved planning, organization, development and strengthening of public health and clinical laboratories including Quality Assurance | NDoH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Support establishment of 10 district and health centre laboratories |  | X | X | X | WHO/GF | Technical assistance | 50,000 | 0 |
| Establishment of PC3 Lab at CPHL to support TB MDR study | X |  |  |  | WHO/GF | Technical assistance | 200,000 | 0 |
| Provision of laboratory supplies and equipment for laboratory service |  | X |  |  | WHO | Supplies | 30,000 | 0 |
| Conduct one training for non-laboratory staffs from the Point of Care |  | X |  |  | WHO | Training | 20,000 | 0 |
| Conduct one malaria microscopy training |  |  | X |  | WHO | Training | 0 | 20,000 |
| Conduct one TB microscopy training |  |  | X |  | WHO | Training | 0 | 20,000 |
| Technical Officer post (P4 -- 66% full time equivalent) | X | X | X | X | WHO | Technical assistance | 143,000 | 0 |
| Expected output | Indicators |  |  |  |  |  |  | Baseline | Annual Target |
| Output code 7.8 | Number of programmes supported for multisectoral approaches for NCD | 0 | 3 |
| To prevent and reduce disease, disability and premature death from chronic noncommunicable diseases and prevent or reduce risk factors for health conditions | Conduct of a nationally representative STEPS survey | 0 | 1 |
|  | Number of schools implementing a structured health-promoting schools approach | 0 | 10 |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Technical support for strategy and policy development | NDoH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Review on the impact of diabetes in rural areas |  | X |  |  | WHO | Technical assistance | 0 | 10,000 |
| TA for the drafting of a policy on road safety |  |  | X |  | WHO | Technical assistance | 0 | 20,000 |
| TA for development of strategy on prevention of injuries in children |  |  | X |  | WHO | Technical assistance | 0 | 25,000 |
| TA for drafting the tobacco control amendment bill | X | X |  |  | WHO | Technical assistance | 0 | 15,000 |
| TA for the revision of the national policy on tobacco control |  |  | X | X | WHO | Technical assistance | 0 | 12,000 |
| Support for the integration of NCD prevention into existing settings-based approach | X | X | X |  | WHO | Technical assistance | 0 | 10,000 |
| Implementation of the Urban Health Equity and Assessment Tool |  |  | X |  | WHO | Training | 0 | 10,000 |
| Support the establishment of a multisectoral taskforce for NCD | X | X | X | X | WHO | Technical assistance | 0 | 10,000 |
| Programme Management Officer (P4 -- 25% full time equivalent) | X | X | X | X | WHO | Technical assistance | 54,250 | 0 |
| Annual Deliverable |  |  |  |  |  |  |  |  | Resp. Party | UN Agency |
| Public education, advocacy and communication to raise awareness and mobilize support of different sectors | NDoH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Awareness Campaign on road safety |  | X | X | X | WHO | Advocacy | 3,000 | 0 |
| World No Tobacco Day 2011 |  | X |  |  | WHO | Advocacy | 3,000 | 0 |
| Training and implementation on social marketing and strategic health communication to communicate health-related messages | X |  |  |  | WHO | Training | 10,000 | 0 |
| Support of tobacco awareness activities in selected provinces | X | X | X | X | WHO | Advocacy | 0 | 25,000 |
| National Professional Officer (NO-B -- 50% full time equivalent) | X | X | X | X | WHO | Technical assistance | 30,000 | 0 |
| Annual Deliverable |  |  |  | Resp. Party | UN Agency |
| Capacity building and training | NDoH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Assessment and review on good practices in health-promoting schools | X |  |  |  | WHO | Technical assistance | 0 | 12,000 |
| National workshop for launching the new regional guidelines on health-promoting schools |  | X |  |  | WHO | Training | 0 | 35,000 |
| Fellowships to increase cancer control capacity |  |  | X |  | WHO | Travel | 0 | 10,000 |
| Strengthening of the workplace-based and healthy villages programmes | X | X | X | X | WHO | Technical assistance | 0 | 15,000 |
| National Professional Officer (NO-B -- 50% full time equivalent) Not recruited | X | X | X | X | WHO | Technical assistance | 0 | 30,000 |
| Annual Deliverable |  |  |  | Resp. Party | UN Agency |
| Development of risk factor surveillance systems | NDoH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Conduct of a national STEPS survey |  | X | X | X | WHO | Technical assistance | 10,000 | 60,000 |
| GYTS Data collection and analysis workshop | X |  |  |  | WHO | Training | 6,000 | 0 |
| National Professional Officer (NO-B -- 50% full time equivalent) Not recruited | X | X | X | X | WHO | Technical assistance | 0 | 30,000 |
| Annual Deliverable |  |  |  | Resp. Party | UN Agency |
| Improved capacity on food control and monitoring | NDoH | WHO |
| Activities | Q1 | Q2 | Q3 | Q4 | Source of funds | Budget Description | Amount (funded) | Amount (unfunded) |
| Complete certified food audit training for two officers |  |  |  |  | WHO | Training | 0 | 12,000 |
| Provision of supplies and equipment – food inspection and sampling tools |  |  |  |  | WHO | Supplies | 0 | 25,000 |