Joint Programme Monitoring Report:

Environment and Climate Change Window

Monitoring Report Template

Section I: Identification and Joint Programme Status

a. Joint Programme Identification and basic data

| Date of Submission: 11/08/2012 Submitted by: Name: Mamunul Hoque Khan Title: Chief Technical Advisor – SAISEM Organization: UNDP Contact information: Mamunul.khan@undp.org Tel: +93 (0) 704500597 |  | Country and Thematic Window Afghanistan/Environment MDGF1713-E-11a-AFG : Strengthened Approach for the Integration of Sustainable Environmental Management in Afghanistan – A FAO-UNDP-UNEP Joint Programme |
| --- | --- | --- |

| MDTF Atlas Project No: 00062490 Title: Strengthened Approach for the Integration of Sustainable Environmental Management in Afghanistan |  | Report Number: 6 Reporting Period: 01 Jan – 30 June 2012 Programme Duration: 4 years and 2 months (End Date: 05 Jan 2013) |
| --- | --- | --- |

| Participating UN Organizations UNDP (United Nations Development Programme) UN FAO (United Nations Food and Agriculture Organization), UNEP (United Nations Environment Programme) |  | Implementing partners National Environmental Protection Agency (NEPA) Ministry of Rural Rehabilitation and Development (MRRD) Ministry of Agriculture, Irrigation and Livestock (MAIL) |
| --- | --- | --- |

The financial information reported should include overhead, M&E and other associated costs.

| Budget Summary |
| --- |
| Total Approved Joint Programme Budget: USD 5,000,000 | UNDP: 2,500,000 UN FAO: 2,500,000 UNEP: 0 Total = 5,000,000 |
| Total Amount Transferred to date | UNDP: 2,254,428 UN FAO: 2,745,572 UNEP: Total = 5,000,000 |
| Total Budget Committed to date | UNDP: 2,254,428 UNFAO: 2,745,572 UNEP: 0 Total = 5,000,000 |
| Total Budget Disbursed to date | UNDP: 2,052,318 UNFAO: 2,154,030 UNEP: 0 Total = 4,206,348 |

BENEFICIARIES

Direct Beneficiaries: “The individuals, groups, or organizations, targeted, that benefit, directly, from the development intervention”.

| Indicate Beneficiary type | Expected number of Institutions | Number of Institutions to date | Expected Number of Women | Number of Women To date | Expected number of Men | Number of men to date | Expected number of individuals from Ethnic Groups | number of individuals from Ethnic Groups to date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| National Institutions | 46 | 46 | N/A | 20 | N/A | 118 | N/A | 0 |
| Local Institutions | 3 | 3 | N/A | 6 | N/A | 33 | N/A | 0 |
| Urban | 8 | 8 | N/A | 60 | N/A | 390 | N/A |  |
| Rural | 55 | 55 | N/A | 1156 | N/A | 1996 | N/A | 909 |
| Total | 112 | 112 | N/A | 1242 | N/A | 2537 | N/A | 909 |

- Joint Programme M&E framework

| Expected Results (Outcomes & outputs) | Indicators | Baseline | Overall JP Expected target | Achievement of Target to date | Means of verification | Collection methods (with indicative time frame & frequency) | Responsibilities | Risks & assumptions |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| JP Outcome 1: Environmental issues mainstreamed into national and sub national policy, planning, and investment frameworks Output 1.1: National environmental concerns reflected in the Afghanistan National Development Strategy (ANDS) and sectoral plans, and Institutional capacity strengthened to operationalise them | 1. National Environmental Advisory Council (NEAC) is functional and sustained as the institutional platform for coordination in Government (as per article 11 of environment law). 2. National Environment Policy and Guideline approved for implementation. 3. One Training Workshop for at least five Environment Units/Cells existed in relevant Ministries 4. National Sustainable Development Vision, Strategy and Action Plan Preparation 5. Second State of Environment Report Preparation 6. NEPA Website technically supported and maintained 7. Final JP evaluation completed. | 1. National Environmental Advisory Council (NEAC) meeting - 2008 2. Draft National Environment Mainstreaming Guidelines 3. Environmental Units/Cells within the relevant ministries 4. Environment Sector Strategy 5. Draft NEPA Strategic Plan 6. NEPA Website 7. Mid-term Evaluation Report | 1. Convening of one National Environmental Advisory Council Meeting 2. Approval of National Environmental Mainstreaming Guideline 3. Training of Environment Units/Cells within the relevant Ministries (at least five) 4. Sustainable Development Vision, Strategy and Action Plan Preparation 5. Second State of Environment Report preparation 6. Functional NEPA website 7. Final Evaluation of Joint Program-SAISEM completed | 1.Based on the NEPA senior Management decision the NEAC meeting will be convened in August 2.Final draft submitted to NEPA for approval. NEAC comments will also be secured before finalization and publication. 3.Once the NEMG is approved, the training session will be convened 4. Preparatory activities completed. Consultant recruitment is under process. 5. Preparatory activities completed, consultant recruitment is under process 6. Technical support is being provided 7. Final evaluation will be done 3 months prior to the project closure | Meeting minutes Draft environment mainstreaming guideline What’s the means of verification Term of References Term of references NEPA Website Term of reference | Time frame Time frame Time frame Time frame Time frame Time frame | UNDP/NEPA UNDP/NEPA UNDP/NEPA UNDP/NEPA UNDP/NEPA UNDP/NEPA UNDP/NEPA | Security: SAISEM is working closely with NEPA and other relevant government organization. Movement restrictions due to deteriorated security situation have always had bad impacts on the project activities. |
| JP Outcome 2: Local management of environmental resources improved and services delivery enhanced. Output 2.1 : Communities are able to develop and implement projects for sustainable use of natural resources and livelihoods. Output 2.2: Institutional knowledge management improved in relation with community based field interventions | Best practices report production Number of kitchen gardens established (Where this indicator comes from?) Number of backyard poultry projects Number of Pistachio gardens established Number of fruit gardens established Number of sapling distributed in Herat, Badghis and Ghor provinces Number of partners’ staff fully trained Number government officials received training Number of people trained | Environment status report 2008 0 0 0 0 0 0 0 0 | Report produced and disseminated RRA/PRA conducted and target communities selected. Formulation of the rangeland management plan initiated in at least one province. Livelihood improvements plan developed and implementation of relevant projects initiated in at least one province Not specified Not specified Not specified Not specified Not specified Not specified Not specified | 159 hectare of deteriorated rangeland reseeded 672 Kitchen gardens established 484 Backyard poultry established 701 Gardens established 520 Gardens established 116,000 Firewood sapling distributed to be planted in the three provinces 16 450 6,438 trained | Project reports, partners and communities, testimony Project reports and community testimony Project reports and community testimony Project reports and community testimony Project reports and community testimony Project reports and government testimony Project reports, partners testimony Project reports, partners testimony Project reports and partners testimony | From direct execution, reports Direct communication, reports Monitoring and reports, Monitoring, reports Monitoring and reports Direct monitoring, reports Training activities, reports Training activities, reports Training activities, reports | FAO FAO FAO FAO FAO FAO FAO FAO FAO | The security situation remains the same or improves Same as above Same as above Same as above Same as above Same as above Same as above Same as above Same as above |

- Joint Programme Results Framework with financial information

|  | JP output: 1.1 |  |
| --- | --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY | Estimated Implementation Progress |  |
|  |  | Y1 | Y2 | Y3 |  | NATIONAL/LOCAL | Total amount Planned for the JP | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |  |
| Output 1.1: National Environmental concerns reflected in the ANDS and sectoral plans and institutional framework | 1.1.1 National Environmental Council (NEAC) consolidated through the approval of the national environmental guidelines and policies |  |  |  | UNDP | Do we have any responsible party here? If yes give the name | 120,000 | 120,000 | 68,904 | 57.4 % |  |
|  | 1.1.2. National Sustainable Development Vision, Strategy and Action Plan Completed. |  |  |  | UNDP | Do we have any responsible party here? If yes give the name | 88,936 | 88,936 | 66,620 | 74.9 % |  |
|  | 1.1.3. Second State of Environment Report Prepared |  |  |  | UNDP | Do we have any responsible party here? If yes give the name | 110,000 | 110,000 | 51,662 | 46.9 % |  |
|  | 1.1.4. Final Evaluation of JP-SAISEM |  |  |  | UNDP | Do we have any responsible party here? If yes give the name | 80329 | 80329 | 22,108 | 27.5 % |  |
|  | 1.1.5. NEPA Website technically supported and maintained |  |  |  | UNDP | Do we have any responsible party here? If yes give the name | 50,000 | 50,000 | 26,210 | 52.4 % |  |
|  | Total |  | 449,265 | 449,265 | 235,504 | 52.4 % |

UNDP Component:

FAO Component:

|  | JP output: 1.1 |
| --- | --- |
| Programme Outputs | Activity | YEAR | UN AGENCY | RESPONSIBLE PARTY | Estimated Implementation Progress as of June 24, 2012 |
|  |  | Y1 | Y2 | Y3 | Y 4 |  | NATIONAL/LOCAL | Total amount Planned for the JP | Estimated Total amount Committed | Estimated Total Amount Disbursed | Estimated % Delivery rate of budget |
| Output 2.1: Communities are able are able to implement projects for sustainable use of natural resources Output 2.2:Institutional knowledge management improved in relation to community-based field interventions | 1.1.1 Seed multiplication |  |  |  |  | FAO | FAO, MAIL, NEPA, MRRD | 410,925 856,680 343,669 30,283 202,667 167,435 197,685 188,552 21,162 146,895 179,617 Total: 2,745,570 | 410,925 856,680 343,669 30,283 202,667 167,435 197,685 188,552 21,162 146,895 179,617 Total: 2,745,570 | 396,202 610,046 254,834 18,227 161,387 119,821 145,755 181,322 9,162 117,608 139,666 Total: 2,154,030 | 96.4 71.2 74.2 60.2 79.6 71.6 73.7 96.2 43.3 80.1 77.8 78.5 |
|  | 1.1.2. Rangeland restoration |  |  |  |  | FAO | FAO, MAIL, NEPA, MRRD |  |  |  |  |
|  | 1.1.3. Kitchen Gardens |  |  |  |  | FAO | FAO, MAIL, NEPA, MRRD |  |  |  |  |
|  | 1.1.4 Backyard poultry |  |  |  |  | FAO | FAO, MAIL, NEPA, MRRD |  |  |  |  |
|  | 1.1.5 Pistachio forest rehabilitation |  |  |  |  | FAO | FAO, MAIL, NEPA, MRRD |  |  |  |  |
|  | 1.1.6 Fruit cultivation |  |  |  |  | FAO | FAO, MAIL, NEPA, MRRD |  |  |  |  |
|  | 1.1.7 Firewood trees plantation |  |  |  |  | FAO | FAO, MAIL, NEPA, MRRD |  |  |  |  |
|  | 1.1.8. Capacity building for government counterparts |  |  |  |  | FAO | FAO, MAIL, NEPA, MRRD |  |  |  |  |
|  | 1.1.9 Capacity building for local communities |  |  |  |  | FAO | FAO, MAIL, NEPA, MRRD |  |  |  |  |

SECTION II: Joint Programme Progress

Are there difficulties in the implementation? What are the causes of these difficulties? Please check the most suitable option

b.

UN agency Coordination

Coordination with Government

Coordination within the Government (s)

Administrative (Procurement, etc)  /Financial (management of funds, availability, budget revision, etc)

Management: 1. Activity and output management 2. Governance/Decision making (PMC/NSC) 4. Accountability

Joint Programme design

c.

External to the Joint Programme (risks and assumptions, elections, natural disaster, social unrest, etc)

Other. Please specify:

- Please, briefly describe (250 words) the current difficulties the Joint Programme is facing. Refer only to progress in relation to the planned in the Joint Program Document. Try to describe facts avoiding interpretations or personal opinions.

c.   Please, briefly explain (250 words) the actions that are or will be taken to eliminate or mitigate the difficulties (internal and external referred B+C) described in the previous text boxes b and c. Try to be specific in your answer.

Inter-Agency Coordination and Delivering as One

The MDG-F Secretariat asks the office of the Resident Coordinator complete this subsection, briefly commenting on the joint programme, providing its perspective from within the broader country context. The aim is to collect relevant information on how the joint programme is contributing to inter-agency work and Delivering as One.

You will find some multiple choice questions where you can select the most appropriate to the case, text boxes to provide narrative information and 2 indicators on common processes and outputs to measure interagency coordination. These indicators have been already used to measure progress on the One UN pilot countries. Please, refer to the examples in the subsection to complete the information requested.

- Is the Joint Programme still in line with the UNDAF? Please check the relevant answer

Yes No

- If not, does the Joint Programme fit into the national strategies?

Yes No

If not, please explain:

What types of coordination mechanisms and decisions have been taken to ensure joint delivery?

Are different joint programmes in the country coordinating among themselves? Please reflect on these questions above and add any other relevant comments and examples if you consider it necessary:

Please provide the values for each category of the indicator table described below:

| Indicators | Baseline | Current Value | Means of Verification | Collection methods |
| --- | --- | --- | --- | --- |
| Number of managerial practices (financial, procurement, etc) implemented jointly by the UN implementing agencies for MDG-F JPs. |  |  |  |  |
| Number of joint analytical work (studies, diagnostic) undertaken jointly by UN implementing agencies for MDG-F JPs. |  |  |  |  |
| Number of joint missions undertaken jointly by UN implementing agencies for MDG-F JPs. |  |  |  |  |

Please provide additional information to substantiate the indicators value (150 words). Try to describe qualitative and quantitative facts avoiding interpretations or personal opinions.

- Development Effectiveness: Paris Declaration and Accra Agenda for Action

This subsection seeks to gather relevant information on how the joint programme is fostering the principles for aid effectiveness by having appropriate ownership, alignment, harmonization and mutual accountability in the last 6 months of implementation.

You will find some multiple choice questions where you can select the most appropriate to the case, text boxes to provide narrative information and 2 indicators on ownership ad alignment. These indicators have been used extensively to measure progress on the Paris Declaration. Please, refer to the examples in the subsection to complete the information requested.

Ownership: Partner countries exercise effective leadership over their development policies, and strategies and co-ordinate development actions

Are Government and other national implementation partners involved in the implementation of activities and the delivery of outputs?

Not involved

Slightly involved

Fairly involved

Fully involved

In what kind of decisions and activities is the government involved? Please check the relevant answer

Policy/decision making

Management:  budget  procurement  service provision  other, specify

Who leads and/or chair the PMC and how many times have they met?

Institution leading and/or chairing the PMC _NEPA and/ the RC_ Number of meetings. For the reporting period 0Times

Is civil society involved in the implementation of activities and the delivery of outputs?

Not involved

Slightly involved

Fairly involved

Fully involved

In what kind of decisions and activities is the civil society involved? Please check the relevant answer

Policy/decision making

Management:  budget  procurement  service provision  other, specify

Are citizens involved in the implementation of activities and the delivery of outputs?

Not involved

Slightly involved

Fairly involved

Fully involved

In what kind of decisions and activities are citizens involved? Please check the relevant answer

Policy/decision making

Management:  budget  procurement  service provision  other, specify

Where is the joint programme management unit seated?

National Government  Local Government  UN Agency  By itself  other, specify

Based on your previous answers, briefly describe the current situation of the government, civil society, private sector and citizens in relation of ownership, alignment and mutual accountability of the joint programmes, please, provide some examples. Try to describe facts avoiding interpretations or personal opinions.

- Communication and Advocacy

Has the JP articulated an advocacy & communication strategy that helps advance its policy objectives and development outcomes?  Please provide a brief explanation of the objectives, key elements and target audience of this strategy, if relevant, please attach (max. 250 words).

Yes   No

What concrete gains are the advocacy and communication efforts outlined in the JP and/or national strategy contributing towards achieving?

Increased awareness on MDG related issues amongst citizens and governments

Increased dialogue among citizens, civil society, local national government in relation to

Development policy and practice

New/adopted policy and legislation that advance MDGs and related goals

Establishment and/or liaison with social networks to advance MDGs and related goals

Key moments/events of social mobilization that highlight issues

Media outreach and advocacy

Others (use box below)

What is the number and type of partnerships that have been established amongst different sectors of society to promote the achievement of the MDGs and related goals? Please explain.

Faith-based organizations     	Number

Social networks/coalitions    	Number 21

Local citizen groups                	Number

Private sector 		      	Number

Academic institutions              	Number 2

Media groups and journalist   	Number

Others (use box below)          	Number

What outreach activities do the programme implement to ensure that local citizens have adequate access to information on the programme and opportunities to actively participate?

Focus groups discussions

Household surveys

Use of local communication mediums such as radio, theatre groups, newspapers, etc

Open forum meetings

Capacity building/trainings

Others

Section III: Millennium Development Goals

- Millennium Development Goals

The MDG-F main objective is to contribute to progress to the attainment of the Millennium Development Goals worldwide. This subsection aims to capture data and information on the joint programmes contribution to 1 or more Millennium Development Goals and targets.

For this purpose the Secretariat has developed a matrix where you should link your joint programme outcomes to 1 or more Millennium Development Goals and Targets. This matrix should be interpreted from left to right. As a first step you should reflect on the contributions that each of the JP outcomes is making to one or more MDGs. Once this linked is established, it needs to be further developed by connecting each joint programme outcome to one or more MDG targets. As a third step you should estimate the number of beneficiaries the JP is reaching in each of the specifics outcomes. Finally you should select the most suitable indicators from your joint programme’s M&E framework as a measure of the Millennium targets selected. Please, refer to the example provided below.

| MDG 7 | Joint Programme Outcome 1 | MDG Target 7.A | # Beneficiaries reached | MDG Indicators | JP Indicator |
| --- | --- | --- | --- | --- | --- |
| Goal 7: Ensure environmental sustainability | Mainstreaming environmental issues in national and sub-national policy, planning and investment frameworks | Integrate the principles of sustainable development into country policies and programmes and reverse the loss of environmental resource |  | Proportion of land area covered by forest CO2 emissions, total, per capita and per $1 GDP (PPP) Consumption of ozone-depleting substances Proportion of fish stocks within safe biological limits |  |
|  | Joint Programme Outcome 2 | MDG Target 7 B |  | Indicator | JP Target |
|  | Improving local management of environmental resources and services delivery | Halve, by 2015, the proportion of people without sustainable access to safe drinking water and basic sanitation |  | Proportion of population using an improved drinking water source Proportion of population using an improved sanitation facility |  |
|  | Joint Programme Outcome 3 | MDG Target 7 C |  | Indicator | JP Target |
|  |  | Does not apply |  |  |  |

Additional Narrative comments

Please provide any relevant information and contributions of the programme to the MDGs, whether at national or local level.

Please provide other comments you would like to communicate to the MDG-F Secretariat:

Section 4: General Thematic Indicators

| Number of sectors or mainstreaming laws, policies or plans supported by the joint programme: Applies Does not apply, if so move to section 2 |
| --- |
| On Environmental Management | On Climate Change |
| Policies Laws Plans | No. National 1 No. National No. National 20 | No. Local No. Local No. Local 25 | Policies Laws Plan | No. National No. National No. National | No. Local No. Local No. Local |
| Please briefly provide some contextual information on the law, policy or plan and the country/municipality where it is (or will be) implemented (base line, stage of development and approval, potential impact of the policy): At National level Environmental Mainstreaming Guideline will help NEPA and all other relevant government agencies to integrate environmental issues into the planning and implementation processes. At Sub-National level environment was mainstreamed in Provincial Strategic Plans and District Development Plans. |
| Sector in which the law(s), policy(ies) or plan(s) is/are focused Nature conservation Water management Sanitation Sustainable management of natural resources Climate Change: Adaptation Mitigation Other , please specify: | Comments: Please specify how indicator 1.1 addresses the selected sectors. |
| Number of citizens and/or institutions that the law(s), policy(ies) or plan(s) directly affects |
| Citizens National Public Institutions Local Public Institutions Private Sector Institutions | Total No. 4775 Total No. 20 Total No 33 Total No. 8 | No. Urban No. Urban X No. Urban No. Urban | No. Rural X No. Urban No. Rural X No. Rural X |

| Government budget allocated to environmental issues before the implementation of the Joint Programme National budget: $ USD Total Local budget (s) : $ USD (in localities of intervention of the JP) | Comments Three different government institutions are involved in the implementation of the project. MDG JP contributes 10% to NEPA budget, MRRD unknown and MAIL unknown. The two unknown institutions are considered the key ministries in terms of Agriculture and Rural Development. Donor’s contributions to these two institutions are more than to NEPA. |
| --- | --- |
| % variation in government budget allocated to environmental policies or programmes from the beginning of the joint programme to present time: National budget: % Overall % Triggered by the Joint Programme | Comments |
| Local budget: % Overall % Triggered by the Joint Programme |  |
| Government budget allocated to Climate Change before the implementation of the Joint Programme National budget: $ USD Total Local budget (s) : $ USD (in localities of intervention of the JP) | Comments |
| % variation in government budget allocated to Climate Change from the beginning of the Joint programme to present time: National budget: % Overall % Triggered by the Joint Programme | Comments |
| Local budget: % Overall % Triggered by the Joint Programme |  |

| 2.1. Number of km2 of land newly managed by a natural resource plan supported by the Joint Programme Applies Does not apply f so move to section 2.4 |
| --- |
| Total of the area managed in Km2. |
| By habitat: tropical forest Temperate forest Savannah Shrub land Grassland | Km2 Km2 Km2 Km2 Km2 - | Wetlands Rocky areas Desert Sea/oceans Artificial terrestrial (pastoral land, arable land, etc) | Km2 Km2 Km2 Km2 Km2 Km2 |
| 2.2 Number of institutions, civil servants and citizens trained by the JP to take informed decisions on environmental issues (excluding climate change): |
| Does not apply Public Institutions Private Sector Institutions NGO/CBO’s Civil servants Citizens | Total No. 2 Total No. Total No. Total No. Total No. | Women Women | Men Men |
| 2.3. Number of citizens supported by the JP that have organised themselves to effectively participate in natural resource management initiatives: Applies Does not apply |
| Total No. 210 | No. Women 63 | No. Men 147 | Ethnic groups 2 (Kochis, Hazara) |

| 2.4. Number of successful environmental service payment mechanisms that have been promoted by the JP : Does not apply |
| --- |
| Total No. | No. Of beneficiaries: | Sectors of application: Forest protection Water resources Management Pollution | Financing source: MDGF Public Fund NGO International Organization Others: |
| 2.5. Has the JP had an impact on the development of national and local policies or regulations that recognize schemes of Payment for Ecosystem Services as an environmental management tool, How? |

| 3.1 Number of Km2 and type of habitat covered by mechanisms and/or actions to adapt to climate change (implemented with the support of the joint programme: Applies Does not apply |
| --- |
| Tropical Forest Km2 Temperate Forest Km2 Savannah Km2 Shrub land Km2 | Grassland Km2 Wetlands Km2 Rocky Areas Km2 Desert Km2 Artificial terrestrial (pastoral land, arable land, etc) Km2 |
| 3.2 Adaptation measures supported by JP that are addressing the following climate change issues: Applies Does not apply |
| Land degradation Soil fertility decrease Atmospheric pollution | Change in native species dynamics Wildfire Drought, Storms/flooding | Alteration of rain patterns, Sea levels rise Acidification |
| 3.3 Based on available data, what kind of improvements on the population’s wellbeing have been achieved through JP supported adaptation measures?: |
| Health Vulnerability (in terms of natural disasters) Improved livelihoods Others |
| 3.4 Number of individuals and institutions with improved capacities to adapt to climate change or mitigate it: Applies Does not apply |
| Adaptation Mitigation | Public Institutions Private Sector Institutions Civil servants Citizens | Total No. Total No. Total No. Total No. | Women Women | Men Men |
| 3.5 Interventions funded by the JP to improve capacities of individuals and institutions to adapt to Climate Change or mitigate it: Does not apply Adaptation Mitigation Capacity building Equipment Knowledge transfer |

3.6 Number of clean development mechanism projects registered to mitigate climate change: Does not apply

CO2 Emissions captured through conservation Total Number CO2 Emission reduction through the use of Renewable Energies Total Number CO2 Emission reduction through the use of clean technologies Total Number

3.6 Number of clean development mechanism projects registered to mitigate climate change: Does not apply

CO2 Emissions captured through conservation Total Number CO2 Emission reduction through the use of Renewable Energies Total Number CO2 Emission reduction through the use of clean technologies Total Number

# Footnotes

Please list all the partners actually working in the joint’s programme implementation, NGOs, Universities, etc.  If you are working with a large number of partners please annex the list.

For indicators 1.5, 1.6, 1.7 and 1.8 the Secretariat acknowledges the potential difficulties to obtain the information requested. Therefore, if not available, please provide the best available estimate. The information requested refers to the budgetary year in which the monitoring report falls

Environmental issues should refer to budget allocated to natural resource management and conservation

IUCN categories

This indicator requires the use of baseline information from which a variation can be observed.  If this data is not available the Secretariat recommends collecting it in order to complete this impact indicator for next reporting period.

# Text boxes

Progress in outcomes:

The Programme promoted the formulation of suitable policy / strategic frameworks, implementation guidelines with due consideration of the environment-poverty linkage through development of National Environmental Mainstreaming Guideline and Provincial Environmental Advisory Councils (PEACs) Guideline having recommendation for relevant sectors for sustainable planning at national and subnational level. The programme established and trained PEACs and Environmental Sub-committees and also trained NEPA, MRRD and MAIL staff at national and sub-national level to ensure institutional capacity development towards the effective implementation of the strategies and projects and integrate environmental considerations in the national and sub-national planning process. The programme also piloted through its FAO components several Community-Based Natural Resources Management interventions in selected Provinces.

Progress in Outputs:

Environment Law 2012 mandates NEPA to update the country’s state of environment report biannually. In line with the AWP 2012, SAISEM is supporting NEPA in development of second state of environment report by creating a sustainable institutional setup within NEPA for data collection, updating and recommendation for improvements. A small NEPA team within its existing structure should be trained and actively involved in the whole process for its future sustainability.

As a follow up of the Rio+20, SAISEM is supporting NEPA in development of sustainable development vision and strategy to forecast and recommend government transition to green economy. This strategy will guide the government to establish a pro-poor framework for sustainable development.

As a part of institutional capacity development, SAISEM is supporting NEPA in convening of NEAC meeting 2012. According to environmental law, NEAC meeting has to be convened by NEPA annually. The purpose of this meeting is to secure the advice of NEPA on financial matters, regulatory matters and environmental matters that are of national public importance.  Based on the NEPA senior management decision and technical working group (TWG) meeting agreement, NEAC meeting will be conducted in August 2012. All the preparatory arrangements have been completed.

A number of SAISEM assets including laptop computers, furniture, cameras, photocopy machine, and other electrical devices have been donated by UNDP component to NEPA.

As preparation for Rio+20 was one of pressing needs of the Government of Afghanistan, SAISEM has collaborated with MoFA and NEPA in preparation of country position paper and developing the capacity of relevant Ministries and Agencies.

This year the project rehabilitated additional 50 hectares of deteriorated rangeland in Badghis province. Now the total rehabilitated area reach to 159 hectares in three provinces. The project helped women in establishing additional 400 new kitchen gardens. The total numbers of 672 kitchen gardens are now operational in the three provinces. About 484 backyard poultry projects which were established last year, have been monitored in Herat and Badghis provinces. Farmers in Badghis were supported to establish 144 new pistachio gardens. The total numbers of gardens have reached to 701. Five nurseries in Badghis province have been established sustain the provision of pistachio saplings to farmers.

As part of capacity building of the local communities, trainings in the areas of rangeland restoration, establishment of pistachio and fruit gardens, sustainable use of natural resources, kitchen gardens, and backyard poultry have been convened. A total of 6,438 participants from the local communities were involved in various training activities. About 16 MAIL, NEPA and MRRD staff has been trained in related project interventions. Now the trained staffs have the skills to continue the activities independently. During reporting period a total of 450 government officials participated in training workshop. These workshops were convened based on NEPAs request and was focused on environmental issues and sustainable use of natural resources.

Coordination within Government: Environment has been referred to as a cross cutting issue in Afghanistan National Development Strategies (ANDS), and the cross cutting nature of environment has put it behind other sectors. NEPA is mandated to mainstream environment into the annual work plan of other institutions, coordinate and properly monitor environment issues. The lack of proper coordination within government sector hampers joint program activities due to delay response of institution to each others.

Security Condition: Deteriorated security situation in the country and UN security role i.e. white cities, movement restrictions etc., affected project activities implementation.

Action Taken:

Coordination within Government: A mechanism has been established i.e. Network of Environmental Focal Points for implementation of National Environmental Mainstreaming Guidelines. On national level, CEC meetings are convened on regular basis to strengthen the coordination. At sub-national level PEACs meeting are being conducted which is effective for improving the coordination within the government institutions.

External (Security):

The security situation is out of project implementation team control

The challenges vary from operational/management issues of each individual UN agency to overall coordination with Government counterparts, security and ever changing priorities at the country level. However, regardless of all these constrain JPs have managed to succeed in setting a foundation, for a more coherent UN approach to joint projects implementation.  The modality of JP implementation was followed by two other initiatives of the UNCT to work jointly. JP was requested to make a presentation on weaknesses and opportunities of joint programming, which was highly appreciated by the UNCT. Although this is a modest step yet presents good opportunities for the UNCT to learn from the lessons of JPs and make necessary adjustments while planning joint initiatives.

Joint Programme is working closely with its government partners MAIL, NEPA, MRRD and all other relevant government agencies, civil societies, private sectors and citizens. Government partners are being involved in all stages of JP planning and implementation. For Instance SAISEM supported NEPA in drafting National Environmental Mainstreaming Guideline (NEMG) by involving all stockholders. The Implementation of NEMG through environmental Focal points, who have already been identified in the relevant ministries will further strengthen NEPA’s role in coordination and monitoring of environment at national level.

At sub-national level 19 Provincial Environmental Advisory Councils (PEACs) (composed of Provincial council chair person, NEPA Director, District Governors, Representative from the Civil Societies, community Elders, Islamic Scholars, formers and Nomads)  have been established to advise NEPA Provincial Directorates on environment and sustainable planning and development. The established 21 Environmental Sub-committees within DDAs/CDCs by SAISEM is fully involved at district and community level sustainable planning process. At local level government is also fully involved in range restoration and management, NRM relevant activities and in kitchen garden/poultry interventions. However, they need more institutional and individual capacity building. The local community sense of ownership is not questionable as far as kitchen gardens/poultry interventions are concerned.  The local communities volunteered their time to provide labour in range restoration activities, an indication of their commitment and sense of ownership.

SAISEM Joint Programme has fully articulated the advocacy and communication strategy by working in collaboration with other UN organizations and government partners. An integrated approach has been adopted for environmental awareness promotion in the country. JP has convened a number of workshops and events on environmental issues at national and sub-national level. Environmental awareness video and audio spots, posters, banners, booklets, brochures and billboards with Joint Programme logos have been used for awareness of the urban and local communities. Gender and Environment and Environmental Awareness through Mosques (Masjid) were event conducted by JP for linking the Gender with Environment and using Mosques as platforms for dissemination of environmental issues. A series of meetings have been conducted with Environment and Natural Resources Commission of the Parliament.

Social Network/coalitions: Total of 21 environmental sub-committees in district and village level have been piloted in DDAs/CDCs.

Academic Institutions: Kabul and Herat Universities

Focus Group Discussion: In training and awareness workshops, participants are involved in the focus group discussion session, where they share their ideas.

Household Surveys: For local implementation of activities household surveys were conducted in three provinces.

Use of local communication mediums: National and Local media were involved in all events conducted by JP for dissemination of information on TV, radio etc.

Capacity Building/Trainings: The JP conducted a number of trainings such as (1) Water Quality Monitoring training for NEPA Staff (2) Website Management and Administration Training for NEPA Staff (3) An Awareness Workshop for Religious Leaders (4) A number of training for local communities on NRM, Rangeland Restoration, Kitchen Gardening and Poultry Forming

National Environmental Mainstreaming will help in nationalization of MDGs into the Afghanistan Government Institutional Planning Processes.

At sub-national level integration of environmental issues in the provincial strategic planning process is being localized through already established PEACs.

Despite of limited resources, a number of challenges and short programme duration, SAISEM has been able to develop a framework for environmental mainstreaming and contributed to the capacity development of NEPA. Environmental Mainstreaming for Sustainable development is a long term process and needs significant commitments of the international community in a country like Afghanistan, where environment has been considerably degraded and the capacity at national and sub-national level requires substantial development.

- Environmental and Climate Change policy development and mainstreaming

1. Environmental and Climate Change policy development and mainstreaming

2. Institutional capacities for environmental management developed and civil society participation increased

2. Institutional capacities for environmental management developed and civil society participation increased

3. Climate change adaptation and mitigation, and development of institutional capacities