El Salvador

| Programme Title: | Protecting children: towards a coordinated food security and nutritional programme |
| --- | --- |
| Programme number & MPTF ref: | MDGF-2039-I-SLV Children (67255) |
| Window: | Children Food Security & Nutrition |
| Approved Budget by NSC (US$): | 4.5 million |
| Participating Organizations: | PAHO/WHO, UNDP, UNICEF,WFP |
| Dates of First /Second installments: | 14-Jan-2010 / 21-Apr-2011 |

ACTIVITIES Reported:

Main Substantive Activities:

National nutrition policy launched and widely disseminated. Food security diagnostic updated. 4 on- line nutrition education modules established. National nutrition monitoring committee established. Baseline study for chosen sites was completed. Community family health teams trained and equipped. 150 health system professionals trained on breast feeding issues. 90 senior officials of local water boards trained in water quality standards. National policy for promotion of breast feeding drafted/launched. 44 key government decision makers trained in food security/nutrition. 552 families received improved seeds and training. 150 people trained on water and sanitation issues.

Problems and lessons learned:

Coordination with Government and the decision about the National Committee for Nutrition and Food Security support.

The programme has communications strategy in place: The strategy for the three JP had been approved and put in place in November 2011. Several target groups had been identified for the implementation phase.

CHARTS & FIGURES

As of 31 December 2011