LEBANON RECOVERY FUND

ANNUAL project NARRATIVE progress report

# REPORT COVER PAGE

| Participating UN Organization: |  | Report Number: |
| --- | --- | --- |
| UNDP |  | 5 |

| LRF Project No: New Atlas Project No: (as per enclosed list) 65541 65550 65556 |  | LRF Project Title: |
| --- | --- | --- |
|  |  | Country energy efficiency and renewable energy demonstration project for the recovery of Lebanon (CEDRO) |

| Reporting Period: |  | Project Budget: |
| --- | --- | --- |
| 1 January to 31 December 2011 |  | LRF-funding: Phase 1: $2.73 million Phase 2: $3.50 million Phase 3: $3.50 million Other funding: N/A |

| List Implementing Partners: |  | Project Coverage/Scope: |
| --- | --- | --- |
| International Partners: Spanish Agency for International cooperation National Partners: Council for Development and Reconstruction; Ministry of Energy and Water; Ministry of Finance, Ministry of Interior and Municipalities |  | CEDRO 1: South, Bekaa and Aakkar CEDRO 2: National coverage CEDRO 3: National coverage |

| Abbreviations and acronyms: |  | Project Duration/Closed Project: |
| --- | --- | --- |
| CEDRO: Community energy efficiency and renewable energy demonstration project for the recovery of Lebanon CO: Country Office DEX: Direct Execution LCECP: Lebanese center for energy conservation project LRF: Lebanon Recovery Fund PMU: Project Management Unit UNDP: United Nations Development Programme. |  | CEDRO 1: Oct 2007 – March 2011 CEDRO 2: Jan 2009 – Jan 2013 CEDRO 3: Jan 2010 – Oct 2013 |

# Purpose

Lebanon imports around 97% of its energy needs in the form of fossil fuel. In 2004, the national energy bill amounted to around 1.6 billion USD (around 20% of the annual public expenditure), and in 2005 it reached 2.1 billion USD (around 26% of the annual public expenditure). Despite major steps taken by the Government of Lebanon since 1990 towards improving the electricity sector, the sector is still facing major challenges including inability to meet increasing national energy demand and large financial subsidies for Electricite du Liban (around 1.0 billion USD in 2006).

  - As a result of the July 2006 conflict, the situation of the energy sector in Lebanon was further aggravated, resulting in a reduction in electricity supply on a national level and an increase in electricity rationing.  This only added to the existing electricity supply challenges faced by Lebanon and further deteriorated the living conditions in the country.

  - In light of this draining situation, the government of Lebanon has placed the reform of the power sector among its highest national priorities, as outlined in the recovery, reconstruction and reform paper submitted at the Paris 3 conference. However, given the enormity of the challenges faced by the power sector, the reform strategy has concentrated on addressing the energy supply side, without extending the scope to the demand side of energy management. The proposed CEDRO project aims at complementing the national power sector reform strategy by targeting the necessary counterpart and that is end-use energy conservation.

As such, the objective of the CEDRO project is to support recovery, reconstruction and reform activities through the implementation of an energy efficiency and renewable energy program for public sector buildings and facilities. To achieve this, the first phase of the CEDRO project (Oct 2007 – Mar 2009) targeted around 30 public sector buildings and facilities in three recovery areas (South, Bekaa and Akkar) highly affected by the July 2006 conflict, while the second phase of the CEDRO project (Jan 2009 – Jan 2011) will target around 10 larger scale public sector buildings and facilities across all Lebanon and approximately 30-40 smaller ones. The third phase of the CEDRO project (Jan 2010 – Oct 2013) further supplements the aforementioned two CEDRO objectives, by a third key objective which is the setting of an enabling environment for the development and implementation of a national sustainable energy strategy and detailed action plan. The third phase of the CEDRO project is the final key component to enable sustainability and a nationwide multi-sectoral scope.

The key outputs of the CEDRO project include: 1) installation of energy efficiency and renewable energy equipments and systems in public sector buildings and facilities; 2) increased public sector awareness and knowledge on energy efficiency and renewable energy applications; 3) availability of validated data on reduced energy consumption and cost; and 4) establishment of relevant policies and procedures to enable the continued implementation of sustainable energy measures in public sector buildings and facilities.

  - The CEDRO project builds on the objectives of the Ministry of Energy and Water to meet increased national energy demand, and the objectives of the Ministry of Finance to reduce government financial burdens.

  - The project’s main national implementing partners are: the Council for Development and Reconstruction (CDR), the Ministry of Energy and Water MEW), and the Ministry of Finance, who are parties to the project formulation and approval, as well as parties to strategic decision making and evaluation throughout the project lifetime.

- Resources

Financial Resources:

  - The Lebanese Centre for Energy Conservation project (LCECP), which is a UNDP nationally executed project executed by the Ministry of Energy and Water, has committed an in-kind contribution to the CEDRO project, in the range of 100,000 USD.

  - Budget rephasals undertaken on an annual basis.

Human Resources:

  - National Project Staff:

- Project Manager (x1)

- Project Assistant (x1)

- Site Engineers (x3)

- Graphic designer (x1/3)

- Marketing expert (x1/2)

- UNV (1/2)

- GIS specialist (x1/3)

- Driver/clerk (x1)

International Staff: Trama TechnoAmbiental (TTA - Spain); Technical Backstopping Agency for CEDRO.

- Implementation and Monitoring Arrangements

  - The Project is executed under the UNDP Direct Implementation modality (DIM), whereby UNDP acts both as the implementing and the executing agency. For the day-to-day management of the project, the UNDP CO has set-up a Project Management Unit (PMU). The PMU works under the direct supervision of the UNDP CO, and in close collaboration with the donor, the Lebanese Government, the local direct and indirect beneficiaries, as well as with the international team of experts and the local contractors recruited for this project. The PMU is led by a full time national Project Manager and is supported by the required national professional and administrative staff as well as national and international consultants.

  - The UNDP CO is responsible for monitoring the progress towards intended results, and for ensuring high-quality managerial and financial implementation of the project, including the responsibility for ensuring proper use of administrated funds to assigned activities, timely reporting of progress, as well as undertaking of mandatory and non-mandatory evaluations.  The UNDP CO undertakes quarterly reports and reviews of the project activities, annual tripartite review meetings in addition to regular and bi-weekly follow-up with the PMU. Furthermore, the procurement of goods and services and the recruitment of personnel are effected in accordance with UNDP standard guidelines, procedures and regulations.

- Results

Programmatic and Reporting Approach

With the approval of the 3 phases of the CEDRO project (CEDRO 1, CEDRO 2 and CEDRO 3) CEDRO became part of a larger project framework which aims not only at supporting Lebanon’s recovery activities, but also at supporting Lebanon’s recovery, reconstruction and reform activities, namely the power sector recovery, reconstruction and reform plan. CEDRO aims to assist the GoL in moving towards a more sustainable energy system.

As such, the overall CEDRO project (Country energy efficiency and renewable energy demonstration project for the recovery of Lebanon) now has three objectives:

1) 	Implementation of end-use energy efficiency and renewable energy projects to reduce national energy consumption and costs;

2) 	Setting an enabling environment for the conversion of all public sector buildings and facilities into energy efficient modalities;

3)   Setting an enabling environment for the development of a national sustainable energy strategy and action plan

The overall CEDRO programme, if defined as being composed of CEDRO 1 - 3 projects, has a total budget of over 9.7 million USD and a total time frame of over 6 years.  Accordingly, and based on a more programmatic approach, all future reporting will cover achievements and financial disbursements for all 3 CEDRO components or projects together as is presented here.

Progress on Outputs

- Project Management

- Coordination and follow-up on a regular basis with the Technical Backstopping Agency, TTA, on all technical assessments for the selection of new sites, installation designs, supervision and monitoring of works;

- Preparation of regular progress reports and financial management of expenditures;

- Organization of field missions and stakeholder meetings (regular meetings with the Ministry of Energy and Water (MEW) and with EDL);

- Daily follow-up with site engineers and project staff;

- Coordination with all national stakeholders and beneficiaries;

- Providing technical and policy advice to decision-makers (MEW) and UNDP CO on renewable energy issues, in particularly CEDRO played an important role in;

  - Enhancing the understanding of the ‘net metering’ concept. Net metering has now made its way to EDL and will be available for all renewable energy installers beginning 2012. This is a big achievement that would considerably increase the success and penetration of renewable energy system. Net metering is the quantitative exchange of electricity between a renewable or low-carbon electricity system and the national grid that enables the grid to bank renewable electricity output at times of low energy requirement with high renewable energy resource, and deduct these from times of net imports from the grid at times of low renewable energy output (for example, during the night for solar power applications).

  - Streamlined CEDRO’s activities to be a solid part of the National Energy Efficiency Action Plan (NEEAP). In fact, CEDRO will contribute to the majority of the 15 initiatives set forward by the NEEAP that cover most of the themes identified, from various renewable energy systems to energy efficiency measure.

- Implementation of end-use energy efficiency and renewable energy demonstration projects for public sector buildings and facilities (in 2011)

The following projects have been implemented in 2011 (or at least begun in 2011);

- 35 photovoltaic sites have been implemented in 2011. These sites consist of PV modules (panels), inverters, charge controllers and data loggers, and the rest of balance of system (BoS) components. The PV system provides the institutions (mostly public schools and municipalities) with renewable electricity for their lighting and for running their computers and equipment. Annex 1 contains the complete PV sites implemented by CEDRO so far.  CEDRO is in the process of collecting data on the operation and impacts of these PV systems. This information should be ready towards the end of 2012, when sufficient data would have been collected spanning at least a 1 year period. It suffices to mention that, from discussion with several sites, the PV systems have provided autonomy for the beneficiaries in that the use of expensive diesel back-up has been reduced to near zero, and only the rent value of electricity from the national grid is being paid, i.e., no bills for electricity usage from the grid. What is more, now that net metering is enable, the systems are likely to generate electricity and export to the national grid.

- 10 sites across Lebanon for wind reading measurement studies has been implemented (completed), using anemometers (wind speed reading equipment) for some, while relying on computer modelling for others. After 10 months of wind readings, 7 of these sites have been identified with sufficient wind for the installation of microwind projects (to be implemented in 2012). The three remaining sites will have PV systems installed. The Table below indicates these sites where Akkar and Bekaa sites are suitable, whereas the South was not.

Akkar

El Mkayteaa Intermediate Public School

El Rihannieh Public School

Karha Public School

Bekaa

Deir el Ahmar Secondary Public School

Kamed Ellouz Intermediate Public School

Ras Baalback Community Center

Lebanese Army Communication Post - Aarsal

South (not feasible for wind due to low speeds)

Chebaa Secondary Public School

Debaal Public School

El Kleile Kindergarden Public School

Like PV systems, microwind is hoped to guarantee the beneficiary renewable electricity. This would reduce doubly the need for diesel back-up generation and the imported electricity from the grid.

- A ground source heat pump (GSHP) project has been launched by CEDRO in Bejji municipality. GSHP systems use/extract the heat in the ground (in this CEDRO case, vertical boreholes down 100 meters have been dug) in the winter to heat the building and use the ground to dump the heat of the building in summer. The project is expected to be completed in Q1 of 2012.

- The installation of 4 solar hot water (SWH) systems in public hospitals have been commenced and completed/commissioned in 2011. These sites are;

| Institution Name | System size (liters) |
| --- | --- |
| Qartaba governmental hospital | 500 |
| Bsharre governmental hospital | 1,000 |
| Dahr El Beshiq governmental hospital | 6,000 |
| Bent Jbeil governmental hospital | 6,000 |

These systems are made up of flat-plate collectors and storage tanks, including data recording equipment. These systems will provide 60 – 75% of the hot water demand by these hospitals, and therefore save similarly on the fuel consumption, fuel cost, and reduction of CO2 emissions. These four hospitals are currently serving 264 beneficiaries (patients), yet will be serving up to 400 in the near future.

- The 12,000 liters x 2 SHW project at the Baalbeck army institute with PV powered water circulation has been completed and the site is now commissioned.  The actual energy savings of this will be recorded in due course when 1 year of operation has passed. It is expected saving, as observed in other SHW sites implemented by CEDRO, should be approximately 60% of baseline diesel use.

- The SHW project of Roumieh Prison (Built to take 1000 prisoners yet is currently taking 3000) is almost complete with jacketing remaining. The commissioning of the site is expected in 2012. Delay in Roumieh has occurred due to the many security lapses that suspended works.

- 439 light emitting diode (LED) street lighting fixtures have been installed in 2011. LED fixtures save 30-40% more energy than normal street lighting fixtures. These fixtures were distributed in the following towns;

| # | Institution Name |
| --- | --- |
| 1 | Galboun |
| 2 | Kfour Aarbeh |
| 3 | Saida |
| 4 | Choufiet |
| 5 | Kfarnabrakh |
| 6 | Rachaya road |
| 7 | Lala |
| 8 | Tell Znoub |

- Setting an enabling environment for the conversion of public sector buildings and facilities into energy efficient modalities

- Issuing of newspaper releases and magazine articles (national coverage);

- Networking and coordination with national project partners and stakeholders such as the Lebanese Order of Engineers, Ministry of Energy and Water, Ministry of Public Works, etc.,

- Synergy with the on-going UNDP project at the Ministry of Energy and Water, Lebanese Centre for Energy Conservation project (LCECP), on ongoing energy audits and activities to build on the project’s technical know-how, experience on the ground, and lessons learnt during the implementation of energy efficiency and renewable energy activities. This entails exchange of technical data and lessons learnt as well as brainstorming session to coordinate and maximise efforts for project implementation;

- The CEDRO website (www.cedro-undp.org) is running and is being continuously updated with new events and projects as they happen.

- Actively participated in Project Lebanon (June 2011) and the Beirut Energy Forum with the LCEC in September/October 2011.

- CEDRO has launched the ‘national wind atlas for Lebanon’ event under the auspices of the Minister of Energy and Water and Spanish Ambassador to Lebanon on the 25th of January, 2011. The event was a huge success despite the political situation at the time. A copy of the wind atlas with a CD was given out to all attendees of the conference (see photo below).

It is important to note the significance of the Wind Atlas study. |Before its’ publication, the potential of Lebanon to generate wind faced various estimates, from 100 MW only to 5000 MW. The Wind Atlas put things in perspective and indicated a lower, mean and upper bound of potential in Lebanon based on a rigorous scientific methodology. The study has shifted a lot of focus on wind as a primary source of renewable energy (mean 6.1 GW of capacity), and pressure now is on policy makers to enable independent power producers to make use of Lebanon’s vase potential. The Wind Atlas also enables investors to zoom up to a 100 M X 100 M resolution unto the land to assess the wind speed at a 50 m and 80 m height, where these heights correspond to the hub height of wind turbines. This is extremely important for micro-analysis, where expensive anemometers can now be better placed for further – investment feasibility – purposes.

Wind atlas conference in Metropolitan Hotel (left), Beirut on 25th January, 2011, and the cover page of the published wind atlas (right)

- Three large events that launched the PV applications of CEDRO occurred in Kfour, the South, and repeated for Akkar and the Bekaa. The event catered for all the school children from ages 5 to 11 (totally 900 students) who attended a play on renewable energy and then a workshop for building a Lego house that runs on renewable energy. CEDRO also distributed lunch boxes, hats, pencil cases and various stationaries, and school bags to all the students as part of the awareness raising activities.

- Such awareness campaigns are key to CEDRO’s objective of assisting in creating a more sustainable energy future. The campaign target the young generation and enabled them to believe that even small changes implemented by individuals lead to large changes on aggregate. Furthermore, CEDRO truly believes that when the targeted young generation becomes of income-generating age, the cost of renewable energy systems will be in parity with conventional sources, and building knowledge of these pathways are important.

Awareness campaign in Kfour Public School. 900 students took part by building their own Lego solar houses (example in south event - left) and by watching a play on climate change and renewable energy (example in south event - right)

- A workshop for Environmental Impact Assessment (EIA) of Wind Farms, including an EIA guideline report to be used as a reference for future wind farms in Lebanon has been held end of September. It is hoped that Lebanon would follow international norms in licensing or permitting wind farms. One of the most important licensing requirement for wind farms is the acceptance of the environmental impact assessment. Wind energy is only ‘green energy’ is it has not serious negative environmental impacts, or can mitigate successfully these impacts. Implementing an EIA and applying its’ recommendations. The workshop enabled the local environmental consultancies to be prepared for undergoing such an EIA.  The conference was successful and a guideline report was prepared with the conference on the same subject matter. Please see Annex 2 for the conference time table, title page of the guideline report, sample of certificate given to attendees and some pictures of the actual event.

- 2 Newsletters were prepared and printed in 2011, Issue 5 and Issue 6 (the latter to be delivered in Q1 of 2012). Newsletter 5 is reproduced in Annex 3.

- Assisting the establishment of a sustainable Energy Strategy for Lebanon

- The Wind Atlas for Lebanon has been completed and the results have been disseminated in a conference in January 2011. The wind atlas is a national document and has been adopted by the Ministry of Energy and Water. Results were very positive, indicated that Lebanon has a minimum of 1.5 GW of energy potential, which goes up to 6.1 GW in the mean case and 12 GW in the maximum case.

- The National Bioenergy assessment Study for Lebanon has been completed. Bioenergy is a little understood (in Lebanon) yet highly important energy source that needs analysis in Lebanon. The study assessed all the potential of various bioenergy sources in Lebanon, including their conversion options, set scenarios of bioenergy uptake into future, all under very strict sustainability criteria and with a focus on barriers in Lebanon for bioenergy uptake. Results will be disseminated in a conference in Q1 of 2012.

- Expenditure to date

The expenditure in all CEDRO projects to date, i.e., from 2007 to end of 2011 is shown in the figure below:

As of end of 2011, CEDRO 1 has spent all its allocated budget and has formally been completed. With respect to CEDRO 2, 3,367,082 USD has been spent from CEDRO 2 (app. 96.2% of total budget), and 526,916 USD has been spent from CEDRO 3 (app. 15% of total budget).

- Constrained and Future Work Plan

In 2011, CEDRO faced a few constraints, namely;

- Import delays due to customs at Beirut International Airport. Controllers, used in the PV systems, remained at Customs for over 1 month until the UNDP successfully cleared the systems. It is important to note as well that CEDRO highly encourages that all duties and customs on renewable energy systems be removed to enable a more cost-competitive environment.

- Roumieh Prison. Roumieh Prison is still facing delays due to the difficulty of access to the prison and the security situation that deteriorated on several occasion and postponed/delayed work on the prison. CEDRO hopes to finish Roumieh by Q2 of 2012.

With respect to future work plans for 2012 in CEDRO would be aimed several aspects;

- Further implementing demonstration projects that would benefit the various public institutions in Lebanon, introducing larger PV sites and replicating 2 SHW technologies (i.e. similar in size as those done before) and yet also focusing on new technologies such as microwind and pico-hydro.

- Maximising more the outreach of CEDRO to focus on all the work CEDRO has implemented and is implementing and to assist in the national awareness campaigns for RE and EE applications

- Undergoing further capacity building workshops for renewable energy professionals, esp. tailored to GSHP applications and microwind.

- Launch two energy manual for the Banking and hospital sectors. These would deliver a guide towards more energy efficiency in these two important sectors.

- To continue in resource assessments for renewable energy. To this end, the national geothermal assessment is to be launched in 2012.

Following through the above objectives/aims, the CEDRO project has many projects in the pipeline. These projects target around 20 sites and/or beneficiaries and include many different types of RE/EE technologies. Annex 4 outlines these projects.

A detailed work plan for 2012 is also shown in Annex 4.

Annex 1 – All CEDRO PV Sites Implemented

Annex 2. Environmental Impact Assessment of Wind Farm Development Workshop and Guideline Report.

Certificate of attendance/completion was given to the attendees

Cover page of Guideline report

Annex 3. CEDRO Newsletter 5

Annex 4. 2012 CEDRO 3 Project list, plan, and estimated budget (to be spent in 2012)

|  | Project | Project type (& status) | Expected budget (USD) |
| --- | --- | --- | --- |
| CEDRO 3 Total | Geothermal Assessment | RFP posted online | 250,000 |
|  | Wastewater treatment plant energy generation | On-going Project | 50,000 |
|  | Solar hot water | 2 sites (ITB being prepared) | 120,000 |
|  | Microwind | 7 sites (ITB being prepared) | 200,000 |
|  | PV | 8 larger sites (ITB being prepared) | 250,000 |
|  | Pico-hydro | 1 site (RfQ being prepared) | 30,000 |
|  | Central Bank Green roof | 1 site (RfP being prepared) | 200,000 |
|  | Batroun Port | 1 site (RfP being prepared) | 100,000 |
|  | Thin Film PV site | 1 site (RfQ being prepared) | 75,000 |
| TOTAL COST | 1,275,000 |

Detailed Work Plan for 2012

| CEDRO 3 - 2012 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Expected Outputs | Planned Activities | Target Year | Status | Q1 | Q2 | Q3 | Q4 |
| Implementation of energy efficiency & renewable energy applications for public sector buildings & facilities (20 sites across Lebanon) Setting an enabling environment for the conversion of public sector buildings and facilities into energy efficient modalities | 1 - Identification of pilot projects |  |  |  |  |  |  |
|  | 1.1 - Identification of Needs for EE/RE | 2012 | Completed |  |  |  |  |
|  | 1.2 - Identification of Technologies | 2012 | Ongoing | X |  |  |  |
|  | 1.3 - Identification of Beneficiary sites | 2012 | Ongoing | X |  |  |  |
|  | 1.4 - Preparation of Tender Documents | 2012 | Ongoing | X | X |  |  |
|  | 2 - Implementation of pilot projects |  |  |  |  |  |  |
|  | 2.1 - Pre-qualification of firms | 2012 | Ongoing | X |  |  |  |
|  | 2.2 - Issuing of Request for Proposal | 2012 | Planned | X | X |  |  |
|  | 2.3 - Commissioning & supervision of works | 2012 | Planned | X | X | X | X |
|  | 2.4 - Hand-over of Installations | 2012 | Planned | X |  | X | X |
|  | 3 - Establishment of data base |  |  |  |  |  |  |
|  | 3.1 - Collection of data on public facilities | 2012 | Ongoing | X | X | X |  |
|  | 3.2 - Set-up of GIS database | 2012 | Ongoing |  | X | X |  |
|  | 3.3 - Collection of data on energy savings | 2012 | Ongoing | X | X | X |  |
|  | 4 - Capacity Building & Info Dissemination |  |  |  |  |  |  |
|  | 4.1 - Development of training material | 2012 | Ongoing |  | X | X |  |
|  | 4.2 - Implementation of training workshops | 2012 | Planned | X | X | X |  |
|  | 4.3 - Development of awareness tools | 2012 | Planned |  | X | X |  |
|  | 4.4 - Dissemination of awareness material | 2012 | Planned | X |  | X |  |
|  | 5 - Establishment of policies / procedures |  |  |  |  |  |  |
|  | 5.1 - Development of procurement tools | 2012 | Planned |  |  | X |  |
|  | 5.2 - Proposal of O&M schemes | 2012 | Planned |  |  | X |  |
|  | 5.3 - Establishment of best practices | 2012 | Planned |  |  | X | X |
|  | 6 - Project validation and sustainability |  |  |  |  |  |  |
|  | 6.1 - Monitoring of site results | 2012/2013 | Ongoing | X | X | X | X |
|  | 6.2 - Development of sustainability plan | 2012/2013 | Planned |  | X | X | X |