### PROGRESS REPORT

| Reporting UN Organization | : | United Nations Development Programme |
| --- | --- | --- |
| Country | : | Lebanon |
| Award ID | : | 00057771 |
| Project ID | : | 00071490 |
| Award Title | : | Hydro Agricultural Development for Marjeyoun Area (Litani) |
| Award Timeframe | : | Oct 2009 – Mar 2013 |
| Reporting Period | : | 1 October 2012 through 31 December 2012 |

I. PURPOSE

Project Summary:

The project will assist local communities in Marjeyoun area to benefit from a main canal supplying water to South Lebanon from West Bekaa. The project will show the advantages and efficiency of modern irrigation techniques, will propose the new cropping patterns in the region, and will support the establishment of a very much needed Water Users Association. The project will have a direct impact on the livelihood of at least 1,250 households within 5 communities affected by the July 2006 conflict through extending the areas suitable for agriculture, and will provide direct assistance to the farmers in the area. The project will produce topo-cadastral maps which are the bases for designing the irrigation distribution networks, will establish a land classification database as a prerequisite for the development of the hydrant implementation plans, and will execute land reclamation works for selected land in an area of 522 ha setting up the infrastructure for the water distribution network.

Project Objective:

The objective of this proposed pilot project is to prepare the infrastructure and to facilitate the implementation of the irrigation distribution network in the “Marjeyoun” North Perimeter through a participatory approach involving the farmers to ensure proper management of water use.

Project Linkages to National Priorities and Reconstruction Goals:

This project will be a model for the other areas which will benefit from Canal 800. It will set the infrastructure for the distribution network, will show the advantages and efficiency of modern irrigation techniques, will propose the new cropping patterns in the region with their socio-economic impact, and will support the establishment of a very much needed Water Users Association.  The project will have a direct impact on the livelihood of the local communities affected by the July 2006 conflict through extending the areas suitable for agriculture and will provide direct assistance to the farmers through providing them with wheat seeds to be cultivated on their lands for two consecutive years (other field crops will be considered as well), awaiting the supply of irrigation water from the main canal.

The project is in line with the Millennium Development Goals, namely goal 7 - Ensure Environmental Sustainability. It works towards the target of proportioning total water resources used in each country. It further meets national priorities on water resource management of the Ministry of Energy and Water and is in line with the water reform programme set by the Lebanese Government.

Project Implementation Partners

- Litani River Authority (LRA)

- Council for Development and Reconstruction (CDR)

- Communities of “Burghoz”, “Blat”, “Dibbine”, “Ibl Essaki”, and “Jdaydit Marjeyoun”.

- Association of the Friends of Ibrahim Abd El Al (AFIAL)

The project’s national partner is the Litani River Authority (LRA), an autonomous public establishment which is under the tutelage of the Ministry of Energy and Water. The LRA’s covers a larger scope than just the Litani River; it includes the execution of works for irrigation, studies and construction of dams and hydroelectric power plants as well as the management of both surface and ground water resources.  Amongst its responsibilities is the implementation of irrigation schemes in Bekaa and South Lebanon (law 221 -Water Authorities Law). The LRA will be the government institution responsible for water distribution from canal 800 and therefore the projects’ outputs will be delivered to LRA and the works are in general executed in coordination with LRA.

The CDR is the Government institution responsible for the execution of Canal 800 and accordingly the project will coordinate some technical aspects of the projects when needed.

The communities of “Burghoz”, “Blat”, “Dibbine”, “Ibl Essaki”, and “Jdaydit Marjeyoun” are the beneficiaries from the project and all land reclamation works are being coordinated with the local communities, farmers and land owners.

The Association of the Friends of Ibrahim Abdel Al (AFIAL), a Lebanese NGO that works on awareness and advocacy on water issues for both decision makers and the general public, has successfully implemented several water projects and continues to raise funds and lobby for the promotion of integrated water resource management at the national level. Its role is to create the Water Users Associations for villages targeted under the project and draft the WUA law along with undertaking the lobbying efforts to pass it in the parliament.

Key Coordination:

- Ministry of Agriculture (MoA) – Green Plan (GP)

- Ministry of Energy and Water (MEW)

- Ministry of the Environment (MoE)

Acronyms:

- Spanish Agency for international development cooperation	≡   AECID

- Association of the Friends of Ibrahim Abd El Al 		≡   AFIAL

- Council for Development and Reconstruction   		≡   CDR

- Green Plan   						≡   GP

- Invitation To Bid						≡   ITB

- Lebanese Agriculture Research Institute			≡   LARI

- Lebanese Armed Forces					≡   LAF

- Lebanon Mine Action Center   				≡   LMAC

- Lebanon Recovery Fund					≡   LRF

- Litani River Authority   					≡   LRA

- Ministry of Agriculture  					≡   MoA

- Ministry of Energy and Water  	 			≡   MEW

- Ministry of the Environment   				≡   MoE

- Request for Proposals					≡   RFP

- Terms of Reference 					≡   ToR

- United Nations Development Programme			≡   UNDP

- United Nations Interim Force in Lebanon			≡   UNIFIL

- United Nations Mine Action Center  				≡   UNMAC

- Unexploded Ordnance					≡   UXO

- Water Users Association					≡   WUA

II. RESOURCES

|  |  | Amount (USD) |
| --- | --- | --- |
| Total budget approved | : | 2,000,000 |
| Total disbursements until 31 December 2012 | : | 1,211,880 |
| Commitments for next quarter | : | 537,472 |
| Available Balance | : | 250,648 |

Budget and Expenditure Breakdown as per LRF Category:

| CATEGORY | Total Budget(USD) | Total Exp. to date (USD) |
| --- | --- | --- |
| 1. Personnel (Incl. staff and consultants) | 443,200 | 417,656.60 |
| 2. Contracts (Incl. companies, professional services) | 1,185,959 | 619,390.85 |
| 3. Training (incl. AV printing / production) | 30,000 | 26,098.61 |
| 4. Transport (local) | 25,000 | 19,645.16 |
| 5. Supplies and commodities (Incl. IT equipment and rental & maintenance) | 90,000 | 8,645.78 |
| 6. Equipment (including installation) | 40,000 | 2,841.83 |
| 7. Travel | 15,000 | 3,001.90 |
| 8. Miscellaneous | 40,000 | 35,317.40 |
| 9. Agency Management Support (7%) | 130,841 | 79,281.87 |
| TOTAL | 2,000,000 | 1,211,880.00 |

III. PROGRESS

- Implementation of  Water Users Associations

The implementation and the establishment of the four Water Users Associations are still in process for the villages of Blat, Jdaydit Marjeyoun, Debbine, Bourghoz, and Ible Essaki. No progress was made since last quarter.

The WUA Law project is still under review at the Ministry of Energy and Water (MEW) and it should be forwarded soon to the MEW Minister in its final form for approval. AFIAL are investing all necessary lobbying efforts to make it move forward.

- Land Reclamation Works

The contract for land reclamation works was signed on July 4 between UNDP and the winning contractor “South for Construction S.A.L”; accordingly, land reclamation works started on July 16 in Borghoz areas.

After having some problems during Q3 where the works were forced to stop by the Internal Security Forces (ISF),works were resumed on 3 November 2012.  Several teams were mobilized gradually to recover the lost time.

Works started first in Bourghoz and Blat; then, additional teams were mobilized to Ibel el Saki and Jdaydet Marjeyoun.  During Q4, approximately 40 ha of plots in different villages were completed.  The annual report will include more details related to reclamation works (number of lands rejected, refused, completed, ongoing, and justification for selection, etc.)

Furthermore, during Q4, the project team purchased wheat seeds from LARI for distribution to the farmers in the area.  The distribution included farmers within the project perimeter and land owners of the land that are under reclamation. Therefore, the following procedures were adopted:

- An assessment was done to check the potential wheat quantity needed and resulted in around 60 tons.

- An announcement was distributed in all municipalities, Mokhtars, mosques, churches, village centers, shops, etc.

- A certificate was to be provided from the Mokhtars to each interested farmer (a sample was distributed to all Mokhtars).

- Once all certificates were collected from Mokhtars with the farmers ID than the following was done to validate that the plots are effectively cultivable:

  - Plots were mapped on satellite imagery by the project GIS expert providing an attribute table with surface areas.

  - The project team conducted a review of the maps and site visits to validate the information received; accordingly, many plots were eliminated and the list of beneficiaries was finalized.

- Assuming a needed wheat rate of 25 Kg/dn for cultivation, the distribution was done through transportation of 3 trucks of around 20 tons each on the same day of transportation.

- A certificate of receipt was signed by each farmer and/or land owner.

- In addition to the above and to avoid possible trading with the distributed wheat, al wheat bags were tagged.

In addition, two workshops were conducted on 25 October 2012 and 3 November 2012 for farmers in the area related to three main topics:

- New wheat varieties breeding program and varieties performances and suitability for Marjeyoun area

- The wheat pests and diseases and means to treat them

- The modern conservation agriculture techniques applied to wheat cultivation

The purpose of the workshops is to train and raise the awareness of the farmers in the region that were noted to be facing several problems related to wheat cultivation.

The farmers were very interested in the topics and the presentations leading to highly valuable discussions between the farmers and the trainers.

- Project Management

Many field visits were conducted by the project team regarding the land reclamation works contacting the land owners to get their approval for accessing their land and for processing; in addition to the review of the project deliverables and overall follow up on the project.

A significant amount of time and effort was put to fulfill the requirements of ISF and MoA in order to get the permit from MoA and clearance of ISF.

| Activity Results | Activity Actions | Progress up to 31 December 2012 | Targets for March 2013 |
| --- | --- | --- | --- |
| Establishment of Water Users Association (WUA) | Draft the required legislation to establish the WUA Financial Management; Lobby with policy makers to pass the required legislation | Creation of 4 WUAs Finalized the draft law Initiated the lobbying efforts Building farmers capacity Registration of 4 WUAs | Continue capacity building trainings Implementation of WUA on the ground Continue lobbying efforts to pass the law Official registration and approval of the WUAs Follow up with the Ministry of Energy and Water to ensure approval of the WUAs |
| Development of land database and hydrant plans | Processing of topo-cadastral maps, using GIS; Conduct physical & chemical laboratory analysis for soil and infiltration measurements (every 4 ha); Obtain data on the geology, slopes, percentage and nature of rocks, stones and gravel on surface, and current land use for the project area; Determine cropping pattern and water needs at farm level; Finalise the hydrant plans | Contract signed with the Mediterranean Agronomic Institute of Bari – CIHEAM to develop an integrated hydro-agricultural development plan Receive the final land classification maps and report Physical and chemical analysis for 145 soil samples First Stakeholder Meeting was conducted in January 2012 Received the final guidelines for the reclamation designs Received of the optimal crop type and cropping pattern Updated cropping pattern designs Received of the hydrant plans design, specifications for every hydrant and the report explaining the methodology Received of the Bills of quantities for the Hydrant Plans and related Costs Estimates Verification and adjustment of the land reclamation maps received from BARI-CIHEAM. Selection of the plots for the land reclamation Technical meeting about “the Irrigation Network Design and Management” took place on July 5th 2012. Received the Operation & Maintenance manual of the network |  |
| Execution of land reclamation works | Develop guideline basis for land reclamation works; Prepare land reclamation designs for uniform geographical region Execution of the base works; Support complementary works (Terraces, walls, stone and gravel removal) to be done by farmers; Provide the farmers with wheat seeds for cultivating their land | Finalised the first tender for land reclamation works however given that higher than expected offers were received, a retendering process was launched. ITB was reposted for interested bidders to apply Technical evaluation and selection of bidders was completed. Contract signed for land reclamation works. Land reclamation works started on 3 November on site and is still ongoing. Launching the procedures of wheat procurement and distribution in the project area in September 2012. Wheat seeds distribution to farmers in the area. Workshops on wheat cultivation successfully completed. | Complete reclamation works on site Stakeholders meeting Purchase of machineries for LRA that will ensure the continuous support to farmers in the region |
| Project Management | Establish PMU; Establish coordination and linkages between all project partners; Ensure timely implementation and reporting on project activities | LRF Approval for an 18 months extension (until March 2013) Replacement of the Administrative Assistant Recruitment of a new Project Manager Recruitment of a site Engineer Recruitment of a Junior Field Assistant | Recruitment of the necessary Consultants Timely reporting on all project activities Follow up on the execution of works |

IV. WORK PLAN PER ACTIVITY FOR THE FIRST QUARTER IN 2012 (January – March 2012)

| Key Milestones Wks | January | February | March |
| --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |
| 1. Establishment of Water Users Associations |  |
| 1.1 Lobbying Efforts to Disseminate the Law |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2 Capacity Building Trainings |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3 WUA Implementation |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.4 Official Registration of the 4 WUAs Created |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. Execution of Land Reclamation Works |  |
| 3.2 Stakeholders Meeting |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3 Workshop on “Wheat Cultivation” |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4 Execution of the works |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. Project Management |  |
| 4.1 Technical, Financial and operational mgt. |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.2 Promotion of synergies with other projects |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.3 Information exchange and coordination |  |  |  |  |  |  |  |  |  |  |  |  |

Implementation Constraints and Lessons Learnt:

The main issues faced by the project are: Works on site were stopped by the Internal Security Forces (ISF) claiming that the project was not investigated by ISF and requires permitting although a permit was given by the Governor. The new decision of Minister of Agriculture related to land reclamation caused additional delays to the project. Land reclamation started in November 2012 and weather conditions caused additional delays in the execution of the works. The communication with the land owners that is consuming significant amount of time to get their feedback and approval for the landownership is very complicated due to the multiplicity of owners in most of the cases. Difficulty of communication with land owners and farmers: They are not reacting seriously towards the Canal 800 since they have been hearing talks about it since the 1970’s. Delay in preparing and submitting the necessary requested papers. Land is already fully or partially cultivated; landowners/farmers are not yet ready to change their crops until water is actually available next to their plots. Some of them refused the reclamation of their plots for reasons that were not clearly revealed to us.