### PROGRESS REPORT

| Reporting UN Organization | : | United Nations Development Programme |
| --- | --- | --- |
| Country | : | Lebanon |
| Project No. | : | 00072768 |
| Project Title | : | Recovery of Nahr El Bared Surrounding Communities Affected by the 2006 and 2007 conflicts |
| Reporting Period | : | January – March 2013 |

I. PURPOSE

Project Objective:

The main objective of the project is to promote recovery and social cohesion. It is designed to restore livelihoods of 2,000 vulnerable households (13,400 individuals) in 28 communities of North-Lebanon who have sustained significant direct or indirect losses related to the conflict of July - August 2006 and/or the NBC conflict in 2007. Additionally, the project aims to provide a solid platform for development efforts in the area by increasing local capacities of participatory planning, management and implementation of development programmes, as well as promoting local level dialogue.

Project Outputs:

- Livelihoods of farmers, fishermen and SME owners improved through socio-economic interventions targeting training, technical and asset needs

- Living conditions and livelihoods of communities improved through small scale infrastructure projects

- Dialogue  improved through local level interventions, particularly targeting youth

The remaining activities in 2013 are the supply and installation of 102 greenhouses in six villages in North-Lebanon (Output 1), the finalization of the Olive Solid Waste Composting project (Output 1), the provision of support to the Halba slaughterhouse (Output 2) and the support of the rehabilitation of sewage networks and of a mini-football field in Bkarzla (Output 2).

Project Linkages to National Priorities and Reconstruction Goals:

The project is linked and contributes to the achievements of two national priorities of the UNDP Country Programme Document for 2010-2014:

- The increase of growth performance and improvement of social indicators

- The enhancement of national capacities for crisis prevention and recovery.

It specifically contributes to the achievement of two outcomes which are to:

- Strengthen local governance structures in the targeted under-served regions, for better representation, participation, and basic local services delivery and

- To improve living conditions and trust in Palestinian and Lebanese surrounding communities.

The project also contributes to the achievement of outcomes 1 and 4 of the 2010-2014 UNDAF through the strengthening of the capacity of civil society groups to foster peace, reconciliation and conflict prevention (outcome 1) and the capacity of institutions and community groups to formulate and implement regional and local development plans effectively (outcome 4). The project also contributes to the improvement of the availability and access to support services for the development of micro, small and medium enterprises, cooperatives and other underserved populations (outcome 4) and the development of the capacity for production and marketing of quality, safe, competitive industrial, agricultural and handicraft products (outcome 4).

Project Implementation Partners:

As per the project document, some activities are implemented in partnership with the ILO and FAO. In particular, both UN agencies are engaged in the implementation of project output 1: “Livelihoods of farmers, fishermen and SME owners improved through socio-economic interventions targeting training, technical and asset needs”. In this respect, FAO provided technical support and assistance to the design and implementation of the agricultural-related aspects of the project, including capacity building. ILO supported the implementation of the micro grant component, through its partnership with the local micro finance institution, known as Al Majmoua, which is another implementing partner.

Other implementing partners include: the Ministry of Agriculture and the Municipalities of Karkaf, Wadi el-Jamous, Kobbet Bchamra, Hmaira, Borj el-Arab, Halba, Bkarzla, Bebnine, Muhammara, Minyeh and Bhanine.

II. RESOURCES

| Total budget approved | 2,499,948.00 USD |
| --- | --- |
| Total disbursements as of 31 March, 2013 | 1,819,811.66 USD |
| Available Balance USD | 680,136.34 USD |
| Commitments for next quarter | 422,431.14 USD |

| CATEGORY | TOTAL BUDGET USD | TOTAL EXPENDITURE USD |
| --- | --- | --- |
| 1. Personnel | 235,400.00 | 246,546.14 |
| 2. Contracts | 1,530,000.00 | 1,157,011.87 |
| 3. Training | 285,000.00 | 172,501.31 |
| 4. Transport | 4,000.00 | 1,563.33 |
| 5. Supplies and commodities | 2,000.00 | 2,109.91 |
| 6. Equipment | 80,000.00 | 54,014.92 |
| 7. Travel | 80,000.00 | 7,940.72 |
| 8. Miscellaneous | 120,000.00 | 59,070.36 |
| Sub-total | 2,336,400.00 | 1,700,758.56 |
| 9. Agency Management Support | 163,548.00 | 119,053.10 |
| TOTAL | 2,499,948.00 | 1,819,811.66 |

| REVISED UNDG CATEGORIES | TOTAL BUDGET (USD) | TOTAL EXPENDITURE (USD) |
| --- | --- | --- |
| 1. Staff and other personnel costs |  | 246,546.14 |
| 2. Supplies, commodities, materials |  | 2,109.91 |
| 3. Equipment, vehicles, furniture |  | 54,014.92 |
| 4. Contractual services |  | 579,031.01 |
| 5. Travel |  | 9504.05 |
| 6. Transfers and grants to counterparts |  | 720,174.93 |
| 7. General operating and direct costs |  | 89,377.60 |
| Sub-total | 2,336,400.00 | 1,700,758.56 |
| Indirect support costs | 163,548.00 | 119,053.10 |
| TOTAL | 2,499,948.00 | 1,819,811.66 |

III. RESULTS

Progress in Project Implementation:

| Project Outputs | Activities | Targets | Status |
| --- | --- | --- | --- |
| Output 1: Livelihoods of farmers, fishermen and SME owners improved through socio-economic interventions targeting training, technical and asset needs | 1. Supply and install greenhouses for 102 farmers in Muhammara, Wadi el-Jamous, Bhanine, Bebnine, Halba and Minyeh 2. Finalize the Olive Solid Waste Composting project and train the beneficiaries on the composting process and management of the unit | Support provided to 102 farmers to restore their income sources and improve their income Support provided to olive farmers and olive cooperatives to improve their income | The full inventory of greenhouses’ materials was completed by UNDP consultant. The concrete works were completed for 65 greenhouses and the installation of the steel structure was completed for 29 greenhouses. All construction works were successfully completed ahead of time. A legal consultancy firm was recruited in order to ensure a proper handing over of the project to a legally recognized entity. The legal consultancy firm has proposed two possible solutions: a union of cooperatives or a united committee of cooperatives. UNDP started negotiating with the cooperatives to agree on the best suitable legal status to adopt in order to handover the facility. On the job training sessions will be organized once the legal status of the cooperatives operating the facility is settled. |
| Output 2: Living conditions and livelihoods of communities improved through small scale infrastructure projects | 1. Provide support to the Halba slaughterhouse 2. Support the Municipality of Bkarzla to rehabilitate the village’s sewage network and the mini-football field | Improvement of the infrastructure of the Municipality of Halba as well as its capacities Improvement of the infrastructure of the Municipality of Halba as well as its capacities | Following reports about the bad health safety system at the slaughterhouse, a food safety expert was recruited to assess the situation of the slaughterhouse. According to his report, many modifications have to be made in order to make the facility compliant with GHP/GMP requirements and implement a HACCP plan. However, the Municipality is unable to enforce the law and the butchers are still using an unsafe slaughterhouse that has been closed by the Municipality and reopened due to political pressures. UNDP provided support to the Municipality to develop the project plans, prepare the study and prepare the request for proposals. The Municipality posted the requests for proposal until February 28. The best bidder was selected for the installation of new sewage channels and for the upgrading of the mini-football field in coordination with UNDP consultant. |
| Output 3: Dialogue improved through local level interventions, particularly targeting youth |  |  | Achieved |

Main activities undertaken and achievements:

Project output 1 “Livelihoods of farmers, fishermen and SME owners improved through socio-economic interventions targeting training, technical and asset needs”

Supply and installation of greenhouses for 102 farmers in six NBC surrounding municipalities:

With technical support from FAO, a field study conducted in 2011 revealed which farmers were in most need of greenhouse support in the six targeted municipalities: Wadi el-Jamous, Muhammara, Bebnine, Halba, Minyeh and Bhanine. A total of 102 farmers were selected as beneficiaries.

The installation of the greenhouses started in January 2012 in Minyeh but the first sample greenhouse constructed by the contractor failed to comply with the required specifications. The sample was modified based on UNDP recommendations and was accepted as compliant in June but by then the contractor was unable to continue the installation of the greenhouses, especially due to the security situation in North-Lebanon.

UNDP initiated a negotiation process to amend the contract of the awarded company to include only the supply of materials and to sign a new contract with a local company for the execution of the installation works. The two new contracts were signed and an agricultural engineer was recruited to supervise the inventory of materials and ensure smooth implementation and coordination between the supply company and the contractor.

A meeting between UNDP, the six municipalities and the company in charge of the installation works was held in early January to re-launch the activity and inform the local stakeholders about the methodology of works. Separate meetings with each municipality and farmers were then held to finalize the schedule of works according to the availability of lands and readiness of farmers in each village.

After the finalization of the installation plan, a full physical inventory of greenhouse materials was conducted over 15 working days between January and February by the consultant in coordination with the supplier and the contracted company. The purpose was to identify both the quality and the quantity of materials already supplied and available in the Minyeh Warehouse and to verify their compliance with tender specifications. Upon completion of the inventory, a detailed report was submitted to the supplier to replace all items revealed missing or damaged during the inventory. The ownership and responsibility of all inventoried items considered as compliant with specifications and in good condition was then transferred from the supplier to the local contractor.

As soon as the inventory was completed, the newly contracted company began the installation works divided into 3 phases:

1. Installation of the concrete bases

2. Installation of the steel structure

3. Installation of the plastic cover and irrigation system

Up until March 31,

- Concrete works were completed for 70 greenhouses: 20 in Bebnine, 16 in Wadi el-Jamous, 13 in Muhammara, 17 in Halba and 4 in Minyeh

- The installation of the steel structure was completed for 42 greenhouses: 15 in Wadi el-Jamous, 13 in Muhammara, 10 in Bebnine and 4 in Minyeh

- 7 greenhouses were completed entirely with the installation of the cover and the irrigation system: 5 of them are located in Wadi el-Jamous, 1 in Bebnine and 1 in Minyeh

The contracted company was unable to fully complete more greenhouses because the installation of the plastic cover and irrigation system requires a certain degree of heat to avoid damaging the plastic cover. Therefore, the third phase of the installation process will be done between May and mid-August. The installation of the 102 greenhouses should be completed entirely by mid-August 2013.

Provision of an olive solid waste composting facility and of technical and management training to agricultural cooperatives in North-Lebanon:

In coordination with FAO and the Directorate of cooperatives, meetings were organized with eight cooperatives and unions of farmers working in the olive sector in the targeted areas. An in-depth assessment selected the Bkarzla, Hosniyeh and Deir Dalloum cooperatives and the Bkarzla union of olive farmers as primary beneficiaries of the olive waste composting initiative.

During the execution of the construction works for the composting facility in 2012, the risk of erosion was identified as a threat to the facility. Therefore, the contract of the construction company was amended to include the execution of cyclopean concrete that would retain and consolidate the soil, and the implementation of a storm water drainage canal that would retain all extra liquids and store them in a tank. The construction works were completed in December 2012.

A legal consultancy firm was then recruited in order to ensure a proper handover as well as maximum benefits to the beneficiaries within a legally sound framework. The consultancy firm studied all possible options and proposed the best solutions for the creation of a legal entity with a permit to produce compost while guaranteeing the rights of all beneficiaries.

Two possible solutions for the creation of a legally recognized entity for the beneficiaries were accepted by UNDP: the creation of a union of cooperatives (ittihad ta‘awouniyat) and the creation of a united committee of cooperatives (jam‘iya muttahida).

The two options are being discussed with the beneficiaries in order to select the option that suits them the most. Meanwhile, the consultancy firm is preparing the needed legal paperwork and processes for the creation of the legally recognized entity.

Once the facility starts producing compost, both the environmental impact of the olive waste and the cost of buying the organic compost in North-Lebanon will be reduced. Around 200 individual farmers should benefit from the olive compost during the first years of operation.

Project output 2 “Living conditions and livelihoods of communities improved through small scale infrastructure projects”

Upgrading the Halba slaughterhouse:

In north Lebanon there is only one centralized slaughterhouse in Tripoli for 176 municipalities of which 100 are located in Akkar. Since it is far for butchers outside Tripoli, many illegal slaughterhouses were built in different areas of the north and many butchers still slaughter in their own butchery. This slaughtering process presents many health hazards and the risks of contamination of the meat are very high which encouraged the Halba Municipality to build its own slaughterhouse in 2010.

The Halba slaughterhouse was meant to serve all 13 municipalities of the Shafat union of municipalities (around 50,000 residents). It was built close to the meat bazaar in Halba in a strategic effort to reinforce linkages with the Akkar community of butchers (starting with 25 butchers in Halba) and to strengthen the value chain of the meat market in the region.

Discussions and meetings were then held with the Municipality to explore ways of supporting the constructed slaughterhouse. It was finally agreed, in coordination with FAO, that a grant will be given to the Municipality to support it in upgrading the structure of the slaughterhouse in order to improve the slaughtering process and in creating a laboratory for meat testing and quality control. All the construction works were completed in 2011 and laboratory equipment for testing and food safety were bought to the Municipality.

Upon the request of the Municipality, UNDP then provided training to the team managing the slaughterhouse in order to implement ante-mortem guidelines developed by FAO. An internal management system was also developed by UNDP and put in place through provision of training sessions to ensure the financial transparency in the management of the slaughter house, and the monitoring of the services.

However, in October 2012, UNDP discovered that the Municipality in charge of managing all the operations of the slaughterhouse still hadn’t hired a veterinarian to test the meat and ensure quality control and that the laboratory equipment had not yet been used. The Lebanon Recovery Fund Monitoring and Evaluation unit then recommended conducting an assessment of the situation and the food safety system in the slaughterhouse.

A food safety expert was therefore recruited in January to conduct an analysis on needed equipment and training for the slaughterhouse to function according to good hygienic and manufacturing practices requirements. Through the on-site evaluation, the expert conducted an assessment of the slaughterhouse situation and recommended the required modifications to be undertaken. He submitted his report in March 2013.

According to the report, many modifications have to be made in order for the facility to meet the international GHP/GMP requirements. Only then the facility will be able to implement a HACCP plan to and ensure that a food safety system is in place. However, the Municipality is still clearly unable to enforce the law: local butchers are still using unsafe slaughterhouses (one of which has been closed by the Municipality and reopened due to political pressures). In addition, the Municipality hasn’t been able to recruit a veterinary, or have one appointed by the Ministry, in order to use the laboratory equipment to test the meat and ensure quality control.

UNDP is still trying to help the Municipality in finding a way to recruit a veterinary to use the laboratory equipment and test the meat when needed. However, UNDP is unable at this stage of the project, to execute the needed works and improvements at the slaughterhouse or further support the Municipality in this regard due to budget restrictions. Therefore, the current situation of the facility will be shared with the concerned ministries, local stakeholders and other UNDP projects to gather support for the slaughterhouse.

Supporting the Municipality of Bkarzla in upgrading the town’s sewerage system and mini-football field

Based on discussions with UNDP, the Bkarzla Municipality submitted a proposal to change the town’s 40-year old main sewerage pipeline and to rehabilitate its mini-football field in October 2012. This initiative would strengthen local governance structures for better basic services delivery and improve living conditions in the area.

The Municipality was asked to prepare a detailed study including a bill of quantities for both projects to be reviewed by UNDP and a consultant (civil engineer) was recruited to review the studies and supervise the works.

Upon the consultant’s request, the Municipality amended the studies, project plans and BOQ in January. After they were approved, the Municipality prepared the requests for quotation for the civil works needed with support from UNDP. They were posted for a period of fifteen working days and three offers were received. The best bidder was then selected in coordination with UNDP consultant.

Based on the selected offers, a grant agreement was signed between UNDP and the Municipality to support it in the implementation of the two projects. The civil works are scheduled to take place between May and August under the supervision of the consultant.

Implementation constraints:

Some challenges were faced during the implementation phase in 2013, leading to unforeseen delays. They include:

- Delays in the installation of the greenhouses (first two phases) due to bad weather conditions in January and February

- Delays in the third phase of the greenhouses installation process (installation of the plastic cover and irrigation system), as it requires a certain degree of heat and limited winds to avoid damage

- Delays in hiring a veterinarian or getting one appointed at the Halba slaughterhouse which resulted in the laboratory equipment not being used

- Delays in the preparation of all the needed documents and processes by the Municipality of Bkarzla for the signature of the grant agreement with UNDP

Key Partnerships & Collaboration

In 2013, the LRF 24 project collaborated with the municipalities of Wadi el-Jamous, Muhammara, Bebnine, Halba, Minyeh and Bhanine to ensure a smooth implementation of the greenhouses installation process. Support was also provided to the Municipality of Halba with regards to the Halba slaughterhouse. In addition, UNDP collaborated with several cooperatives in North-Lebanon to ensure a successful implementation of the olive solid waste composting activity as well as with the Municipality of Bkarzla for all the phases preceding the signature of the grant agreement.

IV. FUTURE WORKPLAN

Output 1:

Supply and install greenhouses for 102 farmers in Muhammara, Wadi el-Jamous, Bhanine, Bebnine, Halba and Minyeh

- The remaining concrete works (for 32 greenhouses) should be completed by mid-May

- The remaining 60 steel structures should be completed by mid-July

- The complete installation (including plastic cover and irrigation) should be completed mid-August

Finalize the Olive Solid Waste Composting project and train the beneficiaries on the composting process and management of the unit

- A legally recognized entity for the olive solid waste composting facility should be created by June

- A consultant who will train the beneficiaries on the management of the unit and on the composting process should be recruited by June

- Raw materials that will be used by the beneficiaries to produce compost during the training will be bought by June

- The steps that have to be taken to obtain a permit to produce compost and sell it on the market should be completed by August

Output 2:

Provide support to the Halba slaughterhouse

- All important reports, documents and findings on the slaughterhouse should be translated by June

- Concerned ministries, municipalities and partners will be contacted  by June to gather support for the slaughterhouse

- A workshop on the dangers of unsafe meat slaughtering and on the importance of upgrading the slaughterhouse for the residents of the area will be organized by July, if budget remains available

Support the Municipality of Bkarzla in the rehabilitation of sewage networks and of a mini-football field

The implementation of the works as per the grant agreement with the municipality of Bkarzla will be completed by  August 2013

Estimated Budget required (including any major funding shortfalls):

|  | Type of contract/supply | Description of goods, services or works | Budget (USD) | Expected dates |
| --- | --- | --- | --- | --- |
| 1 | Contract for the supply of equipment | Company to supply greenhouses equipment | 271,475.00 | Q2 |
| 2 | Contract for works | Company to install the 102 greenhouses | 144,000.00 | Q2-Q3 |
| 3 | Contract for consultancy services | Individual consultant to monitor the installation of the greenhouses | 15,600.00 | Q2-Q3 |
| 4 | Contract for consultancy services | Consultancy law firm to propose a solution to create a legally recognized entity for the olive solid waste project and support the beneficiaries in obtaining the necessary documents and permit | 10,000.00 | Q2-Q3 |
| 5 | Contract for consultancy services | Individual consultant to train the beneficiaries of the olive solid waste project on the management of the unit and the composting process | 5,000.00 | Q2-Q3 |
| 6 | Contract for the supply of materials | Company/farms to supply raw materials for the composting process | 12,000.00 | Q2-Q3 |
| 7 | Contract for translation services | Consultant to translate all needed documents with regards to the Halba slaughterhouse | 5,000.00 | Q2 |
| 8 | Contract for the organization of a workshop for the Halba slaughterhouse | Consultant to prepare and organize the workshop for the Halba slaughterhouse | 5,000.00 | Q2-Q3 |
| 9 | Contract for consultancy services | Consultant to review the studies and the supervision of the works in Bkarzla | 4,500.00 | Q2-Q3 |
| 10 | Grant agreement | Grant agreement with the Municipality of Bkarzla for the provision of civil works | 149,320.00 | Q2-Q3 |
| 11 | Direct and indirect costs | Communication, transport, shipping, maintenance, etc. | 10,000.00 | Q2-Q3 |
| 12 | F&A |  | 44,232.65 | Q2-Q3 |
| Total | 676,127.65 USD |