### LRF PROGRESS REPORT

| Reporting UN Organization | : | United Nations Development Programme |
| --- | --- | --- |
| Country | : | Lebanon |
| Project No. | : | 00073450 |
| Project Title | : | Monitoring & Evaluation Team for the LRF |
| LRF Signature date | : | December 15, 2009 |
| Project Start date | : | December 15, 2009 |
| Project Timeframe | : | Three years until December 2012 |
| Reporting Period | : | 2012-Q3: July – September 2012 |

Contents

I. PURPOSE	1

II. RESOURCES	2

III. RESULTS	3

IV. IMPLEMENTATION CONSTRAINTS AND LESSONS LEARNED	8

V. FUTURE WORK PLAN	8

### List of acronyms

M&E: Monitoring and Evaluation

LRF: Lebanon Recovery Fund

UNRCO: United Nations Resident Coordinator’s Office

FAO: Food and Agriculture Organization

UNIDO: United Nations Industrial Development Organization

UNDP: United Nations Development Programme

UNFPA: United Nations Population Fund

ILO: International Labour Organization

UNESCO: United Nations Educational, Scientific and Cultural Organization

MPTF: Multi-Donor Trust Fund

PAG: Project Approval Group

SC: Steering Committee

HQ: Head Quarters

Q: Quarter

MoM: Minutes of Meeting

I. PURPOSE

Project Summary:

The M&E unit was designed to enhance the LRF monitoring mechanism by incorporating the below activities into a more coherent and efficient framework and by expanding overall oversight management. The M&E unit aims at enhancing the efficiency, preventing unnecessary expenditures and avoiding project delays. This framework will consist of:

- An increased frequency of field trips and monitoring meetings;

- Closer and more technical follow ups on project implementation and financial activities;

- A continuous evaluation and objective re-assessment of project achievements against pre-set targets;

- A support system to meet timely completion with the objective of raising the effectiveness of projects and ensure cost-efficiency in their implementation, and

- A support system to examine the final evaluation of the projects implemented under the LRF.

Effective oversight management of the LRF projects is time-enhancing and cost-efficient to both donors and beneficiaries. And since the M&E team will oversee all aspects of the project activities, Project Managers are supported in achieving their pre-set deadlines in a timely manner. This will be advantageous to the benefactors since it will prevent the postponement of the project’s activities.

Furthermore, any revisions made in the outstanding projects-such as a no cost time extension, a budget reevaluation or change in scope is effectively assessed and evaluated by the M&E team and hence, improving the cost-efficiency and decision making outcomes of those projects by the PAG team and LRF Steering Committee.

Project Objectives:

The development goal of the M&E Team is to generate a framework whereby the operation and delivery of current and prospective projects approved under the LRF are able to improve efficiency, recognize and prevent unnecessary expenditures and project delays that may arise over the present time frame of each individual project.

The immediate objective of establishing an M&E Team is to strengthen the existing LRF monitoring mechanism by improving the timeliness, cost efficiency and reliability of the current LRF project activities.

Project Outputs:

Main outputs include:

- Support Project Managers in achieving their pre-set deadlines in a timely manner, thus working in favor of the beneficiaries of each project, and

- Revisions made in the outstanding projects - such as a no cost time extension, a budget re-evaluation or change in scope - will be effectively assessed and evaluated by the M&E team. This will improve all decision making outcomes and will ensure compliance with the above revisions.

Project Implementation Partners and roles:

- Ministry of Economy and Trade: Chair of the LRF Steering Committee

- Ministry of Finance: Member of the LRF Steering Committee

- Prime Minister’s Office: Member of the LRF Steering Committee

- UNRCO: <ember of the LRF Steering Committee

- UN Implementing Agencies (UNIDO, UNDP, FAO, UNFPA, ILO, UNESCO)

II. RESOURCES

| Total budget approved | USD 200,000.00 |
| --- | --- |
| Total disbursements as of 30 June 2012 | USD 137,188.59 |
| Commitments for next quarter | USD 16,000.00 |
| Available Balance | USD 51,196.60 |

| CATEGORY | TOTAL BUDGET (USD) | TOTAL EXP (USD) to Date |
| --- | --- | --- |
| 1. Personnel (Incl. staff and consultants) | 145,101.00 | 108,970.68 |
| 2. Contracts (Incl. companies, professional services) |  |  |
| 3. Training |  | 400.00 |
| 4. Transport |  |  |
| 5. Supplies and commodities | 5,010 | 1,645.36 |
| 6. Equipment | 9,515 | 19,172.89 |
| 7. Travel |  | 58.00 |
| 8. Miscellaneous | 27,289 | 6,941.66 |
| 9. Agency Management Support | 13,085 |  |
| TOTAL | 200,000 | 137,188.59 |

III. RESULTS

Progress in Project Implementation:

Reporting

The M&E unit completed the evaluation of the progress reports of the LRF on-going projects for the second quarter of 2012 (LRF 17, 23, 10, 16, 21 and 26).

In collaboration with the concerned UN agencies, the reports were revised so that it highlights on the results and the impact of the LRF initiatives. The final versions of the reports have been uploaded on the MPTF gateway.

Extended Projects

The LRF M&E Unit was following up closely with the project on the progress achieved on monthly basis and through filed visits to the targeted areas. Challenges were reported to the LRF PAG and SC for decision.

The LRF 23, Hydro Agriculture Development Project for Marjeyoun area, and the LRF 17, Flood Risk Prevention and Management in Baalbeck Phase II project, were granted 18 months time extension to complete their pending activities by February 2013. The follow up on the progress achieved by the above-mentioned projects was conducted through detailed monthly reports and regular meetings with the projects’ managers and staff to assess the constraints and obstacles and advise the LRF PAG and SC in this regard. Coordination with the projects’ teams on alternative measures to overcome obstacles faced was also in place on monthly basis. The projects are expected to be completed within the new projects’ timeframe.

The LRF 24, “Early recovery for Nahr El Bared Surrounding Lebanese Communities Affected by 2006 and 2007 Conflicts”, has been granted a time extension of seven months to complete the pending activities related to the provision of new models of green houses to the farmers in Akkar area, the establishment of an olive solid waste facility in Bkarzala and a waste water treatment plant in Bkarzala.

The M&E Unit was closely following up with the project on the progress achieved, with regard to listed components, in addition to meeting with the project staff to clarify critical issues pertaining to the implementation of the project’s activities. The Project has been operationally closed by the end of March 2012 with pending activities related to the green houses, the olive solid waste facility and the Bkarzala components.

The Project is currently pending a decision from the SC regarding its request of a no cost time extension of six months to complete the pending activities.

LRF Newsletter, Video and Website

In coordination with the Information Unit at the RCO, the M&E unit designed and produced the fourth issue of the LRF newsletter that aims to share success stories and positive outcomes of the LRF. Along with the LRF video documentary, this newsletter issue has been distributed to the Heads of the UN agencies in Lebanon, the concerned Ministries and other stakeholders including embassies and consulates.

Moreover, and in an effort to maximize the visibility of the LRF, the M&E unit is coordinating the broadcasting of an LRF spot on all local TV stations in Lebanon.

In addition, the M&E unit prepared the fifth issue of the LRF newsletter that will be disseminated during the 4th quarter of 2012.

Finally, the M&E unit is working, in cooperation with the Information Unit at the RCO, to update the design and contents of the LRF webpage on the Lebanon UN website. Updated information will include statistical data, financial figures, and publications which will be available for the public. The updated version will be online during the 4th quarter of 2012.

| Project Outputs | Activities | Indicators |
| --- | --- | --- |
| Support Project Managers in achieving their pre-set deadlines in a timely manner, thus working in favor of the beneficiaries of each project | Quarterly review of the progress reports submitted by the projects; inquiries, comments and suggestions are shared with the program managers with regard to the obstacles faced and the alternative measures to be adopted to overcome the constraints. Monthly reports have resulted in pointing out the obstacles facing the projects’ implementation Coordination meetings with the projects’ teams to assess the progress made and the obstacles facing the implementation. | Activities completed as per the projects’ set up work plans; Obstacles assessed and alternative measures suggested to the LRF PAG and SC; Meetings with the projects’ teams and updating the work plans |
| Revisions made in the outstanding projects - such as a no cost time extension, a budget re-evaluation or change in scope - will be effectively assessed and evaluated by the M&E team. This will improve all decision making outcomes and will ensure compliance with the above revisions. | Periodic site visits to assess the progress achieved. Periodic updates to the LRF PAG and SC on the progress achieved and the obstacles faced. Ensuring visibility of the LRF to publicize the achievements of the projects and support in the resource mobilization process. Production of LRF Quarterly newsletter to disseminate the success achieved by the LRF projects. Attendance of the LRF projects’ events to promote the LRF visibility as funding party. | Missions reports and debriefing meetings PAG and SC minutes of meeting Video disseminated to local TV stations Newsletter produced and disseminated Events debriefing reports, minutes and press releases |

IV. Implementation Constraints and Lessons Learned:

Constraints: The progress reports still lack complete information on the progress achieved on site and the impact made by the LRF projects’ interventions. This is resulting in drafting more than one version of each of the progress reports to answer the M&E inquiries which focus on the achievements and impact rather than activity listing. Additional efforts have been consumed by both the M&E Unit and the implementing UN Agencies. Lack of success stories received from the LRF projects which are resulting in delaying the LRF newsletter and website updates Bureaucratic procedures in the Ministries are resulting in delaying few activities related to the LRF visibility as well as the approval of new projects. The developing security situation in North Lebanon that has resulted in limiting the access of the M&E unit to the sites. Lessons Learned: To improve the quality of the LRF progress reports, the M&E Unit is conducting individual meetings with the project/program managers to clarify the required info to be included in the progress reports in addition to the focus on the coordination terms between the implementing UN Agencies and the M&E Unit vis-à-vis the visibility of the LRF . Monthly reports were requested from the implementing UN Agencies to assess the progress made vis-à-vis the set work plans for projects receiving no-cost time extensions. Periodic site visits were undertaken to assess the progress on site and meet with the beneficiaries for feedback on the project progress and results. Participation in the LRF projects’ major events. Close follow-up with the designated focal points at the Ministries and at the PMO. Meetings with the projects’ teams to assess the progress achieved and consider alternative work plans in light of the developing security situation in North Lebanon.

| V. FUTURE WORK PLAN |
| --- |
| KEY MILESTONES | October-12 | November-12 | December-12 |
|  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 |
| Coordinate with Project/program managers |  |  |  |  |  |  |  |  |  |  |  |  |
| Manage projects progress reports |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct field visits to assess project progress |  |  |  |  |  |  |  |  |  |  |  |  |
| Coordinate with RCO |  |  |  |  |  |  |  |  |  |  |  |  |
| Coordinate with MoET |  |  |  |  |  |  |  |  |  |  |  |  |
| Provide technical support to the SC |  |  |  |  |  |  |  |  |  |  |  |  |
| Provide technical support to the PAG |  |  |  |  |  |  |  |  |  |  |  |  |
| Manage and support the management of LRF visibility (LRF video, website, newsletter…) |  |  |  |  |  |  |  |  |  |  |  |  |
| Support resource mobilization for new LRF phases |  |  |  |  |  |  |  |  |  |  |  |  |
| Coordination with LRF stakeholders |  |  |  |  |  |  |  |  |  |  |  |  |
| Maintain library of key assessments, evaluations, lessons learned and surveys |  |  |  |  |  |  |  |  |  |  |  |  |