JOINT INTEGRATED LOCAL DEVELOPMENT PROGRAMME

ANNUAL PROGRAMME NARRATIVE PROGRESS REPORT

REPORTING PERIOD: 1 JANUARY – 31 DECEMBER 2011

| Programme Title & Project Number |  | Country, Locality(s), Thematic/Priority Area(s) |
| --- | --- | --- |
| Programme Title: Joint Integrated Local Development Programme / JILDP Programme Number: 00073891 MPTF Office Project Reference Number: 00073891 |  | Republic of Moldova |

| Participating Organization(s) |  | Implementing Partners |
| --- | --- | --- |
| UNDP UN Women |  | State Chancellery of the Government of Moldova |

| Programme/Project Cost (US$) |  | Programme Duration |
| --- | --- | --- |
| MPTF/JP Contribution: UNDP 2,315,176.00 UN Women 771,725.33 |  |  | Overall Duration | 36 months |
| Agency Contribution UNDP 150,000.00 |  |  | Start Date | 01 January 2010 |
| Government Contribution (if applicable) |  |  | End Date (or Revised End Date) | 31 December 2012 |
| Other Contributions (donors) (if applicable) |  |  | Operational Closure Date | 31 December 2012 |
| TOTAL: 3,236,901.33 |  |  | Expected Financial Closure Date | 15 March 2013 |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Assessment/Review - if applicable please attach Yes No Mid-Term Evaluation Report – if applicable please attach Yes No |  | Name: Matilda Dimovska Title: Deputy Resident Representative Participating Organization (Lead): UNDP Moldova Email address: matilda.dimovska@undp.org |

ABBREVIATIONS APA Academy of Public Administration CALM Congress of Local Authorities of Republic of Moldova CPA Central Public Administration CSO Civil Society Organization CTA Chief Technical Advisor GE Gender Equality GM Gender Mainstreaming GoM Government of Moldova HR Human Rights HRBA Human Rights Based Approach JILDP Joint Integrated Local Development Programme IACC IMC Inter-Agency Coordination Committee Inter-municipal cooperation IGS International Gender Specialist KN Knowledge Network LPA Local Public Administration NGO Non-Governmental Organization PC Parity Commission on Decentralization PCB Programme Coordination Board RM Republic of Moldova SIDA Swedish International Development Cooperation Agency SC State Chancellery UN UNDAF United Nations United Nations Development Assistance Framework UNDP United Nations Development Programme UN Women United Nations Entity for Gender Equality and the Empowerment of Women USAID United States Agency for International Development WG Working Group

# PURPOSE

The development objective of the JILDP is to assist the Republic of Moldova to ensure that vulnerable groups in poor rural and urban areas take advantage of sustainable socio-economic development opportunities through adequate regional and local policies implemented by LPA and partners in a rights based, gender sensitive manner.

The Immediate Objectives of the programme are:

- To assist the Government of the Republic of Moldova to upgrade national legal, policy and advisory frameworks to support sustainable processes of development at sub-national level.

- To develop capacity of local authorities for rights based and gender responsive planning, budgeting, implementation, monitoring and evaluation of development initiatives.

- To empower rural communities and CSOs in target regions to actively participate in local development planning, implementation and monitoring and have better access to improved  service delivery and community infrastructure.

- To ensure that the communities of Transnistria and of Security Zone are equally benefiting from the improved service delivery and community infrastructure through their active participation in local development initiatives.

While the JILDP applies holistic approach to programming tacking the challenges at all levels of the governance, it puts the human rights and gender equality issues in the centre of all its activities. Thus, at the policy level the programme focused on ensuring transparent, non – discriminative, inclusive and evidence-based policy making. At the local level the programme’s key focus was on development of capacities of local authorities on rights based and gender responsive policy and budget planning and implementation.

The JILDP comprises four inter-related components:

- Policy Advisory and Advocacy Component;

- Local Self-Governance and Participation;

- Community Empowerment;

- Transnistria and Security Zone.

The following outputs are planned for completion in the programme components:

- National legal, policy and advisory frameworks to support decentralization and sustainable processes of development at sub-national level developed;

- Capacities of LPAs in the target regions improved to plan, implement, and monitor in a participatory manner;

- Rural communities and CSOs are empowered to participate in local development planning, implementation and monitoring and local actors are able to deliver services and upgrade the basic infrastructure;

- Communities and CSOs in Transnistrian region of Moldova, as well as in the area of the security zone of the Transnistrian region, are empowered to participate in local development and citizens have better access to information and services.

JILDP builds on the priorities of the Government Programme ‘European Integration. Freedom, Democracy and Wellbeing’, as well as the National Development Strategy (2007-2011) and UNDAF (for 2007-2011), in which the condition of most vulnerable (including elderly, disabled, victims of domestic violence, women at risk and young people) and the need to extend development assistance to the  Transnistrian region are identified as major concerns.

# RESOURCES

Financial resources

The programme is managed as Joint Programme using the pass-through funding modality. The UNDP serves as the Administrative Agent of this Joint Programme to pass resources through participating organizations (UN Women and UNDP) in accordance with the Memorandum of Understanding as per Joint Programme Budget. For pass-through portion of joint funding, UNDP and UN Women are managing funds in accordance with proper financial rules and regulations.

| Received, USD | 2011 |
| --- | --- |
| SIDA - UNDP | 2,315,176.00 |
| SIDA – UN WOMEN | 771,725.33 |
| TRAC allocations UNDP | 150,000.00 |
| Total received | 3,236,901.33 |

During the reporting period there four budget revisions were performed. Three of them were technical budget revisions for assurance of JILDP functionality.  First budget revision was done on 25th of February for a temporary allocation of 160,000 USD from TRAC (UNDP) to cover project expenditure until May 2011, when the second installment from donor (SIDA) was to be received.  Second budget revision was completed in May by allocating additional 100,000 USD from XB (UNDP), when it was clear that the donor’s funds will be transferred later. Third one was done based on Annual Work Plan approved by the steering committee decision dated on May 10, 2011. Last budget revision was a technical one by additional allocation of 150,000 USD from TRAC.

Human Resources

The JILDP team consists of:

- The management team: an International CTA, a Managing Director, Policy Advisors/Managers for program components and UN Women placed the International Gender Specialist (IGS), one Programme Analyst on HR and GE, and one Programme Associate.

Additionally, the programme management is assisted by the following specialists: JILDP Human Rights in Local Development Adviser and Capacity Building & Knowledge Management Adviser, as well as one UN Human Rights Adviser.

- The support team: 1 Financial Associate, 2 administrative assistants and 2 drivers.

The CTA continued to provide substantial inputs to the Decentralization strategy by liaising with the State Chancellery and other national and international partners, so that the decentralization reform moves forward. Meantime, the CTA continued to lead and provide strategic guidance to the national team of JILDP and subcontracted experts.

The Managing Director was responsible for facilitation and coordination of the Programme and of other general activities including communication and mass-media relations, interaction with the Government, as well as reporting, monitoring, and evaluation.

The Policy Advisors/Managers of the programme components were responsible for planning and management of programme activities, as well as for achieving the proposed performance indicators within each component.

The International Gender Specialist (IGS) had the responsibility to ensure an effective management and synergy of the programme, efficient achievement of JILDP programme goals and the objectives on gender equality and women.

The two advisers on HRBA and Knowledge Management have provided advisory support and analytical feedback on incorporation of HRBA principles and tools, Capacity Building and Knowledge Networking in the activities of JILDP.

The UN Human Rights Advisor provided advisory support to the JILDP team on effective HRBA mainstreaming into all components of the project, with emphasis on areas of more strategic importance, as well as inputs on specific HRBA activities.

# IMLEMENTATION AND MONITORING ARRANGEMENTS

The Joint Integrated Local Development Programme is managed as a joint initiative of two development agencies (UNDP and UN Women) and the Government of the Republic of Moldova, State Chancellery being the National Implementation Partner. Working together and in partnership with national implementing partners is a fundamental starting point for all UN priorities in Moldova, as elaborated in the UNDAF for Moldova. Cooperation between national and international partners has been achieved by the following institutional management structure: (1) Programme Coordination Board; (2) Inter-Agency Coordination Committee; (3) JILDP Implementation Team meetings.

The Programme Coordination Board (PCB) had three quarterly meetings, including one on progress reporting and planning held by e-mail in November 2011. The meetings resulted in adopted decisions on progress reports, work plans, quarterly and annual budgets, as well as decisions on specific implementation issues related to the selection of target beneficiaries, establishment of grants’ size to support community initiatives and others. The details of the proposals raised and decisions adopted at each Board Meeting were summarized in minutes, all written, approved and signed right after the meetings. At the PCB session from 11 May, 2011 the JILDP inception phase report and adjustments to the JILDP programme document, work plan and budget were approved.

The Inter-Agency Coordination Committee (IACC) had three sessions (which usually took place before PCB meetings). Each session evolved around discussions of and agreements on quarterly reports, work plans and budgets, as well as on specific issues related to program implementation. The IACC session on February 21, 2011, for example, evolved around the deliverables of the JILDP inception phase with the Vulnerability study being one of the main products, and it was agreed to endorse it at the next Board meeting. The new LFA and organizational structure of the programme has been discussed and agreed upon.

The IAC from March 24, 2011 focused on Community mobilization within JILDP, specifically the methodology and approaches and number of programme target localities. The IAC members agreed on using a unique approach for community mobilization, decrease the number of JILDP target communities and increase the amounts of grants per community.

Monitoring of the implementation of programme activities was conducted by: Inception phase reporting, Quarterly activities report, Operative meetings (held upon necessity), weekly meetings of the Programme Team, and monitoring missions on programme activities’ implementation.

Quarterly reporting was done by preparing narrative and progress reports, accompanied by comments on the achieved activities and performance indicators. They were presented and discussed in the frame of the IACC meetings and have been approved at the PCB meetings. Operative meetings were organized in a planned or ad-hoc manner in order to assess the interim results or the final implementation of certain activities, such as submission and endorsement of studies, incorporation of inputs into the draft Decentralization strategy, community profiles and local development strategies, projects’ proposals, etc. Usually these meetings are accompanied by records (written minutes, shared with all relevant stakeholders, including the State Chancellery).

In 2011, UNDP was subject to UNDAF and ADR evaluation in which the JILDP important contribution to the achievement of the Outcome 3 “By 2011, vulnerable groups in poor rural and urban areas take advantage of sustainable socio-economic development opportunities through adequate regional and local policies implemented by Local Public Authorities (LPAs) and partners” has been mentioned.

- RESULTS

Overview

In accordance with its yearly objectives, in 2011 JILDP supported national and local stakeholders with the required instruments and tools to undertake the promotion of the decentralization reform in the Republic of Moldova:

- Though the 2011 local elections have hampered the many processes related to local governance and development, the Government has made notable progress in moving the decentralization agenda forward with JILDP support. On December 28, 2011 the Decentralization strategy was approved by the Government and was submitted to approval by the Parliament. Before its submission a nationwide consultation process was organized with programme support, involving over 2400 participants. The implementation of the Decentralization strategy has started with the creation of sectoral working groups with particular focus on fiscal and property decentralization.

- Following the local elections in 2011, the Government has launched the National training programme for the 12,000 elected officials with more than 9,000 been trained with assistance granted by JILDP. Building on the successful experience from 2007, newly elected officials got knowledge and expertise in local public administration fundamentals, the decentralization process, as well as the application of human rights and gender equality principles in local affairs. The Academy of Public Administration served as a knowledge hub for this national initiative.

- For the first time since the independence of Moldova, a large, active and dynamic national association LPAs, the Congress of Local Public Authorities (CALM) is emerging to play an important role in pushing the decentralization process forward. Also for the first time in Moldova, a Network of Women Mayors was created under CALM’s aegis with JILDP assistance.

- 70 communities (10 urban and 60 rural) have been supported to elaborate their local development strategies following the community mobilization for empowerment approach, responsive to the needs, which had been jointly identified with communities. 21 communities initiated community initiatives to address the key development priorities, such as: improved social services, access to education services in schools and kindergartens, diversifying services and access to community centers, public illumination, safer roads and ensuring means for transportation for vulnerable, improving access to quality water etc.

- The first Gender Equality Coordination Meeting “Gender Equality in Local Development” was organized in Transnistria.  By launching the quarterly GE Coordination Meetings in Transnistria, the JILDP aims to support the CSOs, women’s and other groups working with the rights of vulnerable groups (single mothers, persons with disabilities, older persons etc.) in creation of a sustainable coordination and information sharing mechanism on gender equality and women rights.

Programme Outputs

Output 1.	National legal, policy and advisory frameworks developed to support sustainable development at sub-national levels with a special focus on Human Rights and Gender Equality.

  - Strengthened Government’s and Parity Commission’s capacity to carry out the decentralization reform:

- 2 operational working groups on financial and property decentralization were supported by JILDP. They are hosted by the Ministry of Finance and the Ministry of Economy respectively. The working groups benefited from international expertise in problem analysis, policy options and legal amendments formulation, which will serve as a basis for decision-making.

- As a result of the technical support offered to the Government, 5 more working groups on sectoral decentralization were created in the education, health, environment, communal services and e-government fields, which are expected to be the Government’s main leverages for carrying out the decentralization reform in the respective fields.

- A functional Parliamentary commission, with weekly well organized and documented meetings was supported by JILDP. The Parliamentary commission engaged for the first time in a direct public consultation process on decentralization in the countryside (4 meetings).

- JILDP supported the participation of 3 key civil servants with key responsibilities in the decentralization reform process from State Chancellery in training programs of reputable national (APA) and international (LGI/CEU, ISP) institutions.

1.2 Consultancy and support for local governance and policy development was ensured by implementing the following activities:

- A qualitative and quantitative sociological study on women and men representing vulnerable groups in local development was conducted to improve understanding of gender and human rights concerns and root causes of vulnerability in the JILDP pilot localities.

- The Chart of Local and Central government responsibilities was drafted and presented to decentralization working groups which after being amended, will be used as a basis for decisions on administrative and financial decentralization.

- An analysis of the current legislation on local governance was carried out and supporting documentation for submission of proposed changes to the Parliament was drafted, which will bring existing legislation in line with the Decentralization Strategy and HR and GE commitments.

- An assessment of national statistical data disaggregated by gender, territory, age and other factors of marginalization, vulnerability and exclusion, was undertaken to serve as a building stone for the monitoring and evaluation framework of the National Decentralization Strategy.

1.3	Facilitating the exchange of information and capacity building of all JILDP partners in the decentralization process by implementing the following activities:

- 2 rounds of public debates on the Draft National Decentralization Strategy with over 2,400 participants were conducted. The recommendations collected were compiled and included in the final Draft Strategy, approved by the Government on December 28, 2011.

- A knowledge product, the Guidebook for the Newly Elected Officials, was produced to increase knowledge of the newly elected officials on their responsibilities, rights and legal requirements, local policy making, ethics and local development, etc. The guide was published in 12,000 copies, in Romanian and Russian languages. In this regard, a partnership with the APA was initiated. The training was conducted for more than 9,000 local elected officials during 348 one-day training sessions.

- JILDP cooperated with the East-East Partnership without Borders Program of OSI to facilitate sharing of experience between Moldovan, Polish and Latvian stakeholders through 2 study visits to Poland and Latvia and an international conference on decentralization in Chisinau.

- A communication strategy for the National Decentralization Strategy containing main actions in communicating about the decentralization reform to various groups was drafted and submitted to Government for endorsement and implementation.

Output 2: Capacities of LPAs in the target regions improved to plan, implement, and monitor local development plans in a participatory, rights based and gender responsive manner.

2.1   Support 10 target towns in developing the SE development strategies based on HRBA

- By receiving a comprehensive JILDP technical assistance packages, 10 out of 32 towns - rayonal centers of Moldova succeeded to initiate, elaborate and approve their socio-economic development plans in full accordance with the HRBA and GE principles.

- The implementation of this innovative approach has been supported by strengthening the national consultancy capacities in the field: the staff of 10 most representative Moldovan consultancy entities (specialized in facilitation of local planning) have been trained and skilled in local development based on HRBA and GM.

- By the end of the year, 5 towns already initiated the implementation of projects granted by JILDP (Telenesti–sewerage system, Calarasi and Nisporeni–extending public lighting, paved path to schools and kindergarten, Hancesti–children playgrounds).

2.2. Develop institutional capacities of 10 target rayons and towns

- 73 target LPAs from South, Central and North regions of Moldova have been supported to draft, approve and initiate the implementation of their institutional development plans. Within this context, LPAs have been guided to implement their institutional priorities through small grants.

- An innovative Guide on HR based and Gender Sensitive Local Development Planning, Budgeting, Implementation, Evaluation and Monitoring has been developed and adapted to the Moldovan development context. The new toolkit has been used to train a large pool of national experts in the field and was disseminated to both LPAs and NGOs specialized in the field.

- 70 pilot LPAs received five Knowledge products (KPs) on human rights and gender equality in decentralization and local development, translated into Romanian to assist them in their daily operations and quality service provision.

2.3. Support for improvement of local public services and utilities management

- Following the Governmental priority to promote the IMC as an important tool in territorial reorganization, a comprehensive Legal Assessment has been carried out aiming to evaluate the permissibility, constrains and limits of the legislation of the Republic of Moldova related to IMC.

- JILDP prepared and delivered a 5 day-TOT on IMC to build local capacities to support target communities in initiating IMC projects (over 20 national experts trained in IMC tools and mechanisms). In order to ensure a comprehensive methodological support in the field, JILDP adapted the ‘IMC Toolkit Manual’ (elaborated by UNDP, LGI and CoE) to the context of the Republic of Moldova and translated it into Romanian, to be published and be widely distributed.

- The Chisinau Municipality has been supported to elaborate and launch the Information System on Urbanism and Land Management, thus ensuring full transparency and quick access of citizens to city land database.

2.4. Support for Association of Mayors

- Within the context of consistent JILDP granting, the Congress of Local Authorities from Moldova (CALM) ensured its institutional and organizational strengthening: fully equipped office, professional and skilled team, internal decision making procedures elaborated, functioning informational tools (web page, newsletter), and financial sustainability building measures.

- In cooperation with Czech Trust Fund, an internal platform has been developed to support CALM be effectively involved in the national decentralization and public administration reform process.

- The JILDP technical support, capacity development and advocacy resulted in establishment of the Women’s Network of Mayors and Local Councillors as a part of CALM. The launch of the Women’s Network was preceded by a series of capacity development events attended by 157 women-mayors, local councillors, LPA secretaries etc.

Output 3: Rural communities and CSOs are empowered to actively participate in planning, implementation and monitoring of local development initiatives in rights based and gender sensitive manner; while local actors are able to deliver services and upgrade the basic infrastructure

3.1. 	Mobilization of the target communities for community-led rights based and gender sensitive development

- A highly participatory community profiling exercise, which in addition to demographic, social and economic analysis implied identification of human rights and gender equality concerns, was accomplished in 60 pilot communities. To attain this, JILDP organized 224 community meetings with a variety of community groups and a particular focus on vulnerable.

- LPAs in 60 pilot communities elaborated rights-based and gender responsive local socio-economic development strategies responsive to the needs, which had been jointly identified with communities.

- Information community centers in 9 pilot villages developed action plans for improving access of vulnerable groups to their services: information services, computer literacy courses, IT technologies trainings, project cycle, effective communication, resource mobilization and other trainings.

3.2 Improving the capacities and knowledge of community actors on local development based on HRBA and gender equality are improved

- 6-day ToT on community-led local development and planning, using an HRBA and GE perspective was conducted for 30 representatives of the partner NGOs, thus strengthening local capacity HRBA and GE planning.

- JILDP supported the Government in the organization of The European Local Democracy Week (ELDW) on the topic “Human Rights and Gender Equality at the Local Level”. The National Conference on “Local public Authorities in promoting human rights and GE at local level” for more than 90 representatives of LPAs and Government; round tables and Open day doors organized in 12 villages and towns around Moldova; school children essay contest with 2 topics: "If I were mayor ...” and “If it my girl- classmate were a mayor” in 10 villages/town; launch of the special postal series of envelopes and stamps with the logo of the ELDW-are worth mentioning.

3.3	Support community-led human rights and gender sensitive monitoring and evaluation of local Social-Economic Strategies and Action Plans

- To ensure consistency in the community mobilization and empowerment initiatives, JILDP commissioned the elaboration of a Guide on Community Mobilization for Empowerment (CME). A 4-day Training of Trainers on Community Mobilization for Empowerment was conducted for 22 members of 4 partner NGOs

3.4	Support the human rights based and gender sensitive local development projects

- 14 communities initiated community project initiatives and received first instalments of the grants to address the key development priorities identified during the community profiling exercise. The key areas covered by the community projects were: improved social services, improving access to education services in schools and kindergartens, diversifying services and access to community centers, public lightening, safer roads and ensuring means for transportation for vulnerable, improving access to quality water etc.

Output 4: Communities and CSOs in Transnistria region of Moldova, as well as in the Government control area of the security zone of the Transnistria region, are empowered to actively participate in local development initiatives in rights based and gender sensitive manner; citizens has better access to information and basic services.

4.1. Target communities are mobilized for community-led gender and human responsive development

- JILDP has accomplished preparatory activities, such us approval of this communities by the Steering Committee  (Bicioc, Grigoriopol region; Hrustovaia and Kuzmin, Kamenka region); selection of partner NGO from Transnistria, to support local communities in the implementation of three gender equality and women’s empowerment local development initiatives for the 3 pilot villages in Transnistria.

4.2 Capacities and knowledge of community actors on local development based on HRBA and gender equality are improved

- 20 representatives of CBOs and NGOs from Transnistria have improved their knowledge about the gender aspects of local development initiatives and developed their skills for gender analysis, gender mainstreaming, gender-responsive budgeting and women’s empowerment for participatory, non-discriminatory and transparent local development. A 3-days Training of Trainers “Gender Mainstreaming and Women’s Empowerment in Local Development” was conducted by Ukrainian Women's Fund.

- More than 30 representatives of the Transnistrian NGOs, government institutions and development partners took part in the first Gender Equality Coordination Meeting in Transnistria “Gender Equality in Local Development”.

4.3 The implementation and monitoring of gender sensitive Local Development Programs in pilot communities is being supported

- 11 target communities from Security Zone and 16 communities from Transnistria, which started the project initiatives in 2010, have finalized their implementation. These initiatives in particular refer to the improvement of community services on: education, sport, public leisure activities and health, for local people, and in particular for vulnerable groups: children, elderly, women, youth etc. and to creation of community centres aimed to strengthen capacity of the communities to provide access of community people to information, counselling, cultural and extracurricular education.

Lessons learned:

- Constant efforts and increased resources should be directed to the institutional capacity building for decentralization. Given the importance of the reform, the assistance should be still focused on building understanding among the main actors of the implications of the decentralization reform, built in mechanisms and of the need to mainstream the HR&GE approach into the reform core actions, i.e sectoral policy interventions, training activities, local development initiatives, etc.

- Consolidated efforts with central authorities and development partners to promote and build IMC capacity are necessary. Inter-municipal cooperation is a key element in a high-quality and efficient service provision. Improvement of local public service activities shall be in line and respond to development trends and actions from the draft Decentralization strategy and the Government Action Plan, but still local capacity on IMC is very limited.

- Community empowerment should be treated as a key element for local development initiatives along with local governance and services. In Moldova, the evidence on how the most vulnerable people are affected by the local development indicates that such groups still face significant challenges at the local level. In this regard, it is clear that unless the decentralization reform includes specific measures to mainstream human rights, gender, and ensures participation of the vulnerable groups in it, the progress remain minimal.

- Considering the specific context in Transnistria, a tailored-made approach for community processes is required and a strong cooperation with other development initiatives in Transnistria is needed. Use of simplified community mobilisation procedures in identifying community development priorities, strategic planning, monitoring and evaluation processes will continue to be the main tools applied in Transnistria. Coordination with other development interventions will ensure complementarity in actions and will avoid overlapping.

# FUTURE WORK PLAN

Based on the results of JILDP implementation during the inception phase, as well as the consultations held with the governmental counterparts, a number of adjustments were introduced into the Programme Document in 2011:

- Adapting technical assistance activities to implement the action plan set out in the draft Decentralization strategy, and responding to the increased volume of activities.

- Specifying and quantifying performance indicators, target outcomes and specific tasks for programme implementation.

- Adjusting the organizational frame and required costs to implement planned activities.

The main amendments targeted the detailing of implementation tools, reduction in number and specification of target beneficiaries. In this essence, considering the main directions from the draft Decentralization strategy, JILDP will focus further its support only on small and medium-sized towns to plan and implement local socio-economic development activities. District councils will be involved at the stage of promoting and implementing IMC, as implied by the need for the administrative reorganization. As per Government request, support to the National training programme for local elected officials after local elections in June 2011, has been granted. Nevertheless, these adjustments do not affect essentially the Programme objectives, main activities and results.

The following main activities and expenditures are planned as per approved 2012 Annual work plan:

| Outputs | Activities | Planned budget, USD |
| --- | --- | --- |
| 1. National legal, policy and advisory framework | 1.1 Develop Government capacity and relevant Parliamentary Commissions for policy analysis, formulation and implementation | 46,000.00 |
|  | 1.2 Provide policy advice, analysis, research and support for elaboration of policies and improvement of legislation | 149,910.40 |
|  | 1.3 Support information sharing, knowledge management and capacity building on decentralization | 34,500.00 |
|  | 1.4 Awareness and Communication | 20,134.20 |
|  | 1.5 Management | 128,966.44 |
|  | Total (+7% GMS) | 406,076.81 |
| 2. Capacities of LPAs | 2.1 Social and Economic Development Strategies of 10 Towns developed and implemented | 241,262.00 |
|  | 2.2 Capacity of 10 Target Rayon’s and Towns developed | 4,000.00 |
|  | 2.3 Support for improvement of local public service and utilities management | 21,500.00 |
|  | 2.4 Support for Association of Mayors | 40,444.65 |
|  | 2.5. CTA/National consultants/management | 197,963.69 |
|  | Total (+7% GMS) | 540,532.26 |
| 3. Empowerment of rural communities and CSOs | 3.1 Target communities mobilized | 116,367.32 |
|  | 3.2 Capacity building & knowledge transfer to target communities | 122,503.00 |
|  | 3.3 Support the development of an information, monitoring and evaluation system | - |
|  | 3.4 Support to local development projects | 730,751.32 |
|  | 3.5 CTA/National consultants | 203,234.04 |
|  | Total (+7% GMS) | 1,254,955.58 |
| 4. Transnistria and Security Zone | 4.1 Communities mobilization | 46,171.20 |
|  | 4.2 Capacity building & knowledge transfer | 39,334.20 |
|  | 4.3 Support local development projects | 91,696.20 |
|  | 4.4. CTA/National consultants | 12,000.00 |
|  | Total (+7% GMS) | 202,445.71 |
| TOTAL | 2,404,010.36 |

|  | Performance Indicators | Indicator Baselines | Planned Indicator Targets | Achieved Indicator Targets | Reasons for Variance (if any) | Source of Verification | Comments (if any) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome To create (1) at policy level an enabling environment in Moldova for democratic local governance and community-led development through a facilitative policy, legal framework and institutionalized participatory, accountable, equitable local governance practices; and (2) at community level self-sustaining processes of social, economic and environmental development. |
| Output 1 National legal, policy and advisory framework | Capacitated institutional framework for decentralization | Institutional framework partially functional | Parity Commission Working groups set up and functional | 5 Parity Commission Working groups in line ministries created |  | -The Minister’s Orders -Minutes of Working groups meetings |  |
|  | Road-mapped decentralization reform | Primary draft for decentralization vision | Strategy consulted and submitted to the Parity Commission | Draft Decentralization Strategy approved by Government |  | Government Decision from 28.12.2012 |  |
|  | # of trainings on decentralization in HRBA and GE manner | No HRBA and GM training | - At least 4 training events on decentralization, including 3 integrating HR & GE approach | - Guide for local officials revised and published - 348 one-day training events for more than 9,000 newly elected local officials |  | - Guide published - Training attendance and evaluation forms |  |
|  | # of debates on decentralization organized | 5 debates on decentralization organized | At least 10 national debates organized | - 25 debates on the Draft Decentralization Strategy with over 2,400 participants - 4 consultations by Parliamentary Commission on Decentralization |  | - Meetings attendance records -Mission reports -Minutes of meetings |  |
|  | # studies on decentralization aspects deriving from the Decentralization Strategy, including HR and Gender dimensions | Limited No studies on Decentralization, including HR/GE aspects | At least 3 studies deriving from the Decentralization Strategy | 4 analysis designed: - Sociological study on equal access to local services of the most vulnerable group - International experience in fiscal decentralization - Foreign experience in property decentralization - Chart of LPA responsibilities |  | Final reports and studies presented and discussed in the working group sessions |  |
|  | Communication and awareness raising strategy designed and launched | No Communication Strategy for the Decentralization Reform | Draft Communication Strategy | - Draft Communication Strategy developed |  | -Draft Communication Strategy |  |
|  | # of awareness raising and communication events organized | Limited number of communication events on Decentralization strategy | 15 awareness raising and communication events organized | - 33 radio, 2 TV shows, 72 articles in local and national newspapers on decentralization issues |  | - Radio and TV websites, local and national newspapers |  |
| Output 2 Capacities of LPAs in the target regions improved | # of towns with approved HR and gender responsive Social and Economic Development Strategies | No urban LPAs with gender sensitive and HRBA development strategies | Social and Economic Development strategies elaborated in 10 towns | 10 towns with approved HR and gender responsive Social and Economic Development Strategies |  | - Local Councils decisions on plans’ approval - Approved yearly programme report |  |
|  | # of LPAs supported to implement their capacity development plans (CDP) | 73 LPAs with difficulties in implementing CDP | Support 73 of LPAs to implement CDP | Support to the implementation of CDP granted to 73 LPAs from South, Central and North regions of Moldova |  | - CPD implementation reports in 73 LPAs - Approved yearly programme report |  |
|  | LPA capacity assessment methodology elaborated | No methodology available in Moldova | LPA Capacity Assessment Methodology elaborated | Adapted LPA capacity assessment methodology |  | Draft methodology in Romanian language |  |
|  | Association of LPAs supported | Limited institutional cooperation between LPAs | Self-sustainable and functional LPAs Association | Congress of Public Authorities is a self-sustainable and functional LPAs Association |  | - CALM 2011 Yearly Activity Report |  |
| Output 3 Rural communities and CSOs are empowered to participate in local development initiatives in rights based and gender sensitive manner | # of representatives of local NGOs trained | Limited capacities of NGOs to conduct community mobilization at local level | 1 TOT on Community Mobilization for Empowerment conducted | 22 representatives of Moldovan NGOs took part in 4 days ToT on Community Mobilization |  | Training toolkit, ToT reports, list of participants, evaluation questionnaires |  |
|  | # of communities conducted rights based and gender sensitive analysis of communities | None of the communities have conducted rights based and gender sensitive analysis | 70 communities mobilized and action plans made in a HRBA and GE manner | 70 communities accomplished the participatory community profiling process |  | Community Profiles |  |
|  | # of community meetings organized to sensitize communities on community-led development | 0 communities meetings in target communities | 140 debates organized | 224 community meetings organized |  | Agenda of the meetings, Lists of participants |  |
|  | # of Human Rights and Gender Equality Based Socio-Economic Strategies developed | 0 Strategic Plans incorporating Human Rights and Gender Equality Based | 60 Human Rights and Gender Equality Based Socio-Economic Strategies developed | 60 Human Rights and Gender Equality Based Socio-Economic Community Development Strategies developed. councils |  | Decisions of Approval from the local councils |  |
|  | # of Community Organizations or community information centres supported | No community centers with action plans for improving access of vulnerable groups to services |  | 9 information community centers in 9 villages developed action plans for improving access of vulnerable to services |  | ToRs List of supported centers Action Plans |  |
|  | # of trainings on inclusive, transparent, accountable, gender sensitive and non-discriminative local development for community actors | Limited capacities of community actors in HRBA development | 70 trainings provided to LPAs to 700 stakeholders by types: CSOs, private sector, population, including 50% women, 20% vulnerable groups) | - 92 local trainings provided to1319 community actors including 65% women - 122 workshops conducted for 1524 persons representing vulnerable groups One 6-day ToT on community-led local development using HRBA and GE approach conducted for 30 NGO participants |  | ToT Agenda Lists of participants Agenda of the trainings Trainers’ report Lists of participants Workshops and meeting reports, lists of participants Lists of group members |  |
|  | #community Programs initiated in a rights based, gender sensitive manner | No community programs in a rights based, gender sensitive manner | 40 community Programs initiated in a rights based, gender sensitive manner | 14 communities initiated community Programs in a rights based, gender sensitive manner | Due to longer community mobilization cycle, the rest of programs were postponed for 2012 | Project files Grant Agreements Project Evaluation Minutes |  |
| Output 4 Rural communities and CSOs in Transnistrian region are empowered to participate in local development | # of representatives of local NGOs trained | Limited capacities of Transnistrian CSOs in integration of Gender Equality local development | 1 TOT on GE local development conducted for 15 CSOs | 22 representatives of 14 Transnistrian CSOs took part in TOT on GE local development conducted |  | TOT report, list of participants |  |

# Footnotes

Strategic Results, as formulated in the Performance Management Plan (PMP) for the PBF; Sector for the UNDG ITF.

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval by the relevant decision-making body/Steering Committee.

All activities for which a Participating Organization is responsible under an approved MPTF programme have been completed. Agencies to advise the MPTF Office.

For PBF: Either country relevant or PMP specific.

# Text boxes

VI. INDICATOR BASED PERFORMANCE ASSESSMENT