|  | Sierra Leone Project Progress Report |
| --- | --- |
| Project Symbol | Project Title | Reporting Period |
| UNJP/SIL/037/UNJ | Capacity Development for SCP Strategic Planning and Economic Analysis Team | May-November 2011 |
| Donor | Government Partner Agency |
| Government of Australia, AusAid | Ministry of Agriculture, Forestry and Food Security (MAFFS) |
| Budget Holder | Lead Technical Unit | Starting Date | NTE Date | Project Budget |
| Gabriel Rugalema | TCIA | 1 May, 2011 | 30 April, 2014 | USD 1,503,711 |

SEMI-ANNUAL REPORT

Note: The present report describes project start-up activities prior to the designation/recruitment of the SCP Strategic Planning and Economic Analysis (SPEA) Team and the entry on duty of the International Economist. Subsequent progress reports will be based on the project work plan to be prepared by the SCP SPEA Team and focus on the results achieved during the reporting period.

A.	Background

The lack of qualified human resources at both national and local level due to insufficient training and professional opportunities is a critical factor slowing development efforts in Sierra Leone. The project will develop the capacity of the Ministry of Agriculture, Forestry and Food Security (MAFFS) staff at both national and district levels for the efficient implementation of the Government’s Smallholder Commercialization Programme 2009-2014 (SCP - hereafter referred to as the Programme). Specifically, the project will strengthen the human and institutional capacity of MAFFS for strategic planning and economic analysis and thereby improve the effectiveness and impact of the SCP. (See Annex 1: Project Overview).

The expected Outcome of the project is that National MAFFS and SCP Secretariat staff and district government officials effectively support the strategic planning and implementation across SCP Components, including National and District Council level.

The project has three expected Outputs:

- Strategic investment plans based on economic and technical studies prepared for each district, focused on key commodities targeted by the SCP.

- Human and institutional capacity improved at national and district government levels for strategic planning and economic analysis.

- Mobility and physical information and communication technology capacity at national and district SCP coordination units improved.

B.	Main Activities undertaken during the Reporting Period

- Introduction of the Project to National and District Authorities and Counterparts

- Recruitment of the International Economist (Strategic Planner)

- Procurement of Vehicles and Equipment

- Project Start-up Support Mission by FAO Lead Technical Officer

- Establishment of the Strategic Planning and Economic Analysis (SPEA) Team

- Establishment of the Project Governance Structure

- Introduction of the Project to National and District Authorities and Counterparts

MAFFS and FAO have introduced the project to national and district authorities to prepare the ground for successful project implementation. To this effect, several meetings have been organized by the SCP Secretariat to present the project to MAFFS staff and development partners in Freetown. In addition, consultation meetings were organized in Freetown and Bo District for all District Agricultural Officers (DAOs) to: (i) solicit DAOs’ support to and participation in the project implementation process; and (ii) review the District Agricultural Office Capacity Audit Report, which was prepared by the Africa Governance Initiative (AGI) in collaboration with MAFFS, and discuss its implications for the implementation of the project. The meetings were instrumental for planning the next steps and laid the foundation to the effective implementation of the project.

- Recruitment of the International Economist (Strategic Planner)

The recruitment process began in June 2011 when the vacancy announcement (VA) was approved by FAO. As the first VA only attracted a limited number of applicants, it was not possible to establish a shortlist of qualified candidates. Consequently, the VA was re-issued and more widely distributed. The recruitment process has now been concluded. The International Economist visited FAO HQ for briefing from 28 Nov. to 3 Dec. 2011 and is expected to report on duty in Freetown on 9 January 2011.

- Procurement of Vehicles and Equipment

In order to enhance mobility and access to Information and Communication Technology (ICT) for effective implementation of the project, the following equipment has been procured and will be distributed once the SCP SPEA Team is established (see point 5 below):

- ICT equipment

- 15 Desktop Computers

- 10 Laptop Computers incl. Bags

-  3 Multifunction Printers

-  15 Laser Jet Printers

-  20 Communication Headsets

- Vehicles

- 4 Four-Wheel Drive Station Wagons

- Project Start-up Support Mission by FAO Lead Technical Officer (LTO)

The LTO Mr. Thomas Muenzel, Senior Economist, FAO-TCIA, visited Sierra Leone from 24 October to 4 November 2011 to provide project start-up support. He worked closely with senior MAFFS staff, in particular the Director of the Planning, Evaluation, Monitoring and Statistics Division (PEMSD) and the SCP Coordinator who will both play a key role in project implementation. On 2 November, the mission organized a brainstorming session for District Agricultural Officers (DAOs) in Bo to discuss the recommendations of the District Agricultural Office Capacity Audit Report, specifically regarding the district agricultural strategy, district work-planning and the next steps. The following outputs were delivered during the mission (see Annexes 2 and 3):

- Revised project outcome and outputs;

- A work plan until end of 2011;

- A list of main stakeholders involved in planning of government agricultural interventions  to be used as a basis for identifying functions/responsibilities and capacity development needs;

- An outline of proposed next steps to implement the recommendations of the District Agricultural Capacity Audit focusing on the district agricultural strategy and work-planning; and

- A template for comprehensive annual work-planning, budgeting and monitoring of Government-supported agricultural interventions at district level.

The mission outputs were discussed at a wrap-up meeting held in MAFFS Freetown on 3 November 2011, which was chaired by the MAFFS Director General and attended by MAFFS Senior Management, FAO Programme Officer and International Experts from ODI and VSO seconded to PEMSD.

- Establishment of the Strategic Planning and Economic Analysis (SPEA) Team

In consultation with the Government, it has been agreed to establish a Strategic Planning and Economic Analysis Team within MAFFS which shall have the following membership:

At MAFFS (National) level:

- Director, Planning Evaluation Monitoring and Statistics Division (PEMSD)

- Six staff of the Planning Unit of PEMSD

- Two PEMSD Unit Heads (Monitoring &Evaluation Unit and Statistics Unit)

At District level (13 Districts):

- District Agricultural Officer (DAO)

- Monitoring &Evaluation Officer

- District SCP Economist (to be recruited under the SCP)

SCP Secretariat:

- Coordinator

- Monitoring &Evaluation Officer

- International Economist (Strategic Planner)

It is expected that all SPEA Team members will be assigned/recruited against agreed Terms of Reference to be developed by MAFFS in consultation with FAO. The recruitment process is expected to be completed by end of January 2012. Under this arrangement all districts shall have an Economist working under the supervision of the DAO and the SCP Secretariat.

- Establishment of the Project Governance Structure

The following two committees have been set up to oversee project implementation:

- FAO Project Task Force

- Gabriel Rugalema, Representative, FAOSL

- Thomas Muenzel, Senior Economist, Lead Technical Officer, TCIA

- Pamela Pozarny, Rural Sociologist, TCIA

- Marc Fantinet, Senior Economist, TCIA

- Giulia Calcagnini, Operations Officer, TCEO

- David Kahan, Senior Officer, AGS

- David Mwesigwa, Programme Officer, FAOSL

- Chakib Zouaghi, International Economist, FAOSL

- Joint Project Management Committee

- Sarah Willis, Development Secretary, Australian High Commission, Accra, Ghana

- Thomas Muenzel, Senior Economist, Lead Technical Officer, FAO-TCIA

- Prince Kamara, SCP Coordinator, MAFFS

- Gabriel Rugalema, Representative, FAOSL

- David Mwesigwa, Programme Officer, FAOSL

- Fatouma Seid, Liaison and Operations Officer, FAO-TCEO

- Chakib Zouaghi, International Economist, FAOSL

The Task Force will deal with day to day operational issues particularly those internal to FAO, while the Management Committee will focus on policy issues. It shall serve as a platform for consultation between the Government of Sierra Leone (GoSL), Australian Government and FAO in matters related to the project.

Annexes

1	Project Overview

2 	Project Start-up Support Mission - Assignment Summary Report

3	Main Outputs from Project Start-up Support Mission

4	Curriculum Vitae of three shortlisted candidates for the post of International 	Economist (Strategic Planner) [on file]

Annex 1: 	Project Overview

Smallholder Commercialization Programme (SCP)

Development Goal: Rural poverty and household food insecurity reduced on a sustainable basis leading to stronger national economy

| Component 1 Smallholder Agriculture Commercialization: Production Intensification, Diversification, Value Addition and Marketing | Component 2 Small-scale Irrigation Development | Component 3 Market Access Expansion through Feeder Road Rehabilitation | Component 4 Smallholder Access to Rural Financial Services | Component 5 Strengthening Social Protection, Food Security, and Productive Social Safety Nets |
| --- | --- | --- | --- | --- |
| Outcomes: Smallholders have increased production, intensification, value addition, and marketing, and reduced rates of post harvest losses Agricultural Business Centres (ABC) in 13 rural Districts established and operating sustainably through self-financing MAFFS extension service and research (SLARI) staff effectively support smallholder commercialization | Outcome: Small-scale irrigation expansion/develop-ment raises levels of smallholder rice production and increases food security, incomes and employment opportunities | Outcome: Rehabilitated roads enable increased market access stimulating smallholder/ABC commercial activities and increased incomes | Outcome: Access of smallholders and the rural poor and their organisations to rural financial services geared to their needs | Outcome: 30 % of food insecure households in the country supported in meeting basic food security and nutritional needs (needs to be rephrased at it is output level) |

Component 6 SCP Planning, Coordination, Monitoring and Evaluation

Outcome: Effective strategic, operational planning, efficient coordination and monitoring of the SCP is ensured

| AusAID/UN Joint Programme – UNJP/SIL/037/UNJ: Capacity Development of SCP Strategic Planning and Economic Analysis Team |
| --- |
| Outcome: National SCP Secretariat staff and district government officials effectively support the strategic planning and implementation across SCP Components, including National and District Council level |
| Output 1: Strategic investment plans based on economic and technical studies prepared for each district, focused on key commodities targeted by the SCP | Output 2: Human and institutional capacity improved at national and district government levels for strategic planning and economic analysis | Output 3: Mobility and information and communication technology (ICT) capacity at district SCP coordination units improved |

Annex 2: 	Project Start-up Support Mission - Assignment Summary Report

Annex 3:	Main Outputs from Project Start-up Support Mission

Annex 4:	Curriculum Vitae of three shortlisted candidates for the post of 			International 	Economist (Strategic Planner) [on file]