RUNO ANNUAL PROJECT REPORT		TEMPLATE 4.4

PEACEBUILDING FUND (PBF)

ANNUAL PROJECT progress report

COUNTRY: Nepal

REPORTING PERIOD: 1 january – 31 December

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: Safeguarding Peacebuilding gains in Nepal: Support for Coordination, Planning, Monitoring and Evaluation of the UNPFN Programme Number (if applicable) PBF/NPL/H-1 MPTF Office Project Reference Number: 00094222 |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: UNDP (RC Office) |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: Ministry of Peace and Reconstuction (MoPR), including Nepal Peace Trust Fund (NPTF), Academic Organisations, NGOs and Consultants |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) UNDP: US$ 669,606 |  |  | Overall Duration (months) 18 months |  |
|  |  |  | Start Date (dd.mm.yyyy) 01.03.2015 |  |
| Government Contribution (if applicable) |  |  | Original End Date (dd.mm.yyyy) | 01.09.2016 |
| Other Contributions (donors) (if applicable) |  |  | Current End date(dd.mm.yyyy) 01.09.2016 |  |
| TOTAL: | US$ 669,606 |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Assessment/Review - if applicable please attach Yes No Date: Mid-Term Evaluation Report – if applicable please attach Yes No Date: |  | Name: Silla Ristimaki Title: Programme Specialist Participating Organization (Lead): RC Office Email address: silla.ristimaki@one.un.org |

PART 1 – RESULTS PROGRESS

  - Assessment of the current project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project is contributing:

Priority Plan Outcome to which the project is contributing. Functioning Secretariat

Priority Plan Outcome indicator(s) to which project is contributing. Governance of peacebuilding resources (including functioning UNPFN Executive Committee and Support Office Secretariat)

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  Effective and Gender sensitive management, coordination, monitoring, reporting, and evaluation of the UNPFN and the projects funded by it

Rate the current status of the outcome:

| Indicator 1: ExCom’s adopted management response following UNPFN evaluation addresses remaining peace building priorities Indicator 2: # of UNPFN projects translated into longer term programmes under UNDAF framework Indicator 3: # of partnerships between UN and government to implement common priorities related to women’s protection and participation | Baseline: None Target: A Management Response Plan with recommendation for addressing remaining peace building priorities (2016) Progress: Evaluation of technical and financial proposals for UNPFN Final Evaluation is on-going, the selected Firm will be on board by the end of November 2015. Reference Group members have been informed about a plan of action as per the group's TOR. Supportive activities (Environmental scanning and Research on youth and pb) to be launched shortly. Baseline: 0 Target: 02 projects (2016) Progress: Results of project end evaluations will be used to select the probable projects translating into longer term programmes. End evaluations are in progress. Advocacy on priority areas such as land, gender equality, empowerment including for NPTF funding are ongoing. Baseline: No formal partnership, only UNCT common messages on conflict related sexual violence approved Target: At least 02 partnerships between UN and government to address women’s protection and participation Progress: Roundtable on CRSV was instrumental to motivate the MoPR Secretary to seek to address the vulnerabilities of CRSV victims and suggest preparation of separate guidelines for providing services to CRSV victims. |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

1) UNPFN Independent Evaluation (2007-2015) was launched. Contracting of competent firm to conduct this evaluation is due to mid November. In addition, final evaluations of individual projects on going; reports due in December. 2) Support to GPI II projects: RFs and M&E plans reviewed and made more result oriented. Joint monitoring tools prepared. Gender mainstreaming strengthened. 3) Research proposal on youth and pb aligned with Amman Declaration developed. Non-violence day and UN day commemorated with youth (I Declare campaign). 4) Two conflict sensitivity orientations for UNCT organised. 5) Environmental scanning (Risk analysis) concept note prepared. 6) UN common position on CRSV used for advocacy. Mapped key laws related to CRSV needing revision. Related lessons from Bosnia being introduced to Nepal. 7) 'I am not a number' communication piece on UNPFN developed. 8) Capacity-dvpt activities planned.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

UNPFN support office strengthened the management, monitoring, evaluation, and reporting system for UNPFN and its projects. Constituting a well-oriented team with a shared workplan and goals was essential for increased support to pb projects in Nepal that have been particularly affected by the earthquake, restraining their implementation. Quality control through in-person meetings, formal and informal guidance, and review and feedback mechanisms resulted in improved coordination and management of the projects. The monitoring and evaluation plans for GPI II projects, enhanced planning and joint programming, improved project final evaluation TORs of at least 4 projects, including more focus on how to address gender and conflict sensitivity and document lessons learned and contribution in peace building, are related achievements.

Agreement among the UNPFN Executive Committee members on the scope and initiation of the evaluation was instrumental to move forward.

The UNPFN SO has also led coordination and seen visible results of the adoption of a harmonised approach towards government stakeholders to address conflict related sexual violence (CRSV). The Ministry of Peace and Reconstruction (MoPR) has begun to echoe some of the UN's key messages on CRSV, and are planning to prepare separate guidelines for providing services to CRSV victims. MoPR is also advocating to extend the NAP on UNSCRs 1325 and 1820 to address CRSV victims. This reaps positive impacts on peace building.

The advocacy efforts of the UNPFN SO on youth and pb, incl the joint UNFPA-UNDP-UNPFN commemoration of non-violence day, with global relevance following the Amman Declaration, have opened avenues for participation in for example UN Day advocacy, UN Youth group and SDG working group, opening opportunities for catalytic provision of evidence, ideas and networks for the longer-term UN work in Nepal.

The ‘I am not a Number’ communications peace developed to disseminate results of the UNPFN is generating attention for the importance of history and storytelling for reconciliation.

Efforts to document and share lessons learned have catalysed interesting potential partnerships between those working on women, peace and security and those working on gender in the earthquake response. Renewed attention to conflict sensitivity and need to build UNCT capacities on this is a similar example.

Therefore, the UNPFN Support Office substantially contributed to creating an enabling environment and facilitating the roles of partners in strengthening the peace process.

Despite recent political tension and unrest, deriving partly from remaining root causes of the conflict yet to be addressed, the theory of change for this outcome is still relevant and valid.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Nepal's earthquakes in April and May significantly hampered project implementation and delayed recruitments. In addition, recent political unrest has slowed down activities due to the sensitive environment. While the risk matrix has identified political unrest as low probability to occur with medium level impact, it occurred and continued. The fuel shortages have further restricted movement, participation and monitoring - and thereby all activities that demand this. UNPFN Support Office discusses challenges regularly with senior RCO management and closely monitores the situation.

As team members have come on board many activities have been advanced simultaneously to make up for lost time. The format of some activities has changed, also identifying new avenues for influence.

The project has taken stock of activities that have been completed and will revisit the work plan to assess whether a no cost extension will be needed. A review of the budget will similarly contribute to decisions about work plan revisions.

Outcome Statement 2:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Outcome Statement 3:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Outcome Statement 4:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender in the reporting period

| Evidence base: What is the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | Monthly update of annual work plan with entire team, six-monthly report, weekly team meeting notes, workshop and event completion reports, meeting minutes of progress review meeting with partners, etc. used as evidence for producing this report. Data and information validated by discussing with respective UNPFN Support Office team members, by analysis of activity implementation. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | With the promulgation of the Constitution, many voices are declaring the peace process as completed. The UNPFN is set to close by mid-2016. However, this needs to be a managed process to identify continuums for key root causes of conflict that remain to be addressed and new methodologies through which these can be addressed as part of the UN's longer-term work, thereby protecting peacebuilding gains achieved, and to document lessons and good practices for others. This funding has allowed for this work to take place. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | 1. The project has created an enabling environment to support the peace process and draw attention to root cause that remain to be addressed and/or other issues that should not be forgotten as part of the UN's long-term activities in Nepal. 2. Together with the four other organisations which the UNPFN Support Office (SO) coordinates in the CRSV Task Force, capacity, momentum and rapport built with the Ministry of Peace and Reconstruction has resulted in MoPR echoing some of the UN's messages on a community based approach to provide services to CRSV victims. MoPR has been proactive to ensure that work on addressing CRSV continues, noting their commitment to development of separate guidelines for addressing CRSV victims. Therefore, it is a good foundation for succeeding in efforts to ensure CRSV survivors are acknowledged and receive dedicated services in the future. Working at the same time with the Conflict Victims Common Platform, whose advocacy now has also begun to reflect CRSV issues means importance is also given to the issues by civil society and INGOs. 3. The long-term advocacy and capacity-bldg work has led to projects themselves initiating regular context analysis indicating an understanding of the value of conflict sensitive approaches. Close to 40 persons signed up for the CS orientations - though not many humanitarian response colleagues, indicating a gap in their understanding of the relevance of CS. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | The project is currently taking two innovative approaches: 1) For communications, telling the stories of real beneficiaries through annimation while building capacity of local artists/ annimators etc in 'I am not a number'; 2) Building connections between researchers in Nepal and Europe through a joint research project. |
| Gender: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | The original gender marker for the project is still valid. Importance of gender considerations is evident from the team composition of UNPFN support office, including two gender and pb officers. UNPFN always puts emphasis and dedicated comments on gender mainstreaming, gender disaggregated information, etc. for all documents, manuals, and guidance notes. Recently developed TORs for UNPFN Independent Evaluation and research proposals address a number of issues related to gender and women empowerment. |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) | Partly the extension of this project should also be linked to the potential extensions of the GPI II projects to ensure continued quality assurance and support until the end. Due to the higher than budgeted evaluation cost, the environmental scanning activity has been cancelled and the TORs will not be advertised. |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (250 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Effective and Gender sensitive management, coordination, monitoring, reporting, and evaluation of the UNPFN and the projects funded by it | Indicator 1.1 ExCom’s adopted management response following UNPFN evaluation address remaining peace building priorities | None | A Management Response Plan with recommendation for addressing remaining peace building priorities (2016) | Evaluation of proposals for UNPFN Final Evaluation is on-going, the Firm will be on board by November 2015. Reference Group members are aware about plan of actions as per their TOR. | The earthquake meant that firstly recruitment and secondly certain activities were delayed in their implementation. |  |
|  | Indicator 1.2 # of Project translated into longer term programme under UNDAF framework | 0 | 02 projects (2016) | Project end evaluations are ongoing - findings and recommendations will support selection of projects to translate into longer term programmes. Advocacy on key issues ongoing w donors. SO colleagues positioned in UN coord groups to advocate further. |  |  |
|  | Indicator 1.3 # of partnerships between UN and government to implement common priorities related to women’s protection and participation | No formal partnership, only UNCT Common messages on conflict related sexual violence approved | At least 02 partnerships between UN and government to address women’s protection and participation by 2016 | Roundtable on CRSV was instrumental to motivate the MoPR Secretary to suggest preparation of separate guidelines for providing services to CRSV victims and advocat for NAP 1325 extension focusing on this priority. | Earthquake took focus of government away from peacebuilding priorities. |  |
| Output 1.1 Strenghtened capacity of the UNPFN to provide technical assistance and quality control of the project with a focus on key peacebuilding, gender and M&E related issues | Indicator 1.1.1 Quality UNPFN executive committee (ExCom) annual report |  | 02 (1 for 2015, 1 for 2016) UNPFN ExCom quality annual reports submitted within deadline, quality of the report rated acceptable by PBSO review team | ExCom Annual Report submitted yet to be submitted. However, despite extensive involvement in the earthquake response, UNPFN Annual Report and project half-yearly reports finalised on time. |  |  |
|  | Indicator 1.1.2 Number of joint UN initiatives to promote addressing conflict related sexual violence |  | At least three joint advocacy and capacity building activities lead to initiatives from government side on providing relief/ reparation/ justice to CRSV. Any new project fully meets selection, including value for money criteria | 1 Govt stakeholder roundtable; MoPR committed to prepare a guideline to provide services to CRSV victims. UNCT report to SG on SV in conflict prepared. SO initiating capacity-building for UNPFN project staff on basis of a capacity assessment. |  |  |
| Output 1.2 UNPFN management and contribution to peacebuilding documented and evaluated to guide future programming priorities | Indicator 1.2.1 Timely quality UNPFN evauation | 0 | Evaluation completed, endorsed by the Reference group, with a management response from key stakeholders and results dissiminated | Evaluation of proposals completed; the firm will be on board by November. Reference group members are informed about their acitivites as per TOR. |  |  |
|  | Indicator 1.2.2 Evidence of UNPFN manual being used by other countries or the PBSO |  | # of UNPFN gender/conflict sensitivity manuals adopted or selection criteria used in other countries | Background work is in progress. Several initiatives to transfer lessons learned from UNPFN to others in Nepal (early recovery, M&E group members) ongoing |  |  |
| Output 1.3 Strengthen capacity for evidence- based gender and conflict sensitive approach to UN Joint transition programming | Indicator 1.3.1 UNDAF outcome level theory of change designed and monitored |  | At lease one UNDAF outcome level (8 or 9) ToC adopted with agreement on related indicators to monitor progress on it | Only a prelimianry discussion took place with UNDAF team | Given the time left before next revision of UNDAF in 2016, developing ToC at this stage might be questionable considering investment of resources. However, the project will discuss further with the aim of influencing the future UNDAF development. |  |
|  | Indicator 1.3.2 UN Risk analysis strenghtened |  | UNDAF reporting adopts outcome level risk analysis and management response reflects how it will impact UN programming | To provide basis for risk analysis, a concept note drafted on environmental scanning has been prepared; research on youth and pb launched; UNCT members are oriented with conflict sensitivity. |  |  |
| Outcome 2 | Indicator 2.1 |  |  |  |  |  |
|  | Indicator 2.2 |  |  |  |  |  |
| Output 2.1 | Indicator 2.1.1 |  |  |  |  |  |
|  | Indicator 2.1.2 |  |  |  |  |  |
| Output 2.2 | Indicator 2.2.1 |  |  |  |  |  |
|  | Indicator 2.2.2 |  |  |  |  |  |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | Involvement of government stakeholders in different activities from the beginning of any initiative can strengthen the relationship, generate ownership, and contribute in sustainability. Together with the four other organisations which the UNPFN Support Office (SO) coordinates in the CRSV Task Force, momentum and rapport has been built with the Ministry of Peace and Reconstruction. Calls to address CRSV have been heard from high level officials in government. Having a united UN message and commitment allows more efficient results to be achieved. The MoPR now motivated to prepare separate guideline for addressing the vulnerability of CRSV victims. |
| --- | --- |
| Lesson 2 (1000 character limit) | Gap in understanding found among implementing partners for a joint project due to lack of effective coordination. Coordination among multi partners (between national organisations, and between national and local organisations) can be instrumental to improve project results. Lack of explicitness on defining leading roles, coordination roles, authorities to make decision, incentives for better coordination at the beginning of the project etc. seems are influencing factors for weak coordination. Further investigation worth considering. |
| Lesson 3 (1000 character limit) | The follow-up to ensure projects complete their baselines within the first four months of project implementation should be more stringent. The lack of baselines causes many challenges (targeting, monitoring, reporting, evaluating including the cost-effectiveness) during project implementation. Baselines selected should try to link with existing data (even if then proxy indicators) and then also be monitored as part of broder UNCT processes (eg UNDAF, any information management unit) to ensure that peacebuilding is mainstreamed. |
| Lesson 4 (1000 character limit) | There are a lot of lessons to be learned from ensuring that peacebuilding work and humanitarian response learn from and build on each other's tools, capacities and knowledge when they occur in the same country/ area. Women's empowerment agenda for example should reflect complementarities between capacity-building of conflict-affected and/or disaster affected persons and response agencies. Also, advocacy around approaches such as conflict sensitivity should be much clearer on why they are also, and in particular, relevant in humanitarian emergencies when they occur in post-conflict contexts. |
| Lesson 5 (1000 character limit) |  |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

Through an UNDP-led inter-agency initiative, eight (8) members of the Common Victims Common Platform (CVCP) undertook a study tour to Bosnia and Herzegovina. The UNPFN funded activity enabled a peer-to-peer exchange on issues related to furthering transitional justice issues including access to justice, unofficial truth telling, memorialisation, and services to survivors of conflict related sexual violence (CRSV).

For one member of the CVCP, this presented a unique opportunity to meet with peers, individuals and organizations dealing with the consequences of CRSV. One of these organizations was Vive Zene, an NGO focusing on psychosocial assistance and support to victims of war, torture and violence. Ms. Suzdina Bijedic, a psychotherapist, provides care, compassion, dedication and commitment to supporting CRSV survivors. For the first time on the trip, one Nepali participant felt comfortable and brave enough to share her experience as a CRSV survivor. She talked about the stigma and discrimination faced by sexual violence victims in Nepal. Everyone in the room was visibly moved. Ms Bijedic could relate to the pain: in Bosnia and Herzegovina, CRSV survivors even 20 years after the conflict are dealing with stigma and discrimination from their families and communities. She explained that her NGO works with survivors to build their self-esteem and help them understand that it was not their fault and they are not to blame for what happened to them.

At the end of the session, the CRSV survivor met personally with Ms Bijedic, and like the relief that comes with unburdening a heavy load carried for a long time, she broke down and became very emotional when sharing the details of her experience. She had found an audience that was not judgmental, but that could relate and wanted to be supportive. She explained that the lack of dedicated services including psychosocial support in Nepal for CRSV survivors has more than taken its toll on survivors who bear the consequences of the experience every day of their lives. The burden is multiplied as a result of the lack of recognition from government, communities and families to victims of CRSV. She added she had never been expressly told that “it was not her fault and she was not to blame for what happened to her”; many survivors needed to hear these words.  In the context of Nepal where deeply embedded social and cultural norms dictate that women and girls are to blame for the sexual violence they experience, it was very moving to witness the positive impact of what simple but powerful words can offer to another person’s healing process.

This session emphasized for UNPFN the need to continue to advocate and work on all levels to ensure official recognition and comprehensive services for all CRSV victims. On the individual level, it showed the power of community, even across continents.

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures are on track, slightly delayed, or off track:

If expenditure is delayed or off track, please provide a brief explanation (500 characters maximum):

Financial expenditure (at October 2015) on some activities is delayed due to 1. the earthquake (particularly caused delays in recruitment and potential to ensure focus on pb projects); 2. the ongoing tensions in many target districts of the UNPFN, compounded by the fuel crisis that has restricted movement; and 3. with changes in government priorities, some activities have to be planned in the new context and environment

Please provide an overview of expensed project budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: Effective and Gender sensitive management, coordination, monitoring, reporting, and evaluation of the UNPFN and the projects funded by it |
| Output 1.1 | Strengthened capacity of the UNPFN to provide technical assistance and quality control of the project with a focus on key peacebuilding, gender and M&E related issues | RCO | 374,821 | 102,708 | Delay in recruitment of human resources (due to earthquake some canddates pulled out). Finance unit has also informed that some costs have been charged elsewhere; these are being reversed |
| Output 1.2 | UNPFN management and contribution to peacebuilding documented and evaluated to guide future programming priorities | RCO | 184,040 |  | Most of this budget (125,000USD) is for the UNPFN Evaluation and research. Both activities will be launched in 2015, though spending will only occur in 2016. |
| Output 1.3 | Strengthen capacity for evidence- based gender and conflict sensitive approach to UN Joint transition programming | RCO | 110,745 | 973 | Common costs (operational costs) have not been included. Actual costs are being prorated by finance unit and will be adjusted by end of Dec 2015. |
| Outcome 2: |
| Output 2.1 |  |  |  |  |  |
| Output 2.2 |  |  |  |  |  |
| Output 2.3 |  |  |  |  |  |
| Outcome 3: |
| Output 3.1 |  |  |  |  |  |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: |
| Output 4.1 |  |  |  |  |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total: |  |  | 669,606 | 103,681 (15%) |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when); or whether any changes are envisaged in the near future (2000 character maximum):

The UNPFN Support Office has managed to build up a new team, albeit after delays, that is well embedded in the overall RCHCO, as intended. This has resulted in joint initiatives (eg study tour to Bosnia with conflict victims together with UNDP and human rights colleagues of RCO and SO representing RCO in the SDG working group, ensuring continuity to address root causes of conflict via long-term UN programming, efforts to work with GenCAP advisor and humanitarian communications colleagues). Capacity-building efforts for UNCT, UNPFN projects and other colleagues (eg M&E working group mbrs) have been initiated. In this, links are also being formed with other PBF countries eg Bosnia.

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.