RUNO ANNUAL PROJECT REPORT		TEMPLATE 4.4

PEACEBUILDING FUND (PBF)

ANNUAL PROJECT progress report

COUNTRY: GUINEA BISSAU

REPORTING PERIOD: 1 january – 31 December

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: Strengthening security and stability in Guinea Bissau Programme Number (if applicable) MPTF Office Project Reference Number: 00091570 |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: UNODC |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: Government of Guinea Bissau, Ministry of Justice, Transnational Crime Unit, UNIOGBIS |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) US$ 500,000 |  |  | Overall Duration (months) 12 |  |
|  |  |  | Start Date (dd.mm.yyyy) 14/08/2014 |  |
| Government Contribution (if applicable) |  |  | Original End Date (dd.mm.yyyy) | 15/06/2015 |
| Other Contributions (donors) (if applicable) |  |  | Current End date(dd.mm.yyyy) 31/08/2015 |  |
| TOTAL: |  |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Assessment/Review - if applicable please attach Yes No Date: Mid-Term Evaluation Report – if applicable please attach Yes No Date: |  | Name: Jose Manuel Lopez Alvarez Title: UNODC Consultant (Transnational Organized Crime Expert) Participating Organization (Lead): ROSEN-UNODC Email address: jose.lopez.alvarez@unodc.org |

PART 1 – RESULTS PROGRESS

  - Assessment of the current project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project is contributing:

Priority Plan Outcome to which the project is contributing.

Priority Plan Outcome indicator(s) to which project is contributing.

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  National and potencially regional security is increased during a volatile political transition through effective intelligence gathering on drug-trafficking and organized crime by the TCU in collaboration with related law enforcement agencies.

Rate the current status of the outcome:

| Indicator 1: Use frequency of intelligence data base (overall and disaggregated per: TCU, LEA`s at national level and use for regional info sharing) Indicator 2: Perception of TCU and related LEA`s as having easy access to intelligence that is key to increase: a) operational effectiveness, b) effectiveness of strategic decision making and c) addressing immediate threats to security and stability Indicator 3: | Baseline: No info system in place providing basic intelligence on the status of drug trafficking and crime organization Target: 2014: Positive trend for each user group in the active use of intelligence database Progress: 20 TCU and other LEA`s pessonnel sucessfully computers trained (already achieved), SOP`s on intelligence gathering and informant handling developed, approved and implemented (already achieved). Baseline: N/A Target: 2014: Positive feedback from major user groups on the quality and relevance of intelligence for more effective decision-making (feedback disaggregated per a), b) and c)) Progress:Initiate exchanges with other TCU`s in the region (expected to be achieved in December), Start of the procurement process for the purchase of a 4x4 vehicle and surveillance equipment, payment of fuel (for the generator) and internet for the TCU HQ. Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Output 1.1: Intelligence data base established(Ongoing):Act 1.1.1: Training of TCU officers and other LEAs in data-base oriented criminal intelligence gathering and analysis(Ongoing) Act. 1.1.2: Technically set up database (Ongoing) Act. 1.1.3.:Delivery of a computer training for the TCU`s and other LEA`s (already achieved), Act 1.1.4.: Develop SOP`s on intelligence gathering and informant handling (already achieved)

Output 1.2: Inter-agency national and regional cooperation on drug trafficking and organized crime enhanced through database .Act. 1.2.1: Establish and develop informations excahnge systems between the TCU and other LEAs.Act 1.2.2:Develop Protocols for bilateral region cooperation. Act 1.2.3.: Initiate exchanges with other TCU`s in the region. Act 1.2.4 :  Joint Operations conducted by the LEAs , based on the intell gathering and analyzes. Act 1.2.5: On the job training and mentoring on intelligence led policing (Ongoing).

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

National and potentially regional security is increased during a volatile political transition through effective intelligence gathering on drug-trafficking and organized crime by the TCU in collaboration with related law enforcement agencies. For expected  results, have been achieved successfully the followings:

1- UNODC Consultant provide expertise to support GB TCU in provision of critical information, analysis, technical advice and training for the fight against illicit drug trafficking and transnational organized crime in the country.

2-Approval of three SOP`s by the Minister of Justice(Intelligence gathering and analyses; working with informants and drug destructions.)

3-From August to November, UNODC  provided expertise to support GB TCU in

Advanced Criminal Investigation related to Drugs Trafficking training to 20 police officers belonging to the TCU and other GB LEA`s) and Advanced computer training to the same LEAs and TCU team.

4- Procurement of Vehicle for TCU  office

5- Procuremnt of Police Equipments in order to improve the TCU operational capacities.

6- Final arrangements for the installation of  Go case System and training on its use, training in Data Base oriented criminal intelligence gathering and analyses.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

N/A

Outcome Statement 2:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Outcome Statement 3:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Outcome Statement 4:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender in the reporting period

| Evidence base: What is the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | -Twenty police officers from GB LEA’s enhanced their law enforcement capacities and capabilities, acquiring better investigation on drug trafficking skills. -TCU and Judiciary Police used the SOP developed through this program for destruction of the illegal drugs that were seized during police operations, obtaining better results in terms of destroying the illegal drugs in accordance with international standards, best practices with appropriate regard for safety of the community. The Implementation and validation of SOP´s for “Drug Destruction”, for ”Intelligence Gathering and Analysis”, and “Working with Informants ” were signed by the Minister of Justice. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | The national authorities acknowledged that without the support of International stakeholders, taking into account the fragility of the country, few improvements could be made to the competent institutions dedicated to combating Organized Crime and Illicit Trafficking. They also recognized that the continuous training in advance techniques and logistical support is a critical asset to the national authorities. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | N/A |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | N/A |
| Gender: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | Gender Marker Score: 01 Taking into account the Gender Mainstreame, for each training it was requested to have female officers. In both trainings provided, 8 females (from POP, National Guard and JP ) attended. |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) | There should be some consideration for extending timelines when the project includes equipment donations due to the time needed to research the technical specifications, location of venders for supplying equipment, including shipping. For example: Implementation of “Go Case System” will take time for vendor processes, shipping, installation and training on its use. |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | Timelines can change for trainings/delivery of equipment of this nature due to extenuating circumstances which impact the actual date for delivery of some items withing the project itself. |
| --- | --- |
| Lesson 2 (1000 character limit) | Additional research may be needed to determine where specialized police equipment can be purchased/shipped from when being considered for projects, as there may be limited vendors within a specific country or the need to seek a wider range of international vendors. |
| Lesson 3 (1000 character limit) | Ensuring that training materials are produced in all of the relevant languages is necessary and translation services may be required. |
| Lesson 4 (1000 character limit) | N/A |
| Lesson 5 (1000 character limit) | N/A |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

N/A

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures are on track, slightly delayed, or off track:

If expenditure is delayed or off track, please provide a brief explanation (500 characters maximum):

Please provide an overview of expensed project budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: |
| Output 1.1 | Output 1.1.: Intelligence data base established:Activity 1.1.1: Training of TCU officers and other LEAs in data-base oriented criminal intelligence gathering and analysis Activity 1.1.2: Technically set up database. Activity 1.1.3.:Delivery of a computer training for the TCU`s and other LEA`s Activity 1.1.4.: Develop SOP`s on intelligence gathering and informant handling |  | 1.1- International Consultant 10 months *7300 USD 1.1- IT Software and other equipments for the data base(Go case System) 100.000 USD 1.1 - Renting of venues, catering and transportation, staples and consumables 28.200 USD | 29.200 56.571.00 12.470,08 |  |
| Output 1.2 | Output 1.2: Inter-agency national and regional cooperation on drug trafficking and organized crime enhanced through database- Activity 1.2.1: Establish and develop informations excahnge systems between the TCU and other LEAs Activity1.2.2:Develop Protocols for bilateral region cooperation. Activity 1.2.3.: Initiate exchanges with other TCU`s in the region Activity 1.2.4 : Joint Operations conducted by the LEAs , based on the intell gathering and analyzes. Activity 1.2.5: On the job training and mentoring on intelligence-ed policing |  | 1.2 - Operating costs for TCU 3000*12 months =36.000 1.2 - Purchase of 1 Toyota SUV 30.000 USD | 9.436.18 22.428.02 |  |
| Output 1.3 |  |  |  |  |  |
| Outcome 2: |
| Output 2.1 |  |  |  |  |  |
| Output 2.2 |  |  |  |  |  |
| Output 2.3 |  |  |  |  |  |
| Outcome 3: |
| Output 3.1 |  |  |  |  |  |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: |
| Output 4.1 |  |  |  |  |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total: |  |  |  |  |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when); or whether any changes are envisaged in the near future (2000 character maximum):

N/A

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.