RUNO ANNUAL PROJECT REPORT		TEMPLATE 4.4

PEACEBUILDING FUND (PBF)

ANNUAL PROJECT progress report

COUNTRY: GUINEA BISSAU

REPORTING PERIOD: 1 january – 31 December

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: Short-term Emergency Support to National PBF Secretariat in Guinea-Bissau Programme Number (if applicable) PBF/IRF-83 MPTF Office Project Reference Number: 00089352 |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: UNDP |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: NA |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) 449,645 (2015) Total 2014 + 2015 = 891,431 |  |  | Overall Duration (months) 12 |  |
|  |  |  | Start Date (dd.mm.yyyy) 15/02/2014 |  |
| Government Contribution (if applicable) |  |  | Original End Date (dd.mm.yyyy) | 31/12/2014 |
| Other Contributions (donors) (if applicable) |  |  | Current End date(dd.mm.yyyy) 31/12/2015 |  |
| TOTAL: | 891,431 |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Assessment/Review - if applicable please attach Yes No Date: Mid-Term Evaluation Report – if applicable please attach Yes No Date: |  | Name: Gabriel Dava Title: OIC PBF Secretariat Participating Organization (Lead): UNDP Email address: gabriel.dava@undp.org |

PART 1 – RESULTS PROGRESS

  - Assessment of the current project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project is contributing:

Priority Plan Outcome to which the project is contributing. (4.3) Governance of peacebuilding resources (including JSC Secretariats)

Priority Plan Outcome indicator(s) to which project is contributing. N/A

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  PB opportunities maximized through PBF & PBC interventions

Rate the current status of the outcome:

| Indicator 1: A New (revised) PBF PRF Allocation Indicator 2: Political/financial support mobilized by the CSC Indicator 3: NA | Baseline: PRF window suspended Target: PRF review completed by September 2015 Progress:Conflict analysis conducted, discussed with relevant stakeholders representing UN, Government, CSOs, Research institutions and International organizations. New PPP for 2015-2017 developed and approved by PBF Executive Committee. PBSO approved the PPP conidtionally. with comments to be incorporated December 2015. PBF PRF envelope of US$ 10 million allocated to GB. Baseline: N/A Target: CSC convened on a regular basis (at least once prior each SC briefing on GB) Progress: CSC met before each SC briefing during the reporting period. CSC Chair travelled to Bissau from 19 to 21 April to meet with national and international partners in the wake of the international partners' round table of March 2015. Following the dismissal of the government, CSC issued a statement on 18 August on the political situation. Baseline: NA Target: NA Progress:NA |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Output 1: PBF and PBC effectively re-engage in the post electoral period

- Conflict analysis conducted, discussed and served to guide the rationale of PBF intervention and the selection of priority areas.

- PPP 2015-2017 developed, approved and financed with a US$ 10 M envelope.

Output 2: IRF portfolio (2013-2015) effectively implemented, contributing to improved political stability, civic empowerment and strenghtened state capacity for planning in lead-up to the elections.

-All projects under the IRF envelope were developed, approved and implemented in a timely manner. 4 of them contributed to sucessful elections.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

A one-year extension of the IRF project for short-term support to the National PBF Secretariat was approved in 2014 (1 January - 31 December 2015) with a primary emphasis on the review of the Peacebuilding Priority Plan (PPP). The project also addressed the need of undertaking of a Conflict Analysis that would serve to build a common analytical framework and approach which would facilitate the development of a targeted peacebuilding plan.

With support of the PBF Secretariat, an Executive Committee was established in January 2015 (replacing the former JSC) to ensure joint oversight and coordination of the operations of the PBF fund by the new government and the UN.

The Conflict Analysis was conducted by an international consultant and the report was discussed with relevant stakeholders representing UN, Government, CSOs, Research institutions and International organizations. The analysis informed the selection of the peacebuilding priority plan areas.

A technical group composed by PBF Secretariat, UN and Government staff worked on the development of the PPP 2015-2017 which was endorsed by the Committee on 19 May and approved conditionally by the PBSO. On 23 June, PBSO announced an allocation of US$ 10 million for implementation of the Plan. The PPP was signed during an Executive Committee meeting co-chaired by the Prime-Minister on 30 July and officially submitted to PBSO.

With the dismissal of the Government on 12 August and subsequent political crisis, there have been some delays in the development and approval of concept notes and projects. A new government has been sworn in on 13 October and the Executive Committee is to resume his functions with the holding of the next meeting scheduled for 4 November.

The project's theory of change is still valid: if a PBF Secretariat is present on the ground to provide technical support to the development of PRF projects and oversee their implementation as well as the reengagement of the PBF and the PBC, PBF funds will be used more effectively, contributing to improved political stability and peace.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

While the project achieved to deliver the proposed outputs, there are some delays on the development and execution of projects under the new PRF envelope due to the dismissal of the government on 12 August and pending protracted negotiations to form a new government. A new government was sworn in on 13 October and the Executive Committee is to resume his functions with the next meeting scheduled for 4 November.

Outcome Statement 2:  NA

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Outcome Statement 3:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Outcome Statement 4:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender in the reporting period

| Evidence base: What is the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | The PBF Secretariat report is based on the successful development of a Peacebuilding Priority Plan to which a US$ 10 million envelope was allocated by PBSO. The establishment and regular functioning of the Executive Committee and PBF funded projects smooth implementation is also an evidence of the progress. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | The PBF Secretariat Support project directly contributed to the development and approval of the PPP which received a US$ 10 M envelope. This fund will contribute to advance important peace-building actions, such as the constitutional review, political dialogue, women and youth participation in political participation, among others described in the PPP. Without this funding, these activities could not be implemented. It also supported the re-establishment of a joint PBF oversight structure in the country (strategic and oversight structure gap). |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | The PBF Secretariat, through its direct support to the development and approval of the PPP, contributed to the overall UN effort to attract funding to the country. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | NA |
| Gender: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | This is a management project in its essence and as such does not have direct influeence on gender aspects. However, it provides guidance in the development of PBF funded projects to ensure that gender issues are properly maistreamed. In addition, the Secretariat oversees the implementation of the Gender Programme Initiative project on women's economic empowerment and is supporting gender mainstreaming throughout the new PRF portfolio. |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) | A perception survey was carried out for the first time in GB in the context of the IRF project in support of employment generation. While the perception survey assessed the impact of the project in particular, the questionnaire had a broader peacebuilding focus, which informed the review of the Peacebuilding Priority Plan. The perception survey demonstrates how important the PBF funded projects are for the citizens. |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) |  |
| --- | --- |
| Lesson 2 (1000 character limit) |  |
| Lesson 3 (1000 character limit) |  |
| Lesson 4 (1000 character limit) |  |
| Lesson 5 (1000 character limit) |  |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures are on track, slightly delayed, or off track:

If expenditure is delayed or off track, please provide a brief explanation (500 characters maximum):

Please provide an overview of expensed project budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: PB opportunities maximized through PBF & PBC interventions |
| Output 1.1 | Output 1: PBF and PBC effectively re-engage in the post electoral period | UNDP | 449,645.03 (2014 allocation) | 262,365 | Preliminary data (as of October 2015) |
| Output 1.2 | IRF portfolio (2013-2015) effectively implemented, contributing to improved political stability, civic empowerment and strenghtened state capacity for planning in lead-up to the elections. | UNDP |  |  | 2 IRF projects are ongoing. One will be concluded in December 2015 (under the Gender Initiative phase I) and the other in February 2016. |
| Output 1.3 |  |  |  |  |  |
| Outcome 2: |
| Output 2.1 |  |  |  |  |  |
| Output 2.2 |  |  |  |  |  |
| Output 2.3 |  |  |  |  |  |
| Outcome 3: |
| Output 3.1 |  |  |  |  |  |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: |
| Output 4.1 |  |  |  |  |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total: |  |  |  |  |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when); or whether any changes are envisaged in the near future (2000 character maximum):

The PBO and head of the PBF Secretariat left in June 2015. Recruitment of a new PBO is undergoing and UNDP DRR/P is currently serving as OiC of the Secretariat.

In consultation with PBSO, the Secretariat is planning to reinforce its M&E capacity during the implementation of the PRF projects.

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.