South Sudan 2014 CHF Standard Allocation Project Proposal for CHF funding against CRP 2014 For further CHF information please visit http://unocha.org/south-sudan/financing/common-humanitarian-fund or contact the CHF Technical Secretariat chfsouthsudan@un.org

This project proposal shall be submitted by cluster partners in two stages to the Cluster Coordinators and Co-coordinators for each project against which CHF funds are sought. In the first stage, before cluster defenses, applying partners fill sections I and II. The project proposal should explain and justify the activities for which CHF funding is requested and is intended to supplement information already available in the CRP Project Sheets. The proposals will be used by the cluster Peer Review Team in prioritizing and selecting projects for CHF funding during CHF Standard Allocation round. Partners should also fill and submit to cluster coordinator/ co-coordinator the CHF Project Summary (Annex 1). In the second stage projects recommended for funding by the CHF Advisory Board must complete Section III of this application and revised/update sections I and II if needed.

SECTION I:

| CRP Cluster | HEALTH |
| --- | --- |

| CHF Cluster Priorities for 2014 Second Round Standard Allocation This section should be filled by the cluster Coordinators/Co-coordinators before sending to cluster partners. It should provide a brief articulation of Cluster priority activities and geographic priorities that the cluster will recommend for funding from the CHF in line with the cluster objectives highlighted in the CRP 2014. |
| --- |
| Cluster Priority Activities for this CHF Round |  | Cluster Geographic Priorities for this CHF Round |
| Maintain emergency primary health care services in targeted areas through provision basic equipment, drugs, medical supplies, basic lab equipment and supplies Support to key hospitals for key surgical interventions to trauma Provision and prepositioning of core pipelines (drug kits, RH kits, vaccines and supplies) Communicable disease control and outbreak response including supplies Strengthen early warning surveillance and response system for outbreak-prone diseases Support immunizations via fixed and mobile health clinics targeting displaced people, and other vulnerable groups including emergency mass vaccination campaigns Maintain surge capacity to respond to any emergencies Provision of the essential package of reproductive health services in affected communities (safe deliveries, acute newborn care, care for victims of SGBV, and mitigating HIV in emergencies); Provision of Emergency mental health and psychosocial care Capacity building interventions will include Emergency preparedness and communicable disease control and outbreak response Emergency obstetrical care, and MISP (minimum initial service package-MISP) Community based interventions including awareness raising, hygiene promotion, education and participation in health-related issues Trauma management for key health staff Support to referral system for emergency health care including medevacs. Support to minor rehabilitation and repairs of health facilities HIV/AIDS awareness raising information dissemination, condom provision, PMTCT, PEP and standard precautions |  | Jonglei – all counties Upper Nile – all counties Unity – all counties Lakes – Awerial, Yirol West, Yirol East and Rumbek North Central Equatoria – Juba (IDP camps) Warrap - Twic, Agok, Gogrial East, Tonj North, Tonj South and Tonj East |

SECTION II

| Project details The sections from this point onwards are to be filled by the organization requesting CHF funding. |
| --- |
| Requesting Organization |  | Project Location(s) - list State and County (payams when possible) where CHF activities will be implemented. If the project is covering more than one State please indicate percentage per State |
| UNFPA |  | State | % | County/ies (include payam when possible) |
| Project CRP Code | CRP Gender Code |  | Jonglei | 30% | All counties |
| SSD-14/H/60451 | 2R |  | Upper Nile | 30% | All counties |
| CRP Project Title (please write exact name as in the CRP) |  | Unity | 20% | All counties |
| Maintaining and scaling up access to quality Reproductive Health (RH) services for IDPs, Returnees, Refugees and other Vulnerable Populations in South Sudan |  | Lakes | 20% | Awerial , Yirol West, Yirol East and Rumbek North |
| Total Project Budget requested in the in South Sudan CRP | US$ 5, 484,195 |  | Funding requested from CHF for this project proposal | US$1,000,000 |
| Total funding secured for the CRP project (to date) | US$ 1,586,000 |  | Are some activities in this project proposal co-funded (including in-kind)? Yes No (if yes, list the item and indicate the amount under column i of the budget sheet) |
| Direct Beneficiaries (Ensure the table below indicates both the total number of beneficiaries targeted in the CRPproject and number of targeted beneficiaries scaled appropriately to CHF request) |  | Indirect Beneficiaries / Catchment Population (if applicable) |
|  | Number of direct beneficiaries targeted in CHF Project | Number of direct beneficiaries targeted in the CRP |  |  |
| Women: | 25,000 | 250,000 |  |  |
| Girls: | 30,250 | 302,500 |  |  |
| Men: | 20,000 | 200,000 |  |  |
| Boys: | 24,750 | 247,500 |  |  |
| Total: | 100,000 | 1,000,000 |  |  |
| Targeted population: Abyei conflict affected, IDPs, Returnees, Host communities, Refugees |  | CHF Project Duration (12 months max., earliest starting date will be Allocation approval date) |

| Implementing Partner/s (Indicate partner/s who will be sub-contracted if applicable and corresponding sub-grant amounts) |  | Indicate number of months: 12 months 1 August 2014 – 31 July 2015 |
| --- | --- | --- |
| Contact details Organization’s Country Office |  | Contact details Organization’s HQ |
| Organization’s Address | UNFPA, UN House, Juba 111 |  | Organization’s Address | 605 3rd Avenue, New York, 10158 |
| Project Focal Person | Dr. James Okara Wanyama , wanyama @unfpa.org, +211-954 134962 |  | Desk officer | Nixon Obia Achieng obia@unfpa.org, : Cell +1 (917)412-2944 Office: +1 (212)297-5154Name, |
| Country Director | Mr. Barnabas Yisa, Yisa@unfpa.org, +211-956444486 |  | Finance Officer | Name, Email, telephone |
| Finance Officer | Manase Kimbo, Kimbo@unfpa.org, +211-955856267 |  |  |  |
| Monitoring & Reporting focal person | Dr. James Okara Wanyama , wanyama @unfpa.org, +211-954 134962 |  |  |  |

A. Humanitarian Context Analysis Briefly describe (in no more than 300 words) the current humanitarian situation in the specific locations where CHF funded activities will be implemented. Provide evidence of needs by referencing assessments and key data, including the number and category of the affected population

In December 2014, violence broke out in South Sudan’s capital city of Juba and spread quickly to other communities and towns. It is estimated that by the end of 2014, the conflict would have resulted in the displacement of 1.5 million people, the largest concentration of which is found in the states of Unity, Jonglei, Upper Nile and Central Equatoria. It is estimated that the crisis will affect over 5 million people in South Sudan. The health cluster partners estimate that, they will be able to reach 2.8 million will services. The states that have experienced greatest increase in the numbers of affected people and are therefore in most urgent need of RH interventions include Central Equatorial, Lakes; Jonglei, Upper Nile, Eastern Equatoria, Unity, and Warrap States. RH reports from these states indicate deteriorating RH indicators, especially related to maternal health and maternal deaths, due to many factors including unavailability of services and weak referral systems. Additional factors include looted, destroyed or closed health facilities due to insecurity, and the displacement of health staff. The ethnic dimension of the conflict even makes it complicated to deploy some staff in certain locations and for patients to access service outlets in particular locations. The conflict has heavily affected young people. Due to high levels of underlying poverty and lack of access to livelihood opportunities, many young people have been drafted into the conflict as combatants. For those who have been displaced into IDPs camps, the breakdown in community social systems that regulates behavior has left them to be exposed to various risks, and there is a critical need to support them on critical life skills and with information. UNFPA will identify and engage young people in community mobilization for RH services and work with them to engage a local community based organization to establish one youth centre each in Awerial and Bor. These locations have some of the highest concentrations of young people. The proposed youth centers will be used to provide life skills training, and adolescent sexual and reproductive health services and information, including supporting the training of peer educators and volunteer community mobilisers. UNFPA has successfully implemented this approach in Juba 3 and Tomping PoC sites, raising awareness on RH including GBV and HIV prevention services.

B. Grant Request Justification Briefly describe (in no more than 300 words) the reasons for requesting CHF funding at this time. Explain how CHF funding will help address critical humanitarian gaps in your cluster. Explain the value added by your organization (e.g. geographical presence). Indicate if any other steps have been taken to secure alternative funding.

Prior to the current crisis, South Sudan had some of the world’s worst RH indicators, particularly among women. Only 14.7 per cent of births were attended by skilled birth attendants, only 11.5 per cent of deliveries took place at a health facility, 80 per cent of births happened at home attended by unskilled birth attendants, and GBV was highly prevalent. The maternal mortality ratio was estimated at 2,054 women dying for every 100,000 live births. Young mothers die due to causes including prolonged obstructed labour, hemorrhage/ bleeding, infection, eclampsia / high blood pressure and complications of unsafe abortion. If RH services are not initiated urgently to reach the growing caseload affected by the current crisis, we will witness more maternal deaths, and many vulnerable young women and boys exposed to life threatening conditions such as HIV and rapes will go unassisted. UNFPA through its work and in partnership seeks to ensure that the right of affected women, men and children enjoy a life of health and equal opportunity. The project implementation will be founded on UNFPA’s global leadership in ensuring that every pregnancy is wanted, every birth is safe, every young person is free of HIV, and every girl and woman is treated with dignity and respect, even and especially those affected by humanitarian crisis UNFPA has been providing technical and RH commodities support to implementing partners to increase access to RH services for refugees, returnees, IDPs and host population in affected locations of the country. Therefore to ensure access to life saving services including reproductive health, there is an urgent need to mobilize resources to maintain ongoing RH humanitarian response. With the first round allocation at the beginning of 2014 and CERF, UNFPA devoted a significant part of that funding to procure RH kits, however, there are glaring gaps in support to distribution of kits from the national warehouse to field level users; lack of funding to support staff who provide day to day support to RH Kits and RH programming in humanitarian settings; and lack of day to day operations costs. ; moreover there are also still exists gaps with the current stock available which may not be sufficient to cover the entire year, especially with the upsurge in the needs in Jonglei. Therefore, UNFPA seeks funding to cover these critical gaps and builds on the work previously initiated under funding from CHF and CERF.

| C. Project Description (For CHF Component only) |
| --- |
| i) Contribution to Cluster Priorities Briefly describe how CHF funding will be used to contribute to the achievement of the cluster priority activities identified for this allocation. |
| This project contributes both directly and indirectly to 7 out of the 8 cluster priorities; (I) provision of drugs/drug kits, medical supplies, reproductive health kits, vaccines and related supplies to facilities in high risk areas; (ii) strengthen or re-establish PHCC s and PHCUs in the affected areas including provision of basic equipment and related supplies to ensure essential basic curative services; (iii) maintain or strengthen medical referral services for emergency cases; (iv) strengthen communicable disease control, prevention, and emergency response capacity including provision of outbreak investigation materials and training of key staff; (v) maintain surge capacity for emergencies and surgical interventions; (vi)conduct training on emergency preparedness and response at all levels; (vii) and provide logistical support to prepositioning of core pipeline supplies to high risk states |
| ii) Project Objective State the objective/s of this CHF project and how it links to your CRP project (one specific geographical area, one set of activities or kickstart/support the overall project). Objective/s should be Specific, Measurable, Achievable, Relevant and Time-bound (SMART) |
| This project aims to reduce maternal and newborn mortality and morbidity among populations affected by humanitarian emergencies in South Sudan. It is intended to cover the core pipeline reproductive health needs for the partners serving the targeted population. The RH kits obtained under this programme will be used for both prepositioning and direct service delivery. |
| iii) Project Strategy and proposed Activities Present the project strategy (what the project intends to do, and how it intends to do it). There should be a logical flow to the strategy: activities should lead to the outputs, which should contribute towards the outcomes, which should ultimately lead to the project objective. List the main activities and results to be implemented with CHF funding. As much as possible link activities to the exact location of the operation and the corresponding number of direct beneficiaries (broken down by age and gender to the extent possible). |
| Using funds from this project, UNFPA will work with partners to establish the MISP for RH. MISP is a global Humanitarian standard and when implemented promptly, it saves lives and prevents illness, especially among those most vulnerable to the effects of the crisis including women, boys and girls. MISP focuses on putting in place a mechanism to prevent and reduce unnecessary loss of life due to RH conditions. The key MISP interventions include prevention and management of STI and HIV; prevention and management of consequences of gender violence; prevention and reduction of excess maternal deaths, and strengthening delivery of comprehensive RH services. Timely implementation of MISP ensures that births are safe, young people are free of HIV, and girls and women are treated with dignity and respect, even, and especially, those displaced due to ongoing violence . Through this project UNFPA will procure and distribute to partners serving IDPs in the locations stated above. The kits will be distributed to partners serving IDPs in Juba PoC sites, Bor PoC site, Mingkamann, Malakal, Bentiu and Kwajok. As more IDP locations become accessible, UNFPA will ensure availability of RH kits and technical support to partners with wider coverage. UNFPA will also deploy 3 RH officers to provide much needed technical support to partners providing the services. Procure Reproductive Health kits- Support local transportation and distribution costs of RH kits Support to pay for core staff for the implementation of this project Conduct refresher trainings on MISP for RH in seven states Conduct social mobilisation to increase service utilisation. |
| iv) Expected Result(s)/Outcome(s) Briefly describe the results you expect to achieve at the end of the CHF grant period. |
| Increased availability of RH kits at the community and facilities to provide SRH services increased capacity of staff at the national and local levels to implement MISP MISP integrated into humanitarian response programs |
| v) List below the output indicators you will use to measure the progress and achievement of your project results. Use a reasonable and measurable number of indicators and ensure that to the most possible extent chosen indicators are taken from the cluster defined Standard Output Indicators (SOI) (annexed). Put a cross (x) in the first column to identify the cluster defined SOI. Indicate as well the total number of direct beneficiaries disaggregated by gender and age. Ensure these indicators are further used in the logframe. |
| SOI (X) | # | Standard Output Indicators (Ensure the output indicators are consistent with the output indicators that will be used in the results framework section III of this project proposal). | Target (indicate numbers or percentages) (Targets should be disaggregated by age and sex as per the standard output indicators list and add-up to the number of direct beneficiaries identified page 1) |
| X |  | # of direct beneficiaries from RH kits | 100,000 ( 25,000 women; 30,250 girls; 20,000 men, and 24,750 boys ) |
| X |  | # of kits distributed | 383 Kits |
| X |  | # of Implementing partners receiving supplies from the pipeline | 15 |
| X |  | # of births attended by skilled birth attendants | 2000 normal deliveries |
| X |  | # of health workers trained in CMR | 50 ( 20 women and 30 men) |
| X |  | # of Health workers trained in MISP | 60( 30 women and 30 men) |
| vi). Cross Cutting Issues Briefly describe how cross-cutting issues (e.g. gender, environment, HIV/AIDS) are addressed in the project implementation. |
| The Minimum Initial Services Package (MISP) for SRH has fiver objectives (i) strengthen coordination (ii) prevent sexual violence and assist survivors (iii) reduce transmission of HIV and manage AIDS (iv) Prevent excess maternal and newborn morbidity & mortality (v) Plan for COMPREHENSIVE RH services, integrated into primary health care. MISP is the most innovative and integrated health strategies that ensure that minimum, but holistic interventions such HIV/AIDS, gender and related crosscutting issues are implemented as a package of interventions. This being largely a core pipeline project, environmental issues related to the activities of the project will be handled by the partners and UNFPA will include the ability of the partner to care of environmental concerns as a criterion for qualification to received RH kits. This project will ensure all these cross cutting issues are part of the implementation of the project as demonstrated in this proposal. |
| vii) Implementation Mechanism Describe planned mechanisms for implementation of the project. Explain if it is implemented through implementing partners such as NGOs, government actors, or other outside contractors. |
| UNFPA will implement this project through implementing partners in the operating in the target states. These partners comprise local and international nongovernmental organization, United Nation Organizations and government (Ministry of Health). UNFPA will build on its experience working with State Ministries of Health and partner humanitarian agencies providing services to affected populations at the state level to clearly define facilities that serve these populations and the service and supply needs. Then, the SMoH and humanitarian agencies will make requisitions based on these pre-identified needs to UNFPA. The requisitions will be reviewed by UNFPA to ensure they serve the needs identified. However, in case of a sudden and acute emergency, UNFPA has pre-defined criteria that are followed to determine the amount of RH kits required while working with its partners to conduct assessments and determine actual needs. In collaboration with partners. UNFPA will procure RH kits and work with partners to develop a cost effective distribution plan utilizing some of the existing distribution channels. The distribution of RH kits will in as much as possible rely on needs as identified by the frontline providers. Where information is scanty, UNFPA will rely on existing demographic data to estimate needs and preposition kits to the field. UNFPA will work with partners to create awareness about the RH kits thereby increasing proper and rational utilization of the kits. The implementing partners will be empowered through training on MISP coordination and implementation at the state and county levels, with funding from other ongoing projects, UNFPA will lead the implementation of the project through the technical leadership of UNFPA’s Emergency RH Advisor and in close collaboration with the State Ministries of Health in the beneficiary states. As RH Kits are part of the Health Cluster Core Pipeline, UNFPA will work closely with the Health Cluster to determine needs and gaps to ensure quick and timely delivery of supplies and support to the implementing partners as needed. Whereas the project is planned to last a whole year from the start, a significant portion of the project will be implemented by end of March 2015. UNFPA will closely monitor the implementation of the project and in case all activities are implemented by March, then UNFPA will work with Health Cluster and CHF Secretariat to provide final project report and close the project. |
| viii) Monitoring and Reporting Plan Describe how you will monitor and report on the progress and achievements of the project. Notably: Explain how will you measure whether a) Activities have been conducted, b) Results have been achieved, c) Cross-cutting issues have been addressed, and d) Project objectives have been met. Indicate what are the monitoring institutional arrangements (e.g. monitoring team, monitoring schedule, updates to management etc.) and monitoring tools and technics will be used to collect data on the indicators to monitor the progress towards the results achieved. Please provide an indication of the frequency data will be collected and if there is already a baseline for the indicators or if a baseline will be collected. Describe how you will analyze the data collected and report on the project achievements in comparison with the project strategy. Ensure key monitoring and reporting activities are included in the project workplan (Section III). |
| The project will be monitored through quarterly review meetings with implementing partners, monthly reports from implementing partners and field spot checks. The project will utilize the newly developed UNFPA IP reporting format for monthly RH kits utilization reports and UNFPA will continue to make monthly core pipeline reports and provide updates on the implementation of MISP including the use of RH kits at various fora including the Health cluster. Based on the distributed kits, UNFPA will be in a position to project the coverage of the population groups that are accessing the RH Kits. The project will also be monitoring through the GVB MIS and the records presented by the MISP trained health workers to track the number of incidents of sexual violence anonymously reported to health and protection services and security officers and link with the number of survivors of sexual violence who seek and receive health care through the project. |

| D. Total funding secured for the CRP project Please add details of secured funds from other sources for the project in the CRP. |
| --- |
| Source/donor and date (month, year) | Amount (USD) |
| CERF | 886,000 |
| CHF | 700,000 |
| Pledges for the CRP project |  |

SECTION III:

| LOGICAL FRAMEWORK |
| --- |
| CHF ref./CRP Code: SSD-14/H/60451 | Project title: Maintaining and scaling up access to quality Reproductive Health (RH) services for IDPs, Returnees, Refugees and other Vulnerable Populations in South Sudan | Organisation: UNFPA |

| Goal/Objectives/Outcomes/Outputs | Indicator of progress | Means of Verification | Assumptions and Risks |
| --- | --- | --- | --- |
| Goal/Impact (cluster priorities) | Provision and prepositioning of core pipelines (drug kits, RH kits, vaccines and supplies) Provision of the essential package of reproductive health services in affected communities (safe deliveries, acute newborn care, care for victims of SGBV, and mitigating HIV in emergencies); Capacity building interventions will include MISP and other RH services | # of direct beneficiaries from RH kits # of kits distributed # of Implementing partners receiving supplies from the pipeline | Project and partner reports |  |
| CHF project Objective | To reduce maternal and newborn mortality and morbidity among populations affected by humanitarian emergencies in South Sudan | Number of referrals for maternal health conditions. Number of emergency Obstetric cases successfully handled by skilled health workers | Facility reports. Project reports Partner reports | Insecurity and lack of qualified health workers |
| Outcome 1 | Reduction in maternal and neonatal mortality | Number of maternal deaths Number of neonatal deaths | Facility reports Community mobilisers reports Project reports | Insecurity and lack of skilled health workers |
| Output 1.1 | Increased availability of RH kits Increased availability of RH services Increased number of staff trained on MISP and other SRH services Increased utilization of RH services | Number of Implementing partners receiving supplies from the pipeline. Number of health facilities/service outlets providing RH services. Number of staff trained on MISP and other RH services. Number of people utilizing RH services | Monitoring reports Project reports Partner reports | Insecurity and lack of skilled health workers |
| Activity 1.1.1 | Procure Reproductive Health kits- |
| Activity 1.1.2 | Train Health workers on Clinical Management of Rape survivors |
| Activity 1.1.3. | Train health workers on core concepts of MISP |
| Activity 1.1.4. | Training on ASRH for peer Educators (5 days targeting 50 peer educators in two locations |
| Activity 1.1.5. | Conduct Community social mobilisation on RH, HIV, ASTH and GBV to increase service uptake through different approaches |

PROJECT WORK PLAN

| Project start date: | 1 August 2014 | Project end date: | 31 July 2015 |
| --- | --- | --- | --- |

| Activities | Q3/2014 | Q4/2014 | Q1/2015 | Q2/2015 | Q3/2015 |
| --- | --- | --- | --- | --- | --- |
|  | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul |  |
| Activity 1. Procure, distribute and pre-position Reproductive Health kits- | X | X | X |  |  |  |  |  |  |  |  |  |  |
| Activity 2. Train Health workers on Clinical Management of Rape survivors |  |  | X | X | X |  |  |  |  |  |  |  |  |
| Activity 3. Train health workers on core concepts of MISP |  |  | X | X |  |  |  |  |  |  |  |  |  |
| Activity 4. Training on ASRH for peer Educators (5 days targeting 50 peer educators in two locations |  | X | X | X | X | X | X | X | X | X | X | X |  |
| Activity 5. Conduct Community social mobilisation on RH, HIV, ASTH and GBV to increase service uptake through different approaches |  | X | X | X | X | X | X | X | X | X | X | X |  |

*: TIMELINE FOR EACH SPECIFIC ACTIVITY MUST BE MARKED WITH AN X AND SHADED GREY 15%

# Footnotes

To the extent possible reference needs assessment findings and include key data such as mortality and morbidity rates and nutritional status, and how the data differs among specific groups and/or geographic regions. Refer situation/data/indicators to national and/or global standards.

CHF minimum narrative reporting requirements will include the submission of a final narrative report and where applicable a narrative mid-term report. Narrative reports will include a progress on the project achievements using the outputs indicators listed in this project proposal.

# Text boxes

Document: SS CHF.SA.02