RUNO ANNUAL PROJECT REPORT		TEMPLATE 4.4

PEACEBUILDING FUND (PBF)

ANNUAL PROJECT progress report

COUNTRY: Bosnia and Herzegovina

REPORTING PERIOD: 1 january – 31 December

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: Dialogue for the Future Programme Number (if applicable) MPTF Office Project Reference Number: 00091334 |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: UNDP, UNICEF, UNESCO |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: Presidency of Bosnia and Herzegovina |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) UNESCO 539,101 UNICEF 544,558 UNDP 916,341 |  |  | Overall Duration (months) 18 |  |
|  |  |  | Start Date (dd.mm.yyyy) 21.07.2014 |  |
| Government Contribution (if applicable) n/a |  |  | Original End Date (dd.mm.yyyy) | 21.01.2016 |
| Other Contributions (donors) (if applicable) |  |  | Current End date(dd.mm.yyyy) 21.01.2016 |  |
| TOTAL: | 2,000,000 |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Assessment/Review - if applicable please attach Yes No Date: Mid-Term Evaluation Report – if applicable please attach Yes No Date: |  | Name: Namik Hadžalić Title: Joint UN Project Coordinator Participating Organization (Lead): UN RCO Email address: namik.hadzalic@undp.org |

PART 1 – RESULTS PROGRESS

  - Assessment of the current project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project is contributing:

Priority Plan Outcome to which the project is contributing. N/A

Priority Plan Outcome indicator(s) to which project is contributing. N/A

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  Established dialogue spaces for decision makers, civil society and citizens that enable country-wide peacebuilding process to promote coexistence, trust building and appreciation of diversity.

Rate the current status of the outcome:

| Indicator 1: Dialogue and Peacebuilding Platform developed. Indicator 2: % of population that benefited from improved dialogue and enhanced appreciation of diversity in the targeted areas across the country. Indicator 3: Number of articles/stories positively depicting peacebuilding, tolerance, multiculturalism and non-violent conflict resolution in select media outlets. | Baseline: No Dialogue Platform. Target: All elements of the dialogue platform functioning. Progress:On track. Baseline: 2014 Baseline assessment of current state of play regarding dialogue and respect of diversity. Target: 20% of population improved dialogue and mutual understanding through Grants Facility awarded community Projects. Progress:On track. Baseline: Number captured through baseline analysis at the start of the project. Target: Number increased by at least 10 % by the end of the project. Progress:On track. |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

1) "Dialogue Platform" Declaration was signed by the Presidency of BiH and the UN providing impetus and scope to Dialogue Platform Conference.

2) Two "Dialogue Platform" conferences were organized, bringing 300 decision-makers and youth activists together, resulting in identification of more than 30 conclusions and over 50 concrete individual activities in the areas of youth policy, education and culture.

3) 40 Grants Facility Projects supported. Grants Facility evaluated 334 applications received. Grantees activities ended with the end of December having been monitored and evaluated.

5) 20 episodes of country wide TV Show "Jump out", were aired, promoting diversity.

6) Social Web Platform developed and functional.

DFF Youth Forum FB Platform functional.

7) 5 Trainings held for media professionals and for Grants Facility beneficiaries.

8) 4 trainings conducted to develop institutional capacities on intercultural dialogue and trust building.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

2015 was a key year in which DFF Project positioned itself amongst critical partners for promoting peacebuilding processes in Bosnia and Herzegovina, focusing on trust building and promotion of diversity initiatives.

To date, Project directly engaged over 54,000 citizens through 2 Dialogue Platforms (400), 26 Youth Forums (600), trainings (300) and 40 Grants Facility Projects (direct beneficiaries 53,031, indirect 26,600).

With over 1,350 positive stories, 20 TV episodes targeting youth engagement, positive stories and Grants Facility initiatives, with estimated 890,560 viewers, 27,494 Youtube and 135,419 FB views, 3,680 social platform users, DFF Project made a tangible impact when it comes to youth focused initiatives in both macro and micro communities, which promote trust building and appreciation of diversity.

In total, based on figures presented above, it is estimated that 1,138,084 persons or more than 29% of the population in Bosnia and Herzegovina were engaged via various Grant Facility, outreach, communications and advocacy activities. Change in perception towards improved dialogue and mutual understanding will further be evaluated upon completion of 2015 KAP study.

Indeed, "Dialogue for the Future" Project formalized relationship with the implementing partner, the Presidency of BiH, by signing the "Dialogue Platform Declaration". This "backbone" document facilitated engagement of decision-makers from all jurisdictional levels at DFF events, most elevated of which is the Dialogue Platform Conference.

With the establishment and organization of two Dialogue Platform Conferences, a functional formal mechanism was developed for interaction between citizens and decision makers on issues pertaining to peacebuilding and trust-building processes. Mechanism's success lies in its ability to identify concrete conclusions and activities in real-time environment from across all governance levels and bring them to high-level decision making bodies. Establishment of the Mechanism is a novelty that goes in hand with Outcome indicators. In 2015, over 30 recommendations with more than 50 concrete activities were identified and forwarded to the Presidency and Youth Coordination Commission for action. However, absorption capacities of institutional decision-making processes with regards to identified priorities require additional attention in 2016.

Provided absorption capacities are improved, the novelty established, lends itself to further enhancement of institutional and CSO cooperation in the future, which should follow transfer of ownership to the beneficiary.

Still, significant portion (19%) of Culture Grants Scheme Projects were allocated to partner institutions.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

DFF Project sought approval of a six (6)-month non-cost extension of the Project due to change in the enabling environment within which the Project operates. The request had no pecuniary implications, nor did it affect the overall Project outcomes and activities, but aimed at ensuring more qualitative achievement of planned objectives.

Governance vacuum left in the period prior to, during and after general elections in BiH changed the enabling environment based on which Project activities could not be completed as initially planned leading to delay in organizing a third Dialogue Platform Conference.

General Elections were held on 12 October 2014, whereas the first session of the new Presidency was held on 23 December 2014. This two and a half month period was preceded with over a month long election campaign and a backlog of pending items that the new Presidency had to prioritize. Additionally, new members of the Presidency, their advisors and support staff that coordinate with the Project required additional time to re-engage with the Project activities.

Finally, procrastinated formation of governments at various levels, including 14 legislative assemblies had additional impact on implementation of Project activities most notably Dialogue Platform Conference whose goal is to engage decision makers and the youth.

Project will hold 3rd Dialogue Platform Conference in early 2016.

Outcome Statement 2:  Increased participation, awareness and influence of youth and youth civil society organisations in policy dialogue with decision makers on issues impacting BiH's development and reform agenda.

Rate the current status of the outcome:

| Indicator 1: Strenghtened youth participation in policy development and governmental initiatives. Indicator 2: Nation-wide youth network established dedicated to intercultural understanding and dialogue. Indicator 3: Perceptions of youth that they have little or no influence on important decisions. | Baseline: B2014 Assesment of existing youth participatory mechanisms. Target: At least three session/conferences organized through the platform for the duration of the programme, establish new or strenghten existing youth participation mechanism/channels with the government. Progress:On track. 2 Conferences organized. Baseline: No dedicated youth network. Target: Network members from all parts of the country, at least three (3) initiatives instigated by the network. Progress:On track. Baseline: All youth responses(%) - at work, in school or college 80% (2008), 88% (2012); In the famly or household 61% (2008), 70% (2012); In the local community 89% (2008), 97 %( 2012; In plitical organizations or NGOs 90% (2008), 99% (2012); Amongst peers and friends 66%(2008), 80% (2012) Target: At work, in school or college 78%; In the family or household 60%; in the local community 87%, in political organizations or NGOs 90%; Amongst peers and friends 70%. Progress:On track. Awaiting KAP results (KAP survey currently being conducted.) |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

1) Two "Dialogue Platform" conferences organized (please note comment under outcome 1. Due to general elections 3rd Conference will be held in 2016.)

2) Nation wide youth network established. Three rounds of four regional "Youth Forums" (total of 12) were organized bringing 350 youth together from across the country to develop their skills and work on local initiatives related to youth policies, activism, education and culture. 3 initiatives developed based on Youth Forum findings.

3) Change in perception of youth indicator will be measurable upon the end of the year once KAP study results are completed.

4) 2 study trips organized, 9 workshops held for youth groups regarding project document preparation and application to the Grants Facility. 5 Workshops held for grants facility beneficiaries and media professionals on trust building and intercultural reporting.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Output achievements listed above clearly indicate a broad set of mechanisms developed and used by DFF Project which increase participation, awareness and influence of youth civil society organizations in policy dialogue.

- To that end, DFF Project initiated cooperation with the three key youth institutional partners: 1) State level Ministry of Civil Affairs (Youth Coordination Commission); 2) FBiH Entity level Ministry of Culture and Sport (Youth Sector); and 3) RS Entity level Ministry for Family, Youth and Sport.

Cooperation will increase awareness on key youth issues, including volunteerism, radicalization, hate speech, hooliganism and diaspora (State level) and strengthen a governmental network of 143 municipal Youth Coordinators with adequate capacity development and overarching communication and coordination capacities (Entity level).

- As mentioned above Dialogue Platform Conferences brought together 300 youth and government officials and developed a comprehensive set of more than 30 innovative recommendations which should position youth engagement in design and improvement of youth policies, education policies and cultural policies.

- 370 Youth participating in regional Youth Forums developed their skills in project development and implementation, and developed local as well as regional initiative, such as local priority list for adressing issues of community security (at the local level) or a inter-ethnic cooperation of political science students from three universities writing an anthology of 20 Years after Dayton Peace Accords on a number of relevant issues affecting youth.

- Additional 9 workshops were held for Grants Facility applicants which focused solely on developing skills necessary for application processes.

- Project increased the scope of engaging youth CSOs by availing non-formal groups and individuals to apply for grants facility projects in order to promote new activism and to move away from traditional youth civil society actors, which already possess means and portfolios to take active part in decision-making processes.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Outcome Statement 3:  Education and peacebuilding initiatives support greater social cohesion at national level and in targeted communities.

Rate the current status of the outcome:

| Indicator 1: Quality, inclusive intercultural education is included in the agenda of the next annual Conference of Ministers of Education. Indicator 2: Percentage of youth, parents and teachers in targeted schools with increased positive perceptions. Indicator 3: No. of children and youth who benefitted from implemented trainings and small-scale projects on quality inclusive and intercultural education. | Baseline: B 2014: N/A Target: T 2015: inclusion on the agenda Progress:Target achieved: The central theme of the Conference of Education Ministers (July 29, 2015) was discrimination and segregation in education whereupon it was concluded that inclusive, intercultural approaches in education should be undertaken by all education authorities in BiH. Baseline: B 2015: 74% fully/ partially agrees that life in a multicultural community has more positive than negative effects. Target: T 2015: T 2015: 84% fully/ partially agrees that life in a multicultural community has more positive than negative effects. Progress:On track: Near the end of implementation of small grants, a final wave of surveys will be conducted to measure changes in perceptions of beneficiaries. Baseline: B 2014: 0 Target: T 2015: at least 3,000 children (in atrgetted schools). Progress:On track: Direct support has been provided to 698 children, 1,975 youth (including 176 Roma youth, 139 youth with disabilities) and 256 teachers from 113 primary and secondary schools. |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

The key outputs achieved in the period Nov 2014 - Nov 2015 include: 3 regional forums on inclusive, intercultural education; 5 local initiatives on inclusive, intercultural education; 11 education projects (out of 75 received applications) selected and currently being implemented; 70 workshops for 541 children, 75 trainings for 596 youth, 5 trainings for 118 teachers successfully held in the fields of intercultural education, tolerance- and peace-building and conflict resolution; school-based activities ongoing in 23 primary and 90 secondary schools in 50 BiH cities and wider; in the reporting period, 11 education projects have provided direct benefits to 698 children, 1,131 youth, 19 parents, 197 teachers and 30 NGOs; 10 entrepreneurship workshops successfully held targeting Roma youth (176) and youth with disabilities (139) from 23 BiH municipalities; 10 initiatives designed and implemented by Roma youth and youth with disabilities benefitting 150 vulnerable youth .

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Under the slogan „Differences inspire“, dialogue on inclusive, intercultural education was initiated through an online campaign and in local communities around the topics of discrimination and segregation in schools and the need for a quality, competence-based education reform. The same thematic discussions were parallely taken up at the higher, national level of the Dialogue Platform whereupon education professionals, NGO activists, students and public officials helped shape a set of concrete recommendations on strengthening quality, inclusive intercultural education in BiH. The same topic of quality inclusive intercultural education was included and heavily discussed at the Conference of Education Ministers in July 2015 whereupon one of their officially adopted conclusions highlights their appeal to all education authorities in BiH to provide inclusive education, free of all discrimination and based on respect for an individual's human rights.

Through Grants Facility, 11 education projects, targeting a wide net of beneficiaries and institutions, are currently being implemented with the purpose of promoting diversity, peacebuilding and social cohesion. A wide range of activities, from teacher trainings, peace camps, student exhibitions, education workshops etc spread out through cc 50 BiH cities is helping empower adolescents and  providing numerous training opportunities. Programmatic interventions have been conceptualized with the purpose of improving individual perceptions of "otherness" and improving intercultural understanding and tolerance; so far, through initial measurements baselines have been collected among project beneficiaries which will be compared to final survey findings to measure project impact and perception changes.

Specific capacity development activities were targeted at vulnerable youth, particularly Roma youth and youth with disabilities. The main purpose was to build their entrepreneurship skills and competences, theoretically and practically, and hence improve their prospects for social inclusion. Initiatives directly benefiting marginalized groups complemented other activities in the education component, with the aim to put front and center the need for a more inclusive and open education in the country.

In conclusion, the theory of change that underpins the project design is still relevant for outcome 3 and its achievement progress is on track.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Outcome Statement 4:  Citizens and communities promote culture, intercultural dialogue, trust building and appreciation of diversity to advance common peacebuilding goals.

Rate the current status of the outcome:

| Indicator 1: Culture issues addressed through the Platform conferences in support of UNESCO Universal Declaration on Cultural Diversity and 2005 Convention on the Protection and promotion of Diversity of Cultural Expressions. Indicator 2: Culture related projects supported and implemented through the Grants facility. Indicator 3: % change of citizens perceptions of the 2013 KAP study question on intercultural understanding | Baseline: n/a Target: At least one session on culture issues in the Platform conferences. Progress:Two sessions realized Baseline: No culture related projects supported and implemented through the Grants facility. Target: At least 5 culture related projects supported and implemented through the Grants facility. At least 3 projects dedicated to the needs of vulnerable groups. Progress:Achieved. 16 project supported. Baseline: 2questions from the KAP studies on Intercultural understending (2012/2013) Target: 5% positive change in responses of general population in comparisation to values captured in 2013 research. Progress:On track. Awaiting KAP results (KAP survey currently being conducted.) |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Two sessions on "Culture" at the Platform Conference. Ten workshops, forums and round tables for youth and vulnerable groups have been held as part of the approved projects. Mapping of relevant stakeholders and projects is done . Eight initiatives on local and regional cultural heritage realized through the Grant Facility. 16 cultural related projects supported and implemented through GF. Five initiatives that target vunerable (2 projects), marginalized groups (2 projects) and gender issues (3 projects) implemented and their CSOs participated at the Dialogue Platform conferences.

Additionally, in the period June-November 2015 DFF project co-financed three grants activities in cooperation with the BiH Ministry of Civil Affairs:

Support to the opening of the National Museum of BiH,

Kid’s Festival (over 35,000 children from BiH) and the

"Space-Form-Touch" exposition targeting blind and low vision persons.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

The program implementation achieved outcome 4 and its respective outputs. From april to November eleven forums and round tables for youth and vulnerable groups have been held as part of the approved projects. These events have been held in Brcko (The European Construction and Peace), Banja Luka (An Environment Conductive to Peace), Mostar (Gender & vulnerable groups) , Tuzla (Social Peace), Sarajevo, DerventaLivno and Tuzla (Active participation of persons with disabilities in the cultural life of B&H in promoting and advocating for better interethnic understanding and appreciation), Mostar ( Regional intercultural cooperation) , Banja Luka (networking and economic empowerment of women in BiH) attended by cca. 500participants.

Based on the evaluation of available opportunities for co-financing at the various governing levels,  UNESCO established agreement (exchange of letters) with the Ministry of Civil Affairs of the Council of Ministers Bosnia and Herzegovina, for supporting peace building and reconciliation activities through grant scheme and in accordance to the availability of the funding sources.  Following this agreement, in cooperation with the Ministry of Civil Affairs of BiH, under the DFF project, UNESCO has organized an Info Day at the Parliament of BiH for the representatives of the culture sector of Bosnia and Herzegovina on the opportunities for co-financing of projects in the area of culture from EU funds. This event was attended by the representatives of public institutions, non-governmental sector as well as the interested private organizations.

Two Dialogue Platform conferences emphasized the networking of culture workers, in particular the youth and the ways for their joint activity. The most current problems were detected in culture, as well as the role from the non-governmental sector in their resolution. The possibilities for use of domestic and foreign funds for culture have been identified. The significance of investing into culture as a profitable branch was pointed out, which is of particular interest for young population. Particular emphasis was made on the necessity of passing strategic documents and action programs in culture at all government levels.

Until mid-November, all of the 16 projects were implemented, out of which 2 projects were intended for persons with disabilities, 3 projects intended for women and addressing women issues, while two projects for the position and cultural heritage of minorities.

Mapping of relevant stakeholders and projects is done in cooperation with DPA office.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender in the reporting period

| Evidence base: What is the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | Project's evidence base in terms of quantitative data is collected from generated participant's lists, Grants Facility beneficiaries' reports, monitoring and evaluation consultants' feedback. Data related to changes in perception is expected to be generated via KAP study which will be conducted by the end of 2015. Communication and advocacy data was generated via official viewer's index (for number of media articles, TV Show,Youtube), whilst social network utilization was monitored by membership figures. In terms of reporting, Report follows on the Half-Yearly Report and the follow up comments sent to PBSO. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | DFF Project filled in critical funding gaps to an extent possible. Indeed it developed a clear comparative advantage over other actors in the peacebuilding arena for having support from the Presidency of BiH which in itself guaranteed amassing over common BiH interests and facilitated development of dialogue mechanisms which are not considered biased nor competitive with alternative interests. Thus, PBF support and UN mandate were critical for filling in gaps in peacebuilding in the country. In terms of funding gaps, DFF Project supported implementation of 40 Projects as well as 2 study trips and a total of 13 Youth Forums and 9 individual workshops, media trainings TV Show and a web platform. Taking into account the interest expressed in all the activities with a specific focus on Grants Funds (where 334 applications received amounted to USD 20 million) and Youth Forums, one can deduce that the funds were critical, yet additional funding space exists which could be utilized to further advance peacebuilding efforts. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | Project set the basis for a number of youth related political developments which went hand in hand with the formation of the new government and adoption of new work plans for youth related issues at both state-level and entity-levels. This particularly relates to advancing position and functionality of the Youth Coordination Commission at the BiH Ministry of Civil Affairs, and strengthening of 143 Youth Coordinators at municipal level charged with streamlining local youth interventions with entity-level youth policies. Moreover, several Grants Facility Projects (which in total reached out to 100 municipalities) had additional catalytic effect in their local communities by co-funding specific activities with bilateral development donors (U.G. Mali Most, Mostar co-funded by JICA) or the private sector (e.g. DVD Jelah co-funded by local businesses). Finally, each of the 11 small grants in the field of education is being co-financed either by the implementation agency or through an additional/complimentary project/donor. Overall co-financing is over 13%. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | As a result of Youth Forum initiatives, Project supported implementation of an additional Youth Project, titled "Youth and Dayton 20 Years later". It brough political science students from three universities in different ethnic regions to work together on political science papers linking youth status and effects of Dayton Peace Accords through specific themes. It presented a risk and a challenge in trust-building which produced positive results and collaboration which will span outside of the DFF Project scope. Additionally, risk taking concerned the engagement of municipal youth coordinator network and their integration into dialogue mechanisms and the engagement of the state-level Youth Coordination Commission. Primary reasons for the risk is a tacit resentment to state-level initiatives through which trust building occurs, which does not necessarily stem from political or societal barriers, but rather to resentfulness of assuming additional work. Advancement of these mechanisms would have additional impact on a state-owned process of youth policy implementation. |
| Gender: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | DFF Gender Marker Score is 2, i.e. "with specific component, activities and budget allocated to women". DFF Project has fully stressed the importance of gender considerations in all its activities. Grant Scheme Fund used PBSO minimum threshold criteria of 15% when evaluating project applications. Three grant scheme project directly supported female populations in terms of programmatic scope, whereas all other Project have a gender representation marker integrated into Project documents. Through participatory mechanisms, such as youth forums, gender issues were specifically discussed as topics. (Topic 3: Gender and Marginalized Groups) Cumulatively, female to male ratio, representing event participants and grant scheme beneficiaries is estimated at 48 (M) / 52 (F). |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) |  |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (250 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Established dialogue spaces for decision makers, civil society and citizens that enable country-wide peacebuilding process to promote coexistence, trust building and appreciation of diversity. | Indicator 1.1 Dialogue and Peacebuilding Platform developed. | No Dialogue Platform. | 2015: All elements of the dialogue platform functioning | On track. Two Dialogue Platform conferences held; Dialogue Platform Declaration signed by BiH Presidency and UN RC. | 2014 General elections in BiH were the major cause of delay. Two new members of the BiH Presidency took office in January 2015 and the overall government formation at all levels lasted until April 2015. | No. |
|  | Indicator 1.2 Number of articles/stories positively depicting peacebuilding, tolerance, multiculturalism and non-violent conflict resolution in select media outlets. | Number captured through baseline analysis at the start of the project. | 2015: Number increased by a least 10% by the end of the project. | On track: 1,350 positive stories reported via DFF Project. Baseline to progress ratio expected by the end of 2015. | No. | No. |
|  | Indicator 1.3 Cooperation of institutional stakeholders with CSOs enhanced for facilitation and support of in-country and regional peacebuilding initiatives | Training needs assessment. | T2015: Cooperation enhanced and trainings assessed for usefulness and relevance by participants. | 5 training sessions on preparing project documents by NGOs held. 2 Dialogue Platform Conferences held brining institutions and CSOs together. Two Conferences with institutional stakeholders and CSOs anticipated. | No. | No. |
| Output 1.1 Established dialogue spaces for decision makers, civil society and citizens that enable country-wide peacebuilding process to promote coexistence, trust building and appreciation of diversity. | Indicator 1.1.1 MoU Signed | No MoU 2014: no | 2014: Signed MoU | MoU/Declaration signed between BiH Presidency and UN RC in April 2015. | No. | No. |
|  | Indicator 1.1.2 High-level conferences of the Dialogue Platform held. | 2014: No conferences held | 2015: 3 Conferences Held | Two Conferences held. | 2014 General elections in BiH were the major cause of delay. Two new members of the BiH Presidency took office in January 2015 and completion of government formation lasted until April 2015. | No. |
| Output 1.2 Small Projects and Grant Facility (GF) is established to support local and civic initatives promoting peaceful coexistence, trust building, intercultural dialogue and appreciation of diversity. | Indicator 1.2.1 No. of small projects implemented (500-50,000 USD) | 2014: Calls for proposals conducted in 2014 | 2015: At least 15 projects implemented | On track. 40 projects currently being implemented. | No. | No. |
|  | Indicator 1.2.2 N/A |  |  |  |  |  |
| Output 1.3 Awareness raised and interest generated among the broader population for participation in the dialogue Platform and Grants Facility | Indicator 1.3.1 TV Show producted and broadcasted nationwide | 2014: No TV Show | 2015: Up to 10 episodes of the TV show producted and broadcast nationwide. | On track. 20 episodes of the TV completed in 2015 | Estimated 890,560 viewers, 27,494 Youtube and 135,419 FB views. Approx. 27% of BiH population. | No. |
|  | Indicator 1.3.2 Web Platform Developed | 2014: No Web Platform | 2015: Web Platform | On track. Web Platform expected to be opeartional in December 2015. | No. | No. |
| Outcome 2 Increased participation, awareness and influence of youth and youth civil society organizations in policy dialogue with decision makers on issues impacting BiH's development and reform agenda. | Indicator 2.1 Strengthened youth participation in policy development and governmental initiatives. | 2014: Assessment of existing youth participatory mechanisms | 2015: At least 3 sessions/conferences organized through platform for the duration of the programme; establish new or strengthen existing yout participation mechanisms with the government. | On track. 2 Dialogue Platform Conferences held. Additional conferences anticipated in December 2015 with the BiH Youth Coordination Commission of Ministry of Civil Affairs BiH and Federal Ministry of Culture and Sports. | No. | No. |
|  | Indicator 2.2 Nation-wide youth network established dedicated to intercultural understanding and dialogue. | 2014: No dedicated youth network | 2015: Network members from all parts of the country, at least 3 intiatives instigated by the network for the duration project. | On track. Dialogue Platform conferences and 3 rounds of regional local Youth Forums brought together young people from across BiH. | No. | No. |
| Output 2.1 Work stream established within the Dialogue Platform for youth and youth civil society organizations that provides and opportunity to influence policy making in on all key development issues in the country and in relation to improving intercultural | Indicator 2.1.1 Workshops and training sessions held/study trips organized. | 2014: 0 | 2015: At least three trainins and workships conducted, at least two study trips conducted | On track. PCM training conducted in five BiH cities. Study trips held. | No. | No. |
|  | Indicator 2.1.2 No. of projects per area of intervention supported. | 2014: N/A | 2015: At least one project per area of intervention supported. | On track. The Grants Facility has supported multiple projects in all areas. | No. | No. |
| Output 2.2 | Indicator 2.2.1 N/A |  |  |  |  |  |
|  | Indicator 2.2.2 N/A |  |  |  |  |  |
| Output 2.3 | Indicator 2.3.1 N/A |  |  |  |  |  |
|  | Indicator 2.3.2 N/A |  |  |  |  |  |
| Outcome 3 Education and peacebuilding initiatives support greater social cohesion at national level and in targeted communities. | Indicator 3.1 No. of boys and girls and youth who benefited from implemented trainings and small- scale projects on quality inclusive intercultural education. | B 2014: 0 | T 2015: At least 3,000 children (in targeted schools) | On track- So far, through ongoing education and peacebuilding initiatives, direct support has been provided to 698 children, 1,975 youth (including 176 Roma youth, 139 youth with disabilities) and 256 teachers from 113 primary and secondary schools | No | No |
|  | Indicator 3.2 Opinion of targeted children/youth towards interculturalism and tolerance improved | B 2015: 74% fully/ partially agrees that life in a multicultural community has more positive than negative effects | T 2015: 84% fully/ partially agrees that life in a multicultural community has more positive than negative effects | On track- Baselines were collected through an initial wave of surveys among beneficiaries and 1,424 valid surveys were collected from respondents (avg age:20): M: 560 (40%), F: 864 (60%), youth: 950 children: 281, teachers: 151, parents: 42 | Near end of implementation of small grants, a final wave of surveys will be conducted to measure changes in perceptions of beneficiaries. | No |
| Output 3.1 Policy-makers, education professionals, civil society and other relevant stakeholders at different levels have discussed the importance of peacebuilding, diversity and social cohesion in the field of education. | Indicator 3.1.1 No. of local forums held | B 2014: no local forums | T2015: 3 local forums held | Indicator reached - 3 regional forums on inclusive, intercultural education held with 59 participants (M20, F39) stating 95% satisfation with forum organization | By widening the scope of the three forums (to neighboring communities), the forums were organized with a regional, rather than a local, focus. | No |
|  | Indicator 3.1.2 No. of initiatives supported | B 2014: no initiatives supported | T 2015: at least 5 initiatives supported | Indicator reached- 5 initiatives promoting inclusive, intercultural education have been implemented by 7 NGOs encompassing cc 200 children and youth | No | No |
| Output 3.2 Educational institutions CSOs and other partners have collaborated to promote peacebuilding, diversity and social cohesion in the field of education. | Indicator 3.2.1 School based programmes implemented | B 2014: n/a | T 2015: At least three school based programmes implemented | On track - The preparation and delivery of school-based programs and non-formal education programs is currently underway through implementation of 11 education small grants | Through 11 education-focused small-scale grant projects, cooperation with more than 70 primary and secondary schools in ¦BiH (and the region) is foreseen. | Based on current projections (through 11 small grants) the target indicator can be expanded from 3 to 20 school-based programs |
|  | Indicator 3.2.2 Trainings and workshops organized | B 2014: n/a | T 2015: At least 3 organized | On track - So far, 145 trainings and workshops have been organized for 1,137 pupils (children and youth) and 5 trainings for 118 teachers | Original target projections have been surpassed as a result of receiving a large number of quality applications through the small grants facility, allowing for a larger number of trainings for a larger, more diverse, target group. | No |
| Output 3.3 Vulnerable groups strengthened their capacities to be equally included in the decision-making process at the municipal/local level | Indicator 3.3.1 Workshops conducted | T2014: n/a | B 2015: At least 5 workshops conducted | Indicator exceeded - 10 entrepreneurship workshops successfully held targeting Roma youth (176) and youth with disabilities (139) from 23 BiH municipalities | Each vulnerable group has specific needs and requires a specific approach. To strengthen the capacities of 2 groups of vulnerable youth (Roma and youth with disabilities) workshops were separately held for each target group (5 workshops x 2 groups) | No |
|  | Indicator 3.3.2 Initiatives implemented | T2014: n/a | B2015: At least three initiatives implemented | Indicator reached - Based on 146 entreprenuership inititiaves proposed through workshops, 10 have been selected and implemented benefitting 150 vulnerable youth | No | No |
| Outcome 4 Citizens and communities promote culture, intercultural dialogue, trust building and appreciation of diversity to advance common peacebuilding goals. | Indicator 4.1 Culture issues addressed through the Platform conferences in support of UNESCO Universal Declaration on Cultural Diversity and 2005 Convention on the Protection and promotion of Diversity of Cultural Expressions | 2014: n/a | 2015: At least one session on culture issues in the Platform conference. | On track - Indicator reached : two conferences organized in April and Sep/Dec 2015 with thematic discussion on Culture. |  |  |
|  | Indicator 4.2 Culture related projects supported and implemented through the Grants facility | B2014: no culture related projects supported and implemented through the Grants facility | T 2015: At least 5 culture related projects supported and implemented through the Grants facility. At least 3 projects dedicated to the needs of vulnerable groups. | On track - Indicator reached : 19 culture related projects being implemented through the Grants facility according to the defined plan. Five projects had the vournable groups as the main beneficaries. |  |  |
| Output 4.1 Enhancing intercultural dialogue and fostering the role of culture through the Dialogue Platform | Indicator 4.1.1 Workshops conducted | B 2014: n/a | T2015: At least three workshops conducted. | On track - Indicator reached: 6 workshops conducted in Brcko, Banja Luka2, Bihac, Mostar and Sarajevo. |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 Increasing participation and engagement by citizens, civil society and leaders in intercultural dialogue activities and initiatives. | Indicator 4.2.1 Initiatives implemented. | B 2014: n/a | T2015: At least 5 initiatives implemented | On track/ Indicator reached : through the implemnation of 7 initiatives. |  |  |
|  | Indicator 4.2.2 Research and analysis projects. | B2014:n/a | T 2015: At least three research and analysis projects | At the stage of data collection and preparation.Mapping relevant stakeholders and interesting projects in the field of culture and peacebuilding completed in cooperation with RCO PDA. |  |  |
| Output 4.3 Vulnerable groups empowered to promote social inclusion, diversity, gender equality and peacebuilding in the field of culture. | Indicator 4.3.1 CSOs representing vulnerable and marginalized groups participating at the Dialogue Platform conferences | B 2014: n/a | T 2015:At least three CSOs . | On track/ Indicator reached: 5 CSO representing marginalized groups participated in two doelogues platform conferences held in 20015. |  |  |
|  | Indicator 4.3.2 Initiatives implemented. | B2014: n/a | T 2015: At least 3 implemented | On track/ Indicator reached: 5 initiatives implemented. |  |  |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | 700,000 youth in BiH make up 20% of the overall population with a highest unemployment rate in Europe (over 60%) and an extremely fragmented education system which offers no connection with real sector employment needs. Youth is thus marginalized, socially excluded and without proper and continuous institutional representation. Such position offers plethora of opportunities for radicalization, hate speech, violence and social unrests. In conjunction with the ongoing DFF peacebuildig and promotion of diversity initiatives a stronger focus should be placed on economic integration of youth, as well as general risks of radicalization of youth. Both these elements are of relevance to peacebuilding initiatives in the country. |
| --- | --- |
| Lesson 2 (1000 character limit) | The need for strengthening institutional cooperation between the governmental and non-governmental sector. The absence of an adequate mechanism, which defines or establishes a form of collaboration that would overcome the lack of communication between them, mostly conducted through grants and financing. There is an absence of everyday communication through which there would be a joint influence on the positive processes for the establishing of dialogue and trust, intercultural understanding , networking. The projects that have been financed through DFF grants for cultural component have demonstrated significant unutilized potential of the non-governmental sector, which initiatives would lead to rapid advances if they were to be institutionally accepted and supported. This is the reason why a dialogue with competent ministries on all levels has been initiated, with the aim of institutionalizing and improving cooperation. |
| Lesson 3 (1000 character limit) | In a highly administratively fragmented country as is BiH, decision-making processes are dissolved over many levels. The fact that the program DFF has maintained strong endorsement from the highest state level, the BiH Presidency, has resulted in a positive catalytic atmosphere, but it was in no way a guarantee for implementation of grant activities in local communities. More specifically, certain initiatives could be blocked at the level of the ministries and schools, despite having had strong support by the BiH Presidency. Such bottleneck procedures highlighted the necessity to combine top-down and bottom-up approaches in grant promotion and implementation. In many cases, a bottom-up push strategy from motivated schools (i.e. directors and teachers) was recognized as key to successful grant implementation. |
| Lesson 4 (1000 character limit) | Institutional positioning of youth, but also of youth policy development, monitoring, evaluation needs to be strengthened and integrated across all governmental sectors. Institutional youth mechanisms should be reconsidered and positioned within council of ministers (BiH) and governments (Entity level) not within specific ministries which incorporate issues of youth. Youth as a cross-sectoral issue needs to be streamlined into all governments' work programmes. |
| Lesson 5 (1000 character limit) | Certain bottlenecks have been identified, which do not relate directly to Project output indicators or the results framework, but primarily the ability to fully operationalize recommendations from dialogue mechanisms which proved its functionality. With a complex state structure and institutional overlaps, as well as open jurisdictional issues, a challenge is to develop a coordination mechanism which could create a pathway for implementation of recommendations. Otherwise, dialogue platform mechanism could raise awareness and create dialogue but its long term results would end with no concrete policy changes. |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

Time to “Jump Out”

Dialogue for the Future Project initiated and facilitated airing of a TV Show titled “Jump Out”. Total of 20 episodes focused on stimulating dialogue amongst youth and bringing positive youth stories closer to youth and the general public. TV Show targets promotion of co-existence and diversity within communities in BiH as a critical peacebuilding element 20 years after the conflict.

“Jump Out” responds to the fact that youth across Bosnia and Herzegovina have very limited possibilities to cooperate and communicate mutually and presents intercultural understanding and education as the basis for developing positive dialogue amongst future decision-makers.

777,000 youth in BiH (aged 15-30), representing 20.5% of the overall BiH population is faced with unemployment (60%), poor connection between the education system and labor and employment sector and lack of ability and/or will for engagement consequently manifesting itself through low political participation (Only 5% of young people are members of youth organization, 6% are members of political parties and 1% are members of representative bodies of youth).

TV Show gave an opportunity to BiH youth to present their projects, challenges, affinities and interests to a country-wide audience. Stories presented “Jump Out” from every day realities faced in BiH. They emphasize brave youth, with courage to stand out, make a first step of trust building and develop friendships that are lifelong.

“Whilst we often hear a platitude remark that the World rests on youth, youth in our country unfortunately have insufficient opportunities to present their problems and opinions and are often remarked upon as passive and uninterested segment of the society. Jump Out definitely sticks out of the pattern as it offers young people an opportunity to be heard.” Ivona Narančić Jump Out TV Show presenter.

To date, 20 TV episodes had an estimated 890,560 viewers on state television, 27,494 Youtube and 135,419 FB views.

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures are on track, slightly delayed, or off track:

If expenditure is delayed or off track, please provide a brief explanation (500 characters maximum):

Please provide an overview of expensed project budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: Established dialogue spaces for decision makers, civil society and citizens that enable country wide peacebuilding process to promote coexistence, trust building and appreciation of diversity. |
| Output 1.1 | Establishment of Dialogue and Peacebuilding Platform. | UNDP | 1. Staff and other personell:73,700.00 USD 2. Supplies commodities, materials: 5,000.00 USD 3. Contractual services including M&E and research: 668,334.00 USD 4. Travel: 25,000.00 5. General operating and other direct costs: 84,359.00 USD | 1. Staff and other personell: 45,379.53 USD 2. Supplies, commodities and materials: 4,363.07 USD 3. Contractual services including M&E and research: 592,025.18 USD 4. Travel. 18,621.67 USD 5. General operating and other direct costs: 10,090.83 USD | The budget approved by the donor has been submitted and approved in form of lump planned costs per category. |
| Output 1.2 | Small Projects and Grants Facility is established to support local and civic initiatives promoting peaceful coexistence, trust building, intercultural dielogue and appreciation of diversity | UNDP | Please see Outcome 1. |  |  |
| Output 1.3 | Awareness raised and interest generated among the broader population for participation in the dialogue Platform and Grants Facility. | UNDP |  |  |  |
| Outcome 2: Increased participation, awareness and influence of youth civil society organizations in policy dialogue with decision makers on issues impacting B&H's development and reform agenda. |
| Output 2.1 | Work stream established within the Dialogue Platform for youth and youth civil society organizations that provides an opportunity to influence policy making on key development issues in the country and in relation to improving intercultural dialogue and understanding in particular. | UNDP |  |  |  |
| Output 2.2 |  |  |  |  |  |
| Output 2.3 |  |  |  |  |  |
| Outcome 3: Education and peacebuilding initiatives support greater social cohesion at national level and in targeted communities |
| Output 3.1 | Policy-makers, education professionals, civil society and other relevant stakeholders at different levels have discussed the importance of peacebuilding, diversity and social cohesion in the field of education | UNICEF | Staff: 40,000.00 USD, Supplies: 3,600.00 USD | 26,156.63 | Preliminary data covers period Nov 2014- Nov 2015 Indirect costs included. |
| Output 3.2 | Educational institutions CSOs and other partners have collaborated to promote peacebuilding, diversity and social cohesion in the field of education | UNICEF | Contractual Services: 438,333.00 USD | 312,110.51 | Preliminary data covers period Nov 2014- Nov 2015 Indirect costs included |
| Output 3.3 | Vulnerable groups strengthened their capacities to be equally included in the decision-making process at the municipal/local level | UNICEF | Travel: 4,000.00 USD General operating and other direct costs: 23,000.00 USD Indirect costs: 35,625 | 27,135.41 | Preliminary data covers period Nov 2014- Nov 2015 Indirect costs included |
| Outcome 4: Citizens and communities promote culture, intercultural dialogue, trust building and appreciation of diversity to advance common peacebuilding goals. |
| Output 4.1 | Enhancing intercultural dialogue and fostering the role of culture through the Dialogue Platform. | UNESCO | Staff and other personnel 35,000 Supplies, Commodities, Materials 4,500.00 Contractual services 438,333(of which 28,333 forM&E and Research and 400,000 for Small Grants*) Travel 3,000.00 General Operating and other Direct Costs 23,000 Indirect Support Costs 35,268 | Staff and other personnel 34,099 Supplies, Commodities, Materials 0 Contractual services 402.936 Travel 2,168.12 General Operating and other Direct Costs 10.482 Indirect Support Costs 22.654 |  |
| Output 4.2 | Increasing participation and engagement by citizens, civil society and leaders in intercultural dialogue activities and initiatives. | UNESCO |  |  |  |
| Output 4.3 | Vulnerable groups empowered to promote social inclusion, diversity, gender equality and peacebuilding in the field of culture. | UNESCO |  |  |  |
| Total: |  |  |  |  |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when); or whether any changes are envisaged in the near future (2000 character maximum):

Whilst the Project was successful in implementing the Outputs, mindful of future continuation of Project activities one should stress the need to place additional efforts on developing better guidelines for streamlining management and supervision arrangements for implementation of UN Joint Programmes. A more focused delineation of duties and responsibilities of all agencies' staff working on the Project as well as more centralized reporting lines is paramount for an effective and efficient implementation of Joint Programmes.

Throughout 2015 Project continuously worked on establishing cooperation with other similar projects in Bosnia and Herzegovina such as USAID financed project PRO Budućnost. Although very similar in structure of activity components, the USAID project differs from the DFF in a sense that it is dealing with the past, working in limited number of local communities, and does not strategically involve decision makers. DFF project initiated several meetings with USAID’s project team, unfortunately, substantive cooperation was absent.

DFF project has close cooperation with UNDP project "Building and Consolidating National Capacities for Conflict Prevention" financed by the EU whereby DFF project used its dialogue platform to introduce the modality of European Youth Parliament work, emphasizing EU perspectives for youth of BiH.

The existing national system for coordination of youth issues was not functioning in previous political setup, however, the DFF received a letter from the Secretary General of the BiH Ministry of Civil Affairs, on behalf of the newly appointed Commission for Coordination of Youth Issues in BiH, seeking cooperation and support for development and implementation of the work plan targeting volunteerism, diaspora, radicalization, hate speech and hooliganism.

The DFF project team, upon invitation, also visited UN CO in Pristina, Kosovo,and shared good practices with colleagues there.

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.