RUNO ANNUAL PROJECT REPORT		TEMPLATE 4.4

PEACEBUILDING FUND (PBF)

ANNUAL PROJECT progress report

COUNTRY: Liberia

REPORTING PERIOD: 1 january – 31 December

| Programme Title & Project Number |  |  |
| --- | --- | --- |
| Programme Title: Community Base Truth Telling & Atonement Project Programme Number (if applicable) PBF/LBR/A-11 MPTF Office Project Reference Number: 00088032 |  |  |

| Recipient UN Organizations |  |  | Implementing Partners |  |
| --- | --- | --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: UNDP |  |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: Independent National Commission on Human Rights |  |
| Programme/Project Budget (US$) |  |  | Programme Duration |  |
| PBF contribution (by RUNO) US$1,000,000.00 |  |  | Overall Duration (months) 36 months |  |
|  |  |  | Start Date (dd.mm.yyyy) 30-10-2013 |  |
| Government Contribution (if applicable) N/A |  |  | Original End Date (dd.mm.yyyy) | 30-10-2016 |
| Other Contributions (donors) (if applicable) $308,000.00 |  |  | Current End date(dd.mm.yyyy) 31-10-2016 |  |
| TOTAL: | US$1,308,000.00 |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Assessment/Review - if applicable please attach Yes No Date: 20-07-14 Mid-Term Evaluation Report – if applicable please attach Yes No Date: |  | Name: Tonieh A. Talery-Wiles Title: Project Manager Participating Organization (Lead): Independent National Commission on Human Rights Email address: |

PART 1 – RESULTS PROGRESS

  - Assessment of the current project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project is contributing:

Priority Plan Outcome to which the project is contributing. Communities in pilot locations have adequate mechanisms for dealing with the past through the Palava Hut process for truth telling, atonement and reconciliation.

Priority Plan Outcome indicator(s) to which project is contributing. 1.1: Proportion of cases taken up by the Palava Hut that are resolved (diaggregated by cases submitted by men/women) 1.2: Proportion of women in the Palava Hut Committees 1.3: Percentage of citizens in pilot locations who are positive about the national reconciliation process disaggregated by men/women

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  Project Outcomes: Communities are reconciled and live in peaceful coexistence utilizing the Palava Hut system/approach to settle their differences.

Rate the current status of the outcome:

| Indicator 1: INCHR has capacity to implement project. Indicator 2: Palava Hut methodology and mechanisms developed and being utilized in communities Indicator 3: | Baseline: Limited technical capacity Target: Responsive technical capacity by 2014 Progress: Eight of the staff members of the INCHR/PMU have acquired new knowledge and skills from a number of trainings in monitoring and evaluation, result-based reporting, project development and management, community building and restorative justice, peacebuilding and conflict resolution, procurement management, and human resource management. The establishment of the PMU and the trainings and knowledge acquired by the staff has capacitated the INCHR in the design and development of project proposals and concept notes, work plans, monitoring and evaluation plans with increased knowledge about baselines, indicators, targets and means of verification and in result-based report writing. The INCHR has a new chairperson, which has restored the confidence of Liberians, CSOs and international partners in working with the Commission to achieve its mandate. Baseline: September 2013: No methodological framework for palava hut. Target: Palava Hut methodology and guidelines developed in 2014 Progress: All of the technical modalities for the conduct of the ethnographic forums whose outcome will inform the development of the methodological framework for the palava hut hearings have been concluded. The UNDP has begun the process of recruiting two consultants (national and international) for the conduct of the ethnographic forums, mapping of war-related violations that can be addrssed under the palava hut and development of methodology and guidelines for the palava hut hearings. Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

PMU set up with seven staff members. Eight staff members of INCHR/PMU trained; Two jeeps, four motorbikes, computers and other equipment received; TOR for institutional assessment developed and UNDP requested to recruit international consultant. TORs for ethnographic forums, mapping  of war-related violations and development of palava hut methodology and guidelines developed and UNDP to recruit consultants. TOR for study tour developed and contacts made in Sierra Leone and Rwanda. One memorial erected to humanize the dead; 4 war-affected districts identified and consultations held with local stakeholders for piloting of  palava hut hearings; 4 palava hut committees restructured; CSOs identified to conduct awareness about palava hut process; 11 forums on clarification of INCHR mandate related to TRC recommendations held in five counties with 290 people attending the forums ensuring gender equitable representation . Quarterly and biannual reports available.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Eight of the staff of the INCHR/PMU have acquired new knowledge and skills in M&E, result-based reporting, project development and management, community building and restorative justice, peacebuilding  & conflict resolution, procurement and human resource managements. The knowledge acquired by the staff has capacitated the INCHR/PMU in the design and development of project proposals and concept notes, work plans, monitoring and evaluation plans with increased knowledge about baselines, indicators, targets and means of verification and in result-based report writing. The INCHR has a new chairperson, which has restored the confidence of Liberians, CSOs and international partners in working with the Commission to achieve its mandate. The initiation of the process of memorialization as a vital agency of community cleansing and healing  and the identification of districts hardly hit by the civil war in which the Palava Hut program will be piloted, is a significanrt marker of progress  made in enhancing and sustaining citizens' confidence in the Palava Hut as the national framework for reconcling communities and fostering peaceful coexistence. The deeper understanding and clarity acquired by political parties, CSOs, student, youth and minority groups about the INCHR mandate related to the TRC recommendations, has further heightened citizens' involvement in the Palava Hut Program as evidenced by the current growing level of strategic engagement between the INCHR, CSOs, traditional leaders, political leaders and other stakeholders through consultations.

During the Technical National Palava Hut Forum held at the Monrovia City Hall in Monrovia on November 13-15, 2013, the son of President William R. Tolbert who was slain during the April 12, 1980 military coup, Rev. William R. Tolbert, III, openly apologized to the people of Liberia for any wrongdoings committed against them by his family and others who had run the political affairs of the country before the bloody coup. He narrated his experiences while in detention in the aftermath of the coup.

In response, the chiefs and traditional leaders from the 15 political sub-divisions of Liberia at the forum apologized to the Tolbert and other families who were victimized as a result of the coup and asked forgiveness. That moment of mutual acknowledgement of wrongdoings and statement of apology involving the son of an assassinated President and the traditional authorities from across the country, combined with their avowed commitments to the palava hut program, constitutes a positive effect on the national reconciliation and healing process in the framework of the National Palava Hut Program.

However, progress toward the implementation of the  key principal activities (development of palava hut methodology, training of CSOs to raise awareness about the process, safety and benefits of the palava hut system and conduct of the palava hut hearings) of the project has been unforeseeably slow.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Challenges that have impeded progress: 1.The Ebola outbreak in Liberia, which was never foreseen, has greatly impeded progress of the achievement of key outputs of the project as a result of restrictions on free movement and right to assembly associated with the state of emergency and curfew imposed by government; 2. Change in leadership of PMU; 3. The bureaucratic process of UNDP to secure logistics/supplies and make payments for services by vendors; 4. Lack of effective internet service to enhance communication between INCHR and its partners 5. Failure of stakeholders to secure a qualified local firm to undertake ethnographic study after a long bidding process; Mitigation strategy: 1. The PMU has used the Ebola period to prepare for post-Ebola activities; 2. New PMU  Manager has been recruited;

3. Continued engagement of the UNDP for bureaucratic flexibility and timely procurement of logistics/supplies and payments for services by vendors.

Outcome Statement 2:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Outcome Statement 3:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Outcome Statement 4:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender in the reporting period

| Evidence base: What is the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | 1. Quarterly and year-end reports 2. Field reports with attendance listing 3. Minutes and note to the file of weekly staff meetings and other internal meetings 4. CDs of radio interviews by staff members 5. Training workshop reports |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | Not much funding has been provided by the Government of Liberia for peace and reconciliation, especially for the palava hut program. For example, for 2013/2014 a total of 5 million was earmarked by the Government, less than $125,000 was made available to INCHR for programs, including the palava hut. For 2014/2015, $600,000 was allocated by the Government but has not yet been made available to the INCHR due to budget challenges posed by the Ebola virus disease. Thus, the PBF project has filled critical funding gaps in peacebuilding in Liberia. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | The project enabled INCHR to clarify its mandate in terms of the implementation of the TRC recommendations affording people the opportunity to understand the core functions of the Commission in monitoring and investigating human rights complaints, abuses and violations. The project has also strengthened INCHR and its civil society partners and given people the confidence that war-related violations will be addressed and lingering psychological wounds will be healed through community truth telling, antonement and reconciliation. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | The traditional palava hut process has always been practised at the community level to address local minor crimes. Using the palava hut to address national war-related crimes is an innovation. The ethnographic study is crucial in this respect because it provides the basis for the formulation of the methodology of a national palava hut process. |
| Gender: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | The project has in-built criteria to ensure equal and equitable women and men representation on the palava hut committees and in the selection of CSOs to implement the palava hut outreach activities. The criteria are also used in other project activities such as workshops, trainings and even the PMU staff. In addition, gender disaggregated data are collected and reflected in all reports. |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) | The issue of Ebola has impacted gravely on the implementation of the project. As a result, we have integrated Ebola awareness and prevention strategies into the 4th quarter activities as well as planning for post-Ebola activities. |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | Despite public skepticism about the commitment of the Government of Liberia to support the implementation of the TRC recommendations including the Palava Hut, the National Traditional Council headed Chief Zarzar Kawah and the majority of citizens still have confidence and belief in the peace process as evidenced by their expressed commitment to support and participate in the national reconciliation process through the National palava Hut Program. |
| --- | --- |
| Lesson 2 (1000 character limit) | The INCHR's coordination role that was initially contested as being beyond its mandate, has now been accepted and supported by relevant stakeholders (traditional and religious leaders, women and youth leaders, student groups, and political leaders) and th citizens in general as a result of awareness created by the INCHR in relation to its mandate on the TRC recommendations that include the Palava Hut Program. |
| Lesson 3 (1000 character limit) | Unless the current sole dependency of the INCHR on international funding support to implement the Palava Hut Program is minimized through government support, the full achievement of reconciliation and peaceful coexistence at the community level as envisioned by the Palava Hut Program is far from realization. |
| Lesson 4 (1000 character limit) | The outbreak of the Ebola epidemic has expanded and deepened the parameters of the original task of the Palava Hut Program by introducing new conflict factors not evisaged under the Reconciliation Roadmap which might require a rethink of its implementation. |
| Lesson 5 (1000 character limit) | The overall coordination of the implementation of the reconciliation activities is weak in terms of information sharing that promote the building of synergies on issues that cut across or are related to individual projects, such as gender, decentralization and land reform issues. |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

The agreement of the community leaders and residents to offer the piece of land that hosts the Duport Road Massacre Site for the contruction of a memorial and their continued involvement in current efforts for the erection of the memorial, testifies to the citizens' appreciation of and support to the process of community healing and cleansing under the Palava Hut Program. The  INCHR now has  a more responsive technical capacity as some of its key staff members have grown in competency,  professionalism  and efficiency through the training opportunities  provided under the project.

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures are on track, slightly delayed, or off track:

If expenditure is delayed or off track, please provide a brief explanation (500 characters maximum):

Please provide an overview of expensed project budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: Communities are reconciled and live in peaceful coexistence utilizing the palava hut system/approach to settle their differences. |  |  |  |  |  |
| Output 1.1 | Output 1:INCHR capacity strengthened | UNDP | 182,926.80 | 122,349.29 |  |
| Output 1.2 | Output 2: Studies conducted | UNDP | 179,500.00 | 4,410.00 |  |
| Output 1.3 | Output 3: Nationwide outreach conducted | UNDP | 186,573.20 | 49,376.00 |  |
| Outcome 2: |  |  |  |  |  |
| Output 2.1 | Output 4: palava hut process piloted | UNDP | 321,000.00 | 11,000.00 |  |
| Output 2.2 | Output 5: aleast 2 regional memorials constructed | UNDP | 130,000.00 | 57,025.00 |  |
| Output 2.3 |  |  |  |  |  |
| Outcome 3: |  |  |  |  |  |
| Output 3.1 |  |  |  |  |  |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: |  |  |  |  |  |
| Output 4.1 |  |  |  |  |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total: |  |  |  |  |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when); or whether any changes are envisaged in the near future (2000 character maximum):

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.