RUNO ANNUAL PROJECT REPORT		TEMPLATE 4.4

PEACEBUILDING FUND (PBF)

ANNUAL PROJECT progress report

COUNTRY: Liberia

REPORTING PERIOD: 1 january – 31 December

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: Enhancing Access to Security and Justice at the Decentralized Level – Harper Hub, covering Maryland, Grand Kru and River Gee; Zwedru Hub, servicing Grand Gedeh and Sinoe Counties. Programme Number (if applicable) PBF/LBR/B-2 MPTF Office Project Reference Number: 00088191 |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: UNDP |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: The Liberian Judiciary; Ministry of Justice and its law enforcement agencies including the Liberia National Police, Bureau for Immigration and Naturalization, Solicitor General’s Office, Bureau for Corrections and Rehabilitation; Probation Program; Juvenile Diversion Program; SGBV Crimes Unit; Independent National Commission on Human Rights |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) US$ 3,062,405 |  |  | Overall Duration (months) 25 months |  |
|  |  |  | Start Date (dd.mm.yyyy) 22.11. 2013 |  |
| Government Contribution (if applicable) In kind contribution to house the existing justice and security officials deployed in Hubs 2 and 3 region in existing infrastructure. Ending 2014/2015 budget cycle, salaries and recurrent costs for justice and security officers deployed to provide 6 priority services. |  |  | Original End Date (dd.mm.yyyy) | 31.12.2015 |
| Other Contributions (donors) (if applicable) ECOWAS construction of BIN border barracks and LNP barracks in hubs 2 and 3 regions. UNDP SGBV Joint Programme support of approximately US$130,000 for motorcycles, fuel and stationery (Grand Gedeh, Grand Kru and River Gee counties). Nationwide support on mobile trial screen, judges training and advance training for investigators. |  |  | Current End date(dd.mm.yyyy) 31.12.2015 |  |
| TOTAL: | US$ 3,062,405 |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Assessment/Review - if applicable please attach Yes No Date: Mid-Term Evaluation Report – if applicable please attach Yes No Date: |  | Name: Joyce Frankfort / Nelson Mbu Title: Program Manager JSJP/Project Manager JSP UNDP Participating Organization (Lead): MOJ/UNDP Email address: jfrankfort@gmail.com / nelson.mbu@undp.org |

PART 1 – RESULTS PROGRESS

  - Assessment of the current project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project is contributing:

Priority Plan Outcome to which the project is contributing. LPP Outcome 1: Enhanced access to justice and community security at the regional and county levels in preparation for UNMIL transition.

Priority Plan Outcome indicator(s) to which project is contributing. 1.1 - % of justice and security services provided by the Harper and Zwedru Regional Hubs. 1.2 - % of people who feel safe or very safe in their community (disaggregated by county in the Hub region). 1.3 - % of people who trust the court system (disaggregated by Hub region). 1.4 - % of criminal cases adjudicated per court term (CT) (disaggregated by type of case and by county). 1.5 - # of trials on SGBV cases held in the Hub regions (disaggregated by county and by court term). 1.6 - # of cases prosecuted by the SGBV CU.

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  Outcome 1: People in Maryland, River Gee and Grand Kru (Hub 2), Grand Gedeh and Sinoe (Hub 3) Counties have increased access to fair and accountable justice services

Rate the current status of the outcome:

| Indicator 1: # of assistant county attorneys and public defenders in Hubs 2 and 3 counties. Indicator 2: Indicator 3: | Baseline: 22 November 2013: 1 county attorney per county (paid by Government of Liberia). 1 public defender per county (paid by Government of Liberia). Target: 31 December 2015: Assistant County Attorney - Harper Hub: Maryland (x3), River Gee (x1), Grand Kru (x1); Zwedru Hub: Grand Gedeh (x3); Sinoe (x1); Public Defenders - Harper Hub: Maryland, River Gee and Grand Kru (1 per county); Zwedru Hub: Grand Gedeh and Sinoe (1 per county) Progress:November 2014: Law school graduates were recruited and trained as legal counsels (x9) and public defenders (x5). Training entailed both pre-deployment and 2 months on-the-job, where individuals shadowed more experience lawyers on the art of prosecution and defense. Deployment was conducted in May 2014 and since then are providing adequate services in the regions. Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Output 1.1: Justice sector institutions have adequate human capacity to provide key justice services.

The deployment of nine legal counsels, five public defenders, 10 human rights and five public outreach officers  to counties in hubs 2 and 3 in May and June 2014 was the achievement of this output.To date, even in light of the Ebola crisis, justice services are being delivered in these counties, albeit at a slower pace, attributed by the onset of EVD.

Output 1.2: Infrastructure and operational arrangements in place to provide key justice services

Mobility has been secured and delivered to justice actors working in the regions. However, the spread of EVD affected the delivery of key operational equipment due to restricted access into ports of entry (sea and air).

Output 1.3: Justice and security  community-based justice & accountability services available to citizens.

Recruitment and deployment of HR monitors ensures citizens rights are upheld, monitored and reported.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

The deployment of additional justice actors to the regions has contributed to an increase in access to justice for the people of these counties.  During this reporting period and as a preventative measure against the deadly EVD and its possible spread in the prison population, the Ministry of Justice and the Judiciary jointly requested that their service providers use other methods within the Law to process offenders of minor crimes.  To this end, reports from all five counties under hubs two and three are showing that measures such as alternative dispute resolutions (ADR) methods, suriety bond, jail delivery and Nolle Pro se Qui [Section 18.1 of the Criminal Procedure Law (CPL)] are being used to divert and reduce offenders of minor crimes from prisons, thereby reducing the pre-trial detention rate and the risk of spreading EVD.  This is important, as before the deployment of additional staff, it is reported that county attorneys and public defenders (1 per county) could not manage on their own to institute these measures and carry out their regular prosecutorial duties.  Therefore the strengthening of criminal justice actors in the counties are making an impact on increased access to justice for citizens in these counties.

For example, the public defender of the Grand Gedeh County 7th Judicial Circuit in collaboration with state prosecutors and human rights monitors reported the disposal of 75 cases in line with Section 18.2 of the CPL between February and October 2014, with most cases administered after the deployment of additional staff.  River Gee, a small and remote county with poor road networks was also able to dispose of four pre-trial detention cases during the August term of Court by again exercising Section 18.2 of the CPL.

All of these small but effective efforts help to set the stage for an increased access to justice for the people of the region.  By the provision of additonal support staff who are willing and capable to attend to the legal needs of the people, more people will be able to seek redress to their individual and collective problems by exercising the rule of law, thereby reducing the need for violence, whilst improving their trust in the justice system.

The project is contributing to peacebuilding as when more people are able to access justice in a reasonable time due to the availability of capable manpower, the need for voilence and conflict triggers, such as 'justice delayed is justice denied', are reduced.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

The project has made tremendous progress and is currently on track with significant peacebuilding results, such as prosecution of cases, reduction in pre-trial detention rate, as justice services are being provided in the region.  However, the spread of the EVD has had a negative impact on the roll out of additional services in hubs 2 and 3.  During the months between February and October, Liberia experienced an aggressive increase in the number of deaths caused by EVD throughout its rural and urban areas.  In an effort to curtail the spread, in August, the Country was placed under a 'state of emergency' for a period of three months.  During this time, movements were limited and government institutions were asked to implement a 'go slow' measure, which affected the daily operation of institutions.

With EVD cases apparently reducing and the imminent lifting of the 'state of emergency', the recruitment, training and deployment of the regional coordinator and sexual gender based violence staff could possibly take place in Q 1 of 2015.  Also taking place in early 2015 will be the public outreach / awareness campaign on services provided by the Hubs, which has been halted by the spread of EVD.

Outcome Statement 2:  People in Maryland, River Gee and Grand Kru Counties (Hub 2); Grand Gedeh and Sinoe (Hub 3) benefit from justice advisory, human rights monitoring, advocacy and support services provided by civil society.

Rate the current status of the outcome:

| Indicator 1: # of human rights monitors deployed to Hubs 2 and 3 counties. Indicator 2: Indicator 3: | Baseline: 22 November 2013: Harper Hub: Maryland - 0, River Gee - 0, Grand Kru - 0; Zwedru Hub: Grand Gedeh - 0, Sinoe - 0 Target: 31 December 2015: Harper Hub: Maryland - 2, River Gee - 2, Grand Kru - 2; Zwedru Hub: Grand Gedeh - 2, Sinoe - 2 Progress:November 2014: 10 human rights monitors recruited, trained and deployed to hubs 2 and 3 counties. Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Output 5.2:  Justice advisory, human rights monitoring, advocacy and support services provided by CSOs to communities in Maryland, River Gee, Grand Kru (Hub 2); Grand Gedeh and Sinoe (Hub 3) Counties.

10 human rights monitors were recruited, trained and deployed to hubs 2 and 3 counties in May and are currently working with key stakeholders to ensure that citizens rights are adhered to.  Recruitment process of CSOs to provide justice advisory services to citizens of the region are ongoing, but slow due to the onset of EVD, as Hubs 2 and 3 counties were quarantined between the months of July to October 2014.

Output 5.3:  Human rights monitoring services provided by the Independent Human Rights Commission (INCHR)

10 human rights monitors (8 male and 2 female) recruited and trained through the INCHR were deployed in May 2014.  These monitors are currently working with justice actors in the regions to ensure that citizens' rights are upheld and violations reduced.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

The recruitment, training and deployment of 10 human rights officers to hubs 2 and 3 counties to effectively monitor and report on human rights violations by justice actors is an important achievement of this outcome.  Reports from prosecutors, human rights monitors and public defenders during this period show that awareness of citizens rights, especially as it relates to the lack of adequate prison facility is highlighted.  For example, the newly deployed Maryland County legal counsels noted the following - "the lack of toilet facilities within prison cells serves as a means for jail breaks, since in most cases, prisoners are compelled to have access to toilet facility away from the prison compound, albeit accompany by untrained prison warders who serve as volunteers in the facility".

Human rights monitors also work closely with justice actors in ensuring that extended over stay of pre-trial detainees are highlighted in the administration of justice and as a result and since their deployment and as stated above, 75 cases have been disposed of in line with Section 18.2 of the CPL between February and October 2014, with most cases adminstered after the deployment of additional staff.  In River Gee, a small and remote county with poor road networks was also able to dispose of four pre-trial detention cases during the August term of Court by again exercising Section 18.2 of the CPL.   Giving that pre-trial detainees are speedily getting their day in court, decreases in the need for rioting and jail breaks are prevalent.   This speaks to the contribution of the outcome to peacebuilding efforts as although two out of five counties reported jail breaks during this period, which could easily be attributed to prolonged pretrial detention and poor or inadequate facilities, the fact that legal counsels from Grand Kru, Sinoe and Maryland are highlighting this issue in their reports gives room for redress by senior authorities, thereby increasing the chances of rehabilitation of these facilities and limiting the recurrence of similar violations.

In addition, monitors provide education to prisoners on their fundamental rights, including their rights to privacy, visitation, property, religion, medical care and how to access the courts and other justice systems.  During this period, it is also reported that monitors, along with public outreach officers worked and supported county health teams during EVD outreach to ensure that human rights messages and services provided by the hub were noted at the helm of services provided in all five counties.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

As stated earlier, the unforseen spread of EVD in Liberia and the imposition of the 'state of emergency' have negatively affected the roll out of the CSO project into the counties, especially because civil society groups and NGOs are expected to work with grass roots institutions, both at county and community levels, which were often times 'blocked' due to limited access.

The spread of EVD currently seems to be slowing down and should this trend continue then it is hoped that the roll out of the CSO project could possibly commence in the first quarter of 2015.

Outcome Statement 3:  People in Maryland, River Gee and Grand Kru (Hub 2) and Grand Gedeh and Sinoe Counties are empowered as communities to manage conflicts in a manner that is integrated with the formal systems and strengthens the interface between statutory and customary systems.

Rate the current status of the outcome:

| Indicator 1: # of local traditional leaders trained and working with CSOs and PSOs on justice advisory and governance issues in hubs 2 and 3 counties. Indicator 2: Indicator 3: | Baseline: 22 November 2013: Harper Hub: Maryland - 0, River Gee - 0, Grand Kru - 0; Zwedru Hub: Grand Gedeh - 0, Sinoe - 0 Target: 31 December 2015: Harper Hub: Maryland - 10, River Gee - 10, Grand Kru - 10; Zwedru Hub: Grand Gedeh - 10, Sinoe - 10 Progress:November 2014: Due to the onset of EVD, there is no progress made yet. Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Output 6.1: Local Traditional leaders (and CSOs working on justice advisory issues) are trained in governance and justice sector rights and obligations and coordination with formal sector actors.

Meetings with key stakeholders focused on the initial mapping of traditional justice issues that are relevant to formal justice/advisory services, including enchanced access to justice for citizens in hubs 2 and 3 counties.  Unfortunately, progress in this project came to a halt with the spread of EVD, as implementation requires consultations with stakeholders, who are based in the counties.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Giving that the project was designed to ensure that traditional authorities work with formal justice actors, both individually and in groups, including through meetings to empower people to interface the formal and informal justice systems as a means of ensuring amicable settlements of dispute in communities, the onset of EVD made this impossible to accomplish.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

The onset of the Ebola Virus Disease hampered the implementation of this project.  The spread of EVD currently seems to be slowing down and should this trend continue then it is hoped that the roll out of the training of traditional leaders on justice advisory and governance issues could possibly commence in the first quarter of 2015.

Outcome Statement 4:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender in the reporting period

| Evidence base: What is the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | This report is based on statistic and written narrative reports received from criminal justice actors deployed to Hubs 2 and 3 counties to provide justice services and increase access to justice for the citizens. Information provided in this report has been discussed and validated by heads of justice and security institutions, who are deployed and operating in hubs 2 and 3 counties. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | This project has filled a critical funding gap in Liberia, as the strengthening of justice and security institutions, in terms of personnel and infrastructure, is a pre-requisite for peace in any post conflict country. After the war, the sector infrastructure was devastated. There was low human capacity with few qualified personnel, including police, judges, prosecutors, public defenders, law professors, legal policy experts and correction officers. Similarly, the physical infrastructure was also non-existent. All of these challenges contributed to the mis-trust citizens held of the system and justice, if any, was centralized in Monrovia and assumed for the rich. Giving that the concept is focused on a holistic and de-concentrated effort for justice and security service delivery at the county and regional level, this funding has been instrumental in securing the peace in the region. The use of the funding to recruit, train and deploy capable and qualified service providers, such as human rights monitors to ensure that citizens rights are upheld and public outreach officers who receive complaints on criminal justice actors who violate their code of conduct and other actors that are willing and able to work to reform the system has helped to restore citizens' hope in the justice system, thereby reducing their need for mob justice, but making use of the rule of law, which maintains the peace. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | The deployment of other justice actors in hubs 2 and 3 counties are intended to strengthen institutions in the administration of justice, including the prosecution of cases at the circuit court level. This strengthening created a gap for qualified prosecutorial staff at the magisterial court level. With the provision of salaries and operational cost for 20 city solicitors included in the Government of Liberia fiscal 2013/2014 budget, but no funding for training, the Solicitor General requested the then Justice and Security Board to approve an amount of US$52,606 to facilitate the recruitment and training of 20 law school graduates into city solicitors. This funding was provided from the Swedish contribution to the justice and security trust fund and approved by the Board in its 31st January 2014 meeting. A six weeks intensive training course was administered during April to May 2014, producing 18 city solicitors (2 dropped out). Trained city solicitors (16 men and 2 women) are scheduled to be deployed nationwide, including four of the five counties covered by hubs 2 and 3. The deployment of city solicitors to these four counties will help fill the gap as identified by prosecutors in their May and August term reports. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | The innovation of this project rests in the deployment of national human rights monitors and public outreach officers, who before the roll out of services into hubs 2 and 3, did not exist. The benefit of public outreach officers to the regions is the provision of referral and complaints mechanisms, whilst that of the human rights monitors is enhanced monitoring and awareness of human rights in the region. The acceptability of the community and criminal justice actors to both these services was a risky venture, as now they are expected to uphold their code of conduct and change how they provide services to the public. The provision of these two service has provided a platform where people know they can access for redress. |
| Gender: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | Gender mainstreaming is an important consideration in this project and it has been made in the framing and implementation of the project, as demonstrated in the recruitment process, which encouraged the participation of female candidates. This consideration is also noted in the number of justice actors recruited, trained and deployed, as well as, in the number of women who benefit from the services provided. Similarly, 2 of 10 human rights monitors and 2 out of the 18 trained city solicitors are women. |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) | - |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | Lesson learned relates to the project processes and management, but specifically to the change in project implementation. The roll of services that do not require infrastructure is innovative; however, criminal justice actors need the required logistics, mobility and equipment to be effective when deployed. This was not the case in the implementation of this project and going forward, deployment should be aligned with the provision of these items in mind, in order that service is not compromised and criminal justice actors can be realistically held to provide the service they were hired to do. |
| --- | --- |
| Lesson 2 (1000 character limit) | This project has triggered the establishment of an enabling environment and forum whereby justice actors from both the Judiciary and the Ministry of Justice meet to analyse / review challenges attendent to the sector and at the same time proffer solutions with the view to accelerate access to justice in hubs 2 and 3 counties. |
| Lesson 3 (1000 character limit) | The complaints mechanism as established in hub 1 and rolled out in this region has shown to be a positive measure, as justice actors within this region are compelled to adhere to their respective codes of conduct, knowing that the absence of which will mean that defaulters will be brought to book. Also, through the various discussions held of this mechanism, those citizens are now aware that there exists an avenue of redress. |
| Lesson 4 (1000 character limit) |  |
| Lesson 5 (1000 character limit) |  |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures are on track, slightly delayed, or off track:

If expenditure is delayed or off track, please provide a brief explanation (500 characters maximum):

Please provide an overview of expensed project budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: |
| Output 1.1 | Justice sector institutions have adequate human capacity to provide key justice service | UNDP | US$971,091.00 | US$588,729.00 | Expenditure does not include outstanding advance to MoJ |
| Output 1.2 | Local Traditional leaders (CSOs working on justice advisory issues) are trained in governance and justice sectors rights and obligations and coordination with formal sector actorsance | UNDP | US$579,010.00 | US$130,153.00 |  |
| Output 1.3 | Justice advisory, human rights monitoring, advocacy and support services provided by CSOs to communities in Maryland, River Gee, Grand Kru (Hub 2); Grand Gedeh and Sinoe (Hub 3) counties | UNDP | US$1,042,219 | US$142,469.00 |  |
| Outcome 2: |
| Output 2.1 | Programme Management | UNDP | US$470,085.00 | US$78,870.00 |  |
| Output 2.2 |  |  |  |  |  |
| Output 2.3 |  |  |  |  |  |
| Outcome 3: |
| Output 3.1 |  |  |  |  |  |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: |
| Output 4.1 |  |  |  |  |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total: |  |  | US$3,062,405.00 | US$960,221.00 |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when); or whether any changes are envisaged in the near future (2000 character maximum):

The management arrangement has been effective albeit with capacity challenges with national partners in the understanding of UNDP rules and procedures and challenges in the timely procurement of goods/logistical support for staff on the part of UNDP.  To increase efficiency   and accelerate programme delivery, UNDP has provided training through a designed project " Support to National Implementation" to build the capacity of technical staff working in these line ministries and agencies on reporting through face form and other UNDP rules. Additionally, UNDP is working closely with national partners in securing specifications in a timely manner for goods and services to be procured.  Quite recently the JSP Board recommended a restructure of itself which gives rights to new structures within the programme namely the Policy Board, Sector Finance Committee and project implementation team. This new structure has so far accelerated implementation of the programme albeit constrained by EVD.

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.