RUNO ANNUAL PROJECT REPORT		TEMPLATE 4.4

PEACEBUILDING FUND (PBF)

ANNUAL PROJECT progress report

COUNTRY: KYRGYZSTAN

REPORTING PERIOD: 1 january – 31 December

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: KGZ/A-1: Strengthening capacities of LSGs for peacebuilding Programme Number (if applicable) Project ID: 00088475 MPTF Office Project Reference Number: |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: UNDP, UNICEF |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: Department for Ethnic and Religious Policy and Collaboration with Civil Society (Office of the President), State Agency on Local Self-Governance and Inter-Ethnic Relations,Ministry of Social Development, Inter-Agency Commission to coordinate implementation of the Concept for National Unity and Interethnic Relations, State Commission on Religious Affairs, Assembly of People of Kyrgyzstan, Local Self-Governance (LSG) bodies in selected districts |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) USD 1,728,877 - UNICEF: 228,876 - UNDP: USD 1,500,001 |  |  | Overall Duration (months) 30 |  |
|  |  |  | Start Date (dd.mm.yyyy) 01.01.2014 |  |
| Government Contribution (if applicable) |  |  | Original End Date (dd.mm.yyyy) | 30.06.2016 |
| Other Contributions (donors) (if applicable) |  |  | Current End date(dd.mm.yyyy) 30.06.2016 |  |
| TOTAL: | USD 1,728,877 |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Assessment/Review - if applicable please attach Yes No Date: Mid-Term Evaluation Report – if applicable please attach Yes No Date: |  | Name: Title: Participating Organization (Lead): Email address: |

PART 1 – RESULTS PROGRESS

  - Assessment of the current project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project is contributing:

Priority Plan Outcome to which the project is contributing. Local self-government bodies, in partnership with related state institutions and civil society bridge divisions and reduce local tensions.

Priority Plan Outcome indicator(s) to which project is contributing. PP Indicator 5: Number of disputes taken up and documented by formal or informal local institutions increased (How many resolved, how many unresolved) PP Indicator 6: Number of violent disputes decreases within targeted LSGs PP Indicator 7: Citizens’ trust in targeted LSGs increased (Disaggregated by geographic location, ethnic minority and gender) PP Indicator 8: Percentage of existing LSG-led local grievance resolution mechanisms and decision-making bodies in targeted communities that include under-represented groups

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  State institutions and LSGs collaborate to bridge local divides and implement the Concept for National Unity and Inter-Ethnic Relations

Rate the current status of the outcome:

| Indicator 1: Number of cases relating to conflicts that LSGs targeted in the project have addressed with support of the Agency for LSG Affairs and Interethnic Relations and their affiliated structures (with breakdown of how many of those were resolved) Indicator 2: Number of joint initiatives carried out by the Agency for LSG Affairs and Interethnic Relations in collaboration with other state bodies and /or civil society to increase the percentage of under-represented groups in LSG-led local grievance resolution mechanisms and decision-making bodies (breakdown of how many of those were successful, e.g. because they resulted in policy changes, actual increase in representation etc.) Indicator 3: | Baseline: Out of 108 conflicts registered in 2014 GAMSUMO intervened in 21 cases. Thus the average percentage of GAMSUMO cooperation with LSGs in resolving local conflicts comprise above 19%. Target: at least 10% increase by 2016 Progress:on track Baseline: TBC Target: at least 20% increase by 2016 Progress:on track Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Monitoring Centre under the Government Agency for LSG and Interethnic Relations (GAMSUMO) prepared 20 analytical notes, 8 full reports and 2 baseline surveys on the most critical topics identified by Office of President and GAMSUMO. Moreover overall facts and findings from monitoring reports form the basis for conflict mapping software which has visualized potential hot spots geographically. Capacities of the Agency and 20 district level public reception centres of GAMSUMO were built in grant management tailored for conflict prevention and peace-building needs. Public reception centers have been linked to 14 multi-stakeholder Local Development Committees (which include under-represented groups) which have drafted and implemented 35 local development projects based on action plans prepared in 2014 as a result of participatory conflict analysis. 20  local projects supported through local budgets after being discussed and approved at the sessions of Local Councils.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reports and analytical notes on interethnic relations prepared by the Monitoring Centre of GAMSUMO helped mobilizing officials at the local and national level to engage in early responses. Reports provided recommendations (through office memos) to Office of President (1), Government Apparatus (1), Intelligence Service (1), Ministry of Interior (1), Ministry of Defense (1), Ministry of Justice (1), and leaders of media houses (2) and LSGs on how to address inter-ethnic issues (number of reports increased during election period). Some immediate responses followed in mass media which discontinue spreading rumors about possible interethnic frictions, Osh airport changed their performance to non-discrimination, Christian cemetery transferred to Tokmok Mayor’s office (to stop private discriminative decision making), political parties receive warning notes for fueling inter-ethnic tensions, number of field visits of the Agency staff to LSGs increased along with cooperation with Peoples Assembly of Kyrgyzstan and #10 Department of the Ministry of Interior. The Agency also responded to conflicts through internal grant component which was widely announced, effectively managed and monitored using revised guidelines. 14 Local Development Committees (chaired by LSGs) organized participatory process of preparing project proposals based on conflict analysis, included projects into agenda of the local councils to get support and funding from local budgets, monitored implementation of 35 local initiatives. The Agency and local LSGs in partnership with Ministry of Interior launched capacity building interventions for Public Preventive Centers (PPC) to strengthen their role in crime prevention and public outreach especially to vulnerable groups.  Local communities reported decreased crime rate after PPCs’s work.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Implementation of some local projects was done through LSG special accounts which required financial reporting to treasury in compliance with national standards. According to new regulations procurement of goods and services should be organized despite any amount received and by certified personnel. It turned out that some LSGs do not have people with such certificates. Moreover LSGs do not have experience in project management including financial management. To address above UNDP through special training center under Ministry of Finance, Treasury staff and NGOs organized field trainings on procurement, financial management and project management.

Outcome Statement 2:  State institutions and LSGs jointly reduce local tensions through gender-responsive peacebuilding initiatives and promotion of religious diversity

Rate the current status of the outcome:

| Indicator 1: % of women in LSG-led local grievance resolution mechanisms and decision-making bodies Indicator 2: National policy on religious affairs in place, providing a framework for the promotion of religious diversity and freedom Indicator 3: Number of vulnerable and poor identified and assisted by LSGs | Baseline: In general the level of women participation in peace-building processes at the local level including women working in executive LSG bodies (in fact decision making bodies) comprise around 41%. Target: At least 10 % increase by June 2016 Progress:on track Baseline: No such policy in place Target: Policy approved by June 2016 Progress:Policy already approved in November 2014 Baseline: 29,632 Target: At least 10 % increase by June 2016 Progress:on track |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

To implement gender responsive local action plans LSGs supported 8 out of 35 local projects which directly address women needs and women's engagement in protest actions and conflicts including 2 Gender Centers.

State Commission for Religious Affairs under Office of President presented new religious policy and action plan to local authorities, law enforcement structures and religious leaders in 7 oblasts which provoked heated debates among the audience. It is expected that local administrations will internalize strategic documents by reviewing local strategic plans.

Government Regulation introducing case management as a way to detect and address social  vulnerabilities was signed by Prime Minister on June 22. To enforce the Regulation set of implementation documents were developed including methodological guidelines, tailored training and coaching programs. 20 per cent of selected municipalities have been trained.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

To implement gender responsive local action plans LSGs' gender focal points and gender councils mobilized local women including those participating in conflicts and protest actions to prepare project proposals. As a result of this participatory process 8 out of 35 projects have been developed based on real needs of local women. Thus instead of attending protest actions women attemt to resolve the problem of shortage of kindergartens, organize inter-cultural exchange festivals between different ethnic groups, provide legal, psychological and life-skills training to vulnerable women and victims of violence, engage in income-generating projects etc.

UNDP supported State Commission for Religious Affairs under Office of President to finalize action plan to religious policy and supporting documents which were presented to key stakeholders in all 7 provinces. During the workshops the authorities, law enforcement structures and religious leaders had an opportunity to get qualified information about religious situation in the country, Government’s strategic priorities, upcoming reforms and changes in legislation etc. and share their concerns, proposals and financial/substantial needs. It is expected that local administrations will internalize strategic documents by reviewing local strategic plans and providing reports on the progress of religious policy implementation.

Coordinated partnership across the sectors and public administration levels, i.e. central, regional and local, around outreach, needs assessment and social support provision to vulnerable people is being institutionalised. The latter contributes to the improvement  in responsiveness of local authorities and service providers.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Local authorities displayed serious resistance to engaging women who attended protest actions into discussions of local priorities and preparing projects (some women were included into black list). This problem was resolved after series of individual consultations with both sides and involvement of external facilitators.                                                                                                                 Delay in approval of the Governmental Regulation on case management has affected planned schedule of capacity buiding activities in targeted municipalities. However, measures were taken to mobilise additional trainers and resources to catch up with initial timeframe.

Outcome Statement 3:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Outcome Statement 4:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender in the reporting period

| Evidence base: What is the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | 20 analytical notes, 8 full reports and 2 baseline surveys were produced by Monitoring Center under GAMSUMO and forwarded to respective government agencies along with official memos. Package of supporting documents to religious policy (action plan, situation brief, guideline how to implement religious policy) have been prepared and discussed at 7 regional workshops. 35 project proposals have been drafted during the participatory workshops chaired by LSGs. Regulation on case management is approved by Government Decree #391 on 22 June 2015 and available in the legal database Toktom. Methodological guidelines and training programs to enforce the Regulation finalised and applied in targeted municipalities. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | Kyrgyzstan practices double budgeting modality (budgets are formed from local and national resources), however most of target LSGs are subsidized through the state budget. In addition, due to limited resources, GAMSUMO and target LSGs only have a very small budget envisaged for activities. Due to budget constraint Government did not approve action plan to religious policy and provided State Commision for Religious Affairs only with limited budget for staffing. Therefore this project fills a critical funding gap. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | Reports and analytical notes prepared by Monitoring Center helped to resolve some tensions. Thus some immediate responses followed in mass media which discontinue spreading rumors about possible interethnic frictions, Osh airport changed their performance to non-discrimination, Christian cemetery transferred to Tokmok Mayor’s office (to stop private discriminatory decision making), political parties receive warning notes for fueling inter-ethnic tensions, number of field visits of the Agency staff to LSGs increased along with cooperation with Peoples Assembly of Kyrgyzstan and #10 Department of the Ministry of Interior. To be able to get local co-funding LSGs and community leaders worked with member of local councils to introduce their projects into their agenda. Implementation of some local projects was done through LSG special accounts which required financial reporting to treasury in compliance with national standards. According to new regulations procurement of goods and services should be organized despite any amount received and by certified personnel. Through this project LSG and community leaders received certified training in procurement, project management including financial management. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | Upon request of GAMSUMO the Monitoring Center prepared conflict mapping software which is based on conflict monitoring during the period 2014-2015 and which identifies potential hot spots. However the nature of conflicts in Kyrgyzstan is so multi-faceted and hidden that it may emerge in any other place different from what is shown on the map. Moreover such maps should be regularly updated but capacity of GAMSUMO at the moment is not sufficient for such exercise. Despite the fact that Government did not approve action plan to religious policy along with budget (possibly due to sensitivity of the issue in the parliamentary elections) UNDP supported State Commission on Religious Affairs in drafting supporting documents to religious policy and organizing regional workshops to discuss those strategic documents and get feedback. Religious policy document mainly refers to legal provisions which will be amended but it did not happen this year. |
| Gender: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | The project applied both qualitative and quantitative approaches to women empowerment. Thus, it ensured women's inclusion in each activity (e.g. at least 30% women representation in trainings, workshops, grant preparation and implementation processes). 8 out of 35 projects either run by women organization or directly address gender equality problem. Moreover gender mainstreamed into the rest projects. 2 projects are implemented by women earlier engaged in protest actions. 2 gender centers established and serve the needs of vulnerable women including victims of violence. |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) |  |

1.3 INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (250 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Local self-government bodies, in partnership with related state institutions and civil society bridge divisions and reduce local tensions. | Indicator 1.1 Number of disputes taken up and documented by formal or informal local institutions increased | To be identified in the inception phase | 15% increase in number over baseline by end of 2016 |  |  |  |
|  | Indicator 1.2 Number of violent disputes decreases within targeted LSGs | To be identified in the inception phase | 10% decrease in number over baseline by end of 2016 |  |  |  |
|  | Indicator 1.3 Citizens’ trust in targeted LSGs increased | To be identified in the inception phase | 20% increase over baseline by end of 2016 |  |  |  |
| Output 1.1 State Institutions and LSGs collaborate to bridge local divides and implement the Concept for National Unity and Interethnic Relations | Indicator 1.1.1 Number of cases relating to conflicts that LSGs targeted in the project have addressed with support of the Agency for LSG Affairs and Interethnic Relations and their affiliated structures (with breakdown of how many of those were resolved) | Out of 108 conflicts registered in 2014 GAMSUMO intervened in 21 cases. Thus the average percentage of GAMSUMO cooperation with LSGs in resolving local conflicts comprise above 19%. | At least 10 % increase by June 2016 | on track |  |  |
|  | Indicator 1.1.2 Number of joint initiatives carried out by the Agency for LSG Affairs and Interethnic Relations in collaboration with other state bodies and /or civil society to increase the percentage of under-represented groups in LSG-led local grievance resolutio | To be identified in the inception phase | At least 20 % increase by June 2016 | on track |  |  |
| Output 1.2 State institutions and LSGs jointly reduce local tensions through gender-responsive peacebuilding initiatives and promotion of religious diversity | Indicator 1.2.1 % of women in LSG-led local grievance resolution mechanisms and decision-making bodies | In general the level of women participation in peace-building processes at the local level including women working in executive LSG bodies (in fact decision making bodies) comprise around 41%. | At least 10 % increase by June 2016 | on track |  |  |
|  | Indicator 1.2.2 National policy on religious affairs in place, providing a framework for the promotion of religious diversity and freedom | No such policy in place | Policy approved by June 2016 | on track |  |  |
| Output 1.3 | Indicator 1.3.1 |  |  |  |  |  |
|  | Indicator 1.3.2 |  |  |  |  |  |
| Outcome 2 | Indicator 2.1 |  |  |  |  |  |
|  | Indicator 2.2 |  |  |  |  |  |
| Output 2.1 | Indicator 2.1.1 |  |  |  |  |  |
|  | Indicator 2.1.2 |  |  |  |  |  |
| Output 2.2 | Indicator 2.2.1 |  |  |  |  |  |
|  | Indicator 2.2.2 |  |  |  |  |  |
| Output 2.3 | Indicator 2.3.1 # of vulnerable and poor (families with children, youth and minorities) identified and assisted at local level | # of requests to LSG for social support | 10% increase in number over baseline | On track. 21,4% (3 out of 14 municipalities trained to identify and assist vulnerable and poor children and families) |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | In 2015 UNDP and GAMSUMO jointly decided to attract National Institute for Strategic Studies (NISS is a national think tank under Prime Minister’s Office) for implementation of the project on monitoring center. NISS status as state body which has direct access to all Government entities and extensive expert pool allowed to substantially improve quality of monitoring reports and research and its relevance (Government sets research priorities to NISS). Thus prior to launching field research NISS experts consulted with GAMSUMO and Office of President and identified three critical topics: integrative role of People’s Assembly of Kyrgyzstan, ‘kayrylmans’ and their integration into society (migrants – ethnic Kyrgyz from other countries) and language policy and its conflict potential. These research projects are tailored in a way to produce practical recommendations to be further translated into policies or reforms. |
| --- | --- |
| Lesson 2 (1000 character limit) | UNDP invested a lot of efforts to persuade LSGs to involve women engaged in protest actions into project activities. For example in Karakol UNDP facilitated women needs assessment (to integrate into gender center program) with involvement of protester-women without representatives of Mayor’s Office while in Maevka protester-women regularly attended project design consultations and authorities of both LSG and District Administration freed from their regular interference/claims and blocking of local meetings and public hearings. However despite numerous efforts problem of exclusion remains acute. Each side stands to their point and does not want to reach compromise. |
| Lesson 3 (1000 character limit) | Re-election of LSG Heads in several LSGs accompanied by power struggle (including dispute resolution through courts) divided not only administration staff but also communities. Small projects based on conflict analysis earlier discussed and approved by previous LSG leaders have to be re-considered and re-visited by new leaders. There were cases when UNDP invested more efforts in working with new leaders and launching mediation processes. |
| Lesson 4 (1000 character limit) |  |
| Lesson 5 (1000 character limit) |  |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures are on track, slightly delayed, or off track:

If expenditure is delayed or off track, please provide a brief explanation (500 characters maximum):

Please provide an overview of expensed project budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: State institutions and LSGs collaborate to bridge local divides and implement the Concept for National Unity and Inter-Ethnic Relations |
| Output 1.1 | State Agency for Local Self-Governance and Inter-Ethnic Relations effectively mentors and supports LSGs and other partners to bridge divisions and reduce tensions at the national and local levels. | UNDP | 65000 | 81206 |  |
| Output 1.2 | Agency for Local Self-Governance and Inter-Ethnic Relations effectively supports LSGs and civil society to monitor local conflicts and inter-ethnic relations and engage in early preventive action | UNDP | 416579 | 314251.6 |  |
| Output 1.3 | The Inter-Agency Committee effectively coordinates the implementation of the Concept for National Unity and Inter-Ethnic Relations | UNDP | 25000 | 23403.67 |  |
| Outcome 2: LSGs monitor and address local tensions in collaboration with other state institutions and civil society, reduce inequalities and engage in the implementation of the Concept for National Unity and Inter-Ethnic Relations |
| Output 2.1 | LSGs and local communities in selected districts support gender-responsive local peacebuilding | UNDP | 45893.35 | 24438 |  |
| Output 2.2 | Improved policy, institutional capacity and awareness to promote ethnic and religious freedom and diversity | UNDP | 133665 | 84718 |  |
| Output 2.3 | Selected LSGs and related state institutions (district state administration and social protection) detect vulnerabilities and reduce tension via direct service delivery and refer to specialized support (social cash transfers and services) | UNICEF | 101658 | 62458 |  |
| Outcome 3: |
| Output 3.1 |  |  |  |  |  |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: |
| Output 4.1 | Administrative and GMS expenses | UNDP | 119912 | 56223 |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total: |  | UNDP | 806049.35 | 584240.70 |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when); or whether any changes are envisaged in the near future (2000 character maximum):

The project has been following the arrangement initially planned in the project proposal. There is a body that oversees overall processes and may perform quality assurance and monitoring functions through its Oversight Group. The day-to-day management of the project is shared across the two agencies. Agencies which coordinate project activities through regular meetings and traditional communication means. UNDP field officers are in a regular contact with the UNICEF implementing partners in field. Government Agency on LSG and Interethnic plays an important role of the national partner, participating in delivering key inputs and monitoring the progress.

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.