| Insert Logo for Participating UN Organisation(s) |  |  |
| --- | --- | --- |

Iraq Public Sector Modernization Programme (I-PSM)-Phase II

MPTF OFfice GENERIC finalprogramme NARRATIVE report

REPORTING PERIOD: from Jan to Dec 2014

| Programme Title & Project Number |  | Country, Locality(s), Priority Area(s) / Strategic Results |
| --- | --- | --- |
| Programme Title: Iraq Public Sector Modernization Programme (I-PSM)-Phase II Programme Number: P1-05 MPTF Office Project Reference Number: |  | (if applicable) Country/Region Nationwide; Piloting in Basra, Najaf, Salaheddine and Duhok Governorates |
|  |  | Priority area/ strategic results UNDAF Priority Area 1: Improved governance, including protection of human rights: The Iraqi state has more efficient, accountable and participatory governance at national and sub-national levels. |
| Participating Organization(s) |  | Implementing Partners |
| Organizations that have received direct funding from the MPTF Office under this programme: UNDP, UNICEF, UNESCO, UNESCWA, UNFPA, UN-Habitat, UNWOMEN, and WHO |  | National counterparts (government, private, NGOs & others) and other International Organizations PMAC, COMSEC, MoP, MoH, MoE, MoP, MoHESR, MMPW, MoST, MoSPA, MoF, MoSWA both in Baghdad and KRG |
| Programme/Project Cost (US$) |  | Programme Duration |
| Total approved budget as per project document: MPTF /JP Contribution: By Agency (if applicable) | US$ 17,845,412 |  | Overall Duration (months) Start Date (dd.mm.yyyy) | 24 Months 1st January 2013 |
| UNDP: US$ 4,173,844 UNESCO: US$ 2,227,228 UNESCWA: US$ 677,608 UNFPA: US$ 1,806,094 UN-Habitat: US$ 2,078,947 UNICEF: US$ 3,122,947 UNWOMEN: US$ 1,081,932 WHO: US$ 2,676,812 |  |  | Original End Date (dd.mm.yyyy) | 31st December 2014 |
| Government Contribution (if applicable) |  |  |  |  |
| Other Contributions (donors) (if applicable) |  |  | Current End date | 31 Dec 2015 |
| TOTAL: |  |  |  |  |
| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| Evaluation Completed Yes No Date: dd.mm.yyyy Evaluation Report - Attached Yes No Date: dd.mm.yyyy |  | Name: Hisham El Azzouni Title: IPSM M&E Specialist Participating Organization (Lead): UNDP Email address: Hisham.elazzouni@undp.org |

# EXECUTIVE SUMMARY

In 2014, with support of the I-PSM Programme, UN Participating Organizations continued its sincere technical support to the implementation of the national Public Administration Reform (PAR) Roadmap and its receptive 2014 AWP, thus aligning official development assistance with national development strategies.  PAR management structures at federal and provincial levels in close collaboration with UN Participating Organizations assumed full responsibilities to implement the reform activities as planned.  This went very well during the first half of the year before the complete halt of implementation due to the collapse of some Iraqi cities in the hands of ISIS, and the subsequent security and humanitarian consequences.  Nevertheless, reflecting a well-established credibility in the eyes of the government as an effective mechanism to advance PAR agenda in Iraq, IPSM received an additional funding from UNDAF TF amounting an aggregate of US$ 2.8 M to implement more mutually agreed PAR activities.    Moreover, the UNDAF SC has extended the program end date to Dec. 2015 instead of Dec. 2014,  The year 2014 has also brought a continued evidence of a behavioral change at the political and leadership levels with regard to the modernization and reform agenda.  The PSM accumulated achievements since the commencement of phase II inspired the new government to consider Public Sector Reform as essential element and high priority area for its four-year program (2015 – 2018) launched early 2015.  However, the delay incurred in passing the Budget Law for 2014 has hindered the implementation of joint activities with the GoI through cost-sharing modality and delivering the intended results.  Moreover, the abrupt deterioration of the security situation during the second half of the year 2014 coupled with the relocation of international staff within and outside Iraq has negatively impacted on the capacity of Participating UN Organizations to implement reform activities as planned. IPSM has technically halted for a period of time during which no activities were implemented and many UN staff members were evacuated.  In addition, some Participating UN Organizations were heavily tasked with the implementation of humanitarian interventions, from their own budget, in the highly affected areas especially in the northern part of Iraq.  However, starting from Oct 2014 UN Participating Organizations gradually resumed their presence in Baghdad and hence supporting the implementation of the reform activities.   On a different note, KPSM project document is still pending KRG approval and a clear political endorsement despite the several high-level meetings and presentations held in this regard.

# Purpose

The Iraq – Public Sector Modernization (I-PSM) Programme is a Government led joint UN programme supporting Iraq’s Strategic Government Plan (SGP) 2015-19 and it’s National Development Plan (NDP) 2013-2017. The programme is fully aligned with the UN Development Assistance Framework (UNDAF) 2011-2014.

The Programme has four themes: i) Developing policy and building machinery at the center of government for managing Public Sector Modernization (PSM); ii) Supporting system-wide reform for development management, gender mainstreaming, e-governance and national statistics; iii) Piloting reform in the three key sectors of health, education and water and sanitation (WATSAN); and iv) Supporting decentralized service delivery and local governance initiatives.

This Phase of the programme builds on lessons learned and recommendations emerging from the implementation and external evaluation of the I-PSM Phase I. I-PSM Phase I is the foundation for the analytical assessment and preparatory work enabling Government to develop a system-wide public administration reform plan, as well as sector-specific modernization plans for three pilot sectors and three pilot governorates.

By focusing on service delivery, the Government can demonstrate to the Iraqi people that public sector modernization has concrete and tangible benefits for the population as a whole. This Programme establishes synergies with existing UN programmes aimed at addressing corruption, involving the active participation of civil society, and integrating cross-cutting themes in relation to employment, gender, social inclusion and environment. The Programme ensures coordination with public sector reform initiatives of other bilateral and multilateral development partners and with other major UN joint programmes, primarily with the Local Area Development Programme (LADP) Phase-II, and also takes into account the achievements of the Private Sector Development Programme – Iraq (PSDP-I) to enhance synergy and avoid duplication.

Relevant NDP Goal(s):

The Iraq – Public Sector Modernization (I-PSM) programme is a Government of Iraq-led UN joint programme supporting Iraq’s Strategic Government Plan (SGP) 2011-14 and its National Development Plan (NDP) 2013-2017. The Programme is fully aligned with the UN Development Assistance Framework (UNDAF) 2011-2014 and the Country Programme Action Plan (CPAP) 2011-2014 of UNDP, UNICEF and UNFPA, as detailed below:

National Development Plan:

- Decentralization and Local Governance:

  - Increasing the level of administrative decentralization in sectoral ministries and governorates

  - Supporting Local government capacities to provide services

- Public Participation

  - Strengthening the principle of participatory planning

- Civil Service

  - Raise the efficiency of the governmental administrative body

- E-Governance

  - Developing a knowledge-based society and closing the digital gap

Millennium Development Goals (MDGs):

- MDG 3: Promote gender equality and empower women

- MDG 8: Develop a global partnership for development

Relevant UNDAF Outcome:

The programme will directly contribute to outcome 2: “The Iraqi state has more efficient, accountable and participatory governance at national and sub-national levels” under the UNDAF Priority Area 1: “Improved governance, including protection of human rights”.  In addition the Programme will indirectly contribute to UNDAF Priority Area 2 - Inclusive, more equitable and sustainable economic growth, and UNDAF Priority Area 4 - Increased access to quality essential services.

Programme Outputs:

The Programme targets the following four joint programme outputs:

- GoI has enhanced capacity to undertake public sector modernization at national, regional and governorate levels;

- GoI has improved public administration systems at national and sub-national levels;

- GoI is implementing reform and modernization plans in Education, Health and WATSAN sectors; and

- GoI sub-national governance and decentralized service delivery systems strengthened through enhanced participatory processes.

# Results

- Narrative reporting on results:

- Outcomes:

The IPSM programme is a full-fledged part of the UNDAF and directly contributes to the realization of outcome 2 of the UNDAF priority 1, which stipulates “the Iraqi state has more efficient, accountable and participatory governance at national and sub-national levels”.  The behavioral change that has been recorded during 2013 at the political and leadership levels as regards the reform agenda has continued in 2014.  The GoI has showcased increased engagement and serious involvement and support in leading the reform process and bringing together all national counterparts who otherwise would work separately in the public sector reform.   Furthermore, the accumulated IPSM achievements on the ground since the inception of phase II has inspired the new government established in Sept 2014 to consider Public Sector Reform as a major pillar and high priority area for its four-year program (2015 – 2018).  Achievements attained have also inspired more ministries/ institution/ governorates to participate in the implementation of PAR roadmap although they weren’t originally at the center of the focus at this stage.  Examples include Ministry of Youth and Sports, Municipality of Baghdad, and Karbala and Maysan Governorates.  Moreover, some ministries created their own teams to review organizational structure and job descriptions, and simplify existing procedures to respond effectively to the new government program while inspired by the momentum created by IPSM and guided by manuals and systems developed as well.

The PAR roadmap developed with the technical support provided by UNDP and endorsed by the Council of Ministers in 2013 has been the cornerstone for the design and implementation of AWP 2014 and successive plans in the years to follow.  The AWP 2014 was developed in a participatory consultative manner involving both Participating UN Organizations and all national counterparts, thus improving national ownership of the developed plans and ensuring alignment of IPSM plans with national development strategies such as the PAR Roadmap.  The clear division of implementation and management responsibilities amongst Participating UN Organizations, management structures and national counterparts enhanced the level of mutual accountability at all levels.

In implementing the AWP 2014, and despite the deteriorated security conditions that prevailed during the second half the year 2014, there was a continuous dialogue and coordination amongst management structures created at federal and provincial levels.  This is to implement activities as planned, deliver intended results and mitigate the negative impact the prevailing security conditions had on the working environment.  However, the implementation performance and hence the achievement of higher-level results were tremendously impacted by a combination of factors as highlighted in the challenges section of this report.  On a different note and with support of the Iraqi co-chairman of UNDAF TF, IPSM managed to mobilize additional resources from UNDAF TF amounting an aggregate of US$ 2.8 M to implement more PAR-related activities, thus reflecting a reliable mechanism to support the national reform agenda in Iraq.

IPSM will as such continue to contribute to the achievement of the UNDAF outcome 2.  However, performance indicators found in the IPSM project document need to be measured in two to three year timeframes to capture the results achieved on the ground and assess IPSM contribution to the achievement of UNDAF outcome 2 and other high level results.

- Outputs:

The Programme targets the following four joint programme outputs: (i) GoI has enhanced capacity to undertake public sector modernization at national, regional and governorate levels; (ii) GoI has improved public administration systems at national and sub-national levels; (iii) GoI is implementing reform and modernization plans in Education, Health and WATSAN sectors; and (iv) GoI sub-national governance and decentralized service delivery systems strengthened through enhanced participatory processes.

- GoI has enhanced capacity to undertake public sector modernization at national, regional and governorate levels:

This output is 83% achieved.  It is delivered by UNDP with support from UNWOMEN with respect to issues related to gender. This output focused on policy and structural level reforms for the whole of the government and in KRG, which is primarily based on the development of a National PSM Strategy. It is achieved through the inclusion of new institutional arrangements and the revision of distribution of roles, authority and decision-making mechanisms within Government, in addition to establishing new systems for Knowledge Management.  While the initial IPSM Project Document has anticipated the establishment of a PAR Directorate, the developments have led to the establishment of a PAR Management Committee at COMSEC.  Besides PMAC and the Council of Ministers Secretariat (COMSEC), the Public Administration Reform Higher Committee (PARHC), the Public Administration Reform Management Committee (PARMC) and Ministerial/ Provincial PAR Committees were established to manage the implementation of Public Administration Reform Agenda at different levels.

Key achievements include:

- As part of the support provided to the PAR Management Committee, the Unites Nations devised a Monitoring and Reporting System that is based on RBM principles and intended to record achievements and progress against planned results within the PAR Roadmap.  The System's conceptual and procedural frameworks have been finalized, automated by the COMSEC's IT department and is being tested.  It is expected that by Q2-2015 reporting on PAR implementation will be performed by implementing agencies through the web-based system.

- At Civil Service Reform (CSR) level, an advocacy and sensitization workshop was held on Feb. 2014 on the enactment of the Civil Service Law and establishment of the Civil Service Council; PMAC

- .  The workshop was sponsored by PMAC and attended by representatives of the key stakeholders with notable contribution of the Shura Council and COMSEC.  The workshop yielded a reconfirmation of the need to mitigate the limitations faced and a clear recommendation to work more closely with the newly elected Council of Representatives (CoR) for the enactment.

- Supporting PAR at Sub-National Level: The first draft of 2014 AWP for PAR activities in Basra, Al Najaf and Salah El Dein governorates was developed through a series of participatory planning workshops during the first quarter of the year. However, the mentioned governorates couldn’t implement the work plans due to the absence of annual budget law of 2014. Furthermore, the security situation was deteriorated in Salah El Dein governorate by third quarter of 2014

- At KRG level, UNDP’s IPSM team held several meetings with KRG Minster of Planning to present the programmatic focus of KPSM Programme, but also the prospected management arrangements in the region. The meetings discussed the limitations of approving the programme under the KRG Vision 2020 Facility Fund and resulted in reconfirming the importance of the proposed interventions.  UNDP will be working with H.E. the Minister of Planning and his team on reviewing the Project Document prior to its re-submission to the Facility Steering Committee for consideration.

- GoI has improved public administration systems at national and sub-national levels

This output is 65% achieved, but a lot is still expected during in the year 2015.  The output is delivered by UNDP jointly with UNESCWA, UNFPA and UNWOMEN and focused on reviewing and reforming existing administrative systems and procedures.  Through strengthening public administration systems, the programme’s lead partners, the Prime Minister’s Office (PMO), COMSEC, PARHC and the newly established PARMC and Ministerial PAR Committees are technically supported to instigate the required systems and procedural upgrades. The realization of this output has also included human resources development through the strengthening of the training capacity of both the federal and regional governments and the capacitation of the NCMDIT and KIPA. In addition, the National Statistical Systems and e-governance systems application were further enhanced, which has improved accountability within the administrative structures.

Key achievements include:

- Components of Senior Executive Service (SES) framework/ system, developed

- Executive Leadership Gap Assessment of SES Initiative completed at federal level and KRG.

- System for Senior Executive skill building developed in support to the humanitarian crisis in KRG

- Re-Structuring and Organizational Strengthening Toolkit, finalized and being applied at COMSEC and Basra Governorate.

- E-Governance Guidelines for National Architecture and Public Data Policy, finalized and launched

- e-HR system at Ministry of Science and Technology,  developed and evaluated for scaling up across Iraq.

- Methodological approach on “Government Interoperability Framework and National Enterprise Architecture (GIF/NEA)” developed and submitted for implementation

- Systems and services of greatest business value for the Iraqi citizen and public organizations and their implementation priority identified for “e-Governance Execution

- National strategy for e-governance, Government Interoperability Framework and National Enterprise Architecture developed.

- E-procurement and e-HR systems are under development

- Mandate, structure, objectives and operating mechanism for the Centre of Excellence, drafted and submitted to MoST together with the UNDP capacity building plan.

- Gender Responsive Budgeting (GRB) concept and principles, presented to ministries and governorates through awareness raising workshops and advocacy activities.

- A National Network on GRB comprises different line ministries, established.

- Gender Responsive Budget teams, established in eight ministries/ institutions, and an awareness- raising program launched.

- TOT modules on GRB, developed and being delivered.

- National Statistics system modernized in the fields of law, policies, and dissemination.

- Policies and procedures of networking are available in three languages (Arabic, Kurdish and English)

- Policy for dissemination of official statistics and media policy in KRSO was adopted, in Arabic language and translated into Kurdish and English, and published on KRSO website.

- A draft guide in Arabic for indicators (165 indicators) and concepts and terminology used in KRSO was prepared.

- A draft metadata structural guide was prepared for statistical variables but still need to update and addendum

- Strategic plans and outreach strategies developed for the NCMDIT and KIPA, developed

- GoI is implementing reform and modernization plans in Education, Health and WATSAN sectors

This output is 62% achieved.  It is supported by UNICEF, UNESCO, WHO, UNFPA and UN-Habitat; UNWOMEN will provide technical inputs in all three sectors in support of gender mainstreaming.  The output focuses on reforms in education, health, and water and sanitation sectors through implementation of sector specific modernization plans and capacity development programs, as per the agreed roadmaps of I-PSM Phase I by the relevant line ministries, including in the KRG. This output aims directly at improving service quality through development of service delivery models, focusing on rationalized use of financial resources in efficient and equitable manner as well as developing a medium-term fiscal framework to be a link between the policy making process, priorities and budget.

Key achievements include:

Education Sector:

- The six thematic studies for Baghdad and Kurdistan on School Based Management supporting sub-national governance and decentralized service delivery systems, completed and translated into Arabic and Kurdish languages and included:

  - Change Management Plan for School Based Management in Iraq

  - Guidelines for Implementing School-Based Management

  - School Financing Study for the Education Sector of Iraq

  - Expenditure Framework for Block Grants

  - Provincial Functional Mandates For the Education Sector of Iraq

  - School-Based Management Vision and Commitment Framework for Iraq

- A training toolkit for the training of school principals and head teachers on principles of SBM and administration, developed and pretested, and a TOT workshop was organized during the last quarter of the year for 16 head trainers who would in turn organize cascaded training in Dohuk, Basrah, Salahaddin and Najaf Governorates for school principals and head teachers A total of 16 education supervisors from 4 governorates where SBM approach is piloted, trained

- Role of the Academic Integrity and Code of Conduct (AICs) and students honor societies to promote academic integrity, developed

- AICs and the students honor societies in Basra and Dahuk universities, established.

- HEMIS Gap analysis, conducted for improved decision support

- Methodology for restructuring MoHESR, drafted

- Guidelines for developing job description for MoHESR, produced

- Under vocational education the following frameworks and reports developed and validated by MoE:

- Mission and tasks of the Directorate of General of Vocational Education developed;

- Mission and tasks of the various directorates of vocational education developed;

- Draft organizational structure of the Directorates General of Vocational Education developed

- General framework to reform the structure of vocational education

- General framework for the internal and external evaluation of vocational schools established.

Health Sector:

- National Health Policy, formally launched

- National Health Accounts (NHA) data, collected and analyzed

- NHA Guidelines, developed

- Mid-term Budget Finance document, developed and approved by the MoH

- Roles and Responsibilities document, developed and approved by MOH

- Roles and Responsibilities at different levels of MoH, developed and adopted

WATSAN Sector:

- Water Demand Management Study for Iraq was completed.

- Draft “Water and Sanitation Services and Management Law for Iraq”, produced and under refinement

- Fundamentals of GIS introduced to Directorate Surrounding Water of Duhok (DSWD) on how to apply them to their work using the ArcGIS software.

- ISO principles and fundamentals presented to MoMPW for application

- Principles of organizational structure, developing job description manuals and decentralization approach, introduced to MMPW to review its current laws and regulations

- GoI sub-national governance and decentralized service delivery systems strengthened through enhanced participatory processes

This output is 38% achieved due to the late selection of the pilot governorates by the government that has led to a subsequent delay in the activity implementation of this output and also the achievement of respective results.  This output is delivered by all Participating UN organizations.  This output is to instigate reform plans at the local level and is expected to strengthen the local governance institutions at the provincial and city-level, promote participatory processes, improve urban governance and support decentralized service delivery, including fiscal decentralization (downstream reform). This output also covers inclusiveness, creating civic and political awareness among marginalized groups, women and youth and will encourage their participation in public sector reform efforts. It also includes supporting organizational and legislative changes at the national and local levels to prepare the institutions to move to management pattern by the private sector, which represent the core of the reform process in changing the state's role in economic life.

Key achievements include:

- PAR Agenda initiated in Pilot Governorates through a series of induction workshops throughout the first half of the year targeting Najaf, Basra and Salahheddine

- 2014 draft PAR AWPs at sub-national level developed in participatory consultative manner for Basra, Al Najaf and Salah El Dein

- The e-province model and how it can be adopted at the governorate level, presented in a number of governorates, and being piloted in Wasit governorate in line with Wasit e-governance initiative

- Institutional Re-Structuring and Performance Enhancement toolkit introduced to Basra governorate

- The e-Province architecture and the ToRs for first six e-services for Misan Governorate developed

- Technical specifications for the design and development of Web Content Management and Collaboration Portal for Missan and Ninawa developed

- An action plan for decentralization process of Heath Sector, developed

- Plan for carrying out a health facility assessment in Duhok finalized, the questionnaires and survey methodology, developed, and the assessment carried out and finalized.

- A draft work plan for the implementation of the modernized health services package, developed in close coloration with Duhok governorate.

- Existing rules and regulations for water sector in Duhok assessed, and reform recommendations to enhance service delivery and related issues proposed and discussed with the counterparts.

- Assessments studies on the participation of women and youth finalized for Basrah and Najaf.

- Delays in implementation, challenges, lessons learned and best practices

Many of the challenges reported for the year 2013 remain valid during the year 2014.  They were further compounded by the prevailing security situation after the devastation of ISIS in June 2014.  In general, the encountered challenges have created unfavorable working conditions that have badly impacted on the ability of Participating UN Organizations to implement reform activities as planned and deliver the intended results.  Several consultancy missions were cancelled and many activities were postponed.  These in combination have ultimately led to a short-falling performance and delayed implementation when compared to the year 2013.  The most prominent challenges faced during 2014 are classified into the following categories:

UN-Specific Challenges

- Extravagant cost of Red Zone movements as well as travel to the governorates set by UNAMI

Security Conditions Prevailing in Iraq

- The abrupt deterioration of the security situation after June 2014 coupled with the relocation of international staff of Participating Organizations within and outside Iraq

- The collapse of some cities in the northern of Iraq in the hands of ISIS and the resultant mobilization of all national and international resources to encounter that danger.

- Prevailing security conditions resulted from sectarian violence restricted the movement of international staff outside the Green zone and hence limited the possibility of engagement with Government counterparts.

- The refusal of many international consultants to participant in events conducted in Iraq particularly Baghdad

Political Conditions

- The political instability and the delay in the formation of the new government in Iraq

- The delay incurred in passing the Budget Law of 2014 and the inability of Participating UN Organizations to tap on the cost sharing budget and hence implement joint activities with the GoI,

- Political deadlock in KR and subsequent slow-down of the KPSM process

- The delay in endorsing KPSM by MoP despite the several attempts led by UNDP to advocate for the importance of the KPSM to KR

- The significant delay in obtaining the Entry Visa to Iraq for the internationally recruited consultants

Management Structures and Performance of National Counterparts

- The conflict resulted from the existence of two parallel structures, PAR and IPSM, inside the participating ministries and the overlap of their responsibilities (WHO and UNESCO)

- The bureaucracy and delay in reviewing and approving the draft reports by line ministries and national counterparts (UNICEF)

- Poor coordination between CSO and KRSO on one hand, and between them and the ministries involved in statistical production on the other hand (UNFPA)

- Lack of a clear plan for CSO and KRSO to build the capacity of their staff in areas related to their project components

- Poor coordination between CSO and KRSO in the fields of manuals preparation, training of staff, awareness raising, and policies and procedures of work.

- Lack of national counterparts’ awareness about the PSM in the context of long-term national reform agenda.  Little work has been done by PARHC and PARMC to conduct awareness raising education sessions under output five of the PAR roadmap.  They could be partially ascribed to the deteriorated security conditions stemmed from the sectarian violence

- Lessons learned:

- In countries where there is high level of uncertainty, political unrest, steep decline in oil prices and/ or fragile economy, annual work planning for donor-funded initiatives should be conducted independently from national contribution, i.e. cost sharing or parallel funding.

- Official development assistance should be aligned with national development strategies to ensure better utilization of donor resources and delivery of significant results.

- Unless the Ministry of Finance is heavily involved in the reform process, Gender Responsive Budgeting will still face challenges in terms of practical implementation.

- Looking at the experiences of many countries, which went through transitions, moving from line item budgeting into program budgeting, which entails adopting sensitive gender programs, is a long and lengthy process. However, country contexts and should be emphasized to adopt country specific policies and approaches. (UNWOMEN)

- Public sector reform cannot be achieved in isolation but must be done within the overall framework of the entire civil service reform in Iraq.  This is because some civil service laws and regulations will have to be reviewed, strengthened or modified before any meaningful reform could be achieved. Apprehension is thus perceived from civil servants when reform ideas are discussed for example in MoE, especially as many assume that it will lead to job losses.

- Because of entrenched practices and outdated civil service rules and regulations, for SBM to be successful, there is the need to review and update by-laws, regulations and rules some at the ministry level and others at the national level.

- Increased engagement of national counterparts in the design, implementation and management of development initiatives increases the ownership of national counterparts to the development initiatives, and thus representing an ingredient of success.

- Joint planning, joint monitoring & evaluation, collaborative decision making and increased national engagement in the whole process side-by-side with Participating UN Organizations facilitate the reduction in duplicative activities across UN Organizations and between UN Organizations and their national counterparts.

- Iraq will require a longer period of time than first anticipated to effectively build the kind of capacity that is required to maximize and build on the assistance that is delivered through IPSM.  An exit strategy has to be then be developed by IPSM and geared toward sustainable phase-out of its activities

(d) Evaluation

As per IPSM Project Document, a mid-term review should have been conducted during the year 2014 by an outside international consultant who would assess the results achieved on the ground and the overall contribution of the programme to national development strategies.  However, due to the security situation prevailed during the second half of the year 2014, it was extremely difficult to conduct such an evaluation.  Most of the governmental institutions were heavily engaged with mitigating the adverse impact that the deteriorated security conditions had on the welfare of affected individuals and communities, and also the related humanitarian aspects.

- Qualitative assessment:

IPSM has established itself as one of the successful joint programs being implemented over the last two years.  It has established a considerable credibility in the eyes of the government as a tangible process that will provide results.  Nevertheless, the overall activity implementation rate during 2014 was in general low but accelerated over the fourth quarter of 2014.  Discrepancies were observed amongst Participating UN Organizations.  In general, IPSM has disbursed by the end of the year 2014 an aggregate of US$ 12,624,503.4, representing 61% of the total fund received.  If the rate of disbursement remains unchanged in the upcoming period, IPSM is highly expected to fully disburse the remaining funding beyond 2015.  The low implementation performance can be mostly ascribed to the prevailing sectarian violence and abrupt deterioration of the security situation during the second half of 2014 coupled with the relocation of international staff within and outside Iraq.  This situation has exhaustedly directed the national efforts to extensively focus on mitigation of the humanitarian consequences of such a crisis.  Participating UN Organizations were not an exception in this regard.  The capacity of Participating UN Organizations to implement reform activities as planned and deliver desired results was adversely impacted, during which period IPSM was technically halted where little if no activities were implemented and many UN staff members were evacuated.  Moreover, joint activities through cost-sharing mechanism haven’t been implemented due to the delay in approving the Budget Law for 2014.

Nevertheless, similar to 2013, year 2014 marked a number of significant milestones that highlighted fairly successful implementation of IPSM Program. Developing a web-based M&E tool for PAR Roadmap, finalizing SES components, finalizing the Scholl-Based Management Model and the start of its pilot testing, the development of the PAR AWP at sub-national level for a number of governorates, were some examples of the important milestones in the year 2014.

The Programme continued to bring together all national stakeholders concerned who otherwise work separately in the public reform sector, and created a common platform for cooperation between and amongst participating UN Agencies and national counterparts in this regards.  Given all above, there will be an enhanced complementarity of reform plans, reduction in duplicative activities across national counterparts, better planning and management of reform initiatives, and hence increased likelihood of achieving PAR results at different levels.

IPSM also implemented activities that were targeted towards the improvement of public administration systems at national and sub-national levels.  Systems were improved with support of participating UN Agencies during 2014 including for example Senior Executive Service, Re-Structuring and Organizational Strengthening Toolkit, eGovernance systems, National strategy for e-governance, Policy for dissemination of official statistics and media policy in KRSO, etc.  Short and medium term consequences of the improved systems on the welfare of individuals and communities have not materialized yet.  However, they are all ultimately intended to satisfy the needs and expectations of target populations by improving the efficiency of operation within public sector institutions and enhance the efficiency and effectiveness of the delivery of basic and essential services.  By focusing on improving service delivery, the Government can demonstrate to the Iraqi people that public sector modernization has concrete and tangible benefits for the population as a whole.

The activity implementation rate of reform and modernization plans in Education, Health and WATSAN sectors were moderate.  Reform and modernization plans in the three sectors were developed, and included for example: HEMIS Gap analysis, National Health Accounts, Roles and Responsibilities document for MoH, Water Demand Management Study for Iraq, etc.

Short-term consequences on the completed activities haven’t yet materialized.  However, strengthening autonomy of educational institutions through school based-management (PTAs) and increased autonomy of higher education institutions will enhance the quality, performance and accountability of educational institutions, and hence enhancing the quality of education.  The long-term goal of the National Heath Policy is to provide the entire Iraqi population with adequate access not only to primary health care but also to secondary and tertiary services through a well-functioning referral system.

With support of the participating UN Agencies, IPSM activities were implemented in close collaboration and partnership with the national counterparts as identified in the AWP 2014.  In addition, IPSM managed to mobilize an additional US$ 2.8 million from the UNDAF TF to support the implementation of UN-supported PAR activities.  On a different note, IPSM has achieved two of the five key principles of Paris Declaration 2005; “Alignment” and “Ownership” by aligning IPSM Programme activities with the PAR Agenda and by developing the PAR Roadmap and respective AWPs in a participatory consultative manner engaging key national stakeholders.  The leadership role of PARHC with the technical assistance provided by UN has led to increased involvement of GoI and hence improved national ownership of the programme.  IPSM has in addition inspired the willingness of many national entities to participate in the implementation PAR during 2014.  Examples include the Ministry of Youth and Sports, Municipality of Baghdad, and Karbala and Maysan Governorates.

The IPSM Joint Management Unit has established an effective coordination mechanism, which meets regularly on monthly basis to discuss achievements, obstacles and means of programme improvements. The periodical Joint Management meetings held combined with continuous consultation with Participating UN Agencies and national counterparts at federal and provincial levels has established IPSM as one consolidated programme focusing on Public Sector Reform. In addition, it secured cohesiveness and a unified programme approach, which translated into coordinated interventions at federal, regional and local level.

Indicator Based Performance Assessment

The following is an updated status of the performance matrix, as per the project document, cumulative since the inception of Phase II.  Some indicators listed in the matrix were thought to be irrelevant as the project has been financially downsized by 50% from its original design due to budget reduction.  On a different note, some new activities were implemented by the Participating UN Organizations during 2014; mostly related to PAR Roadmap, as per the approval of UNDAF SC.  As a result, some associated performance indicators, especially at the output level, were somehow absent from the matrix, but explicitly reported in the output section of this report.  In general, performance status as reported in the matrix has either of three options; achieved, partially achieved and not achieved.  For the last two options, a clear justification is provided on an indicator by an indicator basis.

| UN Agency Specific Output | Indicators | Baseline | Planned Target | Status | Reasons for Variance with Planned | Source of Verification |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1. GoI has a National PSM Strategy promoting integrity and accountability developed | Working group for PSM Strategy is functional | No | Yes | Achieved |  | COMSEC/ GoI Decree |
|  | Agreement on the scope of the PSM Strategy obtained | No | Yes | Achieved |  | Minutes of the meeting of Working Group |
|  | Draft National PSM Strategy prepared, inclusive of integrity and accountability components | Early draft | Final draft | Achieved |  | Draft document |
| 1.2. GoI has institutional and operational arrangements for managing PSM instigated and functional | Administrative unit responsible to lead PSM reform established | No | Yes | Achieved | This indicator underwent a slight deviation as the Unit responsible of PSM/PAR is a Committee and not an institutionalized structure | COMSEC/ GoI decree |
|  | Reform Implementation Monitoring Units (RIMU) established in four pilot ministries | No | Yes | Achieved | Target has been over achieved with the establishment of PAR Committees within all Ministries at Federal level. IN addition, similar structures were established at Governorates level | Administrative circulars establishing RIMUs |
|  | # of staff from newly established administrative unit and RIMUs capacitated on PSM and gender | 0 | 50 | Partially Achieved | Given the shift in the nature of the Monitoring and Follow-up structures that were established (Committees versus Department and RIMUs), the training was limited to advocacy sessions organized by the PAR Management Committee. Technical training will be organized in 2015 as part of the continuous support provided. | Training records |
| 1.3. GoI has institutional arrangement for Knowledge Management (KM) system developed | Concept paper on KM organizational and system arrangements with costed options drafted | No | Yes | Achieved |  | Concept paper |
|  | KM Steering Committee established | No | Yes | Not Achieved | Target deviated based on the GoI's directives. KM was decided to be piloted within the CSO at MoP and no national institutional arrangements were decided. | KM Steering Committee ToR |
|  | Technical architecture for web-based KM prepared and tested | No | Yes | Achieved | Technical assistance and guidelines provided by IAU to CSO, in addition to the general guidelines developed under the eGovernance component of the IPSM for the whole of government. | Technical architecture test report |
| 1.4. KRG civil service Commission supported for public sector modernization | KRG working group on PSM Strategy is functional | No | Yes | Achieved | KPSM Committee established | KRG Decree |
|  | KRG PSM Strategy drafted | No | Yes | Not Achieved | A KPSM Project Document was developed, which included highlights of a strategy for PSM in Kurdistan. The specific strategy is yet to be developed. | KRG PSM Strategy document |
| 2.1. Capacitated institutions and human resources with clear policies and processes including e-governance and knowledge management | # of consultation meetings and workshops for preparing Capacity Development Policy | 0 | 3 | Achieved | 8 Consultative meetings and workshops performed under the eGovernance component for the development of guidelines and training of staff, in addition to the SES Consultations | Records of consultation meetings and workshops |
|  | # of gender sensitive guidelines for public administration functions developed | 0 | 4 | Achieved | 6 guidelines for business transformation and eGovernance developed | Guidelines document |
|  | # of Standard Operating Procedures (SOPs) for the implementation of the guidelines developed | 0 | 4 | Achieved | 6 guidelines for business transformation and eGovernance developed | SOPs |
|  | # of Civil Service Commission and RIMUs staff in GoI and KRG trained on guidelines and SOPs | 0 | 70 | Partially Achieved | 40 Staff from Governorate Councils and federal ministries have been trained on the guidelines. Yet no work has been performed at the level of the PAR Management Committee and KRG. | Training records |
| 2.1. Capacitated institutions and human resources with clear policies and processes including e-governance and knowledge management | # of Strategic Plans for the National Center for Management Development and Information Technology (NCMDIT) & Kurdistan Institute for Public Administration (KIPA) prepared | 0 | 2 | Partially Achieved | Strategic plans are in their final draft format. | Strategic Plan Drafts |
|  | International twinning arrangements in place for NCMDIT & KIPA | 1 | 3 | Not Achieved | Pending the finalization and approval of the strategic plans. | Twinning visit reports |
|  | # of consultation meetings and workshops for developing the Senior Executive Service Policy | 0 | 2 | Achieved | 6 Consultative meetings and workshops were performed at federal and regional levels. The SES was consensually agreed upon and the development of the System. | Reports of meetings Draft SES Policy Workshop reports |
|  | # of exposure visits and senior fellowships schemes for Senior executives (DMs and DGs) organized | 0 | 3 | Not Achieved |  | Exposure visit reports |
|  |  |  |  | Not Achieved |  | Fellowship reports |
| 2.1. Capacitated institutions and human resources with clear policies and processes including e-governance and knowledge management | E-governance strategic plan finalized | No | Yes | Achieved |  | Minutes of the meetings of e governance Steering Committee Revised e governance Strategic Plan |
|  | National Academy of Excellence on eGov established | No | Yes | Partially Achieved | Study Mission was undergone to Korea on establishing the Center for Excellence. The MoST is currently engaged in advocacy for the establishment of this institutional structure at federal level | MoST decree |
|  | # of Action plans for additional e-services prepared | 5 | 15 | Partially Achieved | 6 eServices for the Provincial level have been initiated. Federal ministries are currently been supported in the development of specific eServices | Iraq Web Portal; UNDP reports |
|  | Draft Data Policy Framework prepared | 1 | 2 | Achieved |  | Draft Data Policy Framework Document |
| 2.1. Capacitated institutions and human resources with clear policies and processes including e-governance and knowledge management | # of technical and management staff participating in the training /study visit program on Knowledge Management | Tech- 15 Mgt - 0 | Tech – 40 Mgt - 30 | Achieved | Target was reduced to 22 pursuant to the decision to limit to the CSO pilot. Two officials underwent a Study Mission to South Africa; a total of 20 persons underwent training | Training reports |
|  | IDMS/KDMS version II is functional | No | Yes | Partially Achieved | Additional training was requested by both federal and regional level governments. Training sessions are planned to take place in 2015. | IDMS/KDMS Report |
| 2.2. GoI has improved Gender Responsive approaches and practices in public administration system, public policy, planning, budgeting and evaluation | Gender action plan at national level drafted | No | Yes | Achieved | National strategy for the advancement of women draft completed, but not formally endorsed at national or Kurdish level | Indicators report |
|  | Budget gender analysis guidelines and indicators drafted | No | Yes | Partially Achieved | Budget analysis complete, but indicators still in discussion. Baseline knowledge level even lower than anticipated | Action plan report |
|  | # of GRB unit staff trained | 0 | 50 | Partially Achieved | 25 Key personnel in line ministries trained. Needs more work in ministry of finance | Training reports |
|  | GRB conference to showcase methodology & lessons learned conducted | No | Yes | Not Achieved | Government representatives participated in regional conference with same objective | Conference report |
| 2.3. GoI/KRG have enhanced gender sensitive statistics policy and human resources aligned with e-governance policy and systems | Draft for New Statistics Act prepared | No | Yes | Achieved |  | Draft Statistics Act |
|  | Code of Practice drafted | No | Yes | Achieved |  | Code of Practice |
|  | # of functional IT networks established at national, regional and sectoral level | 0 | 4 | Partially Achieved | Networks established at CSO, but delayed at KRSO, and ongoing with MoH, & delayed with MoE | Network reports |
|  | # of modernized classifications and coding systems developed | No | Yes | Not Achieved | Postponed to 2015 | Drafts |
|  | # of functional data exchange mechanisms | 0 | 3 | Not achieved | Exchange of raw data would require a law to allow such operation | CSO/KRSO/MoP/ line ministries reports |
|  | # of trained nationals on modernizing national statistics systems | NA | 200 | Partially Achieved | Plan was developed, and partially implemented by CSO and KRSO. A total of 80 staff were reported trained on modernizing national statistics systems | Training reports |
|  | Gender sensitized tool developed | 0 | 1 | Achieved |  | CSO/KRSO/MoP/line ministries reports |
|  | National classifications server installed | No | Yes | Not Achieved | Postponed to 2015 | Installation Report |
| 3.1.1. MOE has institutional mechanisms for coordination of Education sector amongst stakeholders | Institutional framework for coordination among education stakeholders drafted | No | Yes | Partially Achieved | First meeting held to develop framework under the auspice of PMAC. A committee was set up between MoE and MoHESR’ to finalize framework | Draft institutional coordination framework |
| 3.1.2 MOE/MoHESR have decentralized, ICT-enabled and gender responsive organizational structures & processes for improved service delivery at central and governorate levels | Reviewed and updated assessment of structures and processes report | Assessments conducted | 1 updated report | Achieved |  | Updated report |
|  | Draft organization change plan prepared for MoE and MoHESR | No | Yes | Partially Achieved | Consultant already engaged and preparation of plan in progress | Draft plan |
|  | Education Gender indicators for planning, budgeting, monitoring and evaluation developed | None | Finalized | Achieved |  | Draft gender indicators |
| 3.1.3. MoE and MoHESR have strengthened human capacity in planning and coordination, M&E, financial management, HRM, use of ICTs and gender mainstreaming | # of mid and senior level government officials trained in MoE and MoHESR | 0 | 100 | Achieved |  | MoE/MoHESR training records |
|  | % of reported improvement in knowledge and skills among trainees after training | 0 | 80% | Partially Achieved | (70%) Given the nature of the subject matters, a series of follow-up trainings are planned for 2015 which will help achieve fully the planned target | Post training Assessment |
| 3.2.1 GoI has policies, plans and organizational framework for better health services including decentralization, public-private partnership, health financing, ICT and gender responsive approaches | National Health Policy (NHP) assessed by JANS and endorsed | No | Yes | Achieved |  | Government decree on NHP |
|  | Guidelines on financial management, Pharmaceuticals, & HIS developed | No | Yes | Partially Achieved | Guidelines on financial management developed. HIS in Family Practice developed and implemented in pilot facilities. Wider roll out delayed. | Minutes of meetings/ |
|  | Ten year strategic plan for health developed | No | Yes | Achieved | Strategic Plan developed. Decentralization elements awaiting endorsement of Law 19 by the Parliament. | Guidelines |
|  | MTEF framework for health sector developed | No | Yes | Achieved | Plan of Action and guidelines developed for MTEF. MTEF awaiting approval by ministry of planning & ministry of finance. | Strategic Plan for Health |
|  | HRM policy developed | No | Yes | Partially Achieved | Roles and Responsibilities at various levels developed for better HRM. Endorsement by government awaited for alignment with Law 19. | MTEF framework document |
|  | Fiscal decentralization modules in health system developed | No | Yes | Partially Achieved | Plan of Action and guidelines developed for MTEF. MTEF awaiting approval by ministry of planning & ministry of finance. | HRM policy document |
|  | Framework for ICT/e-governance in health, including application of telemedicine provided | No | Yes | Not Achieved | Shortage of resources. | Documents & reports |
|  | Gender audit with guidelines for engendering the sector developed | No | Yes | Achieved |  | Framework document Project reports Gender audit report |
| 3.2.2 GoI has enhanced capacity for policy, planning, programme management and health care delivery, including decentralized health care based on PHC &Family practice with policy on PPP | % of management staff trained on decentralized management | NA | 50 | Partially Achieved | Ongoing activity. Some modules not fully developed as policy needs finalization. | Training Reports |
|  | # of skilled staff (physicians, nurses and midwives) per 1000 population | Physicians - .75 Nurses – 1.4 Midwives N.A | 2.3 health staff per 1000 population | Achieved | Physicians - 0.8/1000 population; Nursing staff 1.9/1000 pop | MOH Annual Reports |
| 3.3.1 Institutional, organizational and operational arrangements for a water utility developed | Pilot location identified | No | Yes | Achieved |  | Meeting Minutes |
|  | Organizational arrangements for corporate utility model developed | No | Yes | Partially Achieved | Procurement process to mobilize a specialized consultancy to develop the pilot under supervision of UNHABITAT in Najaf is in the last stage. Duhok pilot delayed by KRG decision making. Activity should be implemented in 2015 | Working group minutes |
|  | ToR for Management Contract and support of procurement process of utility | No | Yes | Not Achieved | To be achieved within the pilot in 2014 based on the results of study that has not been yet launched and decision making by pilot authorities | ToRs |
|  | Key Performance Indicators | No | Yes | Not Achieved | To be developed only in concert with pilot authorities in 2015 | Indicators identified |
|  | Pilot E-services in billing and complaint management initiated | No | Yes | Not Achieved | Should be carried out within the pilot in 2015 | MoMPW/ UN-HABITAT Report |
| 3.3.2 Legislative and regulatory instruments for modernization of water, sewerage and solid waste public service delivery drafted and submitted to Council of Ministries (CoM) | ToR’s for I&KWA’s drafted and approved by C’soM. | No | Yes | Achieved |  | CoM Records Parliamentary Records |
|  | Legislation for formation of I&KWA’s, including ToRs, drafted and recommended to GoI& KRG | No | Yes | Not Achieved | MoP in KRG has requested to slow down the programme until the new cabinet is formed |  |
|  | GoI& KRG national consultations on sector reform conducted |  |  | Achieved |  | GoI approval of process results. |
|  | Applicable water and wastewater charges identified and proposed to be included in legislative process. | No | Yes | Not Achieved | Water and Sanitation Law for Iraq awarded and the international consultant is currently waiting for VISA clearance to Iraq to start data collection starting from KRG | Report on charges and legislative recommendation |
| 3.3.3. Plans for improved operational management prepared and submitted by High Council of Water (HCW) | Water demand management study and consultation conducted by I&RWA and results fed into 3.3.2 | No | Yes | Achieved |  | I&RWA report |
|  | Water quality management study and consultation developed by I&RWA’s and results fed into 3.3.2 | No | Yes | Not Achieved | Technical proposal were received and under review before submitting for bidding process | I&RWA report |
|  | Governorates and GoI to conduct household water consumption data analysis, to feed into 3.3.2 | No | Yes | Not Achieved | Will be conducted under the above item | GoI Report |
|  | National Water Conservation Plan developed by GoI and fed into 3.3.2 | No | Yes | Not Achieved | Will be conducted under the above item | GoI Plan document |
| 3.3.4. Strategies for improved public participation and customer orientation developed | Household water diaries prepared with women | 0 | 3 | Not Achieved | Not included in 2014 AWP | Diaries |
|  | Report on the analysis of water use practices at household level, and findings on water practices prepared | No | Yes | Not Achieved | Not included in 2014 AWP | Report |
|  | % increase in women representation within citizen advisory committees on water | Minimal | 15% | Not Achieved | Not included in 2014 AWP | Citizen advisory committees records |
|  | Performance and service standards on water usage and consumption developed and publicized | No | Yes | Not Achieved | Not included in 2014 AWP | Documents produced |
| 3.3.5. Updated Solid Waste Management strategy, policy, national master and capital investment plans drafted | Sector strategy and policy drafted | No | Yes | Not Achieved | Dropped from UN-HABITAT's List of Activities of 2013 due to insufficient human resources available in Phase II | Strategy document |
|  | National Master plan including hazardous and health care waste updated | No | Yes | Not Achieved | Dropped from UN-HABITAT's List of Activities of 2013 due to insufficient human resources available in Phase II | Draft Plan |
|  | Handbook on ISWM collecting and separating at source developed | No | Yes | Not Achieved | Dropped from UN-HABITAT’s List of Activities of 2013 due to insufficient human resources available in Phase II | ISWM practices’ handbook for private households |
| 4.1 Enhanced decentralization and strengthened local governance | Federal-Provincial Committee in operation | No | Yes | Not Achieved | Work on the decentralization component was postponed in light of the delay in governorate selection | Minutes of the Committee meeting |
|  | # of executive development programs for the political executives, Governors & Council members and senior functionaries of concerned departments | 0 | 50 | Not Achieved | Work on the decentralization component was postponed in light of the delay in governorate selection | Training reports |
|  | Draft strategy paper on participatory approaches and mechanisms | No | Yes | Not Achieved | Work on the decentralization component was postponed in light of the delay in governorate selection | Strategy paper |
|  | Study on institutional arrangements, including administrative structures, at provincial level | No | Yes | Not Achieved | Pending the start-up of the pilots at governorates level | Study |
|  | Study on fiscal decentralization completed | No | Yes | Not Achieved | Dropped in light of the change in focus of the Programme | Study report |
| 4.2 Enhanced gender sensitive planning, budgeting & evaluation capacity at central and governorate levels | # of guidelines on gender sensitive approaches issued in cooperation with sub-national entities | 0 | 5 | Not Achieved | Specific guidelines need to be developed on gender responsive budgeting first before working on any sub national specific guidelines | Guidelines documents |
| 4.3.1 Participatory and inclusive governance approaches enhanced through partnerships with CSOs | # of recommendations identified for the enhancement of Law 21 from the participation perspective and for the localization of MDGs | 1 | 2 | Achieved | 10 Revised Law was enacted in Parliament in 2013, pursuant to the technical assistance provided by UNDP. | Reports and Official Correspondence |
|  | # of officials & politicians at sub-national levels trained in participatory processes | 10 | 150 | Not Achieved | Focus on central and regional (KRG) government did not permit work at local government level WHO part is planned for 2015 | Training & Event reports |
|  | Draft social participation toolkit for government agencies prepared | No | Yes | Not Achieved | Focus on central and regional (KRG) government did not permit work at local government level WHO part is planned for 2015 | Toolkit |
|  | # of advocacy groups established to promote participatory approaches | 0 | 6 | Partially Achieved | 1 Insipient advocacy group fostered in one pilot area | Agency report |
| 4.3.2 Government and partners are supported to enhance youth & women leadership skills for local governance | Policy recommendations and inputs to the civil society law? | No | Yes | Not Relevant | Activity was not included in 2014 AWP | Civil Society organization Law & Parliamentary reports |
|  | # of youth/women advocacy groups established | 0 | 460 males & 530 females | Not Achieved | Late selection of pilot Governorates & limited budget | CSO/CBO reports Youth & women testimonies |
|  | # of tri-partite meetings with youth councils & women networks | 0 | 24 | Not Achieved | Late selection of pilot Governorates & limited budget | Council Committees Reports, Minutes of Meetings |
|  | # of districts/ municipalities covered by the UN led Youth Initiatives | 0 | 6-8 districts / municipalities | Not Achieved | Late selection of pilot Governorates & limited budget | Council Committees Reports |
|  | # of curriculum development tools developed with MoE to mainstream civic and political literacy and engagement | 0 | 3 | Not Achieved | The activity was re-programmed on to 2015 pending finalization of MoE inputs for the development tools | Tool Minutes of meeting with MOEs |
| 4.4 Government is able to implement pilot participatory service delivery projects in Health, Education and WATSAN sectors in three governorates | # of assessments of decentralized service delivery governorates completed | 0 | 3 |  | WHO part is planned for 2015 | Assessment reports |
|  | # of joint-UN pilots promoting participatory governance mechanisms in service delivery launched | 0 | 3 | Achieved | 1. Manuals on the concept of School-Based Management (SBM) developed to enhance knowledge and understanding of the concept. 2. SBM being contextualized at national and regional levels in order to develop guidelines. | GoI/governorates/ Agency reports |
| 4.5.1 Government partners undertake study on the scope of urban local governance including recommended options | Study on local urban governance for Public Sector Modernization conducted and options for pilot implementation in selected urban centers suggested | No | Yes | Not Achieved | This activity is not included in the agreed AWP 2014? | Study reports |
| 4.5.2 Local government able to support public sector modernization at provincial/local levels | Strategic Plan for Training and research institute (TRI)developed | No | Yes | Not Achieved | This activity was not included in the agreed AWP 2014 | Strategic plan report |
|  | Curriculum developed on local governance and urban development | No | Yes | Not Achieved | This activity was not included in the agreed AWP 2014 | Training modules |
|  | # of elected council representatives and line departments staff attending TRI training of trainers (ToT) | Elected: 0 Staff: 0 | Elected: 20 Staff: 60 | Not Achieved | This activity was not included in the agreed AWP 2014 | Training reports |
|  | % of trained elected officials and confirming benefiting from ToT | 0 | 80% | Not Achieved | This activity was not included in the agreed AWP 20134 | Evaluation sheet |
|  | # of political executives and officials participating in Study Tour | NA | 20 | Not Achieved | This activity was not included in the agreed AWP 2014 | Study tour report |

List of Acronyms

AICs		Academic Integrity and Code of Conduct

AWP		Annual Work Plan

CoM		Council of Ministers

COMSEC		Council of Ministers Secretariat

CoR		Council of Representatives

CSO		Central Statistics Office/ Civil Society Organization

GIS		Geographical Information Systems

GoI		Government of Iraq

GRB		gender-responsive budgeting

HRM		Human Resource Management

ICT	 	Information Communication Technology

IDMS 		Iraq Development Management System

I-PSM 		Iraq Public Sector Modernization Programme

IT			Information Technology

ITF	 	Iraq Trust Fund

JP			Joint Programme

KDMS 		Kurdistan Development Management System

KIPA 		Kurdistan Institute for Public Administration

KM 		Knowledge Management

KPSM		Kurdistan Public Sector Modernization Project

KRG 		Kurdistan Regional Government

KRSO 		Kurdistan Regional Statistics Office

MDGs		Millennium Development Goals

M&E		Monitoring and Evaluation

MoE 		Ministry of Education

MoH 		Ministry of Health

MoHESR 		Ministry of Higher Education and Scientific Research

MoP		Ministry of Planning

MoST 		Ministry of Science and Technology

MoU		Memorandum of Understanding

NCMDIT 		National Centre for Management Development and Information Technology

NHA		National Health Accounts

NHP		National Health Plan

NDP		National Development Plan

PAR: 		Public Administration Reform

PARHC		Public Administration Reform Higher Committee

PARMC		Public Administration Reform Management Committee

PMAC		Prime Minster Advisory Committee

PMO		Prime Minster Office

PPP		Public Private Partnership

PSM		Public Sector Modernization

PSMSC 		Public Sector Modernization Steering Committee

RC	 		Resident Coordinator

SC			Steering Committee

SES		Senior Executive Service

SGP		Iraq’s Strategic Government Plan

SOPs		Standard Operating Procedures

ToRs		Terms of References

TOT		Training of Trainers

UNCT		United Nations Country Team

UNDAF 		United Nations Development Assistance Framework for Iraq

UNDP		United Nations Development Programme

UNESCO		United Nations Educational, Scientific and Cultural Organization

UNFPA		United Nations Population Fund

UNICEF		United Nations Children's Fund

USAID 		United States Agency for International Development

WATSAN		Water and Sanitation

WB		World Bank

WHO		World Health Organization

# Footnotes

The term “programme” is used for programmes, joint programmes and projects.

Strategic Results, as formulated in the Strategic UN Planning Framework (e.g. UNDAF) or project document;

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as  “Project ID” on the project’s factsheet page on the MPTF Office GATEWAY.

The MPTF/JP Contribution is the amount transferred to the Participating UN Organizations – see MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee. <OwaStorableObject type="Conversations" version="1" denyCopy="false" denyMove="false"><Conversations FolderId="LgAAAAAKXDNkNaYuTro+zDtvPqk2AQDfgug+t+cWSJyG+kYFABHuABUFIIA1AAAB" IsCrossFolder="false"><Item ItemId="CID.N3tZhML8S2mTqc7kGiklJg==.LgAAAAAKXDNkNaYuTro+zDtvPqk2AQDfgug+t+cWSJyG+kYFABHuABUFIIA1AAAB.ByEAAACbE0IAAAAAK3VcAQEAAAA=" ItemType="IPM.Conversation"/></Conversations></OwaStorableObject>

# Text boxes

ii) Indicator Based Performance Assessment: