Kurdistan Vision 2020 Joint Programming Facility

GENERIC QUARTERLY programme NARRATIVE progress report

REPORTING PERIOD: First Quarter (1st September to 30th November 2014)

| Programme Title & Project Number |  | Programme Location (Country, Locality(s), Thematic/Priority Area(s)) |
| --- | --- | --- |
| Programme Title: Strengthening Urban and Regional Planning in KRG Programme Number (if applicable) MPTF Office Project Reference Number: 00091241 |  | (if applicable) Iraq/Kurdistan Region |
|  |  | Thematic/Priority Infrastructure- Housing for Growing Population |

| Participating UN Organization(s) |  | KRG Institution(s) |
| --- | --- | --- |
| UN-Habitat |  | Ministry of Municipalities and Tourism, Erbil Governorate |

| Programme/Project Cost (US$) |  | Programme Duration |
| --- | --- | --- |
| KR-I Vision 2020 Facility Contribution: US$ 944,000 |  |  | Total Duration (months) 18 months |  |
| UN Agency Contribution US$ 126,950 |  |  | Start Date 01-09-2014 |  |
| Government Contribution (if applicable) |  |  | End Date 29-02-2016 |  |
| Other Contributions (donors) (if applicable) |  |  | Operational Closure Date |  |
| TOTAL: US$ 1,070,950 |  |  | Expected Financial Closure Date |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Assessment/Review - if applicable please attach Yes No Date: dd.mm.yyyy Mid-Term Evaluation Report – if applicable please attach Yes No Date: dd.mm.yyyy |  | Name: Mazin Talat Title: Regional National Coordinator –UN-Habitat Participating Organization (Coordinator): Email address: mazin.talat@unhabitat.org |

NARRATIVE REPORT FORMAT

# Purpose

- Provide the main objectives and expected outcomes of the programme.

The project aims to establish urban planning units in Erbil Governorate and within Ministry of Municipalities and Tourism, and improve the capacity of staff so that they can perform planning duties.

And the expected outcomes reflect the relevant KR-I Vision 2020 Priority Area Outcome:

A vibrant private housing sector in which all residents of the Kurdistan Region have decent shelter.

- Improving land-use regulations

- Reforming land titling and ownership.

- Encouraging development of mixed-income neighborhoods.

A transportation network that connects every inhabited location in the Kurdistan Region to every other inhabited location in the Kurdistan Region and to the world.

Water, sanitation, and electricity services that reach every home and supply every industry.

- Explain how the Programme relates to the applicable Strategic (UN) Planning Framework guiding the operations of the Fund/JP2:

The programme addresses UNDAF Priority 4: Increased access to quality essential services and specifically outcome 4.1: Government of Iraq has participatory and accountable policy framework and implementation mechanisms for the delivery of quality basic services at all levels.

ئامانجی پرۆژەکە باشترکردنی تواناکانی پسپۆڕەکان و تیمی نەخشەدانانی ئاوەدانی و هەروەها شان بەشانی (پلانی شوێنیی هەرێمیی) لەگەڵ ئاراستەکانی گەشەی سەکتەرەیی حکومەتی هەرێمی کوردستان لە ڕێگای پێداچوونەوەی ماستەرپلانی ئێستا و کاریگەری لەسەر گۆڕانکاریەکان لە نەخشەدانانی ئاوەدانی و سیستەمی بەڕێوەبردنی زەوی و زار. ئەو بەرنامەیە مەبەستیەتی ئەو گرفتە گرنگانەی خوارەوە چارەسەر بکات:

- کەمی پسپۆڕە ڕاهێنراوەکان

- پێویستی بوونی دیدگایەکی ڕوون و بەڕێوەبردنێکی باشی تیمەکانی نەخشەدانانی ئاوەدانی

- نەبوون و کەمی (پلانی شوێنیی هەرێمیی) شان بەشانی ئاراستەکانی گەشەی سەکتەرەیی حکومەتی هەرێمی کوردستان، زەمینە خۆشکەر بێت بۆ نەخشەدانانی ئاوەدانی و شارەکان.

- پێویستە ماستەرپلانی ئاوەدانی ئێستا ناوە بە ناوە پێداچوونەوەی بۆ بکرێت.

- پێویستی بوونی سیستەمێکی پەرەپێدراو بۆ پلاندانانی ئاوەدانی و هەرێمیی.

- پێویستی بوونی پاڵپشتی سیاسی و کۆمەڵانی خەڵک بۆ جێگیرکردنی گۆڕانکاریەکان لە نەخشەدانانی ئاوەدانی و سیستەمی بەرێوەبردنی زەوی و زار.

# Resources

Financial Resources:

Provide information on other funding resources available to the project, if applicable. Please refer to information on the  Reporting Cover Page. Quarterly:

Contributions from KRG US$ 944,000 and UN-Habitat US$ 126,950

- Provide details on any budget revisions approved by the appropriate decision-making body, if applicable.

Not applicable

- Provide information on good practices and constraints related to the management of the financial aspects of implementing the programme, including receipt of transfers, administrative bottlenecks and/or other issues affecting the financial management of the programme. Please provide detail of financial report as

Human Resources:

- National Staff: Provide details on the number and type (operation/programme).

- No. of National Staff on programme activities = 3

- No. of National Staff on operations activities = 2

- International Staff: Provide details on the number and type (operation/programme)

- No. of International Staff on programme activities = 3

# Implementation and Monitoring Arrangements

- Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the operating context. The implementation mechanisms are comprised of :

-Structured delivery of lectures for an average of 26 trainees per training session

-Assignments by trainees and plenary presentations.

-Intensive training sessions on technical skills.

- Provide details on the procurement procedures utilized and explain variances in standard procedures.

Procurement procedures for services comprise of identification of service provides, request for quotations, selection of best offers.

Procurement procedures for Urban Planning Specialist are based upon identification of experts with suitable skills, field expertise, years of practice, and training capacity.

Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme, including corrective actions that may have been taken.  Each training session is preceded by a questionnaire testing trainees’ knowledge. The same test is filled in at the end of the session. The project management team is monitoring and recording trainees’ performance. Attendance of trainees is recorded and reported to their supervisors.

- Report on any assessments, evaluations or studies undertaken.

Not conducted yet.

# Results

- Provide a summary of Programme progress in relation to planned outcomes (strategic results with reference to the relevant indicator) and outputs; explain any variance in achieved versus planned outputs during the reporting period.

For outcome 1: Improved substantive and administrative capacities of staff within KRG and Erbil Governorate urban planning units: to date six lectures have been delivered as part of the programme of formal training on key issues in urban and regional planning. The lectures (attended by an average 26 trainees per session) tackled issues related to urban growth, development patterns, land use, density, participatory planning, sustainability, integration, and inclusiveness.

The three-week Geographic Information System (GIS) training course that UN-habitat launched at the end of November was attended by nine technical staff from the urban planning units of the Ministry of Municipalities and Tourism (MoMT) and the Directorate of Urban Planning of Erbil were taught fundamental GIS principles and the role that GIS plays in the scientific processes of measuring, mapping, monitoring and modeling urban and rural areas.  The training course offered three sequential modules on the latest ArcGIS 10 software from ESRI, from Basic GIS skills and concepts to Advanced Spatial Analysis, focusing on how and when to apply ArcGIS tools to create an efficient workflow that supports GIS analysis, the preparation of data for analysis, geo-processing models and associated challenges. At the end of each module, trainees undertook exams.  The highest scores were attained by three young staff members of the Directorate of Urban Planning of Erbil, two of which women, whose hard work and results were praised during the final certificates’ event. Their newly acquired skills may be soon put at good use and contribute to a better understanding of urban development trends in Erbil.

During this reporting period, the project management team has identified and selected consultants and contractors for the delivery of activities to be undertaken in the next quarters.

- Report on the key outputs achieved in the reporting period, including the number and nature of the activities (inputs), outputs and outcomes, with percentages of completion and beneficiaries.

For outcome 1: Improved substantive and administrative capacities of staff within KRG and Erbil Governorate urban planning units:

- Project activity 1.1.1: six lectures delivered. Improved capacity to fulfil urban and regional planning duties as detailed as in table VI

- Project activity 1.1.2: GIS training course (3 weeks) completed. See table VI

- Project activity 1.1.3: Contractor for Admin training selected.

- Project activity 1.1.4: Contractor for IT training selected.

- Project activity 1.2.1: Consultant selected

- Project activity 1.2.2: Consultant selected

- Project activity 1.2.3: Contractor selected

- Project activity 1.3.1: Consultant selected

- Project activity 1.4.1: Consultant selected

- Project activity 1.4.2: Consultant selected

- Project activity 1.4.3: Consultant selected

For outcome 2: Clear Vision and political support for enhanced role of urban and regional planning in KRG:

- Project activity 2.1.1: Consultant selected

- Project activity 2.1.2: Consultant selected

- Explain, if relevant, delays in programme implementation, the nature of the constraints, actions taken to mitigate future delays and lessons learned in the process.

No delays

- List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

The project is implemented in close collaboration with the leadership of MoMT and DUP who have not only provided strategic direction, but also venues, equipment, and human resources.

- Other highlights and cross-cutting issues pertinent to the results being reported on.

Training modules are dedicated to environmental, economic, social, and gender considerations in urban planning.

- Provide an assessment of the programme based on performance indicators as per approved programme document using the template in Section VI, providing clear evidence on the linkages of outputs and outcomes achieved, if applicable.

See table VI.

- Qualitative assessment of overall achievement with reference to the applicable strategic results indicator.

Evaluation results show increased level of confidence among the trainees on urban planning topics.

# Future Work Plan (if applicable)

- Summarize the projected activities and expenditures for the following reporting period, using the lessons learned during the previous reporting period, including outputs that were not achieved previously.

The next reporting period will see the continuation of the lecture programme, and the start of a series of activities such as: institutional assessment and capacity building, hands-on training, delivery of planning products, visioning, and administrative training.

Between expenditures and commitments, it is estimated that the next reporting period will require nearly US$ 200,000

- Indicate any major adjustments in strategies, targets or key outcomes and outputs described in the ProDoc.

No major adjustments are required.

|  | Performance Indicators | Indicator Baselines | Planned Indicator Targets | Achieved Indicator Targets | Reasons for Variance (if any) | Source of Verification | Progress/ Achievements (Yes/No) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome 1: Improved substantive and administrative capacities of staff within KRG and Erbil Governorate urban planning units |
| Output 1.1 Output 1.1: Staff of urban planning directorates (KRG and Erbil) have improved capacity to fulfil urban and regional planning duties through structured learning | Indicator 1.1.1 Substantive technical training | Inadequate knowledge base in urban and regional planning | 30 CTOs in 2 groups have adequate knowledge base | 26 trainees attending each session in average | Limited number of technical staff | Attendance list | Yes |
|  | Indicator 1.1.2 IT skills training for technical staff | Inadequate skills in Total Station and GIS | 10 staff able to use Total Station and 20 staff able to use GIS | 9 trainees have completed GIS course | 1 trainee dropped out | Attendance list | Yes |
|  | Indicator 1.1.3 Administrative training | Inadequate skills in Human Resources, Procurement, and financial management, | 30 admin staff are better able to carry out procurement and financial management tasks | Not conducted yet | Planned for 2015 | N/A | No |
|  | Indicator 1.1.4 IT skills training for technical staff | Inadequate IT skills among admin staff | 60 staff acquired skills in Microsoft Word and Excel | Not conducted yet | Planned for 2015 | N/A | No |
| Output 1.2 Well managed and effective teams are in place at KRG and Erbil Governorate | Indicator 1.2.1 Capacity assessment and clarification of roles and functions | Lack of TORs, annual work plans, capacity assessments for urban planning units and their staff | TORs, work plans, capacity assessments prepared and training needs identified | Not conducted yet | Planned for 2015 | N/A | No |
|  | Indicator 1.2.2 Vision building | Limited team spirit | 90% of staff participate in staff retreat | Not conducted yet | Planned for 2015 | N/A | No |
|  | Indicator 1.2.3 Leadership skills building | Inadequate performance appraisal system | Performance appraisal system prepared and implemented | Not conducted yet | Planned for 2015 | N/A | No |
|  | Indicator 1.2.4 On the job learning – district master plan | Limited project management skills, change management requirements and operation inadequately understood | Unit leaders trained in problem solving, project management and change management | Not conducted yet | Planned for 2015 | N/A | No |
| Outcome 2: Clear vision and political support for enhanced role of urban and regional planning in KRG |
| Output 2.1 KRG has a clear vision for an improved system for planning | Indicator 2.1.1 Baseline study on urban and regional planning system and land management system | No baseline study on urban and regional planning system and land management system | Baseline study in place | Not conducted yet | Planned for 2015 | N/A | No |
|  | Indicator 2.1.2 Vision statement on improved urban and regional planning and land management in KR | No vision statement on urban and regional planning system and land management system | Vision statement in place | Not conducted yet | Planned for 2015 | N/A | No |
|  | Indicator 2.2.2 High level debates within Council of Ministers | Lack of political support | High level meetings conducted | Not conducted yet | Planned for 2015 | N/A | No |

# Kurdistan Vision 2020 Joint Programming Facility

# Joint Programme/Project #:00091241

Date and Quarter Updated: 1st September to 29 February 2016 - First Quarter

| Participating UN Organization(s): UN-Habitat | Vision 2020 Priority Area: Infrastructure- Housing for Growing Population |
| --- | --- |
| Kurdistan Region Government – Responsible KRG Institution(s): Ministry of Municipality and Tourism, and Erbil Governorate |

| Title of JP/ Project | Strengthening Urban and Regional Planning in KRG |
| --- | --- |
| Geographic Location | Kurdistan Region – Erbil Governorate] |
| Total JP/Project Cost | US$ 1,070,950 |
| Facility contribution | Per agency US$ 944,000 | Received contribution agency: US$ 300,213 /UN-Habitat |
| Total Duration | 18 months |
| Approval Date (SC) | Starting Date | 1st September 2014 | Completion Date | 29th February 2016 |
| JP/Project Description | The project aims to improve the capacities of the professionals and urban planning teams and to align regional spatial plan with KRG sectoral development directions through reviewing existing master plans and affecting changes in the urban planning and land management system. This program aims to address the following critical issues: 1. Lack of trained professionals 2. The need for clear vision and well managed urban planning teams 3. Lack of a regional spatial plan aligned with KRG sectoral development directions, that provides context to district and urban plans 4. The need to periodically review the existing urban master plans 5. The need for an improved system for urban and regional planning 6. The need for political and public support to mobilise changes in the urban planning and land management system. |
| ملخص المشروع كورتةيةك لةسةر ثرؤذة | ئامانجی پرۆژەکە باشترکردنی تواناکانی پسپۆڕەکان و تیمی نەخشەدانانی ئاوەدانی و هەروەها شان بەشانی (پلانی شوێنیی هەرێمیی) لەگەڵ ئاراستەکانی گەشەی سەکتەرەیی حکومەتی هەرێمی کوردستان لە ڕێگای پێداچوونەوەی ماستەرپلانی ئێستا و کاریگەری لەسەر گۆڕانکاریەکان لە نەخشەدانانی ئاوەدانی و سیستەمی بەڕێوەبردنی زەوی و زار. ئەو بەرنامەیە مەبەستیەتی ئەو گرفتە گرنگانەی خوارەوە چارەسەر بکات: کەمی پسپۆڕە ڕاهێنراوەکان پێویستی بوونی دیدگایەکی ڕوون و بەڕێوەبردنێکی باشی تیمەکانی نەخشەدانانی ئاوەدانی نەبوون و کەمی (پلانی شوێنیی هەرێمیی) شان بەشانی ئاراستەکانی گەشەی سەکتەرەیی حکومەتی هەرێمی کوردستان، زەمینە خۆشکەر بێت بۆ نەخشەدانانی ئاوەدانی و شارەکان. پێویستە ماستەرپلانی ئاوەدانی ئێستا ناوە بە ناوە پێداچوونەوەی بۆ بکرێت. پێویستی بوونی سیستەمێکی پەرەپێدراو بۆ پلاندانانی ئاوەدانی و هەرێمیی. پێویستی بوونی پاڵپشتی سیاسی و کۆمەڵانی خەڵک بۆ جێگیرکردنی گۆڕانکاریەکان لە نەخشەدانانی ئاوەدانی و سیستەمی بەرێوەبردنی زەوی و زار. |

KR VISION 2020 Priority Area Outcome:

A vibrant private housing sector in which all residents of the Kurdistan Region have decent shelter. • Improving land-use regulations • Reforming land titling and ownership. • Encouraging development of mixed-income neighborhoods. A transportation network that connects every inhabited location in the Kurdistan Region to every other inhabited location in the Kurdistan Region and to the world. Water, sanitation, and electricity services that reach every home and supply every industry.

| Outputs, Key activities and Procurement |
| --- |
| Outputs ( JP outputs and/ or UN Organization specific) | Output 1.1: Staff of urban planning directorates (KRG and Erbil) have improved capacity to fulfil urban and regional planning duties through structured learning Output 1.2. Well managed and effective teams are in place at KRG and Erbil Governorate Output 1.3. The regional planning unit has improved capacity to fulfil urban and regional planning duties through on the job learning Output 1.4. The Erbil urban planning unit has improved capacity to fulfil urban and regional planning duties through on the job learning Output 2.1 KRG has a clear vision for an improved system for planning Output 2.2: Public Awareness and Political Support the Vision |
| Activities | Project activity 1.1.1: six lectures delivered. Improved capacity to fulfil urban and regional planning duties Project activity 1.1.2: GIS training course (3 weeks) completed. Project activity 1.1.3: Contractor for Admin training selected. Project activity 1.1.4: Contractor for IT training selected. Project activity 1.2.1: Consultant selected Project activity 1.2.2: Consultant selected Project activity 1.2.3: Contractor selected Project activity 1.3.1: Consultant selected Project activity 1.4.1: Consultant selected Project activity 1.4.2: Consultant selected Project activity 1.4.3: Consultant selected Project activity 2.1.1: Consultant selected Project activity 2.1.2: Consultant selected |
| Procurement (major items and services ) | Consultancy services for the delivery of training modules on urban planning and GIS. |

| Facility Funds Committed | US$ 84,192.86 | % of approved | 8.91% |
| --- | --- | --- | --- |
| Facility Funds Disbursed | US$ 84,484.25 | % of approved | 8.95% |
| PUNO(s) contribution provided | N/A |  |  |
| Forecast final date | 29th Feb 2016 | Delay (months) | 0 |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Men | 22 |  |
| Women | 13 |  |
| Children | N/A |  |
| IDPs | N/A |  |
| Others | N/A |  |
| Indirect beneficiaries | Citizens in urban centers in KRG |  |

| Quantitative achievements against JP outputs/ UN Organization outputs |
| --- |
| PROJECT OUTPUT 1.1 Training 130 trainees on various topics and skills | 35 trainees | % of planned | 27% |
| PROJECT OUTPUT 1.2: Institutional capacity building |  | % of planned | 0% |
| PROJECT OUTPUT 1.3: District master plan |  | % of planned | 0% |
| PROJECT OUTPUT 1.4: review of Erbil master plan |  | % of planned | 0% |
| PROJECT OUTPUT 2.1: Vision statement |  | % of planned | 0% |
| PROJECT OUTPUT 2.2: Public awareness campaign ¦ |  | % of planned | 0% |

Qualitative achievements against JP outputs/ UN Organization outputs

High attendance to lectures, lively interaction, majority of the trainees undertake assignments, 30% of GIS trainees excelled in final exam.

Key implémentation contraints & challenges (2-3 sentences)

None

Financial Report

| CATEGORY | ITEM DESCRIPTION | UNIT COST | NUMBER OF UNITS | AMOUNT | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Staff and other personnel costs | Programme Staff | Lumpsum | 1 |  | US$ 162,195.87 |  |  |  |
| Sub-Total"1" |  |  |  |  | US$ 162,195.87 |  |  |  |
| 2. Supplies, commodities, Materials |  | Lumpsum | 1 |  | US$ 331.7 |  |  |  |
| Sub-Total"2" |  |  |  |  | US$ 331.7 |  |  |  |
| 3. Equipment, Vehicles and Furniture including Depreciation |  |  |  |  | 0 |  |  |  |
| Sub-Total"3" |  |  |  |  | 0 |  |  |  |
| 4. Contractual Services |  | Lumpsum | 1 |  | US$ 580.20 |  |  |  |
| Sub-Total"4" |  |  |  |  | US$ 580.20 |  |  |  |
| 5.Travel |  | Lumpsum | 1 |  | US$ 3,895.87 |  |  |  |
| Sub-Total"5" |  |  |  |  | US$ 3,895.87 |  |  |  |
| 6.Transfers and Grants Counterparts |  | Lumpsum | 1 |  | US$ 1,673.48 |  |  |  |
| Sub-Total"6" |  |  |  |  | US$ 1,673.48 |  |  |  |
| Sub - Total (1-6) |  |  |  |  | US$ 168,677.11 |  |  |  |
| GRAND TOTAL**** |  |  |  |  | US$ 168,677.11 |  |  |  |

| CATEGORY | APPROVED BUDGET USD | EXPENDITURE IN USD | COMMITMENTS IN USD | REMANINNG BALANCE IN USD |
| --- | --- | --- | --- | --- |
| 1. Staff and other personnel costs | $548,250.00 | $ 72,900.00 | $ 78,684.92 | $ 396,665.08 |
| Sub-Total"1" | $548,250.00 | $ 72,900.00 | $ 78,684.92 | $ 396,665.08 |
| 2. Supplies, commodities, Materials | $ 69,068.00 | $ 310.00 | $ - | $ 68,758.00 |
| Sub-Total"2" | $ 69,068.00 | $ 310.00 | $ - | $ 68,758.00 |
| 3. Equipment, Vehicles and Furniture including Depreciation | $ 3,600.00 | $ - | $ - | $ 3,600.00 |
| Sub-Total"3" | $ 3,600.00 | $ - | $ - | $ 3,600.00 |
| 4. Contractual Services | $ 31,525.00 | $ 542.24 | $ - | $ 30,982.76 |
| Sub-Total"4" | $ 31,525.00 | $ 542.24 | $ - | $ 30,982.76 |
| 5.Travel | $ 63,000.00 | $ 3,641.00 | $ - | $ 59,359.00 |
| Sub-Total"5" | $ 63,000.00 | $ 3,641.00 | $ - | $ 59,359.00 |
| 6.Transfers and Grants Counterparts | $166,800.00 | $ 1,564.00 | $ - | $ 165,236.00 |
| Sub-Total"6" | $166,800.00 | $ 1,564.00 | $ - | $ 165,236.00 |
| Sub - Total (1-6) | $882,243.00 | $ 78,957.24 | $ 78,684.92 | $ 724,600.84 |
| 7. General operating and Other Direct Costs | $ - | $ - | $ - | $ - |
| Total Programme Costs (1-7) | $882,243.00 | $ 78,957.24 | $ 78,684.92 | $ 724,600.84 |
| 8.Indirect Support costs | $ 61,757.00 | $ 5,527.01 | $ 5,507.94 | $ 50,722.06 |
| GRAND TOTAL | $944,000.00 | $ 84,484.25 | $ 84,192.86 | $ 775,322.90 |

Note: UN-Habitat’s budget allocation is an in kind contribution and will be spent during 2015.

# Footnotes

The term “programme” is used for programmes, joint programmes and projects.

Thematic/ Priority area for the Vision 2020

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

All activities for which a Participating Organization is responsible under an approved MPTF programme have been completed. Agencies to advise the MPTF Office.

# Text boxes

VI. INDICATOR BASED PERFORMANCE ASSESSMENT