TEMPLATE 4.4

PEACEBUILDING FUND (PBF)

ANNUAL PROJECT progress report

COUNTRY: SUDAN

REPORTING PERIOD: 1 january – 31 December

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: PBF/ Empowering Women for Peace &Recovery in East Sudan Programme Number (if applicable) MPTF Office Project Reference Number: 00083818 |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: UNWOMEN ILO |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: State Ministries of Welfare and Social Security in Gadarif and Kassala, federal Ministry of Welfare and Social Security, East Sudan Reconstruction Fund Authority, Gadarif University, CSOs/CBOs, Women's IGA groups. |

| Programme/Project Budget (US$) |  | Programme Duration |
| --- | --- | --- |
| PBF contribution (by RUNO) US$ 348,285 |  |  | Overall Duration (months) 19 |  |
|  |  |  | Start Date (dd.mm.yyyy) August 2012 |  |
| Government Contribution (if applicable) N/A |  |  | Original End Date (dd.mm.yyyy) | May 2013 |
| Other Contributions (donors) (if applicable) N/A |  |  | Current End date(dd.mm.yyyy) 31 March 2014 |  |
| TOTAL: | US$348,285 |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Assessment/Review - if applicable please attach Yes No Date: Mid-Term Evaluation Report – if applicable please attach Yes No Date: |  | Name: Jebbeh Forster Title: Country Representative Participating Organization (Lead): UNWOMEN Email address: jebbeh.forster@unwomen.org |

PART 1 – RESULTS PROGRESS

  - Assessment of the current project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project is contributing:

Priority Plan Outcome to which the project is contributing. Early Economic Recovery and Immediate Peace Dividends

Priority Plan Outcome indicator(s) to which project is contributing. Number of women helped by projects for vulnerable groups; change in the number of women clients using micro finance providers disaggregated by age and location; number of state and federal projects and plans integrating the needs of women and girls in economic recovery; number of tribal and community leaders champions for women's rights to land and resources.

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  Early revitalization of the economy, e.g. through promotion of partnerships with private sector to develop micro enterprises and youth employment schemes; revitalizing agricultural sector, technical support to design more inclusive and sustainable policies for the management of natural resources, etc.

Rate the current status of the outcome:

| Indicator 1: Number of women helped by projects for vulnerable groups Indicator 2: Equal rights of women to economic assets is clearly advocated Indicator 3: Micro finance services are accessible to women | Baseline: 1,000 women indirect beneficiairies and 150 direct beneficiaries from reconstruction rehabilitation program. Target: 1,150 beneficiaries Progress:to be implemented Baseline: Target: Progress: Baseline: Limited micro-finance facility Target: 300 direct women clients Progress:to be implemented |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

1. Livelihood assessment report developed and shared with stakeholders

2. A meta-analysis of recommendations in women's economic empowerment in East Sudan commissioned.

3. A total of 48 trainers trained through ToTs on the "Get Ahead business toolkit for women and Entrepreneurship" in agribusinesses training package; 300 women end beneficiairies trained.

4. A total of 47 women trained in food processing.

5. Projects to be supported in 2014through in kind grants and capacity building identified in collaboration with the States' Ministries of Welfare .

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

The interventions and activities made as part of the project aimed to improve women’s access to economic resources and therefore contribute to the revitalization of the economy of Kassala and Gadarif state.  A rapid livelihood assessment helped define the nature and scope of these interventions and activities. The assessment provided information and analysis of women’s access to resources and obstacles preventing them from benefiting from these resources.

To build the capacity of women entrepreneurs, 300 women from 6 different localities, were trained in business development and entrepreneurship. The trainers were selected through 2 ToTs that targeted 48 participants on the modules ‘Get Ahead for Women Entrepreneurs’ and ‘Entrepreneurship skills for Agribusiness’. These trainings were meant to provide women with practical information about income generation and enterprise activities particularly in handicraft and agribusiness. In addition to this, 47 women were trained in food processing skills to further contribute to income diversification and strengthening of the technical skills of women engaged in businesses.

Many studies have been conducted on women's economic status in Sudan and recommendations formulated; but there is still limited evidence to show that programme responses have taken these recommendations into account.  UN Women commissioned a meta-analysis study to examine these findings holistically and come up with concrete recommendations that would address the low economic status of women in East Sudan and their lack of access to resources.  Parallel to this, Gadaref University was contracted to conduct a study on land tenure since this is key to livelihood stability in the region. The study aims to outline the role women play and the challenges they face in accessing these resources. The inception report was finalized. Findings of this study will be shared with community leaders and other stakeholders to articulate recommendations to improve women's participation in local economy.

Additionally, UNWOMEN determined that it was more strategic to provide additional inputs to women's groups that had already received funding from ILO but whose projects needed to be scaled-up or groups that were trained but not funded.The states Ministries of Welfare of Kassala and Gadaref were consulted in the selection to ensure their support and follow up of the beneficiaries. This component will be implemented in the beginning of 2014 and is expected to provide sustainable livelihoods to beneficiaries.

The main causes of conflicts identified in East Sudan are poverty and the friction between tribes present in the region. The livelihood interventions in this project promote collaboration between members of various tribes, furthermore the outputs will contribute to the revitilization of the local economy and the empowerment of disadvantaged women in both states which will contribute to social cohesion and peace building efforts.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

The project had a slow start and did not progress as quickly as expected due to some challenges of which many were unforseen.

East Sudan (Kassala and Gadaref states) is 8 hours away from Khartoum by road.  Local capacity in the region is limited and it is a challenge getting suitable consultants to undertake work in the region. Furthermore, a significant amount of time was required to do a proper screening of IGAs to be funded by UN Women. The expertise knowledge of a recruited Livelihoods Officer helped expedite the selection. Flash floods that occurred in August and September in the two states  also delayed the conduct of the Baseline Survey.

Various agreements had to be reached with state authorities to get their full support for the project activities.  For instance, it was agreed that sensitization of state authorities would start at the federal level to get authorities of the East Sudan Reconstruction Fund and planning officers in the federal ministry of finance and the states Ministries of Finance of kassala and Gadaref to understand their obligation to address gender and women's priorities in administering the East Sudan Reconstruction Fund.  Thereafter sensitisation would be done at the states' level for the planning officers and civil society organisations to understand how to access the fund and conduct the necessary consultations for identifying interventions for women's post conflcit recovery to be forwarded to the Fund for consideration.

Outcome Statement 2:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Outcome Statement 3:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Outcome Statement 4:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender in the reporting period

| Evidence base: What is the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | The inception reports for the baseline strudy and meta-analysis are available. No validation has taken place, only comments from UNWOMEN to strengthen the methodology of both studies. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | The current activities will fill information gaps for programmes on economic empowerment of women and will provide a baseline for measuring progress on women's economic empowerment in East Sudan. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | Not applicable at this stage of implementation. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | Not applicable at this stage of implementation. |
| Gender marker: Is the original gender marker for the project still the right one? Have gender considerations been mainstreamed in the project to the extent possible? Briefly justify. (1500 character limit) | Gender marker 3 is still applicable to the project. Even though the studies commissioned will cover men, the ultimate direct beneficiaries of the studies and project implementation are women. |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | Government support is critical for women's economic empowerment in East Sudan. The society is very conservative and government is key to entering the communities. There are also opportunities within government to support women's economic growth which UNWOMEN was able to negotiate. The government controls women development centres that were established by the European Union several years back The ministry has made a development centre available for one of the projects and will also provide supervision for the projects. |
| --- | --- |
| Lesson 2 (1000 character limit) | There is great lack of awareness on the opportunities available for post conflict recovery for women and the processes for accessing these opportunities. This is true especially for the East Sudan Reconstruction Fund where government and civil society have not been applying for gender and women related activities even though the Fund has been available for several years. |
| Lesson 3 (1000 character limit) | UNWOMEN's technical expertise in livelihoods was a critical factor in identifying the key viable activities to be supported and knowledge of the opportunities within government to support the activities with additional technical expertise and supervision. |
| Lesson 4 (1000 character limit) |  |
| Lesson 5 (1000 character limit) |  |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures are on track, slightly delayed, or off track:

If expenditure is delayed or off track, please provide a brief explanation (500 characters maximum):

Expenditure was delayed because some of the project's activities were delayed.  However, payments were made for training activities, inception reports, and monitoring visits. As of end of December 2013 expenditure was at $231,118.

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when); or whether any changes are envisaged in the near future (2000 character maximum):

UNWOMEN recruited a livelihoods specialist to assist in the implementation of the project to support the peace and security specialist.  This provided expert knowledge for the identification of viable projects, and the additional training needs of the proposed project beneficiairies.

The partnership with ILO is also strong, evidenced by joint monitoring and consultations at country office level. Projects to be supported  by UN Women were chosen from a list provided by ILO, and included some partners who had received insufficient inputs from ILO to ensure viability of their activities and partners who had already been trained on basic business skills. It was determined that the additional inputs would be provided by UNWOMEN.

At the request of the Ministry of Welfare, UN Women will train both selected beneficiaries and staff from the ministry in management and monitoring which will contribute to the sustainability of the projects as the ministry will then be better able to monitor and support the projects beyond the project duration.

Slight modifications were made to the project.  Some of the studies planned by UNWOMEN had been covered to some extent by other studies comissioned by other organizations including ILO for this same project, so a meta-analysis of those studies was considered instead.

In light of challenges mentioned above, a No Cost Extension (NCE) was requested to ensure completion of activities and the achievement of results.

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.