# RUNO Half Yearly Reporting 					TEMPLATE 4.3

[COUNTRY: South Sudan]

PROJECT HALF YEARLY PROGRESS UPDATE

PERIOD COVERED: JANUARY – JUNE 2015

| Project No & Title: | PBF/Peacebuilding Secretariat |
| --- | --- |
| Recipient Organization(s): | UNICEF, UNOPS,ILO/UNIDO,FAO/UNEP |
| Implementing Partners (Government, UN agencies, NGOs etc): | RUNOs: UNICEF, UNOPS,ILO/UNIDO,FAO/UNEP |
| Total Approved Budget : | 10000000 |
| Preliminary data on funds committed : | Usd 4,601,459 | % of funds committed / total approved budget: | 46% |
| Expenditure: | 4,601,459 | % of expenditure / total budget: (Delivery rate) | 46% |
| Project Approval Date: | 11th May 2013 | Possible delay in operational closure date (Number of months) | 7 months |
| Project Start Date: | 11th May 2013 |  |  |
| Expected Operational Project Closure Date: | 30th Dec 2015 |  |  |
| Project Outcomes: | i) Improved economic and employment opportunities for young people and ii) Access to water resources for both human and livestock consumption |
| PBF Focus Area (select one of the Focus Areas listed below) | Promote coexistence and peaceful resolution of conflicts Revitalisation of economy and generate immediate peace dividends |

# Qualitative assessment of progress

| For each intended outcome, provide evidence of progress during the reporting period. In addition, for each outcome include the outputs achieved. (1000 characters max per outcome.) | Outcome 1: Conflict over resources reduced. FAO/UNEP carried out an inventory of existing water harvesting structures built by Government and development partners. The exercise showed evidence of reduced migrations of pastoral youth in search of water due to the provision of haffirs and boreholes, hence more time for youth to engage in other activities. The assessment also indicated that haffirs reduced migration periods in Lokoges area, which in turn reduced conflict and supported peacebuilding efforts. Outcome 2: Access to water improved: UNOPS has completed 2 haffirs and 2 boreholes. Commencement of the remaining 4 water structures (2 boreholes and 2 haffirs) is underway. This has increased the number of water users. Training of the Water User Committees is yet to commence. Outcome 3: Enhanced literacy and livelihood opportunities for youth UNICEF initiated training for 2,522 'At risk out of School youth’, who are undertaking literacy classes in the 6 Accelerated Learning Programs in Minkaman, Akobo and Pibor. Youth dialogue forums and training of youth facilitators also took place in the same locations. The outcome of which is the promotion of non-violent conflict mediation skills among youth in the counties. Outcome 4: UNIDO has trained 1,190 young men and women in different technical skills that include; dairy processing (263 participants), fish training (257 participants), food processing (343 participants), hides and skins training (182 participants) and solar energy training (145 participants). UNIDO/ILO had prior conducted market and training assessments in Jonglei State, particularly in Bor and the Greater Pibor Administrative Area (GPAA). Partners and line ministries were also mobilized for project implementation in order to built in sustainability of the trainings. The impact of the training was that it demonstrated a great need and demand for skills trainings by the demobilized youth especially in Pibor. |
| --- | --- |
| Do you see evidence that the project is having a positive impact on peacebuilding? (1000 characters max.) | The assessment by FAO/UNEP has given evidence to the impact of construction of haffirs and boreholes in reducing the time of migration of water users. However, UNOPS is yet to train 8 Water User Committees in both conflict management skills as well as in Operations and Maintenance, in order to reduce chances of escalated conflict. The youth literacy skills provided by UNICEF and the vocational skills provided by UNIDO/ILO have brought about alternative activities for youth needing to be demilitarized . There has been evidence of a higher demand for the training. |
| Were there catalytic effects from the project in the period reported, including additional funding commitments or unleashing/ unblocking of any peace relevant processes? (1000 characters max.) | None |
| If progress has been slow or inadequate, provide main reasons and what is being done to address them. (1000 characters max.) | The challenges that the partners experienced were varied. UNICEF encountered problems accessing Akobo due to some resistance in Akobo. This led to some delays in their implementation, which was overcome through implementing through another national NGO. UNOPS encountered the problem of conflict while their contractor delivered equipment. ILO did not have any staff on ground following the demise of their colleague in December of 2013. This led to considerable delays in the delivery of the business training of youth. |
| What are the main activities/expected results for the rest of the year? (1000 characters max.) | UNICEF, UNIDO/ILO intend to finalise their training activities with youth in Akobo, Pochalla , Pibor and Bor. UNOPS intends to retender for new borehole contractor as well as a trainer of the Water Users Committee in preparation of the dry season when implementation of the boreholes will begin. |
| Is there any need to adjust project strategies/ duration/budget etc.? (1000 characters max.) | UNICEF and UNIDO/ILO both intend to formally request for No-Cost-Extension to December 2015, while UNOPS requested already requested for an extension to August 2016. |
| What is the project budget expenditure to date (percentage of allocated project budget expensed by the date of the report) – preliminary figures only? (1000 characters max.) | Total UNICEF UNOPS UNDP ILO, UNIDO FAO, UNEP Budget 9,999,957 768,260 5,920,352 1,200,000 1,553,886 557,459 Committed 4,601,459 555,000 2,570,000 258,000 661,000 557,459 Balance 5,398,498 213,260 3,350,352 942,000 892,886 0 % Spent 46% 72% 43% 22% 43% 100% |
| Any other information that the project needs to convey to PBSO (and JSC) at this stage? (1500 characters max.) | There has been a clear indication of the huge need and demand for youth literacy as well as skills training especially in Pibor area. The Greater Pibor Administrative Area (GPAA) Administrator David Yau Yau welcomed more youth activities as an alternative for the armed youth in his area. Due to the accessbility of the GPAA, RUNOs have been able to carry out their activities, raising the number of beneficiaries from the initial targets.UNICEF supassed their target by 1500 beneficiaries, from the initial 1000 targeted. The Peacebuilding Priority Plan expired on the 31st of May. Efforts to extend it on an interim basis are underway to enable RUNOs to continue on with their activities. It is likely that both UNICEF, UNIDO/ILO, will make requests for No-Cost-Extensions (NCE) to December 2015. UNOPS had already submitted their NCE request for August 2016 because of the rainy season. |

INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (250 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Conflicts over resources reduced | Indicator 1.1 Number of violent incidents in target communities | No guidelines, on the four thematic areas published and disseminated namely -Feasibility study -NRM (Natural Resource Management) guidelines - (Environmental and Social Impact Assessment) ESIA guidelines -Gender mainstreaming guidelines available | Guidelines in four thematic areas: -Feasibility study -NRM (Natural Resource Management) guidelines - (Environmental and Social Impact Assessment) ESIA guidelines -Gender mainstreaming guidelines -Training delivered on the four thematic areas above | Completed |  | Completed in December 2014 |
|  | Indicator 1.2 Numbur of youth involved in peacebuilding and conflict resolution | None available | 1000 youth | 2522 youth engaged in training | Denied access to Akobo area | An alternative National NGO took up the task of training the youth |
| Output 1.1 | Indicator 1.1.1 |  |  |  |  |  |
|  | Indicator 1.1.2 |  |  |  |  |  |
| Output 1.2 | Indicator 1.2.1 |  |  |  |  |  |
|  | Indicator 1.2.2 |  |  |  |  |  |
| Output 1.3 | Indicator 1.3.1 |  |  |  |  |  |
|  | Indicator 1.3.2 |  |  |  |  |  |
| Outcome 2 Access to water improved | Indicator 2.1 % of population using an improved water source | None available | Construction of 4 haffirs and 4 boreholes in four locations in Jonglei | 2.5 Haffirs completed, 2 boreholes completed | Some insecurity as well as wet weather. Heavy machinery cannot be moved during the wet season that ends in November/December. Contractual issues with the contruction of 2 boreholes | The remaining water structures to commence in the 4th quarter of 2015 or beginning of the first quarter of 2016 Tendering for new contractors to commence in the 4th quarter of 2015 |
|  | Indicator 2.2 Travel time to water source | None available | To be determined |  |  |  |
| Output 2.1 4 community awareness campaigns on diseases | Indicator 2.1.1 Infection rate for diseases such as diarrhea, intestinal worms and parasitic infections | None available |  | Not commenced | There has been delays due to contracting issues with the INGO in the Prodoc. | Training to commence during the construction of the remaining haffirs and boreholes in the 4th quarter of 2015 or 1st quarter of 2016 |
|  | Indicator 2.1.2 |  |  |  |  |  |
| Output 2.2 8 committees established and trained | Indicator 2.2.1 # of trainings in Operational maintenance | None available | 8 Water User Committees |  | There has been delays due to contracting issues with the INGO in the Prodoc. | Training to commence during the construction of the remaining haffirs and boreholes in the 4th quarter of 2015 or 1st quarter of 2016 |
|  | Indicator 2.2.2 # of trainings in conflict resolution skills | None available | 8 Water User Committees |  | There has been delays due to contracting issues with the INGO in the Prodoc. | Training to commence during the construction of the remaining haffirs and boreholes in the 4th quarter of 2015 or 1st quarter of 2016 |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 Enhanced literacy and livelihood opportunities for youth | Indicator 3.1 # of at risk out of school youth accessing literacy skills development | 50 Advance Learning Program (ALP) centers, approximately 4000 ALP students, Approx. 90 ALP teachers in South Jonglei | - 30 ALP teachers trained - 1000 ALP students enrolled in Twic East, Akobo, Pibor counties | 2522 youth already initiated training in three locations | Access to Akobo location was denied to one of the local partners of UNICEF due to some political misunderstanding | Training will be finalised during the 4th quarter of 2015 |
|  | Indicator 3.2 |  |  |  |  |  |
| Output 3.1 Youth equiped with literacy skills | Indicator 3.1.1 | 50 Advance Learning Program (ALP) centers, approximately 4000 ALP students, Approx. 90 ALP teachers in South Jonglei | 1000 ALP students enrolled in Minkaman, Akobo, Pibor counties | 2522 youth already initiated training in three locations |  | Training will be finalised during the 4th quarter of 2015 |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 ALP teachers eqipped with skills | Indicator 3.2.1 |  | 30 ALP teachers trained - 1000 ALP students enrolled in Minkaman, Akobo, Pibor counties |  | Access to Akobo location was denied to one of the local partners of UNICEF due to some political misunderstanding | Training will be finalised during the 4th quarter of 2015 |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 Youth lifeskills in HIV/AIDS and conflict resolution | Indicator 3.3.1 # of at risk youth equipped with life skills for HIV/AIDS control and peacebuilding and conflict resolution | None available | 1000 in Akobo, Pibor and Minkaman | 2522 youth already initiated training in three locations | Access to Akobo location was denied to one of the local partners of UNICEF due to some political misunderstanding | Training will be finalised during the 4th quarter of 2015 |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 Economic opportunities and employment is generated for young men and women | Indicator 4.1 # of youth and women with access to economic opportunities and income generation | Youth and women currently have extremely limited access to skills training and employment opportunities | Increase by 30% number of youth currently taking literacy classes in target counties 1500 young men and women access learning and skills training opportunities |  | The ILO training component which includes the business skills and coperative group training is yet to commence. They have no staff prescence in Juba yet, after the demise of their colleague in December 2013. | Business skills training will commence in the 3rd quarter of 2015 |
|  | Indicator 4.2 |  |  |  |  |  |
| Output 4.1 Marketable technical skills | Indicator 4.1.1 |  | 1500 young men and women access learning and skills training opportunities | 1190 young men and women with technical skills | As above | Business skills training will commence in the 3rd quarter of 2015 |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 New enterprises or existing ones upgraded | Indicator 4.2.1 # of new enterprises established or existing ones upgraded | Very few registered enterprises exist in Jonglei | 10 new micro-industries established or existing ones upgraded | Not commenced | As above | Business skills training will commence in the 3rd quarter of 2015 |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 Cooperative education and finance training | Indicator 4.3.1 # of cooperative groups undergoing training | Not available | At least 10 new cooperatives established among women | Not commenced | As above | Business skills training will commence in the 3rd quarter of 2015 |
|  | Indicator 4.3.2 |  |  |  |  |  |

# Footnotes

Please note that where there are multiple agencies, only one consolidated project report should be submitted.

Approved budget is the amount transferred to Recipient Organisations.

# Funds committed are defined as the commitments made through legal contracts for services and works according to the financial regulations and procedures of the Recipient Organisations. Provide preliminary data only.

# 4 Actual payments (contracts, services, works) made on commitments.

5 PBF focus areas are:

PBF Focus Areas are:

1: Support the implementation of peace agreements and political dialogue (Priority Area 1):

(1.1) SSR, (1.2) RoL; (1.3) DDR; (1.4) Political Dialogue;

2: Promote coexistence and peaceful resolution of conflicts (Priority Area 2):

(2.1) National reconciliation; (2.2) Democratic Governance; (2.3) Conflict prevention/management;

3:Revitalise the economy and generate immediate peace dividends (Priority Area 3);

(3.1) Employment; (3.2) Equitable access to social services

4) (Re)-establish essential administrative services (Priority Area 4)

(4.1) Strengthening of essential national state capacity; (4.2) extension of state authority/local administration; (4.3) Governance of peacebuilding resources (including JSC/ PBF Secretariats)