# RUNO Half Yearly Reporting 					TEMPLATE 4.3

[COUNTRY: Kyrgyz Republic ]

PROJECT HALF YEARLY PROGRESS UPDATE

PERIOD COVERED: JANUARY – JUNE 2015

| Project No & Title: | PBF/88710/ Building a Constituency for Peace |
| --- | --- |
| Recipient Organization(s): | UN Women Country Office, Kyrgyz Republic |
| Implementing Partners (Government, UN agencies, NGOs etc): | - KR Government Counterparts: Department on Religious Affairs, Inter-ethnic Policy and Public Relations, Office of the President - Rural Advisory Service Jalalabad (RAS) - Foundation of Tolerance International (FTI) |
| Total Approved Budget : | 1602130 |
| Preliminary data on funds committed : | 799'313 | % of funds committed / total approved budget: | 50% |
| Expenditure: | 779'720 | % of expenditure / total budget: (Delivery rate) | 49% |
| Project Approval Date: | 12 December 2013 | Possible delay in operational closure date (Number of months) | N/A |
| Project Start Date: | 1 January 2014 |  |  |
| Expected Operational Project Closure Date: | 30 June 2016 |  |  |
| Project Outcomes: | Local self-government is convening communities by engaging everyone in joint action towards all citizens enjoying equal access to opportunities. Threats to peace, injustice and stability are met across ethnic, economic, gender and religious divisions by creating a stake of individuals in the rule of law and increased loyalty to the state that provides for security and an environment where young people as agents for positive change can secure livelihoods by deploying their skills. |
| PBF Focus Area (select one of the Focus Areas listed below) | 6. Democratic governance |

# Qualitative assessment of progress

| For each intended outcome, provide evidence of progress during the reporting period. In addition, for each outcome include the outputs achieved. (1000 characters max per outcome.) | Outcome 1: Students practice livelihood options on the family farm. Business plans for 13 vegetable crops were elaborated, monitoring visits and consultations in 33 schools are on-going. In total 2466 students (1255 girls) completed the MPF course. The total number of available compost hips is 1052, out of them 493 made by girls and 461 by boys and 98 by teachers. The MPF manual is available in three languages: Kyrgyz, Russian and Uzbek. Students in seven provinces act as agents of positive change under the MSPS component by advocating for and monitroing the protection of their female peers' human rights by duty bearers. 600 peers graduated with distinction and 95 peer educators trained. And successful peer educators are being trained to conduct a gender study. In 19 communities diverse stakeholders at municipal level joined in drafting conflict analysis and implemented the related action plans thus contributing to the mitigation of conflict tensions. Outcome 2: Outcome 3: Outcome 4: |
| --- | --- |
| Do you see evidence that the project is having a positive impact on peacebuilding? (1000 characters max.) | Through MPF students are learning by doing, they apply their knowledge in the family land plot with great interest. Stakeholders have seen that they are key persons on local level to build peace and they can change a situation. For example, in Yrdyk /Issyk-Kul the project participants together with village leaders managed to organise the public hearings on unsatisfactory work of Water Users' Assosiation/WUA which inefficient work leads into conflicts between multiethnic population (Kyrgyz, Russians, Dungans, etc.). The population selected new members of WUA and now it has created a special commission on conflicts which is responsible to address people's complaints on different issues (commission consists of respected and well-known people from 5 villages). Ayil okmotu provided the place for WUA in the building of ayil okmotu and local kenesh increased a budget for 2015 (the new head of WUA managed to promote among deputies the importance of the budget increase). |
| Were there catalytic effects from the project in the period reported, including additional funding commitments or unleashing/ unblocking of any peace relevant processes? (1000 characters max.) | The MPF is of real interest to students, teachers and parents. They learned from MPF how they can better manage their farms, thus one of the parents in Kulundu/Batken shared that he is interested to apply the technology of preparing silage for domestic animals. In some areas (Chaek, Otradnoe) the compost is a new unknown technology, and people interested in its impact. When people sow the quality seeds of vegetables in Toguz-Toro they expressed their high interest. The Project impacted the local population, some communities have found additional funds to support peacebuilding initiatives/solving of local problems. For example, in Chaek (Naryn) ayil okmotu in order to protect children from racketeering and other violence, parents agreed to hire a security service at school. Some parents of school students have financed some events at schools to work with school racket. In Kashka-Suu (Jalal-Abad), people collected 40000 soms to clean irrigation systems. |
| If progress has been slow or inadequate, provide main reasons and what is being done to address them. (1000 characters max.) | The third component was a bit longer than a year as was planned because most LSGs developed more than one action plans and their implementation took more time; some LSGs like Kazarman, Chaek, Alai-Kuu are located in the mountain areas and it is a little bit hard to reach them during winter and early spring to conduct final round tables; three LSGs (Masaliev, Arslanbob and Terek-Sai) were trained and started activities at the end of autumn and they needed more time to complete their action plans. Moreover, in three ayil okmotus the component completed earlier because they were passive, they are Amanbaevo, Minkush and Sulukta. |
| What are the main activities/expected results for the rest of the year? (1000 characters max.) | Monitoring and consultations to schools will be provided more frequently. The kitchen garden works will be monitored and documented. On the basis of schools with best practices on MPF regional workshops on sharing experiences will be conducted. Demonstration funds will be distributed. New peer educators on MSPS for the rest targeted schools will be again trained to organize their groups before the school year to start the MSPS implementation. Open Day for Peace event will be faciliated in the targted schools. |
| Is there any need to adjust project strategies/ duration/budget etc.? (1000 characters max.) |  |
| What is the project budget expenditure to date (percentage of allocated project budget expensed by the date of the report) – preliminary figures only? (1000 characters max.) | 779'720 USD |
| Any other information that the project needs to convey to PBSO (and JSC) at this stage? (1500 characters max.) |  |

INDICATOR BASED PERFORMANCE ASSESSMENT: Using the Project Results Framework as per the approved project document- provide an update on the achievement of key indicators at both the outcome and output level in the table below. Where it has not been possible to collect data on indicators, state this and provide any explanation in the qualitative text above. (250 characters max per entry)

|  | Performance Indicators | Indicator Baseline | End of project Indicator Target | Current indicator progress | Reasons for Variance/ Delay (if any) | Adjustment of target (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1 Local self-government is convening communities by engaging everyone in joint action towards all citizens enjoying equal access to opportunities. Threats to peace, injustice and stability are met across ethnic, economic, gender and religious divisions | Indicator 1.1 Students practice livelihood options on the family farm that will provide them with a livelihood after graduation, should they decide to work in the agricultural sector upon graduation from school or tertiary education | 0 | 1'000 | too early at this stage, however 1052 participants used compost heaps and after the harvest this indicator will be confirmed based on financial records |  |  |
|  | Indicator 1.2 Students in six provinces act as agents of positive change by advocating for and monitoring the protection of their female peers’ human rights by duty bearers 1.3 Diverse stake-holders at muni-cipal level … | 0 & 0 | 1'000 & 18 | 2'000 & 19 |  |  |
| Output 1.1 1.1 9th graders of both genders and various ethnicities in the conflict susceptible PRF project area are able to effectively use scarce land resources to build successful livelihoods and understand the benefit of joint action, also across ethnic divi | Indicator 1.1.1 Number of students 30 PRF project area schools who successfully complete the entire course | 0 | 2'000 | 2'466 |  |  |
|  | Indicator 1.1.2 Number of students in 30 PRF project area schools knowledgeable about business planning in relation to kitchen gardening | 0 | 2'000 | too early, will be confirmed after harvest based on financial records |  |  |
| Output 1.2 1.2 9th, 10th and 11th grade in 30 schools in the conflict susceptible PRF project area knowledgeable about human rights of young women and men, gender equality and how to conduct a conflict analysis taking action to address conflict causes and/or hu | Indicator 1.2.1 Number of students in 30 PRF project area schools successfully completed the entire courses | 0 | 2'000 | 1'000 |  |  |
|  | Indicator 1.2.2 Number of students in 30 PRF project are schools who conducted a conflict analysis in their school and act upon it. 1.2.3Number of students in 30 PRF project are schools who take action, including advocacy action, to protect the rights of female peer | 0 | 2'000 | 1'000 |  |  |
| Output 1.3 20 key individuals in each of 23 municipalities are sensitized to human rights of young women and men; aware of the duties of state and municipal servants to protect human rights, justice and peace; able to conduct a conflict analysis of their commun | Indicator 1.3.1 Number of designated individuals convened for the training, actively participating and completing the course | 0 | 460 | 500 |  |  |
|  | Indicator 1.3.2 Conflict Analysis documented with responsibility matrix denoting who does what when with which available resources 1.3.3Documented evidence of implementation of responsibility matrix | 0 | 18 | 49 |  |  |
| Outcome 2 | Indicator 2.1 |  |  |  |  |  |
|  | Indicator 2.2 |  |  |  |  |  |
| Output 2.1 | Indicator 2.1.1 |  |  |  |  |  |
|  | Indicator 2.1.2 |  |  |  |  |  |
| Output 2.2 | Indicator 2.2.1 |  |  |  |  |  |
|  | Indicator 2.2.2 |  |  |  |  |  |
| Output 2.3 | Indicator 2.3.1 |  |  |  |  |  |
|  | Indicator 2.3.2 |  |  |  |  |  |
| Outcome 3 | Indicator 3.1 |  |  |  |  |  |
|  | Indicator 3.2 |  |  |  |  |  |
| Output 3.1 | Indicator 3.1.1 |  |  |  |  |  |
|  | Indicator 3.1.2 |  |  |  |  |  |
| Output 3.2 | Indicator 3.2.1 |  |  |  |  |  |
|  | Indicator 3.2.2 |  |  |  |  |  |
| Output 3.3 | Indicator 3.3.1 |  |  |  |  |  |
|  | Indicator 3.3.2 |  |  |  |  |  |
| Outcome 4 | Indicator 4.1 |  |  |  |  |  |
|  | Indicator 4.2 |  |  |  |  |  |
| Output 4.1 | Indicator 4.1.1 |  |  |  |  |  |
|  | Indicator 4.1.2 |  |  |  |  |  |
| Output 4.2 | Indicator 4.2.1 |  |  |  |  |  |
|  | Indicator 4.2.2 |  |  |  |  |  |
| Output 4.3 | Indicator 4.3.1 |  |  |  |  |  |
|  | Indicator 4.3.2 |  |  |  |  |  |

# Footnotes

Please note that where there are multiple agencies, only one consolidated project report should be submitted.

Approved budget is the amount transferred to Recipient Organisations.

# Funds committed are defined as the commitments made through legal contracts for services and works according to the financial regulations and procedures of the Recipient Organisations. Provide preliminary data only.

# 4 Actual payments (contracts, services, works) made on commitments.

5 PBF focus areas are:

PBF Focus Areas are:

1: Support the implementation of peace agreements and political dialogue (Priority Area 1):

(1.1) SSR, (1.2) RoL; (1.3) DDR; (1.4) Political Dialogue;

2: Promote coexistence and peaceful resolution of conflicts (Priority Area 2):

(2.1) National reconciliation; (2.2) Democratic Governance; (2.3) Conflict prevention/management;

3:Revitalise the economy and generate immediate peace dividends (Priority Area 3);

(3.1) Employment; (3.2) Equitable access to social services

4) (Re)-establish essential administrative services (Priority Area 4)

(4.1) Strengthening of essential national state capacity; (4.2) extension of state authority/local administration; (4.3) Governance of peacebuilding resources (including JSC/ PBF Secretariats)