RUNO ANNUAL PROJECT REPORT		TEMPLATE 4.4

PEACEBUILDING FUND (PBF)

ANNUAL PROJECT progress report

COUNTRY: Yemen

REPORTING PERIOD: 1 january – 31 December

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: Technical Assistance to the Constitutional Drafting Process in Yemen Programme Number (if applicable) PBF/IRF-89 MPTF Office Project Reference Number: 00090605 |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: UNOPS/OSASG; UNICEF; OHCHR; |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: Main partner: General Secretariat of the Constitution Drafting Commission (referenced here as "the Secretariat") UNICEF partners:YNGO Coalition in Saada Governorate, CSSW- in Hodeidah, SDA LNGO in Rayma and Brotherhood Bridges in Hajja governorate. |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) USD 2,013,202 |  |  | Overall Duration (months) 12 months |  |
|  |  |  | Start Date (dd.mm.yyyy) 21 May 2014 |  |
| Government Contribution (if applicable) USD 10,000,000 |  |  | Original End Date (dd.mm.yyyy) | 20 May 2014 |
| Other Contributions (donors) (if applicable) YNDCRTF USD 7,308,327 |  |  | Current End date(dd.mm.yyyy) 20 May 2014 |  |
| TOTAL: | USD 20,276,512 |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Assessment/Review - if applicable please attach Yes No Date: Mid-Term Evaluation Report – if applicable please attach Yes No Date: |  | Name: Maisoon Alawdi Title: Project Manager Participating Organization (Lead): OSASG Email address: al-awdi@un.org |

PART 1 – RESULTS PROGRESS

  - Assessment of the current project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project is contributing:

Priority Plan Outcome to which the project is contributing. Promote coexistence and peaceful resolution of conflict

Priority Plan Outcome indicator(s) to which project is contributing.

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  Implementation of the CDP advanced according to agreed timelines and steps, on the basis of coherent technical, financial and administrative support

Rate the current status of the outcome:

| Indicator 1: Established CDC-S and a clear structure is created for the upcoming CDP. Indicator 2: CDC plan prepared and endorsed by CDC. Number of workshops/ trainings and consultations provided to the CDC Indicator 3: | Baseline: No Target: Yes Progress:Yes Baseline: No Target: Yes Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Note: only 50% of the following was covered under this project:

-A Secretariat was structered of 45 staff and provided the administrative, logistical and technical support, with the support of UNOPS and the OSASG,  to the Constitutional Drafting Committee.

- The OSASG provided the technical support needed to ensure the Constitution Process is funded through the PBSO funds and YNDCRTF. In addition, political support, including mediation / facilitation assistance was provided as needed by the Secretariat and OSASG.

- Work of the CDC was informed by International experts, 10 deployed by OSASG and an One by OHCHR who provided lessons learned of best practice in Constitution-making, federalism, protections for minorities, the structure of the state, good governance, and finance in federal systems among others.

- International assistance to the NDC (closing phase, communication of NDC outcomes) and the CDP is well coordinated and consestant with the progress of the transitional process.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

The targeted progress under this outcome was achieved regardless the time line extension of the Constitution Drafting Process (CDP). Many external factors contributed to this such as the lack of security and unstable political situation. After the formulation of the CDC, the National Dialogue Secretariat was restructured to form the new Secretariat to provide technical and operational support to the Constitution Process. With the support of UNOPS the Secretariat provided operational support to the CDC meetings and Communication and outreach campaign. The project covered part of the Secretariat staffing costs, Secretariat Office preparations and contributed to the deployment of ten international experts who provided technical support to the CDC members throughout the period. The experts provided technical advice through lessons learned from other constitutional processes in other federal systems. In addition to dozens of working papers and presentations in process design, communications, and a range of issues relating to constitution making in a federal context including foundational principles, finance and allocation of revenues among the different tiers of government, rights and freedoms/human rights among others.

By the end of Nov, the CDC worked on drafting a number of chapters such as Independent institutions finance, rights and freedoms, the judiciary, the legislative authority, the executive authority, police and armed forces and land, water and environment. These chapter were not finalised yet but drafts were completed by end of September. In October, a six week retreat to Abu-Dhabi was held to finalise these chapters and finalise the contradictory issues.

The OSASG channelled the UN expert support and mainly focused in drafting the Bill of Rights (UNICEF and OHCHR experts largely contributed in this document). This document was shared and consulted with the CDC during the drafting process.

UNICEF provided technical advice to the Bill of rights with regards to Legal age of Child, right to access drinking water and minorities rights to ensure these key components of the NDC outcomes are reflected in the new constitution.

OHCHR deployed an international expert who provided technical support to the CDC The inputs included background documents for rights and guarantees enshrined in the draft Bill of Rights such as compilation of international standards relevant to specific rights; UN Treaty Body General Comments; as well as best practices from countries in the region and elsewhere.

In October, a six week retreat to Abu-Dhabi was held to finalise these chapters and finalise the contradictory issues. The retreat cost is covered by the YNDCRTF funds, hence, under this project international experts were deployed to ensure sufficient technical support is available to inform the CDC discussions.

During December, the first draft is anticipated to be ready to share with the National Body and public consultation phase.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Considering the delays which occurred on the timeline of the process, the level of progress in achieving this outcome is on track.  In the beginning of the drafting process, it was anticipated that the first draft would be completed by mid-July, however, issues adjacent to the process affected the progress, such as security, location of work and the deteriorated political situation. All of these factors contributed to extending the timeline of the drafting process. As a consequence the project timeline was extended to make it consistent with the process progress.

Outcome Statement 2:  The outcome of the CDP reflects an inclusive, transparent, meaningful and participatory process.

Rate the current status of the outcome:

| Indicator 1: 2.1 Number of public submissions / comments / contributions received to the CDC Indicator 2: 2.3 Protection of NDC recommendations with regard to: The Legal Age of the child (and its myriad manifestations), and right to Safe Water by the public on the CDP to inform key components related to rights of children and technical support to the CDC in reflecting these issues as relevant to the constitution. Indicator 3: 2.4. Members of the Constitutional Reform Committee and civil society participating in the constitutional drafting process have the capacities to incorporate human rights principles and standards in the Constitution | Baseline: 0 Target: 500 recommendations to the draft constitution Progress:In progress Baseline: No Target: Yes Progress:In progress Baseline: No Target: 80% of constitutional provisions on human rights recommended by members of the Constitutional Reform Committee comply with international human rights standards. Progress:In progress |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

UNOPS/OSASG: the following activities are covered 50% under this project:

Launch of Matlabi campaign in all governorates; 40 radio and TV flashes produced and broadcasted; 2 manuals were developed for promoting NDC outcomes; 4 ToTs for promoting NDC outcomes in four regions for 160 CSOs and activists; 4 ceremonies launching Matlabi campaign; 1 international expert was deployed to assist in planning the NDC outreach and public consultation phase; 3 operator songs produced for NDC outreach activities;

UNICEF: 60 community initiatives (24 FGDS, 15 Jumma sermons, 21 open dialogue forums); 7 wall paintings; 6 puppet shows and 8 mini drama videos were produced,

OHCHR deployed an int expert in rights and freedoms who provided technical advice to the CDC who provided substantive inputs and policy guidance regarding the integration of international human rights standards and principles into the draft Constitution. Organised several consultations with civil society from the south and the north.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

During this reporting period the Secretariat worked closely with the OSASG and UNOPS to implement their outreach and communication campaign for the NDC outcomes. The Secretariat conducted several activities through a bigger project (this project participated 50% in the work mention below and 50% was covered by the YNDCRTF).

The campaign was launched in September the slogan "Matlabi is to implement the NDC outcomes". The campaign launching ceremonies were in 4 governorates. Billboards of the campaign were installed all governorates. The campaign also focused on the traditional media outlets like TV and Radio. 40 Radio and TV flashes were produced and broadcasted in all national TV stations and Radio stations in the last half of the year. The Secretariat ensured daily coverage of the CDC meetings and news updates were circulated and shared with all national TV stations and circulated to a list of +1350 journalist. News tickers were running on four national TV posting updates on the CDC progress and selected NDC outcomes. The NDC website continued to serve as a source to get updates on the CDP and the NDC outcomes promotion. The OSASG deployed an international expert to assist the Secretariat in planning the communication and outreach and to provide lessons learned from other constitutional process on the public consultation phase. Two manuals were developed for community promoters to promote the NDC outcomes. One was designed for preachers, the other was focusing on women rights related outcomes. Other outreach activities were coordinated by the Secretariat in partnership with CSOs. Three song operates were produced by the Secretariat and youth artists to be used in the "Matalbi " campaign.

UNICEF activities focused on promoting the NDC outcomes with regard to: The Legal Age of the child (including right of Yemeni child at birth, safe age of marriage and protection against children recruitment during armed conflicts among others); right to Safe Water and rights of marginalised groups. UNICEF was able to cover 36 districts in different governorates through fruitful partnerships with CSOs in Saada, Hodeidah, Rayma and Hajja governorate. Around 62,000 people were engaged in UNICEF's awareness campaign targeting men, women, young girls and boys, religious leaders, community leaders among others.

OHCHR organised several consultations with CSOs in the south and north to build their capacity and enable democratic space on human rights issues to be incorporated in the new Constitution. Following extensive discussions, CSOs drafted a Bill of Rights to be used as the main advocacy tool during the public consultations phase. The CSO Bill of Rights, which included 13 principles and 60 recommendations, was finalized and endorsed by 650 concerned organisations for publication including the most prominent human Rights CSOs, the National Union for the Disabled, the National Union for the marginalized and representatives of minorities in Yemen.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Outcome Statement 3:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Outcome Statement 4:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender in the reporting period

| Evidence base: What is the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | The produced materials including ( TV and Radio flashes; photos and participants lists of attendees in trainings and other events; project reports; NDC website; News published in newspapers and websites; puppet shows and drama videos produced; Song operates used in the campaign; outdoor visibility materials; CSO Bill of rights and working papers among other; |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | Yes, the project filled a critical funding gap during the transition process in Yemen. The Constitution Drafting Process is critical to the political transition as the step taken to put together the consensus which was built in the NDC for the new vision for the State. This phase will be followed by presidential elections. This process required a high degree of technical support and political mediation and facilitation to assist with the process and to deal with the multiple agendas that needed to be addressed. This project filled a very critical gap in supporting the bigger project "Support to the Constitutional Process". As a key component in building public confidence in the political transition, the Constitutional Drafting Process is essential to supporting a peaceful transition process. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | This project filled in a critical gap in funding the transition process in Yemen: during the inception phases, before other donor funds was raised, this project covered the Secretariat costs and the CDC meetings in addition to the communication and outreach around the NDC outcomes. This project facilitated technical support by the deployment of experts. The experts presented lessons learned from other constitution making processes in different context. Availability of these experts enriched the CDC meetings and assisted in harmonising the deliberations around several issues. The continuous presence of the OSASG political officers in the CDC meetings enabled them to monitor needs of political mediation and facilitation and close observation of the CDC work enabled selecting the appropriate technical experts to assist the CDC members. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | Yes. With in the current security situation in Yemen, the CDC meetings were the most important activity that the Yemeni Government was taking at the time being. Most of the instability in the security situation was caused by multiple political players who were enrolled in the NDC and signed the NDC outcomes document. With Houthies taking over Amran after a long armed fight with government army and other tribal groups and then invading Sana'a in Sep which started by demonstrations and then by armed groups. In addition, the increase of the terrorists attacks on government institutions and army. All of these security hazards were only a way of expressing the unsatisfactory and anger of the politically affiliated armed groups and anger of the government performance. The CDC members were not feeling secured and meetings of the meetings changed several times. All of these changes in the general political/security situation in the country were affecting the peaceful transition. At some point, it was predicted that the situation will deteriorate to a point where the government will lose control. But with the support of the international community and the SASG, the unsatisfied groups all agreed to sign a new agreement called Peace, National Partnership Agreement which ties all the loose ends of the GCC initiative and a follow up for implementing it.. |
| Gender: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | Under this project, as a follow up for the NDC outcomes, all partners monitored the Women Quta was respected. The CDC members had 30% representation for the Women constituency, the new Government had 30% women representations. In addition, specific components of the outreach and communications were specifically targeting women audience through the traditional media or outreach activities around NDC outcomes |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) | The project initial work plan was modified and timeline was extended of the planned activities due to the extended drafting process. |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | UNICEF covered a wide geographic area in their activities. The locations targeted had variety of groups. In general, positive response and participation from citizens and Executive Offices officials' showing support and inclusion. However, UNICEF faced rejection in some locations in Raymah (Makim, Alamaheel, Aladar, Mazhar and Algafareeah districts) where people rejected the whole concept of the National Dialogue and refused to engage in discussions about any outcomes. These are some locations of many not reached by UNICEF, which reflected poor promotion and outreach around the NDC in 2013 in rural areas. |
| --- | --- |
| Lesson 2 (1000 character limit) | This lesson learned describes some alternative ways OHCHR used to address recommendations to the CDC. One of the challenges which OHCHR's and other UN organisations faced during their advocacy efforts with the CDC members was that the CDC members had not agreed to establish the right to live in the draft Constitution implying that the death penalty will remain sanctioned by the new Constitution. OHCHR noted a tendency by the CDC members to include penal provisions in the draft Constitutions. Many CSO members were against abolition of death penalty in the CSO Bill of Rights.. In order to address the above issues, OHCHR and supporting UN organisations continued to provide additional comments and suggestions through written inputs and direct consultations with the members working on the Rights and Freedoms Chapter. And OHCHR used their capacity building and consultations with CSOs and brought them to agree to include a recommendation in CSOs Bill of Rights regarding abolition of |
| Lesson 3 (1000 character limit) |  |
| Lesson 4 (1000 character limit) |  |
| Lesson 5 (1000 character limit) |  |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures are on track, slightly delayed, or off track:

If expenditure is delayed or off track, please provide a brief explanation (500 characters maximum):

Please provide an overview of expensed project budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: Implementation of the CDP advanced according to agreed timelines and steps, on the basis of coherent technical, financial and administrative support. |
| Output 1.1 | 1.1 Well-resourced CDCS provides the administrative, logistical and technical support to the Constitutional process (25% of the CDP is covered in this project ) | UNOPS/OSASG | Outcome1 OSASG/UNOPS budget: $781,089 | 86% has been exhausted of the total budget by September |  |
| Output 1.2 | 1.2 The CDP is provided with technical and political support, including lessons learned and comparative analysis and mediation / facilitation assistance when requested: | UNOPS/OSASG |  |  |  |
| Output 1.3 | Work of the CDC is informed by high-quality international expertise and best practice in Constitution-making and on specific issues including – but not restricted to – federalism, protections for minorities, the structure of the state, good governance, and improved political participation of women and young people: 1.4 International assistance to the NDC (closing phase, communication of NDC outcomes) and the CDP is well coordinated, with limited transaction costs for national actors and efficient allocation of resources. | UNOPS/OSASG; |  |  |  |
| Outcome 2: The outcome of the CDP reflects an inclusive, transparent, meaningful and participatory process. |
| Output 2.1 | Yemenis in the different regions of the country receive information about the CDP and can input their views, in ways accessible to them: (This project covers 25% of the total budget needed for the CDP) | UNOPS/OSASG | OSASG/UNOPS/CDC-S; budget : $732,209; | 86% has been exhausted of the total budget by September |  |
| Output 2.2 | NDC outcomes with reference to women and youth are protected. Through public engagement and technical support to the CDC in reflecting the issues as relevant to the constitution. | UNOPS/OSASG | 2.2 Other sources of funding: Women and Youth Forum/ UNFPA/UNWomen budget : 865K | 100% exhausted (Another IRF project) |  |
| Output 2.3 | 2.3 Protection of NDC recommendations with regard to: The Legal Age of the child (and its myriad manifestations), and right to Safe Water by the public on the CDP to inform key components related to rights of children and technical support to the CDC in reflecting these issues as relevant to the constitution. 2.4 NDC outcomes with reference to rights of minorities and respect of international standards on human rights are protected. Through public engagement and technical support to the CDC in reflecting the issues as relevant to the constitution | UNICEF; OHCHR | 2.3 UNICEF ; budget: 250K 2.4 OHCHR/; Budget: 249.8K | OHCHR by October spent USD 59,937.00 of the total busget. UNICEF N/A |  |
| Outcome 3: |
| Output 3.1 |  |  |  |  |  |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: |
| Output 4.1 |  |  |  |  |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total: |  |  |  |  |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when); or whether any changes are envisaged in the near future (2000 character maximum):

Coordinating the technical support through the Secretariat and OSASG was very functional. The Secretariat coordinated with non UN agencies a retreat to Germany on federalism and several international experts' deployment. OSASG continued to coordinate the UN support to the process through the UN Interagency meetings (16 up to October) and a sub-group for experts was created to work in building a bill of rights and submit it the CDC to inform their work in the rights and freedoms chapter. Input of experts and comments were received from OSASG, UNFPA, UNICEF, UNHCR and OHCHR.

In addition, several activities were covered by other IRF projects such as the Taiz planning retreat for the CDC in June and other complementary activities supporting women and youth participation through another IRF project.

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.