RUNO ANNUAL PROJECT REPORT		TEMPLATE 4.4

PEACEBUILDING FUND (PBF)

ANNUAL PROJECT progress report

COUNTRY: Liberia

REPORTING PERIOD: 1 january – 31 December

| Programme Title & Project Number |  |
| --- | --- |
| Programme Title: Support to the Liberia Peacebuilding Office for coordination, monitoring & evaluation, communication and capacity building in conflict management Programme Number (if applicable) PBF/LBR/H-1 MPTF Office Project Reference Number: 00088471 |  |  |

| Recipient UN Organizations |  | Implementing Partners |
| --- | --- | --- |
| List the organizations that have received direct funding from the MPTF Office under this programme: UNDP |  | List the national counterparts (government, private, NGOs & others) and other International Organizations: Peacebuilding Office (PBO) |
| Programme/Project Budget (US$) |  | Programme Duration |
| PBF contribution (by RUNO) US$ 2,500,000 (for 3 years) |  |  | Overall Duration (months) 36 months |  |
|  |  |  | Start Date (dd.mm.yyyy) 12/12/2013 |  |
| Government Contribution (if applicable) - |  |  | Original End Date (dd.mm.yyyy) | 31/12/2016 |
| Other Contributions (donors) (if applicable) - |  |  | Current End date(dd.mm.yyyy) 31/12/2016 |  |
| TOTAL: | US$ 2,500,000 |  |  |  |

| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| --- | --- | --- |
| Assessment/Review - if applicable please attach Yes No Date: Mid-Term Evaluation Report – if applicable please attach Yes No Date: |  | Name: Wilfred Gray-Johnson Title: Executive Director, PBO Participating Organization (Lead): PBO Email address: grayjohnsonw@yahoo.com |

PART 1 – RESULTS PROGRESS

  - Assessment of the current project implementation status and results

For PRF projects, please identify Priority Plan outcome and indicators to which this project is contributing:

Priority Plan Outcome to which the project is contributing. Peacebuilding Priority Plan 2014-2016 Outcome 9: Effective coordination, monitoring, reporting, evaluation and communication of all PBF-supported projects in Liberia

Priority Plan Outcome indicator(s) to which project is contributing. 1: JSC Annual Reports submitted within 7 days of the deadline. 2: Quality of JSC Annual Reports rated as “acceptable” by PBSO review team. 3: Mid-year and annual reviews, as well as evaluations, conducted on time. 4: Key partners (e.g. RUNOs as well as non-UN stakeholders) satisfied with level and timeliness of PBO communication and coordination.

For both IRF and PRF projects, please rate this project’s overall achievement of results to date:

For both IRF and PRF projects, outline progress against each project outcome, using the format below. The space in the template allows for up to four project outcomes.

Outcome Statement 1:  Effective coordination, monitoring, reporting, evaluation and communication of all PBF-supported projects in Liberia

Rate the current status of the outcome:

| Indicator 1: Number of JSC Annual Reports submitted within 7 days of the deadline Indicator 2: Mid-year and annual reviews, as well as evaluations, conducted on time Indicator 3: Key partners (e.g. RUNOs as well as non-UN stakeholders) satisfied with level and timeliness of PBO communication and coordination. | Baseline: 1 (JSC Annual Report 2012) Target: 5 (JSC Annual Reports 2012-2016) Progress: 2 (JSC Reports 2012 and 2013) Baseline: Annual reviews of PBF-supported projects by the JSC Target: Mid-year and annual reviews, as well as evaluations, conducted on time Progress: Mid-year review of PBF-supported projects held in July 2014. Annual review by the JSC will probably take place in December. Independent evaluation of PBO coducted in June 2014; report expected in November 2014. Baseline: Partnership baseline survey conducted in June 2014 as part of the PBO evaluation Target: To be determined based on the baseline survey Progress: Results of the first partnership survey expected in the PBO evaluation report |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

* PBO as PBF Secretariat organized two JSC meetings on 14 March and 21 May 2014. Due to the Ebola crisis no meetings could be held in Q 3 and 4. Most activities were put on hold or delayed.

* PBO 2013 Annual Report was prepared in January 2014.

* The 3rd SMC Review was organized and the 2013 report prepared by PBO based on inputs from all key stakeholders; report submitted in Q 1 of 2014.

* National Reconciliation Forum organized by PBO in collaboration with ACCORD (Monrovia, April 2014), bringing together 46 key national stakeholders; GoL committed US$ 3 mln for implementing the Reconciliation Roadmap.

* Public Perception Survey on Justice & Security conducted in Bong, Lofa and Nimba counties in June 201; report presented and widely disseminated for stakeholder action.

* Training in conflict sensitivity conducted for local government officials from 7 counties in June 2014.

* PBO Factsheet developed and widely disseminated in Q 2.

* PBO website redesigned and updated.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

As a project supporting the functioning of the PBO as PBF Secretariat in Liberia this is a different type of project than the other ones supported by the PBF in Liberia. Notwithstanding, the theory of change remains relevant and the PBO is contributing to peacebuilding in various ways through the coordination of different initiatives, such as the National Reconciliation Roadmap, and supporting the JSC and the SMC Review. This means convening - and interacting with - a wide variety of stakeholders, including government partners, civil society organizations, NGOs, youth and women groups, local/traditional leaders, UN Agencies, UNMIL, bilateral and multilateral donors, etc. At the same time, during 2014 (as in previous years) the PBO has provided specific technical advice and national capacity building support in the area of M&E as well as conflict management through training and coaching. As a result, the quality of the various project progress reports has gradually improved. Also, over 50 local government staff are now applying a conflict sensitive approach in the design of their County development programs and projects. By conducting a Public Perception Survey on Justice & Security in Bong, Lofa and Nimba counties the PBO - with technical support from LISGIS - contributed to the evidence base in terms of assessing people's views and experiences regarding a wide range of justice and security issues. Based on the survey findings key stakeholders can now better identify short and medium term actions to further enhance access to justice, security and related matters. In addition, efforts were also made to further improve the communication about the various PBF-supported initiatives under the Priority Plan in Liberia, e.g. through the development of a PBO Factsheet with key information about the PBO, the PBF and a number of project examples. The PBO website was also redesigned during the course of 2014. Through its various coordination and support activities PBO is facilitating certain peacebuilding initiatives, rather than necessarily implementing interventions itself.

One example of an event convened by PBO in collaboration with ACCORD was the National Reconciliation Forum held in April 2014. The Forum brought together 46 key national stakeholders, including representatives from government, civil society, the UN and donors. Progress and challenges related to the implementation of the Reconciliation Roadmap were discussed frankly and a series of practical recommendations formulated for key policy makers who joined the last day of the Forum. The Minister of Finance on behalf of the Government of Liberia committed US$ 3 mln to speed up the Roadmap implementation as part of a broader Peacebuilding and Reconciliation Resource Mobilization Strategy. However, further progress was hampered by the Ebola crisis that hit the country.

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

In March 2014 Liberia was confronted with an outbreak of the Ebola virus which spread across the border from Guinea. The number of cases and deaths gradually increased while from June/July onwards a second, more vigorous outbreak seriously affected the whole country and the State of Emergency was declared to combat this national disaster. Practically all the PBF-supported projects were considerably affected with activities either temporarily put on hold, postponed or delayed. In addition, PBO trainings on M&E and conflict management originally scheduled for Q 3 and 4 could not be held and no field monitoring visits could be conducted. This crisis was not foreseen in the risk matrix as nobody could have predicted such a disaster. The national and international response started slowly but gradually increased in scope. Since most of the originally planned activities could not be done ,some of the PBF-supported projects diverted efforts to conduct Ebola outreach e.g. through CSOs, National Youth Volunteers, women's groups and human rights monitors in the various counties. Towards the end of 2014 key national stakeholders were initiating discussions, involving the JSC, PBC and PBSO, about post-Ebola programming in the area of reconciliation. However, the effort to halt the spread of Ebola and address all the cases is expected to still take at least several months into 2015.

Outcome Statement 2:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Outcome Statement 3:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

Outcome Statement 4:

Rate the current status of the outcome:

| Indicator 1: Indicator 2: Indicator 3: | Baseline: Target: Progress: Baseline: Target: Progress: Baseline: Target: Progress: |
| --- | --- |

Output progress

List the key outputs achieved under this Outcome in the reporting period (1000 character limit).Outputs are the immediate deliverables for a project.

Outcome progress

Describe progress made during the reporting period toward the achievement of this outcome. This analysis should reflect the above indicator progress and the output achievement. Is there evidence of the outcome contributing to peacebuilding and to the specific conflict triggers? Is the theory of change that underpins the project design still relevant for this outcome (3000 character limit)?

Reasons for low achievement and rectifying measures

If sufficient progress is not being made, what are the key reasons, bottlenecks and challenges? Were these foreseen in the risk matrix? How are they being addressed and what will be the rectifying measures (1500 character limit)?

  - Assessment of project evidence base, risk, catalytic effects, gender in the reporting period

| Evidence base: What is the evidence base for this report and for project progress? What consultation/validation process has taken place on this report (1000 character limit)? | This report is based on the inputs from PBO records, reports from meetings, workshops, and other documentation. Consultations were held with colleagues within and beyond PBO to provide details on the various questions, and a draft report was shared for comments with key stakeholders. |
| --- | --- |
| Funding gaps: Did the project fill critical funding gaps in peacebuilding in the country? Briefly describe. (1500 character limit) | The Peace and Reconciliation Forum organized in April 2014 was generally considered as an important event that brought all major stakeholders together to prioritize specific interventions to further enhance reconciliation in the country. The Minister of Finance assured participants of the Government’s commitments and informed that an initial US$ 3 million would be included in the Government’s fiscal budget for 2014/2015 to support the implementation of the National Strategic Roadmap on National Healing, Peacebuilding and Reconciliation. However, the allocation did not yet materialize due to Ebola crisis which commanded most of the national resources for the remainder of the year. Despite these challenges, the Government through the Ministry of Internal Affairs assured partners and stakeholders of Government’s commitment through budgetary allocations toward the implementation of the Roadmap. The Government however expressed the need to review the Roadmap in consideration of the impact of Ebola on the country’s socio-economy and political situation. |
| Catalytic effects: Did the project achieve any catalytic effects, either through attracting additional funding commitments or creating immediate conditions to unblock/ accelerate peace relevant processes? Briefly describe. (1500 character limit) | At the Peace and Reconciliation Forum for the first time Peace Ambassador George Weah, heading the Liberia Peace Initiative (LPI), made a formal presentation stating the LPI’s achievements, challenges and commitment to peace and reconciliation in Liberia. The outcome of the April Forum led to several follow-up consultation on reconciliation organized by Amb. Weah. These consultations brought together citizens from Nimba and Grand Gedeh, the two main rival counties during the Liberian civil conflict. Along with citizens these consultations included chiefs, elders, opinion leaders, etc. from the two counties to discuss on breaking from the past and fostering healing and reconciliation among each other. Meanwhile, Amb. Weah resigned in November as Peace Ambassador and this has created a gap that will need to be addressed by the Government, either to reappoint a successor or declare the post nominal. |
| Risk taking/ innovation: Did the project support any innovative or risky activities to achieve peacebuilding results? What were they and what was the result? (1500 character limit) | Especially from August 2014 onwards a number of projects under the Priority Plan shifted their focus on Ebola outreach, e.g. through CSOs, National Youth Volunteers, women's groups and human rights monitors in the various counties, because since most of the originally planned activities could not be carried out. This was considered risky in the sense that there was no guarantee for succes and this was a complete diversion from the original work plans. However, it was generally agreed that not tackling the Ebola crisis heads-on with all means might even lead to tensions and threats to the peaceful situation prevailing hitherto in the country. To this effect, the PBO realigned some of its activities to support the fight against Ebola through its internship/volunteer program by training and deploying 10 volunteers to work in 9 districts in 15 communities to mediate and mitigate emerging conflict issues such as stigmatization, prejudice, cultural practices and denial, which were leading to some tensions between families and communities, hence undermining communal peace and reconciliatory efforts. |
| Gender: How have gender considerations been mainstreamed in the project to the extent possible? Is the original gender marker for the project still the right one? Briefly justify. (1500 character limit) | The Gender Marker score of 1 remains valid. The PBO is not directly implementing activities addressing gender issues, but as the PBF Secretariat and coordinating certain national peacebuilding initiatives PBO is committed to applying a rights-based and gender-sensitive approach. For example, during the discussions of initiatives as part of the Reconciliation Roadmap the PBO actively engaged with institutions like the Ministry of Gender and Development, UN Women, UNMIL Gender Avisors and CSOs to ensure that critical gender issues would be taken into account. For the Gender Promotion Initiative II two joint proposals, with UN Women as lead coordinator, were submitted to PBSO and one of the two was selected for funding. PBO is currently working with UN Women, MoGD and other key stakeholders in developing a full proposal. |
| Other issues: Are there any other issues concerning project implementation that should be shared with PBSO? This can include any cross-cutting issues or other issues which have not been included in the report so far. (1500 character limit) | Given that project implementation has been challenged by the Ebola outbreak, the Government in partnership with UNDP designed and are implementing an Ebola prevention and control project in the 15 counties through the PBO. The project which runs for three to six months as of Octber 2014 with a value of US$450,000 is intended to enhance and accelerate prevention and response to the Ebola epidemic in all counties. This project seeks to strengthen the response and prevention through capacity to provide immediate and urgent support to the County Ebola Task Forces and activities related to sensitization, information, prevention and hygiene initiatives. The project to date has helped to establish accelerated conditions for a reduction in Ebola transmission and built a body of knowledge that hopefully enables maximum positive results in the short term. The PBO Technical Advisor and Head of Programme is the Focal Point between the 15 County Administrations and UNDP in terms of project implementation. |

PART 2: LESSONS LEARNED AND SUCCESS STORY

2.1 Lessons learned

Provide at least three key lessons learned from the implementation of the project. These can include lessons on the themes supported by the project or the project processes and management.

| Lesson 1 (1000 character limit) | Coordination and regular interaction with all key actors in the national reconciliation process has proven to be worthwhile in achieving results, even though progress has been slow in certain instances. The July 2014 mid-year review of the various national reconciliation projects brought 46 persons together in Buchanan, Grand Bassa County, and created an increased understanding by each project team that the various projects were being implemented as part of the National Reconciliation Roadmap rather than as stand-alone initiatives. It helped in ensuring increased coordination in terms of maximizing synergies and linkages between and among projects, all working towards the attainment of an overall peacebuilding outcome. |
| --- | --- |
| Lesson 2 (1000 character limit) | The experiences and lessons shared by PBO staff during the PBSO /ACCORD Workshop on 'Enhancing Peacebuilding Practice' held in Durban in August 2014, generated considerable discussion and were highly appreciated. While oftentimes there are many challenges that affect peacebuilding work in Liberia, this knowledge sharing also showed that in certain aspects PBO and its partners have pioneered some innovative approaches that can be shared with other countries. In addition to follow-up exchanges through the PBF Community of Practice (CoP) there has also been practical peer support to - for example - Guinea-Bissau in terms of a M&E detailed assignment providing technical advice in the design and implementation of a perception survey for a PBF-funded project on peace dividends. |
| Lesson 3 (1000 character limit) | During the course of the year through several discussions as well as the independent evaluation if became clear that some of the stakeholders (ranging from government agencies to CSOs and donors) did not necessarily know exactly the mandate and role of the PBO, its functions, the services it provides, and what PBO can and cannot do. Improving communication is therefore essential. As one of the steps in that direction in the beginning of the year a 'PBO Factsheet' was developed and disseminated. The PBO website was also redesigned and updated, while regular updates were provided by the Executive Director to the JSC and other key stakeholders. However, still more needs to be done to further improve communication and coordination. |
| Lesson 4 (1000 character limit) |  |
| Lesson 5 (1000 character limit) |  |

2.2 Success story (OPTIONAL)

Provide one success story from the project implementation which can be shared on the PBSO website and Newsletter as well as the Annual Report on Fund performance. Please include key facts and figures and any citations (3000 character limit).

PART 3 – FINANCIAL PROGRESS AND MANAGEMENT ARRANGEMENTS

  - Comments on the overall state of financial expenditure

Please rate whether project financial expenditures are on track, slightly delayed, or off track:

If expenditure is delayed or off track, please provide a brief explanation (500 characters maximum):

Please provide an overview of expensed project budget by outcome and output as per the table below.

| Output number | Output name | RUNOs | Approved budget | Expensed budget | Any remarks on expenditure |
| --- | --- | --- | --- | --- | --- |
| Outcome 1: Effective coordination, monitoring, reporting, evaluation and communication of all PBF-supported projects in Liberia |
| Output 1.1 | 1. PBO as PBF Secretariat effectively coordinates JSC meetings, reporting and SMC reviews | UNDP | US$601,742.22 | US$430,746.85 | Preliminary estimate |
| Output 1.2 | PBO M&E Unit ensures effective monitoring, reporting and evaluation of PBF projects | UNDP | US$259,499.72 | US$99,249.99 | Preliminary estimate |
| Output 1.3 | Capacity building in conflict management according to a rights-based and gender-sensitive approach | UNDP | US$128,502.06 | US$50,647.55 | Preliminary estimate |
| Outcome 2: |
| Output 2.1 | Output 1.4: PBF Priority Plan results effectively communicated to key stakeholders | UNDP | US$3,000.00 | US$0.00 | Preliminary estimate |
| Output 2.2 | Output 1.5: PBO adequately capacitated to ensure coordination, M&E and catalytic synergies between all PBF projects | UNDP | US$147,200.00 | US$55,000.00 | Preliminary estimate |
| Output 2.3 |  |  |  |  |  |
| Outcome 3: |
| Output 3.1 |  |  |  |  |  |
| Output 3.2 |  |  |  |  |  |
| Output 3.3 |  |  |  |  |  |
| Outcome 4: |
| Output 4.1 |  |  |  |  |  |
| Output 4.2 |  |  |  |  |  |
| Output 4.3 |  |  |  |  |  |
| Total: |  |  | US$1,139,944 | US$584,997 |  |

  - Comments on management and implementation arrangements

Please comment on the management and implementation arrangements for the project, such as: the effectiveness of the implementation partnerships, coordination/coherence with other projects, any South-South cooperation, the modalities of support, any capacity building aspect, the use of partner country systems if any, the support by the PBF Secretariat and oversight by the Joint Steering Committee (for PRF only). Please also mention if there have been any changes to the project (what kind and when); or whether any changes are envisaged in the near future (2000 character maximum):

The coordination of and support to the various projects under the Peacebuilding Priority Plan has at times been challenging during the year, mainly because of the many complex and sensitive issues surrounding peacebuilding and reconciliation, as well as the sometimes divergent views of various stakeholders on such issues. Throughout the year PBO endeavoured to support the JSC as best as possible. Probably more can be done however to further enhance coordination and synergies between the different projects supported by the PBF and others. From July onwards it became increasingly difficult if not impossible to convene meetings, trainings, etc. as the primary focus throughout the country was on combatting the Ebola epidemic. As a way of South-South cooperation in particular the collaboration between PBO and ACCORD could be highlighted, e.g. in the organization of the Peacebuilding Forum and the efforts to set up a Liberian Peacebuilding Coordination Network (LPCN) with a first training/learning event for a diverse group of Liberian civil society members in June 2014. Another example of South-South exchange was the M&E advice and hands-on support provided by the PBO to one of the PBF-supported projects (managed by UNDP) on providing temporary jobs to youth and women as 'peace dividends' in Guinea-Bissau. Two short missions were conducted in October and November 2014 to assist the colleagues in Guinea-Bissau to design, coordinate and implement a perception survey. This was a practical example of the Community of Practice (CoP) in action and the feedback so far has been very positive. Key focus areas for the PBO in 2015 are still to be discussed with PBSO and the JSC, probably in December.

# Footnotes

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to “Project ID” on the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed.

Please note that financial information is preliminary pending submission of annual financial report to the Administrative Agent.